## Menu
Dashboard: Moldova - HIV / AIDS
HIV / AIDS Round 8, Phase 1 | Grant No.: MOL-809-G06-H
V1.0
Finance
Programmatic
Management
Select the option you want to see:
Recommendations
Actions
Grant Detail
List of Indicators
Data Entry
Grant Information
Indicators
Reports

## List of Indicators
Dashboard: Moldova - HIV / AIDS
Financial information
Name: | Definition | Measurement |  | Data Sources
F1: Budget and disbursements by Global Fund | Cumulative budget: Sum of the grant budget from period one (quarter, trimester, or semester) of the current phase, up to and including the dashboard reporting period. Cumulative Disbursments by GF: Sum of all the funds transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to and including the dasboard reporting period. | Currency of the grant ($ or Euro) Cumulative – Figures refer to budget and disbursements for all the periods of the phase up to and including the dashboard reporting period |  | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F2: Budget and actual expenditures by Grant Objective | Cumulative Budget per Objective: Sum of the grant budget by Objective, from period one of the current phase up to and including the dashboard reporting period. Cumulative Expenditure per Objective: Sum of amounts spent by Objective directly by the PR plus the amounts transferred by the PR to all SRs from the beginning of the phase up to and including dashboard reporting period, by Objective | • Cumulative – Figures refer to budget, disbursements or expenditure for all the periods of the phase up to and including the dashboard reporting period. |  | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F3: Disbursements and expenditures | Disbursement by GF: Prior to this Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to but not including dashboard reporting period. Disbursement by GF: Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), during dashboard reporting period. PR disbursements and expenditure: Prior to this Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) up to but not including dashboard reporting period. PR disbursements and expenditure: Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) during dashboard reporting period. Disbursements to SRs: Prior to this Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), up to but not including dashboard reporting period. Disbursements to SRs:Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), in dashboard reporting period. SR expenditures: Prior to this Reporting period: The sum of all expenditures reported by the SRs, up to but not including dashboard reporting period. SR expenditures: Reporting period: The sum of all expenditures reported by the SRs, during dashboard reporting period. | Currency of the grant ($ or Euro) • Reporting period – Figures refer to budget, disbursements or expenditure for the reporting period to which the dashboard refers. • Prior to reporting period - Figures refer to the total budget, disbursements or expenditure for all the periods before but not including the current period. |  | PU/DR; PR data: SR reports to PR
F4: Latest PR reporting and disbursement cycle | Days taken to submit final PU/DR to LFA – This indicator measures the number of calendar days it took the PR to send a final Performance Update and Disbursement Request (PU/DR) to the LFA after the end of the period. A 'final' PU/DR would be one for which the LFA did not require any further clarifications from the PR. The expected value is 45 days from the end of the period, as defined in the Grant Agreement. The actual value is the number of calendar days from the end date of the period to the date on which the PR sent to the LFA the final PU/DR. Days taken for disbursement to reach PR – This indicator measures the number of calendar days it took the Global Fund to send the latest disbursement to the PR's account after receipt of the acceptable PU/DR by the LFA. The expected number is 45 days. The actual number is the number of days from the date of transmission by the PR to the LFA of the acceptable PU/DR to the date the disbursement is received by the PR at its bank. Days taken for disbursement to reach SRs – This indicator measures the average number of days for disbursements to be made to all the SRs. The expected value for this indicator will be set locally by the PR and SRs, preferably in the Grant Operations Manual. The actual value is the average of the number of days from the receipt of the funds from the GF by the PR to the date the funds are received by each SR. Different SRs coudl receive funds on different dates and this indicator is the average across all SRs for the latest disbursement. | Number of calendar days; it refers only to reporting period for which the latest disbursement was received and is not cumulative |  | PR, LFA, GF emails and records; bank notification document or the notice of receipt by the PR to GF; SR reports to PR based on bank records
Management Information
Name: | Definition | Measurement |  | Data Source
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) | Number of Conditions Precedent (CPs) and Time Bound Actions (TBAs ) fulfilled, or unfulfilled. Within the Unfulfilled category, we distinguish between those CPs and TBAs whose deadline has not passed and those for which the deadline has passed. | Number, cumulative to the dashboard reporting period. Number of fulfilled CPs and/or TBAs plus unfulfilled CPs and/or TBAs should equal the total number set by the Global Fund on the grant |  | PR records; Grant Performance Reports;
M2: Status of key PR management positions | Number of PR grant management positions planned currently filled or vacant. Full time equivalents of the managerial positions that are on the organizational chart (or otherwise planned) and directly responsible for ensuring grant implementation at the PR, and lead SRs (if necessary). This will include new hires, current staff who are assigned to work on the grant’s management, as well as any staff seconded from other divisions or partner organizations. | Number, in current reporting period |  | PR records
M3: Contractual arrangements (SRs) | Identified: Total number of potential SRs identified by the PR for the phase. Assessed: Total number of potential SRs assessed by the PR to determine whether they qualify to function as SRs for the grant. Approved: Total number of SRs that have been approved. Signed: Total number of SRs that have signed agreements/contracts with the PR under the grant. Receiving funding: Total number of SRs that are getting funds and/or supplies from the PR. Numbers of SRs Identified, Assessed, Approved, Signed and Receiving funds are cumulative for the phase, with the following exceptions: If an SR does not need new approval in Phase II, then approval in Phase I is counted. If an SR was signed in a previous Phase but is not working in the current Phase, that SR is no longer counted in Identified, Assessed, Approved. | Number, cumulative to the reporting period. A SR is an institution or program with its own workplan, budget and performance targets. |  | PR records; Sub-agreements/MOUs; CCM records
M4: Number of complete reports received on time | The total number of periodic reports with up-to-date financial, management and performance (programmatic) data received by the PR from SRs and by SRs from the SubSRs (SSRs) by the expected date. A 'complete' report is one that contains all the data that the PR requires for the PU/DR. The expected date would be set by the PR in the sub-agreements. | Number of reports received. The figure reflects only the period of reporting; it is not cumulative. |  | PR and SR records
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals | This indicator measures the budget approved for the current phase of the grant for purchase of health products and equipment and pharmaceuticals and medicines (categories 4 and 5 in the new Enhanced Financial Report), and the cumulative amounts of financial obligations and expenditures up to the dashboard reporting period. Budget approved: Total approved budget for purchases (categories 4 and 5) for the entire phase of the grant. It does not include the amounts for fees, management, operational costs, etc. Cumulative Obligations: Total of all order(s) placed and monies committed for these purchases by the PR up to and including the dashboard reporting period. Ideally, by the end of the Phase, budget should equal obligations. Cumulative expenditure: Total of actual Expenditures on category 4 and 5 up to and including the dashboard reporting period (whether paid by PR or authorized to be paid by another entity like GF or other). | Currency of the grant ($ or Euro) |  | Grant agreement approved budget (for categories 4 and 5 of Enhanced Finance Reporting in current phase); and PR financial data (for expenditures), and/or PSM unit (for orders placed and funding committed or obligated).
Note: Category 6 of the EFR will not be considered as part of the budget for pharmaceuticals. Category 6 has several expenditures that are difficult to disaggregate or quantify, such as warehousing costs, distribution costs (particularly when distibution is done by MOHs), and others that are related to operational costs of the PSM component.
M6: Difference between current and safety stock | This indicator is a snapshot of the difference between the current (or last month) stock level of a specific product (medicine in single, fixed-dose combination, bednets, diagnostic kits, etc.) of a particular dose, expressed in monthly needs (number of months of treatment available) for all patients in the program, and the safety or buffer stock (also expressed in months) as established by the disease program, warehouse system or essential drugs program, for the particular product and dosage. The table will show the difference in months in colors: • RED: when the difference is negative or 0, showing that months of existing stock are lower than or equal to what has been established as months of safety stock • YELLOW: when we have more than the level of safety stock (>0) but less than 3 months (+3). • GREEN: when the difference is between 3 and 18 months. • VIOLET: When the difference shows that the level above the safety stock is greater than or equal to 18 months indicating a potential overstock) problem. For a full description of how this indicator is calculated, please see the User’s Manual. | Number of months |  | PR records: Warehouse data.
Programmatic Indicators (from Performance Framework)
Indicator | Definition (from M&E Plan, September 2009) | Measurement |  | Data Source
Number of medical (doctors and nurses) and non-medical staff (psychologists, social assistants, peer consultants) trained in HIV/AIDS | It is a composite indicator, related activities: capacity building of health specialists from the ART treatment facilities in HIV/AIDS case management abroad; capacity building in HIV/AIDS management for the non-medical staff from the MDT teams; increasing knowledge on HIV/AIDS in staff of the Medical Colleges; training of medical staff in palliative care; training of infectious diseases specialists and primary care specialists; incipient trainings for the e-learning course ; training of the staff of the Ministry of Social Protection in HIV/AIDS (strategic planning, M&E etc) | all persons who signed the list of participation at training |  | List of participants trained
Number of PLWHA receiving palliative care | HIV infected patients that receive palliative care services within the ARV Treatment facility during reported period (care of skin, hair, nails, eyes, mouth, pneumonia prophylactic treatment, symptomatic treatment, alimentation, etc.). | all persons who received services during the reported period |  | Register of beneficiaries
Number of PLWHA receiving food parcels to improve ARV treatment adherence | PLWHA is considered "reached" if he/she has received at least one food package per month during 3 consecutive months. | new persons who received services during the reported period |  | Database
Number of children infected and affected by HIV/AIDS who receive social support | The social support includes food parcels, clothing and school supplies. | new children who received services during the reported period | all persons who received services during the reported period | Database
Number of IDUs on oppoid substitution therapy that receive at least 3 support services from NGOs working in DUs rehabilitation | The beneficiaries are provided with the following services: psycho-social support, self-support groups, peer to peer education, distributions of information materials, etc. The beneficiary is considered "reached" if he/she has received at least three of the services listed. | new persons who received at least 3 support services during the reported period |  | Database
Number and percentage of individuals currently on OST who have been on OST continuously at least 6 months for the past 12 months | Numerator: number of individuals completing at least 6 months of continuous treatment on OST that initiated treatment 6-12 months prior to the end of the reporting period. Denominator: total number of individuals that initiated treatment 6-12 months prior to the end of the reporting period. The indicator is linked to percentage, absolute numbers will be provided when reporting results. The targets refer to the patient cohort (both new and repeated cases) that initiated treatment in the first 6 months of the last 12 months period. | determine the number of people who initiated TS (first time as well as repeated) in the first six months of the last 12 months and assessed how many of these people remained in continuous TS at least 6 months |  | Register of beneficiaries
Number of people living with HIV/AIDS reached with care and support services | The beneficiaries are provided with the following services: psycho-social counseling and registration, distribution of information materials and peer health counseling. The beneficiary is considered "reached" if he/she has received at least one of the three listed services. | new persons who received at least 3 support services during the reported period |  | Database
Number of lawyers from the free legal system and ombudsmen institutes trained in HR, non-discrimination and principles of legal aid. | It is a composite indicator, related activities: training of lawyers from the free legal aid system guaranteed by the state and training on HR, non-discrimination, reparations for moral prejudice and principles of legal aid for lawyers and the Ombudsment Institute | all persons who signed the list of participation at training |  | List of participants trained
Number of human rights strategic litigation cases for PLWH initiated. | Human rights strategic litigation cases for PLWH initiated. | total number of human rights strategic litigation cases registered in the register |  | Register of beneficiaries
Number of PLWHA assisted by legal aid (consultancies offered by legal network) | PLWHA receiving legal aid offered by legal network | all persons who received services during the reported period |  | Register of beneficiaries
Number of the PLWHA League members trained in languages, strategic planning, M&E etc. | It is a composite indicator, related activities: trainings for the members of the league and capacity building of the members of the League in languages and in strategic planning, M&E etc | all persons who signed the list of participation at training |  | List of participants trained
Indicator Number: Name (Perf Framework No.) | Definition | Measurement |  | Data Source
The indicators should be selected by the PRs and members of the CCM or the CCM Technical Committee, from the Performance Framework |  |  |  | Performance Framework
Menu

## Data Entry
Grant information
| Country: | Moldova |  | Title of the Grant: |  | Reducing HIV-related burden in the Republic of Moldova
| Grant No.: | MOL-809-G06-H |  | Component: |  | HIV / AIDS | Total Funding: | 7102866
| Principal Recipient: | PAS Center |  |  | Round: | Round 8 | Phase: | Phase 1
| Start Date (dd/Mmm/yy): | January 01, 2010 |  | Local Fund Agent: |  | PwC (PricewaterhouseCoopers)
| Latest Rating: | A2 |  | Fund Portfolio Manager: |  | Nicolas Cantau
Information reporting period
| Report Period: | P6 | From: | January 01, 2011 | To: | June 30, 2011 | Date of entry of information: |  | August 31, 2011
| Prepared by: |  | PAS Center
Information on indicators
Enter the data based on the colour-coded cells
| Financial Information: |  | Management Information: |  |  | Programmatic Information:
| Financial Information: | [8 empty] | Enter finance data in every orange cell like this.
| Currency of the grant |  | €
F1: Budget and disbursements by Global Fund
| Disbursement | [15 empty] | 700858.51
| Reporting period | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12 | % Cumulative |  |  | 2385726.02
| Budget (in €) | P1: 700858.51; P2: 1684867.51; P3: 944476.51; P4: 788448; P5: 730629; P6: 766003.94 | 101.8% |  |  | 3330202.53
| Disbursements by GF (in €) | P1: 2830201; P4: 1671393; P6: 1215219 |  |  |  | 4118650.53
| Cumulative budget | 700858.51 | 2385726.02 | 3330202.53 | 4118650.53 | 4849279.53 | 5615283.47 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4849279.53
| Cumulative disbursements | 2830201 | 2830201 | 2830201 | 4501594 | 4501594 | 5716813 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5615283.47
|  | 0% | 0% | 0% | 0% | 0% | 101.8% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0
F2: Budget and actual expenditures by Grant Objective
| Grant Objective | P1: Cumulative Budget (in €); P2: Cumulative Expenditures (in €)
| Improve performance of GFATM Round VI through improved infrastructure | P1: 711488; P2: 639215
| Improve quality of Life of PLWH | P1: 3758983; P2: 2914738
| Strengthen the National League of PLWH | P1: 465567; P2: 404231
| Planning and administration | P1: 679245; P2: 630975
| Total | P1: 5615283; P2: 4589159; P4: OK: Data match
| F3: Disbursements and expenditures | [15 empty] | 0
0
|  | P1: Prior to reporting period; P2: Current reporting period; P3: Total Spent and Disbursement (in €) |  |  | 0
| Disbursed by Global Fund | P1: 4501594; P2: 1215219; P3: 5716813
| PR expenditure and disbursement | P1: 2831080; P2: 1758079; P3: 4589159
| Disbursed to SRs | P1: 1686755; P2: 1009740; P3: 2696495
| SR expenditures | P1: 1531884.14; P2: 775784.86; P3: 2307669
F4: Latest PR reporting and disbursement cycle
Last fund disbursement: Number of calendar days
|  | Expected (days) | Actual (days)
| Days taken to submit final PU/DR to LFA | P1: 45; P2: 33
| Days taken for disbursement to reach PR | P1: 45; P2: 50
| Days taken for disbursement to reach SRs | P1: 20; P2: 9
| Management Information: | P6: Enter management data in every blue cell.
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs)
|  |  | Fulfilled | Not fulfilled, but within deadline | Not fulfilled, and past the deadline | Total
| Conditions precedent (CPs) | P2: 4; P3: 1; P5: 5
| Time Bound Actions (TBAs) | P5: 0
M2: Status of key PR management positions
|  | Planned | Filled | Vacant
| PMU | P1: 11; P2: 12; P3: -1
M3: Contractual arrangements (SRs)
|  | Identified | Assessed | Approved | Signed | Receiving Funding
| SRs | P1: 4; P2: 4; P3: 4; P4: 4; P5: 3
M4: Number of complete reports received on time
|  | # Expected | # Received | Pending
| SSR to SR | P1: 27; P2: 25; P3: 2
| SRs to PR | P1: 3; P2: 3; P3: 0
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals
|  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
Budget Approved*
Obligations
Expenditures
| Budget Approved cumulative* | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Obligations cumulative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Expenditures cumulative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
* Includes only EFR category 4 and 5 (Health products and health equipment & Medicines and Pharmaceuticals)
M6: Difference between current and safety stock
| Component | Products | (1) Number of tablets per patient per day (Review country treatment guidelines) | (2 = 1 x 30) Monthly treatment (Tablets per patient x 30 days) | (3) Total patients in treatment | (4 = 2 x 3) Total # tab/pills required for all patients per month | (5) Current stock in central warehouse (that does not expire within the next 3 months) | (6 = 5 / 4) Stock level expressed in months of treatment for all current patients | (7) Level of safety stock (expressed in months and defined by country) | (8 = 6 - 7) Difference between current stock and safety stock
| HIV / AIDS | P1: Please Select
Please Select
Please Select
Please Select
| Programmatic Information: | P9: Enter performance data in every yellow cell.
| Programmatic indicators (Performance Framework ) |  |  | Code | Directly Tied? |  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
TOP 3 | Number of people living with HIV/AIDS reached with care and support services |  |  | 1.7. | Yes | Target | P1: 3250; P2: 3500; P3: 3750; Enter performance data in every yellow cell. P4: 4000; Enter performance data in every yellow cell. P5: 4375; Enter performance data in every yellow cell. P6: 4750
[6 empty] | Achieved | P1: 2093; P2: 2817; P3: 3197; Enter performance data in every yellow cell. P4: 3717; Enter performance data in every yellow cell. P5: 3976; Enter performance data in every yellow cell. P6: 4296
| Number of IDUs on oppoid substitution therapy that receive at least 3 support services from NGOs working in DUs rehabilitation |  |  | 1.5. | Yes | Target | P1: 54; P2: 108; P3: 162; Enter performance data in every yellow cell. P4: 216; Enter performance data in every yellow cell. P5: 280; Enter performance data in every yellow cell. P6: 344
[6 empty] | Achieved | P1: 61; P2: 131; P3: 180; Enter performance data in every yellow cell. P4: 225; Enter performance data in every yellow cell. P5: 284; Enter performance data in every yellow cell. P6: 322
| Number of medical (doctors and nurses) and non-medical staff (psychologists, social assistants, peer consultants) trained in HIV/AIDS |  |  | 1.1. | Yes | Target | P1: 25; P2: 150; P3: 225; Enter performance data in every yellow cell. P4: 400; Enter performance data in every yellow cell. P5: 500; Enter performance data in every yellow cell. P6: 625
[6 empty] | Achieved | P1: 50; P2: 174; P3: 268; Enter performance data in every yellow cell. P4: 594; Enter performance data in every yellow cell. P5: 788; Enter performance data in every yellow cell. P6: 1099
| Number of PLWHA receiving palliative care |  |  | 1.2. | No | Target | P1: n/a; P2: n/a; P3: n/a; Enter performance data in every yellow cell. P4: 15; Enter performance data in every yellow cell. P5: 20; Enter performance data in every yellow cell. P6: 25
[6 empty] | Achieved | P1: n/a; P2: n/a; P3: n/a; Enter performance data in every yellow cell. P4: 7; Enter performance data in every yellow cell. P5: 18; Enter performance data in every yellow cell. P6: 34
| Number of PLWHA receiving food parcels to improve ARV treatment adherence |  |  | 1.3. | Yes | Target | P1: 108; P2: 216; P3: 324; Enter performance data in every yellow cell. P4: 432; Enter performance data in every yellow cell. P5: 573; Enter performance data in every yellow cell. P6: 715
[6 empty] | Achieved | P1: 108; P2: 269; P3: 462; Enter performance data in every yellow cell. P4: 588; Enter performance data in every yellow cell. P5: 803; Enter performance data in every yellow cell. P6: 961
| Number of children infected and affected by HIV/AIDS who receive social support |  |  | 1.4. | Yes | Target | P1: 95; P2: 125; P3: 155; Enter performance data in every yellow cell. P4: 185; Enter performance data in every yellow cell. P5: 216; Enter performance data in every yellow cell. P6: 248
[6 empty] | Achieved | P1: 91; P2: 133; P3: 195; Enter performance data in every yellow cell. P4: 236; Enter performance data in every yellow cell. P5: 298; Enter performance data in every yellow cell. P6: 332
| Number and percentage of individuals currently on OST who have been on OST continuously at least 6 months for the past 12 months |  |  | 1.6. | No | Target | P1: n/a; P2: n/a; P3: n/a; Enter performance data in every yellow cell. P4: n/a; Enter performance data in every yellow cell. P5: n/a; Enter performance data in every yellow cell. P6: 50%
[6 empty] | Achieved | P1: n/a; P2: n/a; P3: n/a; Enter performance data in every yellow cell. P4: n/a; Enter performance data in every yellow cell. P5: n/a; Enter performance data in every yellow cell. P6: 53.18%
| Number of lawyers from the free legal system and ombudsmen institutes trained in HR, non-discrimination and principles of legal aid. |  |  | 1.8. | Yes | Target | P1: 50; P2: 100; P3: 150; Enter performance data in every yellow cell. P4: 200; Enter performance data in every yellow cell. P5: 250; Enter performance data in every yellow cell. P6: 300
[6 empty] | Achieved | P1: 51; P2: 102; P3: 152; Enter performance data in every yellow cell. P4: 244; Enter performance data in every yellow cell. P5: 294; Enter performance data in every yellow cell. P6: 426
| Number of PLWHA assisted by legal aid (consultancies offered by legal network) |  |  | 1.10. | Yes | Target | P1: 10; P2: 20; P3: 30; Enter performance data in every yellow cell. P4: 40; Enter performance data in every yellow cell. P5: 55; Enter performance data in every yellow cell. P6: 70
[6 empty] | Achieved | P1: 25; P2: 78; P3: 108; Enter performance data in every yellow cell. P4: 142; Enter performance data in every yellow cell. P5: 163; Enter performance data in every yellow cell. P6: 182
| Number of the PLWHA League members trained in languages, strategic planning, M&E etc. |  |  | 1.11. | Yes | Target | P1: 35; P2: 70; P3: 105; Enter performance data in every yellow cell. P4: 140; Enter performance data in every yellow cell. P5: 190; Enter performance data in every yellow cell. P6: 240
[6 empty] | Achieved | P2: 78; Enter performance data in every yellow cell. P6: 340
| Table is automatically updated. No data or information is to be entered here. |  |  | Code | Directly Tied? |  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
| Number of people living with HIV/AIDS reached with care and support services |  |  | 1.7. | Yes | Target | 3250 | 3500 | 3750 | 4000 | 4375 | 4750 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Achieved | 2093 | 2817 | 3197 | 3717 | 3976 | 4296 | 0 | 0 | 0 | 0 | 0 | 0
| Number of IDUs on oppoid substitution therapy that receive at least 3 support services from NGOs working in DUs rehabilitation |  |  | 1.5. | Yes | Target | 54 | 108 | 162 | 216 | 280 | 344 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Achieved | 61 | 131 | 180 | 225 | 284 | 322 | 0 | 0 | 0 | 0 | 0 | 0
| Number of medical (doctors and nurses) and non-medical staff (psychologists, social assistants, peer consultants) trained in HIV/AIDS |  |  | 1.1. | Yes | Target | 25 | 150 | 225 | 400 | 500 | 625 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Achieved | 50 | 174 | 268 | 594 | 788 | 1099 | 0 | 0 | 0 | 0 | 0 | 0
Note on B30: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.
Note on B72: If data are not available, do not enter zeros; rather, leave the cells in the table blank.
Note on B73: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B79: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B94: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.
Menu

## Grant Detail
Dashboard: Moldova - HIV / AIDS
Country: | Moldova |  | Title of the Grant: |  | Reducing HIV-related burden in the Republic of Moldova
Component: | HIV / AIDS | Grant No. | MOL-809-G06-H | Start Date: |  | January 01, 2010 | Total Funding | 7102866
Round: | Round 8 | Phase: | Phase 1 | Principal Recipient: |  | PAS Center
Report Period: | P6 | from: | January 01, 2011 | to: |  | June 30, 2011 | Latest Rating: | A2
Local Fund Agent: | PwC (PricewaterhouseCoopers) |  |  | Fund Portfolio Manager: |  | Nicolas Cantau
Prepared by: | PAS Center |  |  | Report preparation date: |  | August 31, 2011
http://www.crwflags.com/fotw/flags/country.html
Menu

## Finance
Dashboard: Moldova - HIV / AIDS
Round 8 | Phase 1 |  |  |  | Report Period: |  | P6
Latest Rating: | A2 |  | PAS Center |  | From: |  | January 01, 2011
|  | Reducing HIV-related burden in the Republic of Moldova |  |  |  | To: | June 30, 2011
Financial Indicators
F1: Budget and disbursements by Global Fund - in (€) Report Period: P6 |  |  |  | F3: Disbursements and expenditures - in (€) Report Period: P6
Comments: |  |  |  | Comments:
F2: Budget and actual expenditures by Grant Objective - in (€) Report Period: P6 |  |  |  | F4: Latest PR reporting and disbursement cycle Report Period: P6
Comments: | The variance between budget and expenditure is mainly constituting commitments/forecastings to payment, predominantly for refurbishment and equipment of Social Regional Centers for PLHIV and commitments to be transferred to SRs at request for the implementation of the activities that SRs are responsible for. The difference is part of CCM request addressed to FPM on July 28 for allocation of funding available as savings until the end of Phase I of the Round 8 HIV grant for refurbishment and equipping of the Center of Excellence for management of TB/HIV cases at the premises of the TB Hospital in Vorniceni. |  |  | Comments:
Last fund disbursement: Calendar days
[6 empty] | Expected (days) | Actual (days)
|  |  |  | Days taken to submit final PU/DR to LFA |  | 45 | 33
|  |  |  | Days taken for disbursement to reach PR |  | 45 | 50
|  |  |  | Days taken for disbursement to reach SRs |  | 20 | 9
Menu

## Management
Dashboard: Moldova - HIV / AIDS
Round 8 | Phase 1 |  |  |  |  | Report Period: |  | P6
Latest Rating: | A2 |  | PAS Center |  |  | From: |  | January 01, 2011
|  | Reducing HIV-related burden in the Republic of Moldova |  |  |  |  | To: | June 30, 2011
Management Indicators
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) Report Period: P6 |  |  |  | M2: Status of key PR management positions Report Period: P6
Comments: | From five conditions precedent and/or other special conditions, four have been fulfilled. The fifth condition (Rehabilitation of infrastructures) is tied to the approval of bidding documents for refurbishment of the palliative care department and four Social Regional Centers for PLHIV and has been fulfilled in proportion of 80% (for four out of five buildings). The bidding documents for the fifth building (Social regional Center for PLHIV from Comrat) will be sent for approval in the first week of September 2011 following the evaluation of bids. |  |  | Comments: | Two full time positions and 10 part time.
M3: Contractual arrangements (SRs) Report Period: P6 |  |  |  | M4: Number of complete reports received on time Report Period: P6
Comments: | Four Sub-recipients (SRs) have been identified to implement different components within the program: Soros Foundation-Moldova (SFM); League of people living with HIV of Moldova; New Life, Moldovan Institute for Human Rights. One SR (SFM) has been earlier assessed by the governmental PR of GF grants as it acts as an SR since GF Round one. Two other SRs have been assessed (New Life and Moldovan Institute for Human Rights) were assessed by PAS Center the last one (League of people living with HIV of Moldova) by GF Local Fund Agent. Following the assessments four sub-grant agreements have been signed. In September 2011, due to lack of capacity for adequate implementation of the grant portion contracted the sub-grant agreement with one of the SRs (League of people living with HIV) was terminated and the management of activities has been entrusted to SFM. Respectively three sub-recipients are currently receiving funds within the grant. |  |  | Comments: | The SRs’ quarterly reports (financial report, activity report and performance framework) are due to the PR not later than 25 days after the close of each quarter and are generally submitted in time. For the SR SFM the Sub-subrecipients financial reports are due quarterly and can be submitted during the following quarter, the activity reports are due not later than 10 days from the end of each month and are generally submitted in time except two Ssrs - League of people living with HIV of Moldova and NGO Master in Public Health. For the SR New Life the reports (financial, activity and indicators) are due not later than 15 days after the close of each quarter and are generally submitted in time.
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals |  |  |  | M6: Difference between current and safety stock Report Period: P6
Comments: | N/A |  |  | Comments: | N/A
|  |  |  | Component | Products | Stock level expressed in months of treatment for all current patients | Months of safety stock | Difference between current stock and safety stock
|  |  |  | HIV / AIDS | Please Select |  | 0
[5 empty] | Please Select |  | 0
[5 empty] | Please Select |  | 0
[5 empty] | Please Select |  | 0
* Includes only EFR category 4 and 5 (Health products and health equipment & Medicines and Pharmaceuticals)
Menu

## Programmatic
Dashboard: Moldova - HIV / AIDS
Round 8 | Phase 1 | [8 empty] | Report Period: |  | P6
Latest Rating: | A2 |  | PAS Center | [7 empty] | From: | January 01, 2011
|  | Reducing HIV-related burden in the Republic of Moldova | [8 empty] | To: | June 30, 2011 | [7 empty] | Raiting |  | Valor
Programmatic Indicators
Number of people living with HIV/AIDS reached with care and support services |  |  |  | Number of IDUs on oppoid substitution therapy that receive at least 3 support services from NGOs working in DUs rehabilitation |  |  |  | Number of medical (doctors and nurses) and non-medical staff (psychologists, social assistants, peer consultants) trained in HIV/AIDS
Comment: P1 | The baseline for this indicator at the stage of country application submission was overestimated and settled at 2000 people for the year 2009. At the end of year 2009 though the number of PLHIV reached with care and support services was much lower - 1707. The variance between cumulative result and cumulative target is due to the difference in baseline and real result at the end of year 2009. |  |  | Comment: P2 |  |  |  | Comment: P3 | The targets for this indicator have been substantially exceeded due to the organization of additional training within the framework of the initial budget (as per the GF approval), as well as the identification of co financing for other trainings which allowed for the coverage of a much bigger number of trainees.
Indicators |  |  | Target (cumulative over program term) | Achieved (cumulative over program term) | 0% - 59% | 60% - 89% | > 90% | Comments |  |  |  |  | min | 0 | 30% | 60% | 90% | 100% |  | min | 0 | 20% | 40% | 60% | 80%
Number of people living with HIV/AIDS reached with care and support services |  |  | 4750 | 4296 | 90.44% |  |  | During S3 a total 579 PLHIV were primarily reached with care and support services provided by 10 organizations working in this area all over the country. The beneficiaries are provided with the following services: psycho-social counseling and registration, medical consultations, distribution of informational materials and peer health counseling, referalservices provided by public institutions, self soupport groups, etc. |  |  |  |  | max | 30% | 60% | 90% | 100% | 200% |  | max | 20% | 40% | 60% | 80% | 100%
Number of IDUs on oppoid substitution therapy that receive at least 3 support services from NGOs working in DUs rehabilitation |  |  | 344 | 322 | 93.6% |  |  | During S3 a total of 97 IDUs on oppioide substitution therapy (primarily reached) received at least 3 support services from the package provided by four day care centers and the penitentiary sector support team. The package of services include psychological counseling, food support (food parcels), peer to peer counseling, legal advice, referral to medical and social services, referral to ST, ST counseling, services in the territory, information activities and distribution of informational materials, self support groups, etc. | [5 empty] | de 0 a 0.3 | de 0.3 a 0.6 | de 0.6 a 0.9 | de 0.9 a 1 | de 1 a 2 | Rating | Valor | de 0 a 0.2 | de 0.2 a 0.4 | de 0.4 a 0.6 | de 0.6 a 0.8 | de 0.8 a 1
Number of medical (doctors and nurses) and non-medical staff (psychologists, social assistants, peer consultants) trained in HIV/AIDS |  |  | 625 | 1099 | 175.8% |  |  | A total of 505 persons were trained in S3, from them: 53 medical staff trained in international trainings in Clinica Lavra in various aspects such as revention of mother to child transmission of HIV, organ and system complications in patients with HIV Infection, etc.; 119 non-medical staff from MDT under National Social Reference System were trained in protection and assistance to victims of human trafficking, domestic violence and people living with HIV within the National Reference System; 98 primary health care specialists were trained HIV infection; 119 social assistants in most affected regions were trained in HIV/AIDS; 92 Health System managers and medical staff were trained in HIV/AIDS and e-learning methodology; and 24 specialists from the Ministry of Social Protection were trained in HIV/AIDS. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number of PLWHA receiving palliative care |  |  | 25 | 34 | 136% |  |  | 27 HIV infected patients received palliative care services within the ARV Treatment facility during reported period (care of skin, hair, nails, eyes, mouth, pneumonia prophylactic treatment, symptomatic treatment, alimentation, etc.). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number of PLWHA receiving food parcels to improve ARV treatment adherence |  |  | 715 | 961 | 134.4% |  |  | A total of 375 PLHIV received food parcels during S3 (primarily reached): 215 during Q5 and 160 during Q6. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number of children infected and affected by HIV/AIDS who receive social support |  |  | 248 | 332 | 133.9% |  |  | A total of 101 children received social support during S3 (primarily reached): 62 children during Q5 and 39 children during Q6. This indicator refers to children infected and affected by HIV covered with social support (quarterly food parcels and semiannual clothing and school supplies sets for HIV infected children, and quarterly food support for children born from HIV positive mothers with unknown status). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Number and percentage of individuals currently on OST who have been on OST continuously at least 6 months for the past 12 months |  |  | 50% | 53.18% | 106.4% |  |  | A total of 92 individuals out of 173 (53,18%) that initiated OST during P3-P4 (July - December 2010) have completing at least 6 months of continuous treatment on OST. Curently OST is provided in three sites: Republican Narcological Dispensary, Balti Municipal Hospital and the Department of Penitentiary Institutions (in 7 penitenciaries). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Number of lawyers from the free legal system and ombudsmen institutes trained in HR, non-discrimination and principles of legal aid. |  |  | 300 | 426 | 142% |  |  | A total of 182 advocates and lawyers from the system of legal assistance guaranteed by the state have been trained during S3 within 8 training courses on human rights, non-discrimination, confidentiality and reparation for moral prejudices of people living with HIV. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Number of PLWHA assisted by legal aid (consultancies offered by legal network) |  |  | 70 | 182 | 260% |  |  | A total of 40 free legal consultancies were offered remotely by 3 lawyers by travelling to project sites , during S3; they offered legal assistance related to issues of legal, civil (including disclosure of HIV status), administrative nature to all PLHIV in need. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Number of the PLWHA League members trained in languages, strategic planning, M&E etc. |  |  | 240 | 340 | 141.7% |  |  | 196 representatives of NGOs providing services to PLHIV were trained during S3. 40 participants were attending Romanian language course (B1 and B2 level) and 39 people have followed Romanian language courses (C1 level). 39 persons were trained in developing and improving service quality of self-support groups; 29 people were trained in fundraising and procurement; 23 people were trained in NGO management and 26 in advocacy. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Menu

## Recommendations
Dashboard: Moldova - HIV / AIDS
Round 8 | Phase 1 |  |  |  |  | Report Period: | P6
Latest Rating: | A2 |  | PAS Center |  |  | From: | January 01, 2011
|  |  | Reducing HIV-related burden in the Republic of Moldova |  |  | To: | June 30, 2011
Recommendations
Are all funds reaching implementation levels and being spent according to budget?
Financial |  | Summary Comments |  |  | Recommendations
F1
F2 |  | The variance between budget and expenditure is mainly constituting commitments/forecastings to payment, predominantly for refurbishment and equipment of Social Regional Centers for PLHIV and commitments to be transferred to SRs at request for the implementation of the activities that SRs are responsible for. The difference is part of CCM request addressed to FPM on July 28 for allocation of funding available as savings until the end of Phase I of the Round 8 HIV grant for refurbishment and equipping of the Center of Excellence for management of TB/HIV cases at the premises of the TB Hospital in Vorniceni.
F3
F4
Are procurement and hiring on schedule?
Management |  | Summary Comments |  |  | Recommendations
M1 |  | From five conditions precedent and/or other special conditions, four have been fulfilled. The fifth condition (Rehabilitation of infrastructures) is tied to the approval of bidding documents for refurbishment of the palliative care department and four Social Regional Centers for PLHIV and has been fulfilled in proportion of 80% (for four out of five buildings). The bidding documents for the fifth building (Social regional Center for PLHIV from Comrat) will be sent for approval in the first week of September 2011 following the evaluation of bids.
M2 |  | Two full time positions and 10 part time. | #DIV/0! | #DIV/0!
M3 |  | Four Sub-recipients (SRs) have been identified to implement different components within the program: Soros Foundation-Moldova (SFM); League of people living with HIV of Moldova; New Life, Moldovan Institute for Human Rights. One SR (SFM) has been earlier assessed by the governmental PR of GF grants as it acts as an SR since GF Round one. Two other SRs have been assessed (New Life and Moldovan Institute for Human Rights) were assessed by PAS Center the last one (League of people living with HIV of Moldova) by GF Local Fund Agent. Following the assessments four sub-grant agreements have been signed. In September 2011, due to lack of capacity for adequate implementation of the grant portion contracted the sub-grant agreement with one of the SRs (League of people living with HIV) was terminated and the management of activities has been entrusted to SFM. Respectively three sub-recipients are currently receiving funds within the grant.
M4 |  | The SRs’ quarterly reports (financial report, activity report and performance framework) are due to the PR not later than 25 days after the close of each quarter and are generally submitted in time. For the SR SFM the Sub-subrecipients financial reports are due quarterly and can be submitted during the following quarter, the activity reports are due not later than 10 days from the end of each month and are generally submitted in time except two Ssrs - League of people living with HIV of Moldova and NGO Master in Public Health. For the SR New Life the reports (financial, activity and indicators) are due not later than 15 days after the close of each quarter and are generally submitted in time.
M5 |  | N/A
M6 |  | N/A
Are technical targets being achieved?
Programmatic |  | Summary Comments |  |  | Recommendations
P1 - trend |  | The baseline for this indicator at the stage of country application submission was overestimated and settled at 2000 people for the year 2009. At the end of year 2009 though the number of PLHIV reached with care and support services was much lower - 1707. The variance between cumulative result and cumulative target is due to the difference in baseline and real result at the end of year 2009.
P2 - trend
P3 - trend |  | The targets for this indicator have been substantially exceeded due to the organization of additional training within the framework of the initial budget (as per the GF approval), as well as the identification of co financing for other trainings which allowed for the coverage of a much bigger number of trainees.
P1 |  | During S3 a total 579 PLHIV were primarily reached with care and support services provided by 10 organizations working in this area all over the country. The beneficiaries are provided with the following services: psycho-social counseling and registration, medical consultations, distribution of informational materials and peer health counseling, referalservices provided by public institutions, self soupport groups, etc.
P2 |  | During S3 a total of 97 IDUs on oppioide substitution therapy (primarily reached) received at least 3 support services from the package provided by four day care centers and the penitentiary sector support team. The package of services include psychological counseling, food support (food parcels), peer to peer counseling, legal advice, referral to medical and social services, referral to ST, ST counseling, services in the territory, information activities and distribution of informational materials, self support groups, etc.
P3 |  | A total of 505 persons were trained in S3, from them: 53 medical staff trained in international trainings in Clinica Lavra in various aspects such as revention of mother to child transmission of HIV, organ and system complications in patients with HIV Infection, etc.; 119 non-medical staff from MDT under National Social Reference System were trained in protection and assistance to victims of human trafficking, domestic violence and people living with HIV within the National Reference System; 98 primary health care specialists were trained HIV infection; 119 social assistants in most affected regions were trained in HIV/AIDS; 92 Health System managers and medical staff were trained in HIV/AIDS and e-learning methodology; and 24 specialists from the Ministry of Social Protection were trained in HIV/AIDS.
P4 |  | 27 HIV infected patients received palliative care services within the ARV Treatment facility during reported period (care of skin, hair, nails, eyes, mouth, pneumonia prophylactic treatment, symptomatic treatment, alimentation, etc.).
P5 |  | A total of 375 PLHIV received food parcels during S3 (primarily reached): 215 during Q5 and 160 during Q6.
P6 |  | A total of 101 children received social support during S3 (primarily reached): 62 children during Q5 and 39 children during Q6. This indicator refers to children infected and affected by HIV covered with social support (quarterly food parcels and semiannual clothing and school supplies sets for HIV infected children, and quarterly food support for children born from HIV positive mothers with unknown status).
P7 |  | A total of 92 individuals out of 173 (53,18%) that initiated OST during P3-P4 (July - December 2010) have completing at least 6 months of continuous treatment on OST. Curently OST is provided in three sites: Republican Narcological Dispensary, Balti Municipal Hospital and the Department of Penitentiary Institutions (in 7 penitenciaries).
P8 |  | A total of 182 advocates and lawyers from the system of legal assistance guaranteed by the state have been trained during S3 within 8 training courses on human rights, non-discrimination, confidentiality and reparation for moral prejudices of people living with HIV.
P9 |  | A total of 40 free legal consultancies were offered remotely by 3 lawyers by travelling to project sites , during S3; they offered legal assistance related to issues of legal, civil (including disclosure of HIV status), administrative nature to all PLHIV in need.
P10 |  | 196 representatives of NGOs providing services to PLHIV were trained during S3. 40 participants were attending Romanian language course (B1 and B2 level) and 39 people have followed Romanian language courses (C1 level). 39 persons were trained in developing and improving service quality of self-support groups; 29 people were trained in fundraising and procurement; 23 people were trained in NGO management and 26 in advocacy.
Menu

## Actions
Dashboard: Moldova - HIV / AIDS
| Round 8 | Phase 1 |  |  |  | Report Period: |  | P6
| Latest Rating: | A2 |  | PAS Center |  | From: |  | January 01, 2011
|  |  | Reducing HIV-related burden in the Republic of Moldova |  |  |  | To: | June 30, 2011
Decisions and Actions
What is the overall status of this grant implementation?
| Key Recommendations from Oversight Group(s) |  |  |  | CCM Decision | Due Date | Person Responsible
Current Reporting Period
Actions to Implement / Previous Period
What is the overall status of this grant implementation?
| CCM Decision |  |  |  | Action Taken | Date | Person Responsible
Previous Reporting Period
Menu

## Setup (hidden)
Dashboard: Moldova - HIV / AIDS
Set-up = List of validation for Grant Detail page
Component | Currency | Round | Phase | Period | Rating | LFA | Medicaments | Countries
Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select
HIV / AIDS | $ | Round 1 | Phase 1 | P1 | A1 | CA (Crown Agents) | Isoniazid | Afghanistan
MALARIA | € | Round 2 | Phase 2 | P2 | A2 | DEL (Deloitte) | Ethambutol | Albania
TB |  | Round 3 | RCC | P3 | B1 | DTT (DTT Emerging Markets) | Rifampicin | Algeria
HIVAIDS / TB |  | Round 4 |  | P4 | B2 | FIN (Finconsult) | Pyrazimamide | Angola
HSS |  | Round 5 |  | P5 | C | GT (Grant Thornton) | RDT | Argentina
|  | Round 6 |  | P6 |  | H-C (Hodar-Conseil) | NVP | Armenia
|  | Round 7 |  | P7 |  | KPMG (KPMG) | 3TC | Azerbaijan
|  | Round 8 |  | P8 |  | MSCI (MSCI) | D4T | Bangladesh
|  | Round 9 |  | P9 |  | PwC (PricewaterhouseCoopers) | AZT | Belarus
|  | Round 10 |  | P10 |  | STI (Swiss Tropical Institute), | DDI | Belize
|  |  |  | P11 |  | UNOPS | EFV | Benin
|  |  |  | P12 |  |  | AS/LF | Bhutan
[7 empty] | AS/AQ | Bolivia
[7 empty] | AS/MQ | Bosnia and Herzegovina
[7 empty] | Al/Lum | Botswana
Brazil
[7 empty] | TB nutri'l supplements | Bulgaria
[7 empty] | E-PAP | Burkina Faso
Burundi
Cambodia
Cameroon
Cape Verde
Central African Republic
Chad
Chile
China
China
Colombia
Comoros
Congo (Democratic Republic of the)
Congo (Republic of the)
Costa Rica
Cote d'Ivoire
Croatia
Cuba
Djibouti
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Ethiopia
Fiji
Gabon
Gambia
Georgia
Ghana
Global(LWF)
Guatemala
Guinea
Guinea-Bissau
Guyana
Haiti
Honduras
India
Indonesia
Iran (Islamic Republic of)
Iraq
Jamaica
Jordan
Kazakhstan
Kenya
Korea, Democratic Peoples Republic of
Kosovo (Serbia)
Kyrgyzstan
Lao PDR
Lesotho
Liberia
Macedonia, FYR
Madagascar
Malawi
Maldives
Mali
Mauritania
Mauritius
Moldova
Mongolia
Montenegro
Morocco
Mozambique
Multi-country Africa (West Africa Corridor Program)
Multi-country Africa(RMCC)
Multi-country Americas (Andean)
Multi-country Americas (CARICOM)
Multi-country Americas (CRN+)
Multi-country Americas (Meso)
Multi-country Americas (OECS)
Multi-country Americas (REDCA+)
Multi-country Western Pacific
Myanmar
Namibia
Nepal
Nicaragua
Niger
Nigeria
Pakistan
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Romania
Russian Federation
Rwanda
Sao Tome and Principe
Senegal
Serbia
Sierra Leone
Solomon Islands
Somalia
South Africa
Sri Lanka
Sudan
Suriname
Swaziland
Syrian Arab Republic
Tajikistan
Tanzania
Thailand
Timor-Leste
Togo
Tunisia
Turkey
Uganda
Ukraine
UN Theme Group on HIV/AIDS (West Bank and Gaza)
Uzbekistan
Viet Nam
Yemen
Zambia
Zanzibar (Tanzania)
Zimbabwe