## Menu
Dashboard: Moldova - HIV / AIDS
HIV / AIDS SSF (Round 8), Phase 1 | Grant No.: MOL-809-G06-H
V1.0
Finance
Programmatic
Management
Select the option you want to see:
Recommendations
Actions
Grant Detail
List of Indicators
Data Entry
Grant Information
Indicators
Reports

## List of Indicators
Dashboard: Moldova - HIV / AIDS
Financial information
Name: | Definition | Measurement |  | Data Sources
F1: Budget and disbursements by Global Fund | Cumulative budget: Sum of the grant budget from period one (quarter, trimester, or semester) of the current phase, up to and including the dashboard reporting period. Cumulative Disbursments by GF: Sum of all the funds transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to and including the dasboard reporting period. | Currency of the grant ($ or Euro) Cumulative – Figures refer to budget and disbursements for all the periods of the phase up to and including the dashboard reporting period |  | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F2: Budget and actual expenditures by Grant Objective | Cumulative Budget per Objective: Sum of the grant budget by Objective, from period one of the current phase up to and including the dashboard reporting period. Cumulative Expenditure per Objective: Sum of amounts spent by Objective directly by the PR plus the amounts transferred by the PR to all SRs from the beginning of the phase up to and including dashboard reporting period, by Objective | • Cumulative – Figures refer to budget, disbursements or expenditure for all the periods of the phase up to and including the dashboard reporting period. |  | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F3: Disbursements and expenditures | Disbursement by GF: Prior to this Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to but not including dashboard reporting period. Disbursement by GF: Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), during dashboard reporting period. PR disbursements and expenditure: Prior to this Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) up to but not including dashboard reporting period. PR disbursements and expenditure: Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) during dashboard reporting period. Disbursements to SRs: Prior to this Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), up to but not including dashboard reporting period. Disbursements to SRs:Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), in dashboard reporting period. SR expenditures: Prior to this Reporting period: The sum of all expenditures reported by the SRs, up to but not including dashboard reporting period. SR expenditures: Reporting period: The sum of all expenditures reported by the SRs, during dashboard reporting period. | Currency of the grant ($ or Euro) • Reporting period – Figures refer to budget, disbursements or expenditure for the reporting period to which the dashboard refers. • Prior to reporting period - Figures refer to the total budget, disbursements or expenditure for all the periods before but not including the current period. |  | PU/DR; PR data: SR reports to PR
F4: Latest PR reporting and disbursement cycle | Days taken to submit final PU/DR to LFA – This indicator measures the number of calendar days it took the PR to send a final Performance Update and Disbursement Request (PU/DR) to the LFA after the end of the period. A 'final' PU/DR would be one for which the LFA did not require any further clarifications from the PR. The expected value is 45 days from the end of the period, as defined in the Grant Agreement. The actual value is the number of calendar days from the end date of the period to the date on which the PR sent to the LFA the final PU/DR. Days taken for disbursement to reach PR – This indicator measures the number of calendar days it took the Global Fund to send the latest disbursement to the PR's account after receipt of the acceptable PU/DR by the LFA. The expected number is 45 days. The actual number is the number of days from the date of transmission by the PR to the LFA of the acceptable PU/DR to the date the disbursement is received by the PR at its bank. Days taken for disbursement to reach SRs – This indicator measures the average number of days for disbursements to be made to all the SRs. The expected value for this indicator will be set locally by the PR and SRs, preferably in the Grant Operations Manual. The actual value is the average of the number of days from the receipt of the funds from the GF by the PR to the date the funds are received by each SR. Different SRs coudl receive funds on different dates and this indicator is the average across all SRs for the latest disbursement. | Number of calendar days; it refers only to reporting period for which the latest disbursement was received and is not cumulative |  | PR, LFA, GF emails and records; bank notification document or the notice of receipt by the PR to GF; SR reports to PR based on bank records
Management Information
Name: | Definition | Measurement |  | Data Source
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) | Number of Conditions Precedent (CPs) and Time Bound Actions (TBAs ) fulfilled, or unfulfilled. Within the Unfulfilled category, we distinguish between those CPs and TBAs whose deadline has not passed and those for which the deadline has passed. | Number, cumulative to the dashboard reporting period. Number of fulfilled CPs and/or TBAs plus unfulfilled CPs and/or TBAs should equal the total number set by the Global Fund on the grant |  | PR records; Grant Performance Reports;
M2: Status of key PR management positions | Number of PR grant management positions planned currently filled or vacant. Full time equivalents of the managerial positions that are on the organizational chart (or otherwise planned) and directly responsible for ensuring grant implementation at the PR, and lead SRs (if necessary). This will include new hires, current staff who are assigned to work on the grant’s management, as well as any staff seconded from other divisions or partner organizations. | Number, in current reporting period |  | PR records
M3: Contractual arrangements (SRs) | Identified: Total number of potential SRs identified by the PR for the phase. Assessed: Total number of potential SRs assessed by the PR to determine whether they qualify to function as SRs for the grant. Approved: Total number of SRs that have been approved. Signed: Total number of SRs that have signed agreements/contracts with the PR under the grant. Receiving funding: Total number of SRs that are getting funds and/or supplies from the PR. Numbers of SRs Identified, Assessed, Approved, Signed and Receiving funds are cumulative for the phase, with the following exceptions: If an SR does not need new approval in Phase II, then approval in Phase I is counted. If an SR was signed in a previous Phase but is not working in the current Phase, that SR is no longer counted in Identified, Assessed, Approved. | Number, cumulative to the reporting period. A SR is an institution or program with its own workplan, budget and performance targets. |  | PR records; Sub-agreements/MOUs; CCM records
M4: Number of complete reports received on time | The total number of periodic reports with up-to-date financial, management and performance (programmatic) data received by the PR from SRs and by SRs from the SubSRs (SSRs) by the expected date. A 'complete' report is one that contains all the data that the PR requires for the PU/DR. The expected date would be set by the PR in the sub-agreements. | Number of reports received. The figure reflects only the period of reporting; it is not cumulative. |  | PR and SR records
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals | This indicator measures the budget approved for the current phase of the grant for purchase of health products and equipment and pharmaceuticals and medicines (categories 4 and 5 in the new Enhanced Financial Report), and the cumulative amounts of financial obligations and expenditures up to the dashboard reporting period. Budget approved: Total approved budget for purchases (categories 4 and 5) for the entire phase of the grant. It does not include the amounts for fees, management, operational costs, etc. Cumulative Obligations: Total of all order(s) placed and monies committed for these purchases by the PR up to and including the dashboard reporting period. Ideally, by the end of the Phase, budget should equal obligations. Cumulative expenditure: Total of actual Expenditures on category 4 and 5 up to and including the dashboard reporting period (whether paid by PR or authorized to be paid by another entity like GF or other). | Currency of the grant ($ or Euro) |  | Grant agreement approved budget (for categories 4 and 5 of Enhanced Finance Reporting in current phase); and PR financial data (for expenditures), and/or PSM unit (for orders placed and funding committed or obligated).
Note: Category 6 of the EFR will not be considered as part of the budget for pharmaceuticals. Category 6 has several expenditures that are difficult to disaggregate or quantify, such as warehousing costs, distribution costs (particularly when distibution is done by MOHs), and others that are related to operational costs of the PSM component.
M6: Difference between current and safety stock | This indicator is a snapshot of the difference between the current (or last month) stock level of a specific product (medicine in single, fixed-dose combination, bednets, diagnostic kits, etc.) of a particular dose, expressed in monthly needs (number of months of treatment available) for all patients in the program, and the safety or buffer stock (also expressed in months) as established by the disease program, warehouse system or essential drugs program, for the particular product and dosage. The table will show the difference in months in colors: • RED: when the difference is negative or 0, showing that months of existing stock are lower than or equal to what has been established as months of safety stock • YELLOW: when we have more than the level of safety stock (>0) but less than 3 months (+3). • GREEN: when the difference is between 3 and 18 months. • VIOLET: When the difference shows that the level above the safety stock is greater than or equal to 18 months indicating a potential overstock) problem. For a full description of how this indicator is calculated, please see the User’s Manual. | Number of months |  | PR records: Warehouse data.
Programmatic Indicators (from Performance Framework)
Indicator | Definition (from M&E Plan, September 2009) | Measurement |  | Data Source
Number of medical (doctors and nurses) and non-medical staff (psychologists, social assistants, peer consultants) trained in HIV/AIDS | It is a composite indicator, related activities: capacity building of health specialists from the ART treatment facilities in HIV/AIDS case management abroad; capacity building in HIV/AIDS management for the non-medical staff from the MDT teams; increasing knowledge on HIV/AIDS in staff of the Medical Colleges; training of medical staff in palliative care; training of infectious diseases specialists and primary care specialists; incipient trainings for the e-learning course ; training of the staff of the Ministry of Social Protection in HIV/AIDS (strategic planning, M&E etc) | all persons who signed the list of participation at training |  | List of participants trained
Number of PLWHA receiving palliative care | HIV infected patients that receive palliative care services within the ARV Treatment facility during reported period (care of skin, hair, nails, eyes, mouth, pneumonia prophylactic treatment, symptomatic treatment, alimentation, etc.). | all persons who received services during the reported period |  | Register of beneficiaries
Number of PLWHA receiving food parcels to improve ARV treatment adherence | PLWHA is considered "reached" if he/she has received at least one food package per month during 3 consecutive months. | new persons who received services during the reported period |  | Database
Number of children infected and affected by HIV/AIDS who receive social support | The social support includes food parcels, clothing and school supplies. | new children who received services during the reported period | all persons who received services during the reported period | Database
Number of IDUs on oppoid substitution therapy that receive at least 3 support services from NGOs working in DUs rehabilitation | The beneficiaries are provided with the following services: psycho-social support, self-support groups, peer to peer education, distributions of information materials, etc. The beneficiary is considered "reached" if he/she has received at least three of the services listed. | new persons who received at least 3 support services during the reported period |  | Database
Number and percentage of individuals currently on OST who have been on OST continuously at least 6 months for the past 12 months | Numerator: number of individuals completing at least 6 months of continuous treatment on OST that initiated treatment 6-12 months prior to the end of the reporting period. Denominator: total number of individuals that initiated treatment 6-12 months prior to the end of the reporting period. The indicator is linked to percentage, absolute numbers will be provided when reporting results. The targets refer to the patient cohort (both new and repeated cases) that initiated treatment in the first 6 months of the last 12 months period. | determine the number of people who initiated TS (first time as well as repeated) in the first six months of the last 12 months and assessed how many of these people remained in continuous TS at least 6 months |  | Register of beneficiaries
Number of people living with HIV/AIDS reached with care and support services | The beneficiaries are provided with the following services: psycho-social counseling and registration, distribution of information materials and peer health counseling. The beneficiary is considered "reached" if he/she has received at least one of the three listed services. | new persons who received at least 3 support services during the reported period |  | Database
Number of lawyers from the free legal system and ombudsmen institutes trained in HR, non-discrimination and principles of legal aid. | It is a composite indicator, related activities: training of lawyers from the free legal aid system guaranteed by the state and training on HR, non-discrimination, reparations for moral prejudice and principles of legal aid for lawyers and the Ombudsment Institute | all persons who signed the list of participation at training |  | List of participants trained
Number of human rights strategic litigation cases for PLWH initiated. | Human rights strategic litigation cases for PLWH initiated. | total number of human rights strategic litigation cases registered in the register |  | Register of beneficiaries
Number of PLWHA assisted by legal aid (consultancies offered by legal network) | PLWHA receiving legal aid offered by legal network | all persons who received services during the reported period |  | Register of beneficiaries
Number of the PLWHA League members trained in languages, strategic planning, M&E etc. | It is a composite indicator, related activities: trainings for the members of the league and capacity building of the members of the League in languages and in strategic planning, M&E etc | all persons who signed the list of participation at training |  | List of participants trained
Indicator Number: Name (Perf Framework No.) | Definition | Measurement |  | Data Source
The indicators should be selected by the PRs and members of the CCM or the CCM Technical Committee, from the Performance Framework |  |  |  | Performance Framework
Menu

## Data Entry
Grant information
| Country: | Moldova |  | Title of the Grant: |  | Reducing HIV-related burden in the Republic of Moldova
| Grant No.: | MOL-809-G06-H |  | Component: |  | HIV / AIDS | Total Funding: | 8430291
| Principal Recipient: | PAS Center |  |  | Round: | SSF (Round 8) | Phase: | Phase 1
| Start Date (dd/Mmm/yy): | January 01, 2010 |  | Local Fund Agent: |  | PwC (PricewaterhouseCoopers)
| Latest Rating: | A1 |  | Fund Portfolio Manager: |  | Nicolas Cantau
Information reporting period
| Report Period: | P8 | From: | July 01, 2011 | To: | December 31, 2011 | Date of entry of information: |  | March,2012
| Prepared by: |  | PAS Center
Information on indicators
Enter the data based on the colour-coded cells
| Financial Information: |  | Management Information: |  |  | Programmatic Information:
| Financial Information: | [8 empty] | Enter finance data in every orange cell like this.
| Currency of the grant |  | €
F1: Budget and disbursements by Global Fund
| Disbursement | [15 empty] | 0
| Reporting period | [5 empty] | P1-P6 | P7 | P8 | P9 | P10 | P11 | P12 | % Cumulative |  |  | 0
| Budget (in €) | [5 empty] | 4589159 | P7: 695010.9167; P8: 895030.9167 | 92.52% |  |  | 0
| Disbursements by GF (in €) | [5 empty] | 5716813 | [9 empty] | 0
| Cumulative budget | [5 empty] | 4589159 | 5284169.9167 | 6179200.8333 | 0 | 0 | 0 | 0 |  |  |  | 0
| Cumulative disbursements | [5 empty] | 5716813 | 5716813 | 5716813 | 0 | 0 | 0 | 0 |  |  |  | 4589159
|  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 92.52% | 0% | 0% | 0% | 0% |  |  |  | 5284169.9167
F2: Budget and actual expenditures by Grant Objective
| Grant Objective | Cumulative Budget (in €) | Cumulative Expenditures (in €)
| Improve performance of GFATM Round VI through improved infrastructure | 753747 | 696520.4958
| Improve quality of Life of PLWH | 3971438.8333 | 3779414.678
| Strengthen the National League of PLWH | 610298 | 506169.7023
| Planning and administration | 843717 | 805991.7854
| Total | 6179200.8333 | 5788096.6616 |  | OK: Data match | bar: P7
| F3: Disbursements and expenditures | [15 empty] | 6179200.8333
0
|  | Prior to reporting period | Current reporting period | Total Spent and Disbursement (in €) | [11 empty] | 0
| Disbursed by Global Fund | 5716813 |  | 5716813
| PR expenditure and disbursement | 4589159 | 1198937.66 | 5788096.66
| Disbursed to SRs | 2696495 | 751329.31 | 3447824.31
| SR expenditures | 2307668.9537 | 974918 | 3282586.9537
F4: Latest PR reporting and disbursement cycle
Last fund disbursement: Number of calendar days
|  | Expected (days) | Actual (days)
| Days taken to submit final PU/DR to LFA | 45 | 35
| Days taken for disbursement to reach PR | 45 | 206
| Days taken for disbursement to reach SRs | 20 | 5
| Management Information: | [5 empty] | Enter management data in every blue cell. | bar: P10
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs)
|  |  | Fulfilled | Not fulfilled, but within deadline | Not fulfilled, and past the deadline | Total
| Conditions precedent (CPs) |  | 5 |  |  | 5
| Time Bound Actions (TBAs) |  |  |  |  | 0
M2: Status of key PR management positions
|  | Planned | Filled | Vacant
| PMU | 11 | 13 | -2
M3: Contractual arrangements (SRs)
|  | Identified | Assessed | Approved | Signed | Receiving Funding
| SRs | 4 | 4 | 4 | 4 | 3
M4: Number of complete reports received on time
|  | # Expected | # Received | Pending
| SSR to SR | 23 | 21 | 2
| SRs to PR | 3 | 3 | 0
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals
|  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
Budget Approved*
Obligations
Expenditures
| Budget Approved cumulative* | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Obligations cumulative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Expenditures cumulative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
* Includes only EFR category 4 and 5 (Health products and health equipment & Medicines and Pharmaceuticals)
M6: Difference between current and safety stock
| Component | Products | (1) Number of tablets per patient per day (Review country treatment guidelines) | (2 = 1 x 30) Monthly treatment (Tablets per patient x 30 days) | (3) Total patients in treatment | (4 = 2 x 3) Total # tab/pills required for all patients per month | (5) Current stock in central warehouse (that does not expire within the next 3 months) | (6 = 5 / 4) Stock level expressed in months of treatment for all current patients | (7) Level of safety stock (expressed in months and defined by country) | (8 = 6 - 7) Difference between current stock and safety stock
| HIV / AIDS | P1: Please Select
Please Select
Please Select
Please Select
| Programmatic Information: | P9: Enter performance data in every yellow cell.
| Programmatic indicators (Performance Framework ) |  |  | Code | Directly Tied? |  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
TOP 3 | Number of people living with HIV/AIDS reached with care and support services (Numărul persoanelor care trăiesc cu HIV / SIDA au primit suport social) |  |  | 1.7. | Yes | Target | 3250 | 3500 | 3750 | 4000 | 4375 | 4750 | 4832 | 5207
[6 empty] | Achieved | 2093 | 2817 | 3197 | 3717 | 3976 | 4296 | 4564 | 4853
| Number of IDUs on oppoid substitution therapy that receive at least 3 support services from NGOs working in DUs rehabilitation (Numărul de UDI care sunt în terapia de substituţie cu metadonă şi primesc cel puţin 3 servicii de suport din partea ONG-urilor care lucrează la reabilitarea UDI) |  |  | 1.5. | Yes | Target | 54 | 108 | 162 | 216 | 280 | 344 | 407 | 471
[6 empty] | Achieved | 61 | 131 | 180 | 225 | 284 | 322 | 368 | 437
| Number of medical (doctors and nurses) and non-medical staff (psychologists, social assistants, peer consultants) trained in HIV/AIDS (Numărul personalului medical (medici şi aistente medicale) şi non-medical (psihologi, asistenţi sociali, educatori de la egal la egal) instruiţi în HIV/SIDA) |  |  | 1.1. | Yes | Target | 25 | 150 | 225 | 400 | 500 | 625 | 1224 | 1410
[6 empty] | Achieved | 50 | 174 | 268 | 594 | 788 | 1099 | 1224 | 1395
| Number of PLWHA receiving palliative care (Numărul de PTH care primesc îngrijiri paliative) |  |  | 1.2. | No | Target | n/a | n/a | n/a | 15 | 20 | 25 | 39 | 44
[6 empty] | Achieved | n/a | n/a | n/a | 7 | 18 | 34 | 49 | 59
| Number of PLWHA receiving food parcels to improve ARV treatment adherence (Numărul de PTH care primesc pachete alimentare pentru a îmbunătăți aderenţa la tratamentul ARV) |  |  | 1.3. | Yes | Target | 108 | 216 | 324 | 432 | 573 | 715 | 1011 | 1061
[6 empty] | Achieved | 108 | 269 | 462 | 588 | 803 | 961 | 1134 | 1257
| Number of children infected and affected by HIV/AIDS who receive social support (Numărul de copii infectaţi şi afectaţi de HIV/SIDA care primesc suport social) |  |  | 1.4. | Yes | Target | 95 | 125 | 155 | 185 | 216 | 248 | 352 | 372
[6 empty] | Achieved | 91 | 133 | 195 | 236 | 298 | 332 | 363 | 395
| Number and percentage of individuals currently on OST who have been on OST continuously at least 6 months for the past 12 months (Numărul şi procentul persoanelor aflate în tratamentul de substituție cu metadonă (TS) care au fost în TS continuu cel puțin 6 luni pe parcursul ultimelor 12 luni) |  |  | 1.6. | No | Target | n/a | n/a | n/a | n/a | n/a | 50% | n/a | 55%
[6 empty] | Achieved | n/a | n/a | n/a | n/a | n/a | 53.18% | n/a | 56.04%
| Number of lawyers from the free legal system and ombudsmen institutes trained in HR, non-discrimination and principles of legal aid (Numărul de avocaţi din sistemul juridic gratuit şi institutele de mediatori instruiţi în drepturile omului, non-discriminării şi a principiilor de asistenţă juridică) |  |  | 1.8. | Yes | Target | 50 | 100 | 150 | 200 | 250 | 300 | 526 | 601
[6 empty] | Achieved | 51 | 102 | 152 | 244 | 294 | 426 | 524 | 602
| Number of PLWHA assisted by legal aid (consultancies offered by legal network) (Numărul PTH furnizate cu ajutor juridic (consultaţii oferite de către reţeaua juridică)) |  |  | 1.10. | Yes | Target | 10 | 20 | 30 | 40 | 55 | 70 | 212 | 242
[6 empty] | Achieved | 25 | 78 | 108 | 142 | 163 | 182 | 210 | 251
| Number of the PLWHA League members trained in languages, strategic planning, M&E etc.(Numărul de membri ai Ligii PTH instruiţi în limbi, planificare strategică, M&E, etc.)) |  |  | 1.11. | Yes | Target | 35 | 70 | 105 | 140 | 190 | 240 | 390 | 440
[6 empty] | Achieved | P2: 78; Enter performance data in every yellow cell. P6: 340; Enter performance data in every yellow cell. P7: 411; Enter performance data in every yellow cell. P8: 542
| Table is automatically updated. No data or information is to be entered here. |  |  | Code | Directly Tied? |  | 0 | 0 | 0 | 0 | 0 | P1-P6 | P7 | P8 | P9 | P10 | P11 | P12
| Number of people living with HIV/AIDS reached with care and support services (Numărul persoanelor care trăiesc cu HIV / SIDA au primit suport social) |  |  | 1.7. | Yes | Target | 3250 | 3500 | 3750 | 4000 | 4375 | 4750 | 4832 | 5207 | 0 | 0 | 0 | 0
[6 empty] | Achieved | 2093 | 2817 | 3197 | 3717 | 3976 | 4296 | 4564 | 4853 | 0 | 0 | 0 | 0
| Number of IDUs on oppoid substitution therapy that receive at least 3 support services from NGOs working in DUs rehabilitation (Numărul de UDI care sunt în terapia de substituţie cu metadonă şi primesc cel puţin 3 servicii de suport din partea ONG-urilor care lucrează la reabilitarea UDI) |  |  | 1.5. | Yes | Target | 54 | 108 | 162 | 216 | 280 | 344 | 407 | 471 | 0 | 0 | 0 | 0
[6 empty] | Achieved | 61 | 131 | 180 | 225 | 284 | 322 | 368 | 437 | 0 | 0 | 0 | 0
| Number of medical (doctors and nurses) and non-medical staff (psychologists, social assistants, peer consultants) trained in HIV/AIDS (Numărul personalului medical (medici şi aistente medicale) şi non-medical (psihologi, asistenţi sociali, educatori de la egal la egal) instruiţi în HIV/SIDA) |  |  | 1.1. | Yes | Target | 25 | 150 | 225 | 400 | 500 | 625 | 1224 | 1410 | 0 | 0 | 0 | 0
[6 empty] | Achieved | 50 | 174 | 268 | 594 | 788 | 1099 | 1224 | 1395 | 0 | 0 | 0 | 0
Note on B30: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.
Note on B72: If data are not available, do not enter zeros; rather, leave the cells in the table blank.
Note on B73: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B79: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B94: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.
Menu

## Grant Detail
Dashboard: Moldova - HIV / AIDS
Country: | Moldova |  | Title of the Grant: |  | Reducing HIV-related burden in the Republic of Moldova
Component: | HIV / AIDS | Grant No. | MOL-809-G06-H | Start Date: |  | January 01, 2010 | Total Funding | 8430291
Round: | SSF (Round 8) | Phase: | Phase 1 | Principal Recipient: |  | PAS Center
Report Period: | P8 | from: | July 01, 2011 | to: |  | December 31, 2011 | Latest Rating: | A1
Local Fund Agent: | PwC (PricewaterhouseCoopers) |  |  | Fund Portfolio Manager: |  | Nicolas Cantau
Prepared by: | PAS Center |  |  | Report preparation date: |  | March,2012
http://www.crwflags.com/fotw/flags/country.html
Menu

## Finance
Dashboard: Moldova - HIV / AIDS
SSF (Round 8) | Phase 1 |  |  |  | Report Period: |  | P8
Latest Rating: | A1 |  | PAS Center |  | From: |  | July 01, 2011
|  | Reducing HIV-related burden in the Republic of Moldova |  |  |  | To: | December 31, 2011
Financial Indicators
F1: Budget and disbursements by Global Fund - in (€) Report Period: P8 |  |  |  | F3: Disbursements and expenditures - in (€) Report Period: P8
Comments: | In Semester 2, 2011 the R8 HIV (grant number MOL-809-G06-H) implemented by the Center for Health Policies and Studies (PAS Center) has been consolidated into a Single Stream of Funding. The SSF implementation and commitment period for the HIV program under PAS Center run from July 2011 until the end of December 2012. The PU for semester 1, 2011 and DR for Semester 2, 2011 (period one of SSF) have been submitted to GF on August 02, 2011, yet no funds have been received for the implementation of the SSF by the end of year 2011. To mention that grant fund have been exhausted since December 2011, even despite the fact that budgeted funds for first semester under SSF for SRs have not been fully disbursed (ex, SR- SFM – disbursement for S1 SSF was smaller), some payments under contracts have been delayed, new commitments to be made in accordance with the work plan have been postponed. The disbursement for period one of SSF has only been performed on February 23, 2012 (206 days after the DR). |  |  | Comments:
F2: Budget and actual expenditures by Grant Objective - in (€) Report Period: P8 |  |  |  | F4: Latest PR reporting and disbursement cycle Report Period: P8
Comments: | Variance between budget and expenditure mainly due to funds committed/forecasted for equipment for RSCs, trainings, guides, software, clinical protocols, mhealth project, etc. that could not be disbursed due to lack of funds. The start of some activities and procurement of equipment have been delayed. |  |  | Comments: | The DR for Semester 2, 2011 (period one of SSF) has been submitted to GF on August 02, 2011, yet the disbursment reached PR only on February 23, 2012 (206 days after the DR).
Last fund disbursement: Calendar days
[6 empty] | Expected (days) | Actual (days)
|  |  |  | Days taken to submit final PU/DR to LFA |  | 45 | 35
|  |  |  | Days taken for disbursement to reach PR |  | 45 | 206
|  |  |  | Days taken for disbursement to reach SRs |  | 20 | 5
Menu

## Management
Dashboard: Moldova - HIV / AIDS
SSF (Round 8) | Phase 1 |  |  |  |  | Report Period: |  | P8
Latest Rating: | A1 |  | PAS Center |  |  | From: |  | July 01, 2011
|  | Reducing HIV-related burden in the Republic of Moldova |  |  |  |  | To: | December 31, 2011
Management Indicators
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) Report Period: P8 |  |  |  | M2: Status of key PR management positions Report Period: P8
Comments: | All five conditions precedent and/or other special conditions have been fulfilled in strict accordance with their provisions and timeline. |  |  | Comments: | Two full time positions and 11 part time.
M3: Contractual arrangements (SRs) Report Period: P8 |  |  |  | M4: Number of complete reports received on time Report Period: P8
Comments: | Four Sub-recipients (SRs) have been identified to implement different components within the program: Soros Foundation-Moldova (SFM); League of people living with HIV of Moldova; New Life, Moldovan Institute for Human Rights. One SR (SFM) has been earlier assessed by the governmental PR of GF grants as it acts as an SR since GF Round one. Two other SRs have been assessed (New Life and Moldovan Institute for Human Rights) were assessed by PAS Center the last one (League of people living with HIV of Moldova) by GF Local Fund Agent. Following the assessments four sub-grant agreements have been signed. In September 2011, due to lack of capacity for adequate implementation of the grant portion contracted the sub-grant agreement with one of the SRs (League of people living with HIV) was terminated and the management of activities has been entrusted to SFM. Respectively three sub-recipients are currently receiving funds within the grant. |  |  | Comments: | The SRs’ quarterly reports (financial report, activity report and performance framework) are due to the PR not later than 25 days after the close of each quarter and are generally submitted in time. The clearance period vary from one SR to an other subject to the completeness and consistence of the reports. The clearance of reports for SR IDOM for Q3, 2011 has lasted for one and a half month due to the identification of a series of violations and ended with refund of amounts that was not used in accordance with the terms and conditions of the Sub-grant agreement. For the SR SFM the Sub-subrecipients financial reports are due quarterly and can be submitted during the following quarter, the activity reports are due not later than 10 days from the end of each month and are generally submitted in time except one Ssr - NGO Master in Public Health – that is constantly late in reporting. During the reporting period reflected in this dashboard the organization Your Generation, Drochia that received a small grant for World AIDS Day has substantially delayed the report. For the SR New Life the reports (financial, activity and indicators) are due not later than 15 days after the close of each quarter and are generally submitted in time.
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals |  |  |  | M6: Difference between current and safety stock Report Period: P8
Comments: | N/A |  |  | Comments: | N/A
|  |  |  | Component | Products | Stock level expressed in months of treatment for all current patients | Months of safety stock | Difference between current stock and safety stock
|  |  |  | HIV / AIDS | Please Select |  | 0
[5 empty] | Please Select |  | 0
[5 empty] | Please Select |  | 0
[5 empty] | Please Select |  | 0
* Includes only EFR category 4 and 5 (Health products and health equipment & Medicines and Pharmaceuticals)
Menu

## Programmatic
Dashboard: Moldova - HIV / AIDS
SSF (Round 8) | Phase 1 | [8 empty] | Report Period: |  | P8
Latest Rating: | A1 |  | PAS Center | [7 empty] | From: | July 01, 2011
|  | Reducing HIV-related burden in the Republic of Moldova | [8 empty] | To: | December 31, 2011 | [7 empty] | Raiting |  | Valor
Programmatic Indicators
Number of people living with HIV/AIDS reached with care and support services (Numărul persoanelor care trăiesc cu HIV / SIDA au primit suport social) |  |  |  | Number of IDUs on oppoid substitution therapy that receive at least 3 support services from NGOs working in DUs rehabilitation (Numărul de UDI care sunt în terapia de substituţie cu metadonă şi primesc cel puţin 3 servicii de suport din partea ONG-urilor care lucrează la reabilitarea UDI) |  |  |  | Number of medical (doctors and nurses) and non-medical staff (psychologists, social assistants, peer consultants) trained in HIV/AIDS (Numărul personalului medical (medici şi aistente medicale) şi non-medical (psihologi, asistenţi sociali, educatori de la egal la egal) instruiţi în HIV/SIDA)
Comment: P1 | The main part of PLHIV have been reached by project: from the 5,383 PLHIV by the end December 2011 (prevalence) a total of 4,853 were covered with care and support services. Currently the number of new PLHIV that can be covered with support services is mostly related to new people diagnosed with HIV. To mention that not every PLHIV will be covered with support due to refusal to receive psycho-social services, migration, etc. |  |  | Comment: P2 | Due to the fact that the main number of the OST clients were reached (those who received at least 3 or more services), at present we reach out the new OST clients. Respectively the number of potential new OST clients to be reached with support services is directly related to the new entries in OST treatment. |  |  | Comment: P3 | One training planed for S2, 2011 has been postponed for S1, 2012 due to the fact that the teams of RSCs planned to be trained in case management were not complete by the end of year 2011.
Indicators |  |  | Target (cumulative over program term) | Achieved (cumulative over program term) | 0% - 59% | 60% - 89% | > 90% | Comments |  |  |  |  | min | 0 | 30% | 60% | 90% | 100% |  | min | 0 | 20% | 40% | 60% | 80%
Number of people living with HIV/AIDS reached with care and support services (Numărul persoanelor care trăiesc cu HIV / SIDA au primit suport social) |  |  | 5207 | 4853 | 93.2% |  |  | During S4 a total 557 PLHIV were primarily reached with care and support services from 10 organizations work in this area. The beneficiaries are provided with the following services: psycho-social counseling and registration, medical consultations, distribution of informational materials and peer health counseling, referral services provided by public institutions, self support groups, etc. (în semestrul 4, 557 de PTH au fost primari acoperiți cu îngrijire şi suport în cadrul a 10 organizaţii care lucrează în acest domeniu. Beneficiariilor le sunt oferite următoarele servicii: consiliere psiho-socială, consultaţii medicale, distribuţia materialelor informaţionale şi consiliere de la egal la egal, servicii de referinţă furnizate de către instituţiile publice, grupuri de auto-suport, etc. ) |  |  |  |  | max | 30% | 60% | 90% | 100% | 200% |  | max | 20% | 40% | 60% | 80% | 100%
Number of IDUs on oppoid substitution therapy that receive at least 3 support services from NGOs working in DUs rehabilitation (Numărul de UDI care sunt în terapia de substituţie cu metadonă şi primesc cel puţin 3 servicii de suport din partea ONG-urilor care lucrează la reabilitarea UDI) |  |  | 471 | 437 | 92.78% |  |  | During S4 a total of 115 IDUs on oppioide substitution therapy (primarily reached) received at least 3 support services from the package (psychosocial support, self-support groups, peer to peer education, distributions of informational materials and food parcels) offered by NGOs working in DUs rehabilitation. (în timpul S4 un total de 115 de UDI aflați în terapia de substituţie cu metadonă (primari atinși) au primit cel puţin 3 servicii de suport social din pachetul (sprijin psiho-social, grupuri de suport reciproc, educație de la egal la egal, distribuţia de materiale informaţionale şi pachete alimentare și igienice) oferite în cadrul centrelor de zi de ONG-uri care lucrează în domeniul reabilitării UDI). | [5 empty] | de 0 a 0.3 | de 0.3 a 0.6 | de 0.6 a 0.9 | de 0.9 a 1 | de 1 a 2 | Rating | Valor | de 0 a 0.2 | de 0.2 a 0.4 | de 0.4 a 0.6 | de 0.6 a 0.8 | de 0.8 a 1
Number of medical (doctors and nurses) and non-medical staff (psychologists, social assistants, peer consultants) trained in HIV/AIDS (Numărul personalului medical (medici şi aistente medicale) şi non-medical (psihologi, asistenţi sociali, educatori de la egal la egal) instruiţi în HIV/SIDA) |  |  | 1410 | 1395 | 98.94% |  |  | A total of 296 persons trained in S4, from them: 27 medical staff were trained in international training in Clinica Lavra in various aspects such as "ARV adverse reactions:diagnoses and clinical management", "Viral Hepatitis B and C and HIV infection" and "Adverse reactions of ARV treatment: diagnosis and tactics" ; 78 non-medical staff from MDT under National Social Reference System were trained in Protection and assistance to victims of human trafficking, domestic violence and people living with HIV within the National Reference System; 15 laboratory personnel were trainded in "Laboratory Monitoring of HIV Infection and Antiretroviral Therapy, ARV drug resistance", 51 primary health care specialists were trained HIV infection; 102 social assistants in most affected regions were trained in HIV/AIDS; and 23 specialists from the Ministry of Social Protection were trained in HIV/AIDS. (un total de 296 persoane au participat la training-uri în semestrul 4, dintre care: 27 lucrători medicali au fost instruiţi la training-urile internaţionale organizate la Clinica Lavra, în mai multe aspecte, cum ar fi: „Reacţii adverse ale ARV:diagnostic, tactică” , „Hepatitele Virale B şi C şi infecţia HIV” şi „Reacţii adverse ale ARV:diagnostic şi managementul clinic”; 78 lucrători non-medicali din echipele multidisciplinare din cadrul Sistemului Naţional Social de Referinţă au fost instruiţi în protecţia şi asistenţa victimelor traficului uman, violenţa domestică şi PTH în cadrul Sistemului Naţional de Referire; 15 medici laboranţi au fost instruiţi în "Flowcitometria şi PCR+ metode de laborator utilizate în diagnosticul infecţiei cu HIV", 51 specialişti în asistenţă medicală primară au fost instruiţi în infecţia HIV; 102 asistenţi sociali din cele mai afectate regiuni au fost instruiţi în HIV/SIDA; şi 23 specialişti a Ministerului Protecţiei Sociale au fost instruiţi în HIV/SIDA). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number of PLWHA receiving palliative care (Numărul de PTH care primesc îngrijiri paliative) |  |  | 44 | 59 | 134.1% |  |  | 25 HIV infected patients received palliative care services within the ARV Treatment facility during reported period (care of skin, hair, nails, eyes, mouth, pneumonia prophylactic treatment, symptomatic treatment, alimentation, etc.). (25 de pacienţi infectaţi cu HIV au primit servicii de îngrijiri paliative în cadrul departamentului de tratament ARV în timpul perioadei raportate (îngrijire a pielii, părului, unghiilor, cavității bucale, ochilor, tratamentul profilactic al pneumoniei, tratamentul medicamentos simptomatic, alimentaţie, etc.)) | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number of PLWHA receiving food parcels to improve ARV treatment adherence (Numărul de PTH care primesc pachete alimentare pentru a îmbunătăți aderenţa la tratamentul ARV) |  |  | 1061 | 1257 | 118.5% |  |  | A total of 296 PLHIV received food parcels during S4 (primarily reached): 173 during Q7 and 123 during Q8. (Un număr total de 296 de PTH au primit pachete alimentre în timpul semestrului 4 (beneficiari unici): 173 – în timpul trimestrului 7 şi 123 în trimestrul 8). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number of children infected and affected by HIV/AIDS who receive social support (Numărul de copii infectaţi şi afectaţi de HIV/SIDA care primesc suport social) |  |  | 372 | 395 | 106.2% |  |  | A total of 63 children received social support during S4 (primarily reached): 31 children during Q7 and 32 children during Q8. (un număr total de 63 copii au primit suport social în timpul semestrului 4 (beneficiari unici): 31 de copii în timpul trimestrului 7 şi 32 – în trimestrul 8). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Number and percentage of individuals currently on OST who have been on OST continuously at least 6 months for the past 12 months (Numărul şi procentul persoanelor aflate în tratamentul de substituție cu metadonă (TS) care au fost în TS continuu cel puțin 6 luni pe parcursul ultimelor 12 luni) |  |  | 55% | 56.04% | 101.9% |  |  | A total of 51 individuals out of 91 that initiated OST during P5-P6 have completing at least 6 months of continuous treatment on OST. Currently OST is provided in three sites: Republican Narcological Dispensary, Balti Municipal Hospital and the Department of Penitentiary Institutions (in 7 penitentiaries). (un total de 51 de persoane din 91 care a initiat TS în timpul P5-P6 au finalizarea cel puţin 6 luni de tratament continuu. Actualmente TS este oferită in trei site-uri: Dispensarul Republican de Narcologie, Spitalul Municipal Bălţi şi Departamentul Instituţiilor Penitenciare (în 7 penitenciare)). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Number of lawyers from the free legal system and ombudsmen institutes trained in HR, non-discrimination and principles of legal aid (Numărul de avocaţi din sistemul juridic gratuit şi institutele de mediatori instruiţi în drepturile omului, non-discriminării şi a principiilor de asistenţă juridică) |  |  | 601 | 602 | 100.2% |  |  | A total of 176 lawyers have been trained during S4 within 7 training courses on human rights, non-discrimination, confidentiality and reparation for moral prejudices of people living with HIV. (un număr total de 176 de avocaţi au fost instruiţi în semestrul 4 în cadrul a 7 cursuri de instruire în drepturile omului, non-discriminarea, confidenţialitatea şi despăgubirea prejudiciile morale ale PTH). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Number of PLWHA assisted by legal aid (consultancies offered by legal network) (Numărul PTH furnizate cu ajutor juridic (consultaţii oferite de către reţeaua juridică)) |  |  | 242 | 251 | 103.7% |  |  | A total of 69 consultancies were offered remotely by traveling to project sites of 4 lawyers, during S4; they offered legal assistance related to issues of legal, civil (including disclosure of HIV status), administrative nature to all PLHIV in need. (pe parcursul semestrului 4 au fost oferite 69 de consultaţii în teren de către 4 avocaţi;aceștea au oferit asistenţă juridică pe aspecte de natură legală, civilă (incluzând divulgarea statutului HIV) şi administrative ale tuturor PTH care au solicitat ajutor). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Number of the PLWHA League members trained in languages, strategic planning, M&E etc.(Numărul de membri ai Ligii PTH instruiţi în limbi, planificare strategică, M&E, etc.)) |  |  | 440 | 542 | 123.2% |  |  | 202 representatives of NGOs providing services to PLHIV were trained during S4. 42 participants were attending Romanian language course (C2 level) and 39 people have followed Romanian language courses (C2 professional level). 29 persons were trained in “Non-Medical Services for PLHIV". A number of 42 participants attended English language course (elementary). A number of 27 participants took part in the training "Psycho-social assistance for HIV infected children and their families". A number of 23 participants took part in the training "Monitoring and Evaluation". (202 de reprezentanţi ai ONG-urilor care furnizează servicii PTH au fost instruiţi în semestrul 4. 42 de persoane au participat la cursurile de limbă română (nivelul C2) şi 39 de persoane au urmat cursuri de limbă română (nivelul C2 profesional). 29 de persoane au fost instruite în " Serviciile nemedicale acordate persoanelor care trăiesc cu HIV" , 42 de persoane au urmat cursuri de limbă engleză (nivelul elementar); 27 de persoane au participat la training-ul „Asistenţa psihosocială pentru copiii cu HIV şi familiile lor ” şi 23 de persoane au fost instruiți în monitorizare si evaluare). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Menu

## Recommendations
Dashboard: Moldova - HIV / AIDS
SSF (Round 8) | Phase 1 |  |  |  |  | Report Period: | P8
Latest Rating: | A1 |  | PAS Center |  |  | From: | July 01, 2011
|  |  | Reducing HIV-related burden in the Republic of Moldova |  |  | To: | December 31, 2011
Recommendations
Are all funds reaching implementation levels and being spent according to budget?
Financial |  | Summary Comments |  |  | Recommendations
F1 |  | In Semester 2, 2011 the R8 HIV (grant number MOL-809-G06-H) implemented by the Center for Health Policies and Studies (PAS Center) has been consolidated into a Single Stream of Funding. The SSF implementation and commitment period for the HIV program under PAS Center run from July 2011 until the end of December 2012. The PU for semester 1, 2011 and DR for Semester 2, 2011 (period one of SSF) have been submitted to GF on August 02, 2011, yet no funds have been received for the implementation of the SSF by the end of year 2011. To mention that grant fund have been exhausted since December 2011, even despite the fact that budgeted funds for first semester under SSF for SRs have not been fully disbursed (ex, SR- SFM – disbursement for S1 SSF was smaller), some payments under contracts have been delayed, new commitments to be made in accordance with the work plan have been postponed. The disbursement for period one of SSF has only been performed on February 23, 2012 (206 days after the DR).
F2 |  | Variance between budget and expenditure mainly due to funds committed/forecasted for equipment for RSCs, trainings, guides, software, clinical protocols, mhealth project, etc. that could not be disbursed due to lack of funds. The start of some activities and procurement of equipment have been delayed.
F3
F4 |  | The DR for Semester 2, 2011 (period one of SSF) has been submitted to GF on August 02, 2011, yet the disbursment reached PR only on February 23, 2012 (206 days after the DR).
Are procurement and hiring on schedule?
Management |  | Summary Comments |  |  | Recommendations
M1 |  | All five conditions precedent and/or other special conditions have been fulfilled in strict accordance with their provisions and timeline.
M2 |  | Two full time positions and 11 part time. | #DIV/0! | #DIV/0!
M3 |  | Four Sub-recipients (SRs) have been identified to implement different components within the program: Soros Foundation-Moldova (SFM); League of people living with HIV of Moldova; New Life, Moldovan Institute for Human Rights. One SR (SFM) has been earlier assessed by the governmental PR of GF grants as it acts as an SR since GF Round one. Two other SRs have been assessed (New Life and Moldovan Institute for Human Rights) were assessed by PAS Center the last one (League of people living with HIV of Moldova) by GF Local Fund Agent. Following the assessments four sub-grant agreements have been signed. In September 2011, due to lack of capacity for adequate implementation of the grant portion contracted the sub-grant agreement with one of the SRs (League of people living with HIV) was terminated and the management of activities has been entrusted to SFM. Respectively three sub-recipients are currently receiving funds within the grant.
M4 |  | The SRs’ quarterly reports (financial report, activity report and performance framework) are due to the PR not later than 25 days after the close of each quarter and are generally submitted in time. The clearance period vary from one SR to an other subject to the completeness and consistence of the reports. The clearance of reports for SR IDOM for Q3, 2011 has lasted for one and a half month due to the identification of a series of violations and ended with refund of amounts that was not used in accordance with the terms and conditions of the Sub-grant agreement. For the SR SFM the Sub-subrecipients financial reports are due quarterly and can be submitted during the following quarter, the activity reports are due not later than 10 days from the end of each month and are generally submitted in time except one Ssr - NGO Master in Public Health – that is constantly late in reporting. During the reporting period reflected in this dashboard the organization Your Generation, Drochia that received a small grant for World AIDS Day has substantially delayed the report. For the SR New Life the reports (financial, activity and indicators) are due not later than 15 days after the close of each quarter and are generally submitted in time.
M5 |  | N/A
M6 |  | N/A
Are technical targets being achieved?
Programmatic |  | Summary Comments |  |  | Recommendations
P1 - trend |  | The main part of PLHIV have been reached by project: from the 5,383 PLHIV by the end December 2011 (prevalence) a total of 4,853 were covered with care and support services. Currently the number of new PLHIV that can be covered with support services is mostly related to new people diagnosed with HIV. To mention that not every PLHIV will be covered with support due to refusal to receive psycho-social services, migration, etc.
P2 - trend |  | Due to the fact that the main number of the OST clients were reached (those who received at least 3 or more services), at present we reach out the new OST clients. Respectively the number of potential new OST clients to be reached with support services is directly related to the new entries in OST treatment.
P3 - trend |  | One training planed for S2, 2011 has been postponed for S1, 2012 due to the fact that the teams of RSCs planned to be trained in case management were not complete by the end of year 2011.
P1 |  | During S4 a total 557 PLHIV were primarily reached with care and support services from 10 organizations work in this area. The beneficiaries are provided with the following services: psycho-social counseling and registration, medical consultations, distribution of informational materials and peer health counseling, referral services provided by public institutions, self support groups, etc. (în semestrul 4, 557 de PTH au fost primari acoperiți cu îngrijire şi suport în cadrul a 10 organizaţii care lucrează în acest domeniu. Beneficiariilor le sunt oferite următoarele servicii: consiliere psiho-socială, consultaţii medicale, distribuţia materialelor informaţionale şi consiliere de la egal la egal, servicii de referinţă furnizate de către instituţiile publice, grupuri de auto-suport, etc. )
P2 |  | During S4 a total of 115 IDUs on oppioide substitution therapy (primarily reached) received at least 3 support services from the package (psychosocial support, self-support groups, peer to peer education, distributions of informational materials and food parcels) offered by NGOs working in DUs rehabilitation. (în timpul S4 un total de 115 de UDI aflați în terapia de substituţie cu metadonă (primari atinși) au primit cel puţin 3 servicii de suport social din pachetul (sprijin psiho-social, grupuri de suport reciproc, educație de la egal la egal, distribuţia de materiale informaţionale şi pachete alimentare și igienice) oferite în cadrul centrelor de zi de ONG-uri care lucrează în domeniul reabilitării UDI).
P3 |  | A total of 296 persons trained in S4, from them: 27 medical staff were trained in international training in Clinica Lavra in various aspects such as "ARV adverse reactions:diagnoses and clinical management", "Viral Hepatitis B and C and HIV infection" and "Adverse reactions of ARV treatment: diagnosis and tactics" ; 78 non-medical staff from MDT under National Social Reference System were trained in Protection and assistance to victims of human trafficking, domestic violence and people living with HIV within the National Reference System; 15 laboratory personnel were trainded in "Laboratory Monitoring of HIV Infection and Antiretroviral Therapy, ARV drug resistance", 51 primary health care specialists were trained HIV infection; 102 social assistants in most affected regions were trained in HIV/AIDS; and 23 specialists from the Ministry of Social Protection were trained in HIV/AIDS. (un total de 296 persoane au participat la training-uri în semestrul 4, dintre care: 27 lucrători medicali au fost instruiţi la training-urile internaţionale organizate la Clinica Lavra, în mai multe aspecte, cum ar fi: „Reacţii adverse ale ARV:diagnostic, tactică” , „Hepatitele Virale B şi C şi infecţia HIV” şi „Reacţii adverse ale ARV:diagnostic şi managementul clinic”; 78 lucrători non-medicali din echipele multidisciplinare din cadrul Sistemului Naţional Social de Referinţă au fost instruiţi în protecţia şi asistenţa victimelor traficului uman, violenţa domestică şi PTH în cadrul Sistemului Naţional de Referire; 15 medici laboranţi au fost instruiţi în "Flowcitometria şi PCR+ metode de laborator utilizate în diagnosticul infecţiei cu HIV", 51 specialişti în asistenţă medicală primară au fost instruiţi în infecţia HIV; 102 asistenţi sociali din cele mai afectate regiuni au fost instruiţi în HIV/SIDA; şi 23 specialişti a Ministerului Protecţiei Sociale au fost instruiţi în HIV/SIDA).
P4 |  | 25 HIV infected patients received palliative care services within the ARV Treatment facility during reported period (care of skin, hair, nails, eyes, mouth, pneumonia prophylactic treatment, symptomatic treatment, alimentation, etc.). (25 de pacienţi infectaţi cu HIV au primit servicii de îngrijiri paliative în cadrul departamentului de tratament ARV în timpul perioadei raportate (îngrijire a pielii, părului, unghiilor, cavității bucale, ochilor, tratamentul profilactic al pneumoniei, tratamentul medicamentos simptomatic, alimentaţie, etc.))
P5 |  | A total of 296 PLHIV received food parcels during S4 (primarily reached): 173 during Q7 and 123 during Q8. (Un număr total de 296 de PTH au primit pachete alimentre în timpul semestrului 4 (beneficiari unici): 173 – în timpul trimestrului 7 şi 123 în trimestrul 8).
P6 |  | A total of 63 children received social support during S4 (primarily reached): 31 children during Q7 and 32 children during Q8. (un număr total de 63 copii au primit suport social în timpul semestrului 4 (beneficiari unici): 31 de copii în timpul trimestrului 7 şi 32 – în trimestrul 8).
P7 |  | A total of 51 individuals out of 91 that initiated OST during P5-P6 have completing at least 6 months of continuous treatment on OST. Currently OST is provided in three sites: Republican Narcological Dispensary, Balti Municipal Hospital and the Department of Penitentiary Institutions (in 7 penitentiaries). (un total de 51 de persoane din 91 care a initiat TS în timpul P5-P6 au finalizarea cel puţin 6 luni de tratament continuu. Actualmente TS este oferită in trei site-uri: Dispensarul Republican de Narcologie, Spitalul Municipal Bălţi şi Departamentul Instituţiilor Penitenciare (în 7 penitenciare)).
P8 |  | A total of 176 lawyers have been trained during S4 within 7 training courses on human rights, non-discrimination, confidentiality and reparation for moral prejudices of people living with HIV. (un număr total de 176 de avocaţi au fost instruiţi în semestrul 4 în cadrul a 7 cursuri de instruire în drepturile omului, non-discriminarea, confidenţialitatea şi despăgubirea prejudiciile morale ale PTH).
P9 |  | A total of 69 consultancies were offered remotely by traveling to project sites of 4 lawyers, during S4; they offered legal assistance related to issues of legal, civil (including disclosure of HIV status), administrative nature to all PLHIV in need. (pe parcursul semestrului 4 au fost oferite 69 de consultaţii în teren de către 4 avocaţi;aceștea au oferit asistenţă juridică pe aspecte de natură legală, civilă (incluzând divulgarea statutului HIV) şi administrative ale tuturor PTH care au solicitat ajutor).
P10 |  | 202 representatives of NGOs providing services to PLHIV were trained during S4. 42 participants were attending Romanian language course (C2 level) and 39 people have followed Romanian language courses (C2 professional level). 29 persons were trained in “Non-Medical Services for PLHIV". A number of 42 participants attended English language course (elementary). A number of 27 participants took part in the training "Psycho-social assistance for HIV infected children and their families". A number of 23 participants took part in the training "Monitoring and Evaluation". (202 de reprezentanţi ai ONG-urilor care furnizează servicii PTH au fost instruiţi în semestrul 4. 42 de persoane au participat la cursurile de limbă română (nivelul C2) şi 39 de persoane au urmat cursuri de limbă română (nivelul C2 profesional). 29 de persoane au fost instruite în " Serviciile nemedicale acordate persoanelor care trăiesc cu HIV" , 42 de persoane au urmat cursuri de limbă engleză (nivelul elementar); 27 de persoane au participat la training-ul „Asistenţa psihosocială pentru copiii cu HIV şi familiile lor ” şi 23 de persoane au fost instruiți în monitorizare si evaluare).
Menu

## Actions
Dashboard: Moldova - HIV / AIDS
| SSF (Round 8) | Phase 1 |  |  |  | Report Period: |  | P8
| Latest Rating: | A1 |  | PAS Center |  | From: |  | July 01, 2011
|  |  | Reducing HIV-related burden in the Republic of Moldova |  |  |  | To: | December 31, 2011
Decisions and Actions
What is the overall status of this grant implementation?
| Key Recommendations from Oversight Group(s) |  |  |  | CCM Decision | Due Date | Person Responsible
Current Reporting Period
Actions to Implement / Previous Period
What is the overall status of this grant implementation?
| CCM Decision |  |  |  | Action Taken | Date | Person Responsible
Previous Reporting Period
Menu

## Setup (hidden)
Dashboard: Moldova - HIV / AIDS
Set-up = List of validation for Grant Detail page
Component | Currency | Round | Phase | Period | Rating | LFA | Medicaments | Countries
Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select
HIV / AIDS | $ | Round 1 | Phase 1 | P1 | A1 | CA (Crown Agents) | Isoniazid | Afghanistan
MALARIA | € | Round 2 | Phase 2 | P2 | A2 | DEL (Deloitte) | Ethambutol | Albania
TB |  | Round 3 | RCC | P3 | B1 | DTT (DTT Emerging Markets) | Rifampicin | Algeria
HIVAIDS / TB |  | Round 4 |  | P4 | B2 | FIN (Finconsult) | Pyrazimamide | Angola
HSS |  | Round 5 |  | P5 | C | GT (Grant Thornton) | RDT | Argentina
|  | Round 6 |  | P6 |  | H-C (Hodar-Conseil) | NVP | Armenia
|  | Round 7 |  | P7 |  | KPMG (KPMG) | 3TC | Azerbaijan
|  | Round 8 |  | P8 |  | MSCI (MSCI) | D4T | Bangladesh
|  | Round 9 |  | P9 |  | PwC (PricewaterhouseCoopers) | AZT | Belarus
|  | Round 10 |  | P10 |  | STI (Swiss Tropical Institute), | DDI | Belize
|  |  |  | P11 |  | UNOPS | EFV | Benin
|  |  |  | P12 |  |  | AS/LF | Bhutan
[7 empty] | AS/AQ | Bolivia
[7 empty] | AS/MQ | Bosnia and Herzegovina
[7 empty] | Al/Lum | Botswana
Brazil
[7 empty] | TB nutri'l supplements | Bulgaria
[7 empty] | E-PAP | Burkina Faso
Burundi
Cambodia
Cameroon
Cape Verde
Central African Republic
Chad
Chile
China
China
Colombia
Comoros
Congo (Democratic Republic of the)
Congo (Republic of the)
Costa Rica
Cote d'Ivoire
Croatia
Cuba
Djibouti
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Ethiopia
Fiji
Gabon
Gambia
Georgia
Ghana
Global(LWF)
Guatemala
Guinea
Guinea-Bissau
Guyana
Haiti
Honduras
India
Indonesia
Iran (Islamic Republic of)
Iraq
Jamaica
Jordan
Kazakhstan
Kenya
Korea, Democratic Peoples Republic of
Kosovo (Serbia)
Kyrgyzstan
Lao PDR
Lesotho
Liberia
Macedonia, FYR
Madagascar
Malawi
Maldives
Mali
Mauritania
Mauritius
Moldova
Mongolia
Montenegro
Morocco
Mozambique
Multi-country Africa (West Africa Corridor Program)
Multi-country Africa(RMCC)
Multi-country Americas (Andean)
Multi-country Americas (CARICOM)
Multi-country Americas (CRN+)
Multi-country Americas (Meso)
Multi-country Americas (OECS)
Multi-country Americas (REDCA+)
Multi-country Western Pacific
Myanmar
Namibia
Nepal
Nicaragua
Niger
Nigeria
Pakistan
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Romania
Russian Federation
Rwanda
Sao Tome and Principe
Senegal
Serbia
Sierra Leone
Solomon Islands
Somalia
South Africa
Sri Lanka
Sudan
Suriname
Swaziland
Syrian Arab Republic
Tajikistan
Tanzania
Thailand
Timor-Leste
Togo
Tunisia
Turkey
Uganda
Ukraine
UN Theme Group on HIV/AIDS (West Bank and Gaza)
Uzbekistan
Viet Nam
Yemen
Zambia
Zanzibar (Tanzania)
Zimbabwe