## Menu
Dashboard: Moldova - TB
TB Phase 1 | Grant No.: MOL-S10-G08-T
V1.0
Finance
Programmatic
Management
Select the option you want to see:
Recommendations
Actions
Grant Detail
List of Indicators
Data Entry
Grant Information
Indicators
Reports

## List of Indicators
Dashboard: Moldova - TB
Financial information
Name: | Definition | Measurement | Data Sources
F1: Budget and disbursements by Global Fund | Cumulative budget: Sum of the grant budget from period one (quarter, trimester, or semester) of the current phase, up to and including the dashboard reporting period. Cumulative Disbursments by GF: Sum of all the funds transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to and including the dasboard reporting period. | Currency of the grant ($ or Euro) Cumulative – Figures refer to budget and disbursements for all the periods of the phase up to and including the dashboard reporting period | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F2: Budget and actual expenditures by Grant Objective | Cumulative Budget per Objective: Sum of the grant budget by Objective, from period one of the current phase up to and including the dashboard reporting period. Cumulative Expenditure per Objective: Sum of amounts spent by Objective directly by the PR plus the amounts transferred by the PR to all SRs from the beginning of the phase up to and including dashboard reporting period, by Objective | • Cumulative – Figures refer to budget, disbursements or expenditure for all the periods of the phase up to and including the dashboard reporting period. | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F3: Disbursements and expenditures | Disbursement by GF: Prior to this Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to but not including dashboard reporting period. Disbursement by GF: Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), during dashboard reporting period. PR disbursements and expenditure: Prior to this Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) up to but not including dashboard reporting period. PR disbursements and expenditure: Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) during dashboard reporting period. Disbursements to SRs: Prior to this Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), up to but not including dashboard reporting period. Disbursements to SRs:Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), in dashboard reporting period. SR expenditures: Prior to this Reporting period: The sum of all expenditures reported by the SRs, up to but not including dashboard reporting period. SR expenditures: Reporting period: The sum of all expenditures reported by the SRs, during dashboard reporting period. | Currency of the grant ($ or Euro) • Reporting period – Figures refer to budget, disbursements or expenditure for the reporting period to which the dashboard refers. • Prior to reporting period - Figures refer to the total budget, disbursements or expenditure for all the periods before but not including the current period. | PU/DR; PR data: SR reports to PR
F4: Latest PR reporting and disbursement cycle | Days taken to submit final PU/DR to LFA – This indicator measures the number of calendar days it took the PR to send a final Performance Update and Disbursement Request (PU/DR) to the LFA after the end of the period. A 'final' PU/DR would be one for which the LFA did not require any further clarifications from the PR. The expected value is 45 days from the end of the period, as defined in the Grant Agreement. The actual value is the number of calendar days from the end date of the period to the date on which the PR sent to the LFA the final PU/DR. Days taken for disbursement to reach PR – This indicator measures the number of calendar days it took the Global Fund to send the latest disbursement to the PR's account after receipt of the acceptable PU/DR by the LFA. The expected number is 45 days. The actual number is the number of days from the date of transmission by the PR to the LFA of the acceptable PU/DR to the date the disbursement is received by the PR at its bank. Days taken for disbursement to reach SRs – This indicator measures the average number of days for disbursements to be made to all the SRs. The expected value for this indicator will be set locally by the PR and SRs, preferably in the Grant Operations Manual. The actual value is the average of the number of days from the receipt of the funds from the GF by the PR to the date the funds are received by each SR. Different SRs coudl receive funds on different dates and this indicator is the average across all SRs for the latest disbursement. | Number of calendar days; it refers only to reporting period for which the latest disbursement was received and is not cumulative | PR, LFA, GF emails and records; bank notification document or the notice of receipt by the PR to GF; SR reports to PR based on bank records
Management Information
Name: | Definition | Measurement | Data Source
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) | Number of Conditions Precedent (CPs) and Time Bound Actions (TBAs ) fulfilled, or unfulfilled. Within the Unfulfilled category, we distinguish between those CPs and TBAs whose deadline has not passed and those for which the deadline has passed. | Number, cumulative to the dashboard reporting period. Number of fulfilled CPs and/or TBAs plus unfulfilled CPs and/or TBAs should equal the total number set by the Global Fund on the grant | PR records; Grant Performance Reports;
M2: Status of key PR management positions | Number of PR grant management positions planned currently filled or vacant. Full time equivalents of the managerial positions that are on the organizational chart (or otherwise planned) and directly responsible for ensuring grant implementation at the PR, and lead SRs (if necessary). This will include new hires, current staff who are assigned to work on the grant’s management, as well as any staff seconded from other divisions or partner organizations. | Number, in current reporting period | PR records
M3: Contractual arrangements (SRs) | Identified: Total number of potential SRs identified by the PR for the phase. Assessed: Total number of potential SRs assessed by the PR to determine whether they qualify to function as SRs for the grant. Approved: Total number of SRs that have been approved. Signed: Total number of SRs that have signed agreements/contracts with the PR under the grant. Receiving funding: Total number of SRs that are getting funds and/or supplies from the PR. Numbers of SRs Identified, Assessed, Approved, Signed and Receiving funds are cumulative for the phase, with the following exceptions: If an SR does not need new approval in Phase II, then approval in Phase I is counted. If an SR was signed in a previous Phase but is not working in the current Phase, that SR is no longer counted in Identified, Assessed, Approved. | Number, cumulative to the reporting period. A SR is an institution or program with its own workplan, budget and performance targets. | PR records; Sub-agreements/MOUs; CCM records
M4: Number of complete reports received on time | The total number of periodic reports with up-to-date financial, management and performance (programmatic) data received by the PR from SRs and by SRs from the SubSRs (SSRs) by the expected date. A 'complete' report is one that contains all the data that the PR requires for the PU/DR. The expected date would be set by the PR in the sub-agreements. | Number of reports received. The figure reflects only the period of reporting; it is not cumulative. | PR and SR records
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals | This indicator measures the budget approved for the current phase of the grant for purchase of health products and equipment and pharmaceuticals and medicines (categories 4 and 5 in the new Enhanced Financial Report), and the cumulative amounts of financial obligations and expenditures up to the dashboard reporting period. Budget approved: Total approved budget for purchases (categories 4 and 5) for the entire phase of the grant. It does not include the amounts for fees, management, operational costs, etc. Cumulative Obligations: Total of all order(s) placed and monies committed for these purchases by the PR up to and including the dashboard reporting period. Ideally, by the end of the Phase, budget should equal obligations. Cumulative expenditure: Total of actual Expenditures on category 4 and 5 up to and including the dashboard reporting period (whether paid by PR or authorized to be paid by another entity like GF or other). | Currency of the grant ($ or Euro) | Grant agreement approved budget (for categories 4 and 5 of Enhanced Finance Reporting in current phase); and PR financial data (for expenditures), and/or PSM unit (for orders placed and funding committed or obligated).
Note: Category 6 of the EFR will not be considered as part of the budget for pharmaceuticals. Category 6 has several expenditures that are difficult to disaggregate or quantify, such as warehousing costs, distribution costs (particularly when distibution is done by MOHs), and others that are related to operational costs of the PSM component.
M6: Difference between current and safety stock | This indicator is a snapshot of the difference between the current (or last month) stock level of a specific product (medicine in single, fixed-dose combination, bednets, diagnostic kits, etc.) of a particular dose, expressed in monthly needs (number of months of treatment available) for all patients in the program, and the safety or buffer stock (also expressed in months) as established by the disease program, warehouse system or essential drugs program, for the particular product and dosage. The table will show the difference in months in colors: • RED: when the difference is negative or 0, showing that months of existing stock are lower than or equal to what has been established as months of safety stock • YELLOW: when we have more than the level of safety stock (>0) but less than 3 months (+3). • GREEN: when the difference is between 3 and 18 months. • VIOLET: When the difference shows that the level above the safety stock is greater than or equal to 18 months indicating a potential overstock) problem. For a full description of how this indicator is calculated, please see the User’s Manual. | Number of months | PR records: Warehouse data.
Programmatic Indicators (from Performance Framework)
Indicator | Definition (from M&E Plan, June 2007) | Measurement | Data Source
Impact Indicator 1. TB mortality rate - Estimated number of deaths due to TB (all forms) per year, per 100,000 population | Numerator: Number of deaths attributable to TB (all forms) registered in a specified period per 100,000 population; Denominator: Total population in country | Collected annually | TB notification forms (089); Register of TB cases (03); TB patients health cards (01).
Outcome indicator 4. MDR-TB prevalence among new smear positive cases, % | Numerator: Number of new culture positive TB cases tested to DST to first line drugs and diagnosed with MDR over the given year; Denominator: Total number of new culture positive TB cases tested to DST to first line drugs over the given year cohort | Collected annually | MDR TB notification forms (090); Register of MDR TB cases (03MDR= category IV register); MDR TB patients health cards (01).
1.1 Number of new smear-positive TB patients reported to the national health authority | Numerator: Number of new smear-positive TB patients reported to the national health authority; Denominator: None | Y - cumulative annually | R&R TB system, quarterly reports. SYME TB.
1.2 Number of people receiving DOTS treatment - (Absolute number of TB patients with instituted treatment (directly observed treament, short course (DOTS) based) | Numerator: Number of people receiving DOTS treatment - (Absolute number of TB patients with instituted treatment (directly observed treatment, short course (DOTS) based); Denominator: None | Y - over program term | R&R TB system, quarterly reports
1.3 Number and percentage of new smear-positive TB cases, registered under DOTS, who are successfully treated | Numerator: Number of new smear-positive pulmonary TB patients in a given year who subsequently were successfully treated [sum of WHO outcome categories "cured" plus "treatment completed]" during a specified period; Denominator: Total number of new-smear pulmonary TB patients registered for treatment in the same specified period | Y - cumulative annually | R&R TB system, quarterly reports. SYME TB.
1.4 Number of medical staff trained in DOTS activities | Numerator: Number of medical staff trained in DOTS activities; Denominator: None | Y - over program term | Training records. Quarterly reports.
1.5 Number and percentage of TB patients who had an HIV test result recorded in the TB register among the total number of registered TB patients | Numerator: Number of TB patients registered during a given time period who had an HIV test result recorded in the TB register; Denominator: Total number of TB patients registered during the same time period | Y - cumulative annually | R&R TB system, quarterly reports. SYME TB.
1.7 Number of released prison inmates on TB treatment supported through the TB treatment follow-up program | Numerator: Number of released prison inmates on TB treatment supported through the TB treatment follow-up program; Denominator: None | Y - over program term | Program reports.
2.1 Number of laboratory-confirmed MDR-TB patients enrolled in second-line anti-TB treatment | Numerator: Number of laboratory-confirmed MDR-TB patients enrolled in second-line anti-TB treatment; Denominator: None | Y - cumulative annually | R&R TB system, quarterly reports. SYME TB, DOTS Plus module.
2.3 Number and percentage of laboratory-confirmed MDR-TB patients, successfully treated (cured plus completed treatment), among those enrolled in the second -line anti-TB treatment | Numerator: Number of laboratory-confirmed MDR-TB patients successfully treated (cured plus completed treatment) during a specified period; Denominator: Total number of laboratory-confirmed MDR-TB patients enrolled in second -line anti-TB treatment during a specified period | Y - cumulative annually | R&R TB system, quarterly reports. SYME TB, DOTS Plus module.
Indicator Number: Name (Perf Framework No.) | Definition | Measurement | Data Source
The indicators should be selected by the PRs and members of the CCM or the CCM Technical Committee, from the Performance Framework |  |  | Performance Framework
Menu

## Data Entry
Grant information
| Country: | Moldova |  | Title of the Grant: |  | Strengthening Tuberculosis Control in the Republic of Moldova
| Grant No.: | MOL-S10-G08-T |  | Component: |  | TB | Total Funding: | 5796648
| Principal Recipient: | IP UCIMP RSS |  |  | Round: | Please Select | Phase: | Phase 1
| Start Date (dd/Mmm/yy): | 2010-10-01 |  | Local Fund Agent: |  | PwC (PricewaterhouseCoopers)
| Latest Rating: | Please Select |  | Fund Portfolio Manager: |  | Nicolas Cantau
Information on the reporting period
| Report Period: | P3 | From: | 2011-04-01 | To: | 2011-06-30 | Date of entry of information: |  | 2011-09-01
| Prepared by: |  | IP UCIMP RSS
Information on indicators
Enter the data based on the colour-coded cells
| Financial Information: |  | Management Information: |  |  | Programmatic Information:
| Financial Information: | [8 empty] | Enter finance data in every orange cell like this.
| Currency of the grant |  | €
F1: Budget and disbursements by Global Fund
| Disbursement | [15 empty] | 602888
| Reporting period | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12 | % Cumulative |  |  | 1332965
| Budget (in €) | P1: 602888; P2: 730077; P3: 1313165 | 117.8% |  |  | 2646130
| Disbursements by GF (in €) | P1: 2983758.95; P2: 52214; P3: 81828 |  |  |  | 0
| Cumulative budget | 602888 | 1332965 | 2646130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Cumulative disbursements | 2983758.95 | 3035972.95 | 3117800.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
|  | 0% | 0% | 117.8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0
F2: Budget and actual expenditures by Grant Objective
| Grant Objective | P1: Cumulative Budget (in €); P2: Cumulative Expenditures (in €)
| Strengthening DOTS realization to improve TB detection and case management | P1: 269333.02; P2: 226284.03
| Ensure universal access to diagnosis and treatment of drug-resistant tuberculosis | P1: 1959266.14; P2: 1472504.52
| Strengthening the M&E system and management and coordination of the National Healthcare System for TB patients | P1: 171404.25; P2: 83999.27
| Increase public awareness of tuberculosis and reduce stigmatization | P1: 58541; P2: 51280.75
| Strengthening of Project management | P1: 187586; P2: 216981.51
| Total | P1: 2646130.41; P2: 2051050.08; P4: OK: Data match
| F3: Disbursements and expenditures | [15 empty] | 0
0
|  | P1: Prior to reporting period; P2: Current reporting period; P3: Total Spent and Disbursement (in €) |  |  | 0
| Disbursed by Global Fund | P1: 3035972.95; P2: 81828; P3: 3117800.95
| PR expenditure and disbursement | P1: 1276571.2; P2: 774478.88; P3: 2051050.08
| Disbursed to SRs | P1: 63579.28; P2: 26551.72; P3: 90131
| SR expenditures | P1: 34464.59; P2: 23634.8; P3: 58099.39
F4: Latest PR reporting and disbursement cycle
Last fund disbursement: Number of calendar days
|  | Expected (days) | Actual (days)
| Days taken to submit final PU/DR to LFA | P1: 45; P2: 45
| Days taken for disbursement to reach PR | P1: 45; P2: 30
| Days taken for disbursement to reach SRs | P1: 20; P2: 20
| Management Information: | P6: Enter management data in every blue cell.
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs)
|  |  | Fulfilled | Not fulfilled, but within deadline | Not fulfilled, and past the deadline | Total
| Conditions precedent (CPs) | P5: 0
| Time Bound Actions (TBAs) | P5: 0
M2: Status of key PR management positions
|  | Planned | Filled | Vacant
| IP UCIMP RSS | P1: 6; P2: 5; P3: 1
M3: Contractual arrangements (SRs)
|  | Identified | Assessed | Approved | Signed | Receiving Funding
| SRs | P1: 2; P2: 2; P3: 2; P4: 2; P5: 2
M4: Number of complete reports received on time
|  | # Expected | # Received | Pending
| SSR to SR | P3: 0
| SRs to PR | P1: 2; P2: 2; P3: 0
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals
|  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
| Budget Approved* | P1: 24875; P2: 191226; P3: 934545
| Obligations | P1: 530082.36; P2: 53082.42; P3: 777281.16
| Expenditures | P1: 530082.36; P2: 53082.42; P3: 378670.16
| Budget Approved cumulative* | 24875 | 216101 | 1150646 | 1150646 | 1150646 | 1150646 | 1150646 | 1150646 | 1150646 | 1150646 | 1150646 | 1150646
| Obligations cumulative | 530082.36 | 583164.78 | 1360445.94 | 1360445.94 | 1360445.94 | 1360445.94 | 1360445.94 | 1360445.94 | 1360445.94 | 1360445.94 | 1360445.94 | 1360445.94
| Expenditures cumulative | 530082.36 | 583164.78 | 961834.94 | 961834.94 | 961834.94 | 961834.94 | 961834.94 | 961834.94 | 961834.94 | 961834.94 | 961834.94 | 961834.94
* Includes only EFR category 4 and 5 (Health products and health equipment & Medicines and Pharmaceuticals)
M6: Difference between current and safety stock
| Component | Products | (1) Number of tablets per patient per day (Review country treatment guidelines) | (2 = 1 x 30) Monthly treatment (Tablets per patient x 30 days) | (3) Total patients in treatment | (4 = 2 x 3) Total # tab/pills required for all patients per month | (5) Current stock in central warehouse (that does not expire within the next 3 months) | (6 = 5 / 4) Stock level expressed in months of treatment for all current patients | (7) Level of safety stock (expressed in months and defined by country) | (8 = 6 - 7) Difference between current stock and safety stock
| Please Select | P1: Please Select
Please Select
Please Select
Please Select
| Programmatic Information: | P9: Enter performance data in every yellow cell.
| Programmatic indicators (Performance Framework ) |  |  | Code | Directly Tied? |  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
TOP 3 | TB mortality rate - Estimated number of deaths due to TB (all forms) per year, per 100,000 population |  |  | impact 1 | Yes | Target | P1: 13; P2: 13; P3: 13
[6 empty] | Achieved | P1: 17.7; P2: 17.7; P3: 17.8
| MDR-TB prevalence among new smear positive cases, % |  |  | outcome 4 | Yes | Target | P1: 17; P2: 17; P3: 17
[6 empty] | Achieved | P1: 26.1; P2: 25.2; P3: 24.33
| Number of new smear-positive TB patients reported to the national health authority |  |  | 1.1 | Yes | Target | P1: 1410; P2: 360; P3: 720
[6 empty] | Achieved | P1: 1263; P2: 312; P3: 640
| Number of people receiving DOTS treatment - (Absolute number of TB patients with instituted treatment (directly observed treament, short course (DOTS) based) |  |  | 1.2 | Yes | Target | P1: 18488; P2: 19791; P3: 21093
[6 empty] | Achieved | P1: 17925; P2: 19107; P3: 20790
| Number and percentage of new smear-positive TB cases, registered under DOTS, who are successfully treated |  |  | 1.3 | Yes | Target | P1: 73; P2: 77; P3: 77
[6 empty] | Achieved | P1: 53.11; P2: 42.32; P3: 43.84
| Number of medical staff trained in DOTS activities |  |  | 1.4 | Yes | Target | P1: 1665; P2: 1815; P3: 1960
[6 empty] | Achieved | P1: 1900; P2: 1956; P3: 2125
| Number and percentage of TB patients who had an HIV test result recorded in the TB register among the total number of registered TB patients |  |  | 1.5 | Yes | Target | P1: 90; P2: 90; P3: 90
[6 empty] | Achieved | P1: 92.57; P2: 85.35; P3: 86.11
| Number of released prison inmates on TB treatment supported through the TB treatment follow-up program |  |  | 1.7 | Yes | Target | P1: 0; P2: 50; P3: 75
[6 empty] | Achieved | P1: 0; P2: 17; P3: 30
| Number of laboratory-confirmed MDR-TB patients enrolled in second-line anti-TB treatment |  |  | 2.1 | Yes | Target | P1: 555; P2: 145; P3: 270
[6 empty] | Achieved | P1: 795; P2: 189; P3: 416
| Number and percentage of laboratory-confirmed MDR-TB patients, successfully treated (cured plus completed treatment), among those enrolled in the second -line anti-TB treatment |  |  | 2.3 | Yes | Target | P1: 66; P2: 68; P3: 68
[6 empty] | Achieved | P1: 52.37; P2: 55; P3: 49.33
[6 empty] | Target | P3: 75
[6 empty] | Achieved | P3: 30
[6 empty] | Target | P3: 270
[6 empty] | Achieved | P3: 416
[6 empty] | Target | P3: 68
[6 empty] | Achieved | P3: 49
| Table is automatically updated. No data or information is to be entered here. |  |  | Code | Directly Tied? |  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
| TB mortality rate - Estimated number of deaths due to TB (all forms) per year, per 100,000 population |  |  | impact 1 | Yes | Target | 13 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Achieved | 17.7 | 17.7 | 17.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MDR-TB prevalence among new smear positive cases, % |  |  | outcome 4 | Yes | Target | 17 | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Achieved | 26.1 | 25.2 | 24.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of new smear-positive TB patients reported to the national health authority |  |  | 1.1 | Yes | Target | 1410 | 360 | 720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Achieved | 1263 | 312 | 640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on B72: If data are not available, do not enter zeros; rather, leave the cells in the table blank.
Note on B73: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B30: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.
Note on B79: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B94: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.
Menu

## Grant Detail
Dashboard: Moldova - TB
Country: | Moldova |  | Title of the Grant: |  | Strengthening Tuberculosis Control in the Republic of Moldova
Component: | TB | Grant No. | MOL-S10-G08-T | Start Date: |  | 2010-10-01 | Total Funding | 5796648
Round: |  | Phase: | Phase 1 | Principal Recipient: |  | IP UCIMP RSS
Report Period: | P3 | from: | 2011-04-01 | to: |  | 2011-06-30 | Latest Rating:
Local Fund Agent: | PwC (PricewaterhouseCoopers) |  |  | Fund Portfolio Manager: |  | Nicolas Cantau
Prepared by: | IP UCIMP RSS |  |  | Report preparation date: |  | 2011-09-01
http://www.crwflags.com/fotw/flags/country.html
Menu

## Finance
Dashboard: Moldova - TB
| Phase 1 |  |  |  | Report Period: |  | P3
Latest Rating: |  |  | IP UCIMP RSS |  | From: |  | 2011-04-01
|  | Strengthening Tuberculosis Control in the Republic of Moldova |  |  |  | To: | 2011-06-30
Financial Indicators
F1: Budget and disbursements by Global Fund - in (€) Report Period: P3 |  |  |  | F3: Disbursements and expenditures - in (€) Report Period: P3
Comments: | Timely disbursements by the Global Fund. |  |  | Comments: | PR has commitments with a total amount of ~1 384 K € which will be paid during next semesters.
F2: Budget and actual expenditures by Grant Objective - in (€) Report Period: P3 |  |  |  | F4: Latest PR reporting and disbursement cycle Report Period: P3
Comments: | No major variance is observed under Objectives 1, 3, 4 and PM activities. There is a difference, with a total amount of ~490 K €, between Budget and Actual disbursements under Objective 2. At the same time, IP UCIMP RSS has commitments under this Objective with a total amount of ~1 384 K €, which will be paid during next semesters. |  |  | Comments: | OK
Last fund disbursement: Calendar days
[6 empty] | Expected (days) | Actual (days)
|  |  |  | Days taken to submit final PU/DR to LFA |  | 45 | 45
|  |  |  | Days taken for disbursement to reach PR |  | 45 | 30
|  |  |  | Days taken for disbursement to reach SRs |  | 20 | 20
Menu

## Management
Dashboard: Moldova - TB
| Phase 1 |  |  |  |  | Report Period: |  | P3
Latest Rating: |  |  | IP UCIMP RSS |  |  | From: |  | 2011-04-01
|  | Strengthening Tuberculosis Control in the Republic of Moldova |  |  |  |  | To: | 2011-06-30
Management Indicators
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) Report Period: P3 |  |  |  | M2: Status of key PR management positions Report Period: P3
Comments: | No CPs or management issues have arisen. |  |  | Comments: | The recruitment process shall start in Quarter 3.2011.
M3: Contractual arrangements (SRs) Report Period: P3 |  |  |  | M4: Number of complete reports received on time Report Period: P3
Comments: | No management issues, regarding contractual arrangements with SRs, have arisen. |  |  | Comments: | SRs have sent to the PR all quarterly reports on time.
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals |  |  |  | M6: Difference between current and safety stock Report Period: P3
Comments: | PR has commitments with a total amount of ~1 384 K €, which will be paid during next semesters. |  |  | Comments: | There is no risk of stock-out for FLD. The rational stock level of FLD is available for an average period of 8-10 months, except the ethambutol, with a stock level covering about 20 months. The stock of SLD covers the supply to MDR-TB patients by planned cohorts, according to the treatment schemes.
|  |  |  | Component | Products | Stock level expressed in months of treatment for all current patients | Months of safety stock | Difference between current stock and safety stock
|  |  |  | Please Select | Please Select |  | 0
[5 empty] | Please Select |  | 0
[5 empty] | Please Select |  | 0
[5 empty] | Please Select |  | 0
* Includes only EFR category 4 and 5 (Health products and health equipment & Medicines and Pharmaceuticals)
Menu

## Programmatic
Dashboard: Moldova - TB
| Phase 1 | [8 empty] | Report Period: |  | P3
Latest Rating: |  |  | IP UCIMP RSS | [7 empty] | From: | 2011-04-01
|  | Strengthening Tuberculosis Control in the Republic of Moldova | [8 empty] | To: | 2011-06-30 | [7 empty] | Raiting |  | Valor
Programmatic Indicators
TB mortality rate - Estimated number of deaths due to TB (all forms) per year, per 100,000 population |  |  |  | MDR-TB prevalence among new smear positive cases, % |  |  |  | Number of new smear-positive TB patients reported to the national health authority
Comment: P1 | The TB mortality rate is higher because of the high level of MDR TB among new and retreatment cases, as well as belated diagnosis of cases. |  |  | Comment: P2 | The level of MDR TB among new TB cases is higher than it was estimated in 2008. |  |  | Comment: P3 | The targets for this indicator have not been reached because, during the last 5 years, a stable decrease in the number of all TB cases is registered, including new SS+ detected in country. Moldova entered into a stabilisation stage of epidemic TB.
Indicators |  |  | Target | Achieved | 0% - 59% | 60% - 89% | > 90% | Comments |  |  |  |  | min | 0 | 30% | 60% | 90% | 100% |  | min | 0 | 20% | 40% | 60% | 80%
TB mortality rate - Estimated number of deaths due to TB (all forms) per year, per 100,000 population |  |  | 13 | 17.8 | 136.9% |  |  | Final data for 2010: 727 deaths among TB patients occurred during the 2010 year (17,7 deaths due to TB (all forms) per 100,000 population). |  |  |  |  | max | 30% | 60% | 90% | 100% | 200% |  | max | 20% | 40% | 60% | 80% | 100%
MDR-TB prevalence among new smear positive cases, % |  |  | 17 | 24.33 | 143.1% |  |  | Final data for 2010: Out of 1,381 new culture positive TB cases, tested to DST to first line drugs, in 2010, a total of 336 cases have been diagnosed with MDR-TB (24,33%). | [5 empty] | de 0 a 0.3 | de 0.3 a 0.6 | de 0.6 a 0.9 | de 0.9 a 1 | de 1 a 2 | Rating | Valor | de 0 a 0.2 | de 0.2 a 0.4 | de 0.4 a 0.6 | de 0.6 a 0.8 | de 0.8 a 1
Number of new smear-positive TB patients reported to the national health authority |  |  | 720 | 640 | 88.89% |  |  | Preliminary data: A total of 640 new SS+ cases were detected during the reported period. The targets for this indicator have not been reached because, during the last 5 years, a stable decrease in the number of all TB cases is registered, including new SS+, detected in country. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number of people receiving DOTS treatment - (Absolute number of TB patients with instituted treatment (directly observed treament, short course (DOTS) based) |  |  | 21093 | 20790 | 98.56% |  |  | Preliminary data: 2,865 patients have started the DOTS treatment during the reported period, and 20,790 patients - during project implementation. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number and percentage of new smear-positive TB cases, registered under DOTS, who are successfully treated |  |  | 77 | 43.84 | 56.94% |  |  | Preliminary data: A total of 313 new SS+ TB patients, from 714 diagnosed since Q.1. 2010 to Q.2.2010, were successfully treated, which represents 43,84%, namely: 151/345 in Q.1.2010 (43,77%) and 162/369 in Q.2.2010 (43,90%). The low success rate (43.84%) is determined by the (1) high level of MDR TB among new SS positive cases; (2) diagnosis of the majority of cases with an advanced disease degree, with low therapeutic success rate; (3) failure to finalize the treatment in the continuation phase (usually in ambulatory conditions) in a big number of cases. From the total number of 714 new SS+ cases, registered since Q.1.2010 to Q.2.2010, 104 have been diagnosed with MDR TB and transferred for treatment on the DOTS Plus scheme. If this number is excluded from the evaluation, the success rate increases to 51,31 %. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number of medical staff trained in DOTS activities |  |  | 1960 | 2125 | 108.4% |  |  | 225 persons out of the medical staff, were trained during the reported semester: 76 TB doctors, 87 PHC personnel (0 doctors and 87 nurses) and 62 laboratory specialists. A total of 2,125 people has been trained since the beginning of grant implementation: 246 TB doctors, 1,625 PHC personnel (593 doctors and 1,032 nurses), and 254 laboratory specialists in bacteriological and microscopical TB diagnosis. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Number and percentage of TB patients who had an HIV test result recorded in the TB register among the total number of registered TB patients |  |  | 90 | 86.11 | 95.68% |  |  | Preliminary data: TB patients, among the total number of registered TB patients during the reported semester, that had an HIV test result recorded in the TB register, represent 85,35% (1,095/1,283) in Q.1.2011, and 86,11% (2,182/2,534) in Q.2.2011. The cumulative result for semester 1, 2011, represents 85,9% (3,277/3,817) of TB patients that had an HIV test result recorded in the TB register. The result for this indicator will be modified due to the fact that at the end of the semester, not all the HIV tests results are known and updated. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Number of released prison inmates on TB treatment supported through the TB treatment follow-up program |  |  | 75 | 30 | 40% |  |  | The target for this indicator is hard to be reached due to a series of matters: the prisoners are released directly from the court with no medical evidence upon them; the prisoners are released on a non-programmatic basis due to belated court decisions; the majority of prisoners lack identity cards or indicate wrong adresses and phone numbers, so that to benefit from the treatment follow-up program. Note: The social support activities towards the TB patients, released from prisons, participating in the treatment follow-up program, was initiated in Quarter I, 2011. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Number of laboratory-confirmed MDR-TB patients enrolled in second-line anti-TB treatment |  |  | 270 | 416 | 154.1% |  |  | 416 TB-MDR patients were enrolled in second-line anti-TB treatment, during Q.2.2011, and 189 TB-MDR patients - during Q.1.2011. The cumulative result for semester 1, 2011, represents a total of 605 TB-MDR patients that were enrolled in second-line anti-TB treatment. The target was exceeded due to the extension of the DOTS Plus treatment adherence criteria by the Recruitment Committee. Nevertheless, the DOTS Plus treatment adherence criteria have been reevaluated and diminished, so that the total number of patients to be included in the program not to exceed the treatment possibilities. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Number and percentage of laboratory-confirmed MDR-TB patients, successfully treated (cured plus completed treatment), among those enrolled in the second -line anti-TB treatment |  |  | 68 | 49.33 | 72.54% |  |  | Preliminary data: 175 laboratory-confirmed MDR-TB patients, out of the 371 enrolled in the second -line anti-TB treatment, in the Q1-2, 2008 cohort, were successfully treated (cured plus completed treatment). Note: The targets refer to the patient cohort of the preceding 36 months. The low success rate (47,17%), is determined by the (1) diagnosis of the majority of cases with an advanced disease degree, with low therapeutic success rate, (2) high level of cases diagnosed post-mortem, (3) failure or impossibility to finalize the treatment in the continuation phase (usually in ambulatory conditions) in a big number of cases. The situation described above is explained by (1) the low level of compliance of patients due to their psycho-behavioristic specificity; (2) lack of socio-material support of patients, leading to treatment abandonment; and (3) insufficiency of medical staff in both, the PHC and the phtysio-pulmonology systems, necessary to ensure the treatment success. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Menu

## Recommendations
Dashboard: Moldova - TB
| Phase 1 |  |  |  |  | Report Period: | P3
Latest Rating: |  |  | IP UCIMP RSS |  |  | From: | 2011-04-01
|  |  | Strengthening Tuberculosis Control in the Republic of Moldova |  |  | To: | 2011-06-30
Recommendations
Are all funds reaching implementation levels and being spent according to budget?
Financial |  | Summary Comments |  |  | Recommendations
F1 |  | Timely disbursements by the Global Fund.
F2 |  | No major variance is observed under Objectives 1, 3, 4 and PM activities. There is a difference, with a total amount of ~490 K €, between Budget and Actual disbursements under Objective 2. At the same time, IP UCIMP RSS has commitments under this Objective with a total amount of ~1 384 K €, which will be paid during next semesters.
F3 |  | PR has commitments with a total amount of ~1 384 K € which will be paid during next semesters.
F4 |  | OK
Are procurement and hiring on schedule?
Management |  | Summary Comments |  |  | Recommendations
M1 |  | No CPs or management issues have arisen.
M2 |  | The recruitment process shall start in Quarter 3.2011. | #DIV/0! | #DIV/0!
M3 |  | No management issues, regarding contractual arrangements with SRs, have arisen.
M4 |  | SRs have sent to the PR all quarterly reports on time.
M5 |  | PR has commitments with a total amount of ~1 384 K €, which will be paid during next semesters.
M6 |  | There is no risk of stock-out for FLD. The rational stock level of FLD is available for an average period of 8-10 months, except the ethambutol, with a stock level covering about 20 months. The stock of SLD covers the supply to MDR-TB patients by planned cohorts, according to the treatment schemes.
Are technical targets being achieved?
Programmatic |  | Summary Comments |  |  | Recommendations
P1 - trend |  | The TB mortality rate is higher because of the high level of MDR TB among new and retreatment cases, as well as belated diagnosis of cases.
P2 - trend |  | The level of MDR TB among new TB cases is higher than it was estimated in 2008.
P3 - trend |  | The targets for this indicator have not been reached because, during the last 5 years, a stable decrease in the number of all TB cases is registered, including new SS+ detected in country. Moldova entered into a stabilisation stage of epidemic TB.
P1 |  | Final data for 2010: 727 deaths among TB patients occurred during the 2010 year (17,7 deaths due to TB (all forms) per 100,000 population).
P2 |  | Final data for 2010: Out of 1,381 new culture positive TB cases, tested to DST to first line drugs, in 2010, a total of 336 cases have been diagnosed with MDR-TB (24,33%).
P3 |  | Preliminary data: A total of 640 new SS+ cases were detected during the reported period. The targets for this indicator have not been reached because, during the last 5 years, a stable decrease in the number of all TB cases is registered, including new SS+, detected in country.
P4 |  | Preliminary data: 2,865 patients have started the DOTS treatment during the reported period, and 20,790 patients - during project implementation.
P5 |  | Preliminary data: A total of 313 new SS+ TB patients, from 714 diagnosed since Q.1. 2010 to Q.2.2010, were successfully treated, which represents 43,84%, namely: 151/345 in Q.1.2010 (43,77%) and 162/369 in Q.2.2010 (43,90%). The low success rate (43.84%) is determined by the (1) high level of MDR TB among new SS positive cases; (2) diagnosis of the majority of cases with an advanced disease degree, with low therapeutic success rate; (3) failure to finalize the treatment in the continuation phase (usually in ambulatory conditions) in a big number of cases. From the total number of 714 new SS+ cases, registered since Q.1.2010 to Q.2.2010, 104 have been diagnosed with MDR TB and transferred for treatment on the DOTS Plus scheme. If this number is excluded from the evaluation, the success rate increases to 51,31 %.
P6 |  | 225 persons out of the medical staff, were trained during the reported semester: 76 TB doctors, 87 PHC personnel (0 doctors and 87 nurses) and 62 laboratory specialists. A total of 2,125 people has been trained since the beginning of grant implementation: 246 TB doctors, 1,625 PHC personnel (593 doctors and 1,032 nurses), and 254 laboratory specialists in bacteriological and microscopical TB diagnosis.
P7 |  | Preliminary data: TB patients, among the total number of registered TB patients during the reported semester, that had an HIV test result recorded in the TB register, represent 85,35% (1,095/1,283) in Q.1.2011, and 86,11% (2,182/2,534) in Q.2.2011. The cumulative result for semester 1, 2011, represents 85,9% (3,277/3,817) of TB patients that had an HIV test result recorded in the TB register. The result for this indicator will be modified due to the fact that at the end of the semester, not all the HIV tests results are known and updated.
P8 |  | The target for this indicator is hard to be reached due to a series of matters: the prisoners are released directly from the court with no medical evidence upon them; the prisoners are released on a non-programmatic basis due to belated court decisions; the majority of prisoners lack identity cards or indicate wrong adresses and phone numbers, so that to benefit from the treatment follow-up program. Note: The social support activities towards the TB patients, released from prisons, participating in the treatment follow-up program, was initiated in Quarter I, 2011.
P9 |  | 416 TB-MDR patients were enrolled in second-line anti-TB treatment, during Q.2.2011, and 189 TB-MDR patients - during Q.1.2011. The cumulative result for semester 1, 2011, represents a total of 605 TB-MDR patients that were enrolled in second-line anti-TB treatment. The target was exceeded due to the extension of the DOTS Plus treatment adherence criteria by the Recruitment Committee. Nevertheless, the DOTS Plus treatment adherence criteria have been reevaluated and diminished, so that the total number of patients to be included in the program not to exceed the treatment possibilities.
P10 |  | Preliminary data: 175 laboratory-confirmed MDR-TB patients, out of the 371 enrolled in the second -line anti-TB treatment, in the Q1-2, 2008 cohort, were successfully treated (cured plus completed treatment). Note: The targets refer to the patient cohort of the preceding 36 months. The low success rate (47,17%), is determined by the (1) diagnosis of the majority of cases with an advanced disease degree, with low therapeutic success rate, (2) high level of cases diagnosed post-mortem, (3) failure or impossibility to finalize the treatment in the continuation phase (usually in ambulatory conditions) in a big number of cases. The situation described above is explained by (1) the low level of compliance of patients due to their psycho-behavioristic specificity; (2) lack of socio-material support of patients, leading to treatment abandonment; and (3) insufficiency of medical staff in both, the PHC and the phtysio-pulmonology systems, necessary to ensure the treatment success.
Menu

## Actions
Dashboard: Moldova - TB
|  | Phase 1 |  |  |  | Report Period: |  | P3
| Latest Rating: |  |  | IP UCIMP RSS |  | From: |  | 2011-04-01
|  |  | Strengthening Tuberculosis Control in the Republic of Moldova |  |  |  | To: | 2011-06-30
Decisions and Actions
What is the overall status of this grant implementation?
| Key Recommendations from Oversight Group(s) |  |  |  | CCM Decision | Due Date | Person Responsible
Current Reporting Period
Actions to Implement / Previous Period
What is the overall status of this grant implementation?
| CCM Decision |  |  |  | Action Taken | Date | Person Responsible
Previous Reporting Period
Menu

## Setup (hidden)
Dashboard: Moldova - TB
Set-up = List of validation for Grant Detail page
Component | Currency | Round | Phase | Period | Rating | LFA | Medicaments | Countries
Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select
HIV / AIDS | $ | Round 1 | Phase 1 | P1 | A1 | CA (Crown Agents) | Isoniazid | Afghanistan
MALARIA | € | Round 2 | Phase 2 | P2 | A2 | DEL (Deloitte) | Ethambutol | Albania
TB |  | Round 3 | RCC | P3 | B1 | DTT (DTT Emerging Markets) | Rifampicin | Algeria
HIVAIDS / TB |  | Round 4 |  | P4 | B2 | FIN (Finconsult) | Pyrazimamide | Angola
HSS |  | Round 5 |  | P5 | C | GT (Grant Thornton) | RDT | Argentina
|  | Round 6 |  | P6 |  | H-C (Hodar-Conseil) | NVP | Armenia
|  | Round 7 |  | P7 |  | KPMG (KPMG) | 3TC | Azerbaijan
|  | Round 8 |  | P8 |  | MSCI (MSCI) | D4T | Bangladesh
|  | Round 9 |  | P9 |  | PwC (PricewaterhouseCoopers) | AZT | Belarus
|  | Round 10 |  | P10 |  | STI (Swiss Tropical Institute), | DDI | Belize
|  |  |  | P11 |  | UNOPS | EFV | Benin
|  |  |  | P12 |  |  | AS/LF | Bhutan
[7 empty] | AS/AQ | Bolivia
[7 empty] | AS/MQ | Bosnia and Herzegovina
[7 empty] | Al/Lum | Botswana
Brazil
[7 empty] | TB nutri'l supplements | Bulgaria
[7 empty] | E-PAP | Burkina Faso
Burundi
Cambodia
Cameroon
Cape Verde
Central African Republic
Chad
Chile
China
China
Colombia
Comoros
Congo (Democratic Republic of the)
Congo (Republic of the)
Costa Rica
Cote d'Ivoire
Croatia
Cuba
Djibouti
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Ethiopia
Fiji
Gabon
Gambia
Georgia
Ghana
Global(LWF)
Guatemala
Guinea
Guinea-Bissau
Guyana
Haiti
Honduras
India
Indonesia
Iran (Islamic Republic of)
Iraq
Jamaica
Jordan
Kazakhstan
Kenya
Korea, Democratic Peoples Republic of
Kosovo (Serbia)
Kyrgyzstan
Lao PDR
Lesotho
Liberia
Macedonia, FYR
Madagascar
Malawi
Maldives
Mali
Mauritania
Mauritius
Moldova
Mongolia
Montenegro
Morocco
Mozambique
Multi-country Africa (West Africa Corridor Program)
Multi-country Africa(RMCC)
Multi-country Americas (Andean)
Multi-country Americas (CARICOM)
Multi-country Americas (CRN+)
Multi-country Americas (Meso)
Multi-country Americas (OECS)
Multi-country Americas (REDCA+)
Multi-country Western Pacific
Myanmar
Namibia
Nepal
Nicaragua
Niger
Nigeria
Pakistan
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Romania
Russian Federation
Rwanda
Sao Tome and Principe
Senegal
Serbia
Sierra Leone
Solomon Islands
Somalia
South Africa
Sri Lanka
Sudan
Suriname
Swaziland
Syrian Arab Republic
Tajikistan
Tanzania
Thailand
Timor-Leste
Togo
Tunisia
Turkey
Uganda
Ukraine
UN Theme Group on HIV/AIDS (West Bank and Gaza)
Uzbekistan
Viet Nam
Yemen
Zambia
Zanzibar (Tanzania)
Zimbabwe