## Menu
Dashboard: Moldova - HIV / AIDS
HIV / AIDS SSF (Round 8), Phase 1 | Grant No.: MOL-809-G06-H
V1.0
Finance
Programmatic
Management
Select the option you want to see:
Recommendations
Actions
Grant Detail
List of Indicators
Data Entry
Grant Information
Indicators
Reports

## List of Indicators
Dashboard: Moldova - HIV / AIDS
Financial information
Name: | Definition | Measurement |  | Data Sources
F1: Budget and disbursements by Global Fund | Cumulative budget: Sum of the grant budget from period one (quarter, trimester, or semester) of the current phase, up to and including the dashboard reporting period. Cumulative Disbursments by GF: Sum of all the funds transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to and including the dasboard reporting period. | Currency of the grant ($ or Euro) Cumulative – Figures refer to budget and disbursements for all the periods of the phase up to and including the dashboard reporting period |  | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F2: Budget and actual expenditures by Grant Objective | Cumulative Budget per Objective: Sum of the grant budget by Objective, from period one of the current phase up to and including the dashboard reporting period. Cumulative Expenditure per Objective: Sum of amounts spent by Objective directly by the PR plus the amounts transferred by the PR to all SRs from the beginning of the phase up to and including dashboard reporting period, by Objective | • Cumulative – Figures refer to budget, disbursements or expenditure for all the periods of the phase up to and including the dashboard reporting period. |  | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F3: Disbursements and expenditures | Disbursement by GF: Prior to this Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to but not including dashboard reporting period. Disbursement by GF: Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), during dashboard reporting period. PR disbursements and expenditure: Prior to this Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) up to but not including dashboard reporting period. PR disbursements and expenditure: Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) during dashboard reporting period. Disbursements to SRs: Prior to this Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), up to but not including dashboard reporting period. Disbursements to SRs:Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), in dashboard reporting period. SR expenditures: Prior to this Reporting period: The sum of all expenditures reported by the SRs, up to but not including dashboard reporting period. SR expenditures: Reporting period: The sum of all expenditures reported by the SRs, during dashboard reporting period. | Currency of the grant ($ or Euro) • Reporting period – Figures refer to budget, disbursements or expenditure for the reporting period to which the dashboard refers. • Prior to reporting period - Figures refer to the total budget, disbursements or expenditure for all the periods before but not including the current period. |  | PU/DR; PR data: SR reports to PR
F4: Latest PR reporting and disbursement cycle | Days taken to submit final PU/DR to LFA – This indicator measures the number of calendar days it took the PR to send a final Performance Update and Disbursement Request (PU/DR) to the LFA after the end of the period. A 'final' PU/DR would be one for which the LFA did not require any further clarifications from the PR. The expected value is 45 days from the end of the period, as defined in the Grant Agreement. The actual value is the number of calendar days from the end date of the period to the date on which the PR sent to the LFA the final PU/DR. Days taken for disbursement to reach PR – This indicator measures the number of calendar days it took the Global Fund to send the latest disbursement to the PR's account after receipt of the acceptable PU/DR by the LFA. The expected number is 45 days. The actual number is the number of days from the date of transmission by the PR to the LFA of the acceptable PU/DR to the date the disbursement is received by the PR at its bank. Days taken for disbursement to reach SRs – This indicator measures the average number of days for disbursements to be made to all the SRs. The expected value for this indicator will be set locally by the PR and SRs, preferably in the Grant Operations Manual. The actual value is the average of the number of days from the receipt of the funds from the GF by the PR to the date the funds are received by each SR. Different SRs coudl receive funds on different dates and this indicator is the average across all SRs for the latest disbursement. | Number of calendar days; it refers only to reporting period for which the latest disbursement was received and is not cumulative |  | PR, LFA, GF emails and records; bank notification document or the notice of receipt by the PR to GF; SR reports to PR based on bank records
Management Information
Name: | Definition | Measurement |  | Data Source
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) | Number of Conditions Precedent (CPs) and Time Bound Actions (TBAs ) fulfilled, or unfulfilled. Within the Unfulfilled category, we distinguish between those CPs and TBAs whose deadline has not passed and those for which the deadline has passed. | Number, cumulative to the dashboard reporting period. Number of fulfilled CPs and/or TBAs plus unfulfilled CPs and/or TBAs should equal the total number set by the Global Fund on the grant |  | PR records; Grant Performance Reports;
M2: Status of key PR management positions | Number of PR grant management positions planned currently filled or vacant. Full time equivalents of the managerial positions that are on the organizational chart (or otherwise planned) and directly responsible for ensuring grant implementation at the PR, and lead SRs (if necessary). This will include new hires, current staff who are assigned to work on the grant’s management, as well as any staff seconded from other divisions or partner organizations. | Number, in current reporting period |  | PR records
M3: Contractual arrangements (SRs) | Identified: Total number of potential SRs identified by the PR for the phase. Assessed: Total number of potential SRs assessed by the PR to determine whether they qualify to function as SRs for the grant. Approved: Total number of SRs that have been approved. Signed: Total number of SRs that have signed agreements/contracts with the PR under the grant. Receiving funding: Total number of SRs that are getting funds and/or supplies from the PR. Numbers of SRs Identified, Assessed, Approved, Signed and Receiving funds are cumulative for the phase, with the following exceptions: If an SR does not need new approval in Phase II, then approval in Phase I is counted. If an SR was signed in a previous Phase but is not working in the current Phase, that SR is no longer counted in Identified, Assessed, Approved. | Number, cumulative to the reporting period. A SR is an institution or program with its own workplan, budget and performance targets. |  | PR records; Sub-agreements/MOUs; CCM records
M4: Number of complete reports received on time | The total number of periodic reports with up-to-date financial, management and performance (programmatic) data received by the PR from SRs and by SRs from the SubSRs (SSRs) by the expected date. A 'complete' report is one that contains all the data that the PR requires for the PU/DR. The expected date would be set by the PR in the sub-agreements. | Number of reports received. The figure reflects only the period of reporting; it is not cumulative. |  | PR and SR records
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals | This indicator measures the budget approved for the current phase of the grant for purchase of health products and equipment and pharmaceuticals and medicines (categories 4 and 5 in the new Enhanced Financial Report), and the cumulative amounts of financial obligations and expenditures up to the dashboard reporting period. Budget approved: Total approved budget for purchases (categories 4 and 5) for the entire phase of the grant. It does not include the amounts for fees, management, operational costs, etc. Cumulative Obligations: Total of all order(s) placed and monies committed for these purchases by the PR up to and including the dashboard reporting period. Ideally, by the end of the Phase, budget should equal obligations. Cumulative expenditure: Total of actual Expenditures on category 4 and 5 up to and including the dashboard reporting period (whether paid by PR or authorized to be paid by another entity like GF or other). | Currency of the grant ($ or Euro) |  | Grant agreement approved budget (for categories 4 and 5 of Enhanced Finance Reporting in current phase); and PR financial data (for expenditures), and/or PSM unit (for orders placed and funding committed or obligated).
Note: Category 6 of the EFR will not be considered as part of the budget for pharmaceuticals. Category 6 has several expenditures that are difficult to disaggregate or quantify, such as warehousing costs, distribution costs (particularly when distibution is done by MOHs), and others that are related to operational costs of the PSM component.
M6: Difference between current and safety stock | This indicator is a snapshot of the difference between the current (or last month) stock level of a specific product (medicine in single, fixed-dose combination, bednets, diagnostic kits, etc.) of a particular dose, expressed in monthly needs (number of months of treatment available) for all patients in the program, and the safety or buffer stock (also expressed in months) as established by the disease program, warehouse system or essential drugs program, for the particular product and dosage. The table will show the difference in months in colors: • RED: when the difference is negative or 0, showing that months of existing stock are lower than or equal to what has been established as months of safety stock • YELLOW: when we have more than the level of safety stock (>0) but less than 3 months (+3). • GREEN: when the difference is between 3 and 18 months. • VIOLET: When the difference shows that the level above the safety stock is greater than or equal to 18 months indicating a potential overstock) problem. For a full description of how this indicator is calculated, please see the User’s Manual. | Number of months |  | PR records: Warehouse data.
Programmatic Indicators (from Performance Framework)
Indicator | Definition (from M&E Plan, September 2009) | Measurement |  | Data Source
Number of medical (doctors and nurses) and non-medical staff (psychologists, social assistants, peer consultants) trained in HIV/AIDS | It is a composite indicator, related activities: capacity building of health specialists from the ART treatment facilities in HIV/AIDS case management abroad; capacity building in HIV/AIDS management for the non-medical staff from the MDT teams; increasing knowledge on HIV/AIDS in staff of the Medical Colleges; training of medical staff in palliative care; training of infectious diseases specialists and primary care specialists; incipient trainings for the e-learning course ; training of the staff of the Ministry of Social Protection in HIV/AIDS (strategic planning, M&E etc) | all persons who signed the list of participation at training |  | List of participants trained
Number of PLWHA receiving palliative care | HIV infected patients that receive palliative care services within the ARV Treatment facility during reported period (care of skin, hair, nails, eyes, mouth, pneumonia prophylactic treatment, symptomatic treatment, alimentation, etc.). | all persons who received services during the reported period |  | Register of beneficiaries
Number of PLWHA receiving food parcels to improve ARV treatment adherence | PLWHA is considered "reached" if he/she has received at least one food package per month during 3 consecutive months. | new persons who received services during the reported period |  | Database
Number of children infected and affected by HIV/AIDS who receive social support | The social support includes food parcels, clothing and school supplies. | new children who received services during the reported period | all persons who received services during the reported period | Database
Number of IDUs on oppoid substitution therapy that receive at least 3 support services from NGOs working in DUs rehabilitation | The beneficiaries are provided with the following services: psycho-social support, self-support groups, peer to peer education, distributions of information materials, etc. The beneficiary is considered "reached" if he/she has received at least three of the services listed. | new persons who received at least 3 support services during the reported period |  | Database
Number and percentage of individuals currently on OST who have been on OST continuously at least 6 months for the past 12 months | Numerator: number of individuals completing at least 6 months of continuous treatment on OST that initiated treatment 6-12 months prior to the end of the reporting period. Denominator: total number of individuals that initiated treatment 6-12 months prior to the end of the reporting period. The indicator is linked to percentage, absolute numbers will be provided when reporting results. The targets refer to the patient cohort (both new and repeated cases) that initiated treatment in the first 6 months of the last 12 months period. | determine the number of people who initiated TS (first time as well as repeated) in the first six months of the last 12 months and assessed how many of these people remained in continuous TS at least 6 months |  | Register of beneficiaries
Number of people living with HIV/AIDS reached with care and support services | The beneficiaries are provided with the following services: psycho-social counseling and registration, distribution of information materials and peer health counseling. The beneficiary is considered "reached" if he/she has received at least one of the three listed services. | new persons who received at least 3 support services during the reported period |  | Database
Number of lawyers from the free legal system and ombudsmen institutes trained in HR, non-discrimination and principles of legal aid. | It is a composite indicator, related activities: training of lawyers from the free legal aid system guaranteed by the state and training on HR, non-discrimination, reparations for moral prejudice and principles of legal aid for lawyers and the Ombudsment Institute | all persons who signed the list of participation at training |  | List of participants trained
Number of human rights strategic litigation cases for PLWH initiated. | Human rights strategic litigation cases for PLWH initiated. | total number of human rights strategic litigation cases registered in the register |  | Register of beneficiaries
Number of PLWHA assisted by legal aid (consultancies offered by legal network) | PLWHA receiving legal aid offered by legal network | all persons who received services during the reported period |  | Register of beneficiaries
Number of the PLWHA League members trained in languages, strategic planning, M&E etc. | It is a composite indicator, related activities: trainings for the members of the league and capacity building of the members of the League in languages and in strategic planning, M&E etc | all persons who signed the list of participation at training |  | List of participants trained
Indicator Number: Name (Perf Framework No.) | Definition | Measurement |  | Data Source
The indicators should be selected by the PRs and members of the CCM or the CCM Technical Committee, from the Performance Framework |  |  |  | Performance Framework
Menu

## Data Entry
Grant information
| Country: | Moldova |  | Title of the Grant: |  | Reducing HIV-related burden in the Republic of Moldova
| Grant No.: | MOL-809-G06-H |  | Component: |  | HIV / AIDS | Total Funding: | 8430291
| Principal Recipient: | PAS Center |  |  | Round: | SSF (Round 8) | Phase: | Phase 1
| Start Date (dd/Mmm/yy): | January 01, 2010 |  | Local Fund Agent: |  | PwC (PricewaterhouseCoopers)
| Latest Rating: | A1 |  | Fund Portfolio Manager: |  | Tatiana Vinichenko
Information reporting period
| Report Period: | P12 | From: | July 01, 2012 | To: | December 31, 2012 | Date of entry of information: |  | April, 2013
| Prepared by: |  | PAS Center
Information on indicators
Enter the data based on the colour-coded cells
| Financial Information: |  | Management Information: |  |  | Programmatic Information:
| Financial Information: | [8 empty] | Enter finance data in every orange cell like this.
| Currency of the grant |  | €
F1: Budget and disbursements by Global Fund
| Disbursement | [15 empty] | 0
| Reporting period | [5 empty] | P1-P6 | P7 | P8 | P9 | P10 | P11 | P12 | % Cumulative |  |  | 0
| Budget (in €) | [5 empty] | 4589159 | 695010.92 | 438931.92 | 782033.17 | 612913 | 716244 | 596000 | 96.27% |  |  | 0
| Disbursements by GF (in €) | [5 empty] | 5716813 | P9: 1139286; P10: 1193451; P12: 66587 |  |  |  | 0
| Cumulative budget | [5 empty] | 4589159 | 5284169.92 | 5723101.84 | 6505135.01 | 7118048.01 | 7834292.01 | 8430292.01 |  |  |  | 0
| Cumulative disbursements | [5 empty] | 5716813 | 5716813 | 5716813 | 6856099 | 8049550 | 8049550 | 8116137 |  |  |  | 4589159
|  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 96.27% |  |  |  | 5284169.92
F2: Budget and actual expenditures by Grant Objective
| Grant Objective | Cumulative Budget (in €) | Cumulative Expenditures (in €)
| Improve performance of GFATM Round VI through improved infrastructure | 1053668.01 | 943249.53
| Improve quality of Life of PLWH | 5375800.84 | 5320872.17
| Strengthen the National League of PLWH | 730937.24 | 566892.17
| Planning and administration | 1269885.57 | 1234977.29
| Total | 8430291.66 | 8065991.16 |  | OK: Data match | bar: P7
| F3: Disbursements and expenditures | [15 empty] | 5723101.84
6505135.01
|  | Prior to reporting period | Current reporting period | Total Spent and Disbursement (in €) | [11 empty] | 7834292.01
| Disbursed by Global Fund | 8049550 | 66587 | 8116137
| PR expenditure and disbursement | 6844559.9448 | 1282767 | 8127326.9448
| Disbursed to SRs | 4082741.6869 | 772678.7631 | 4855420.45
| SR expenditures | 4082742.98 | 711332 | 4794074.98
F4: Latest PR reporting and disbursement cycle
Last fund disbursement: Number of calendar days
|  | Expected (days) | Actual (days)
| Days taken to submit final PU/DR to LFA | 45 | 34
| Days taken for disbursement to reach PR | 45 | 82
| Days taken for disbursement to reach SRs | 20 | 20
| Management Information: | [5 empty] | Enter management data in every blue cell. | bar: P10
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs)
|  |  | Fulfilled | Not fulfilled, but within deadline | Not fulfilled, and past the deadline | Total
| Conditions precedent (CPs) |  | 5 |  |  | 5
| Time Bound Actions (TBAs) |  |  |  |  | 0
M2: Status of key PR management positions
|  | Planned | Filled | Vacant
| PMU | 11 | 13 | -2
M3: Contractual arrangements (SRs)
|  | Identified | Assessed | Approved | Signed | Receiving Funding
| SRs | 4 | 4 | 4 | 4 | 3
M4: Number of complete reports received on time
|  | # Expected | # Received | Pending
| SSR to SR | 23 | 22 | 1
| SRs to PR | 3 | 3 | 0
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals
|  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
Budget Approved*
Obligations
Expenditures
| Budget Approved cumulative* | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Obligations cumulative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Expenditures cumulative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
* Includes only EFR category 4 and 5 (Health products and health equipment & Medicines and Pharmaceuticals)
M6: Difference between current and safety stock
| Component | Products | (1) Number of tablets per patient per day (Review country treatment guidelines) | (2 = 1 x 30) Monthly treatment (Tablets per patient x 30 days) | (3) Total patients in treatment | (4 = 2 x 3) Total # tab/pills required for all patients per month | (5) Current stock in central warehouse (that does not expire within the next 3 months) | (6 = 5 / 4) Stock level expressed in months of treatment for all current patients | (7) Level of safety stock (expressed in months and defined by country) | (8 = 6 - 7) Difference between current stock and safety stock
| HIV / AIDS | P1: Please Select
Please Select
Please Select
Please Select
| Programmatic Information: | P9: Enter performance data in every yellow cell.
| Programmatic indicators (Performance Framework ) |  |  | Code | Directly Tied? |  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
TOP 3 | Number of people living with HIV/AIDS reached with care and support services (Numărul persoanelor care trăiesc cu HIV / SIDA au primit suport social) |  |  | 1.7. | Yes | Target | 3250 | 3500 | 3750 | 4000 | 4375 | 4750 | 4832 | 5207 | 5357 | 5507 | 5657 | 5807
[6 empty] | Achieved | 2093 | 2817 | 3197 | 3717 | 3976 | 4296 | 4564 | 4853 | 5107 | 5327 | 5519 | 5704
| Number of IDUs on oppoid substitution therapy that receive at least 3 support services from NGOs working in DUs rehabilitation (Numărul de UDI care sunt în terapia de substituţie cu metadonă şi primesc cel puţin 3 servicii de suport din partea ONG-urilor care lucrează la reabilitarea UDI) |  |  | 1.5. | Yes | Target | 54 | 108 | 162 | 216 | 280 | 344 | 407 | 471 | 511 | 551 | 591 | 631
[6 empty] | Achieved | 61 | 131 | 180 | 225 | 284 | 322 | 368 | 437 | 462 | 481 | 500 | 534
| Number of medical (doctors and nurses) and non-medical staff (psychologists, social assistants, peer consultants) trained in HIV/AIDS (Numărul personalului medical (medici şi aistente medicale) şi non-medical (psihologi, asistenţi sociali, educatori de la egal la egal) instruiţi în HIV/SIDA) |  |  | 1.1. | Yes | Target | 25 | 150 | 225 | 400 | 500 | 625 | 1224 | 1410 | 1510 | 1610 | 1710 | 1810
[6 empty] | Achieved | 50 | 174 | 268 | 594 | 788 | 1099 | 1224 | 1395 | 1448 | 1608 | 1804 | 1898
| Number of PLWHA receiving palliative care (Numărul de PTH care primesc îngrijiri paliative) |  |  | 1.2. | No | Target | n/a | n/a | n/a | 15 | 20 | 25 | 39 | 44 | 49 | 54 | 59 | 64
[6 empty] | Achieved | n/a | n/a | n/a | 7 | 18 | 34 | 49 | 59 | 76 | 76 | 86 | 103
| Number of PLWHA receiving food parcels to improve ARV treatment adherence (Numărul de PTH care primesc pachete alimentare pentru a îmbunătăți aderenţa la tratamentul ARV) |  |  | 1.3. | Yes | Target | 108 | 216 | 324 | 432 | 573 | 715 | 1011 | 1061 | 1101 | 1141 | 1181 | 1221
[6 empty] | Achieved | 108 | 269 | 462 | 588 | 803 | 961 | 1134 | 1257 | 1257 | 1452 | 1554 | 1611
| Number of children infected and affected by HIV/AIDS who receive social support (Numărul de copii infectaţi şi afectaţi de HIV/SIDA care primesc suport social) |  |  | 1.4. | Yes | Target | 95 | 125 | 155 | 185 | 216 | 248 | 352 | 372 | 392 | 412 | 432 | 452
[6 empty] | Achieved | 91 | 133 | 195 | 236 | 298 | 332 | 363 | 395 | 395 | 462 | 482 | 509
| Number and percentage of individuals currently on OST who have been on OST continuously at least 6 months for the past 12 months (Numărul şi procentul persoanelor aflate în tratamentul de substituție cu metadonă (TS) care au fost în TS continuu cel puțin 6 luni pe parcursul ultimelor 12 luni) |  |  | 1.6. | No | Target | n/a | n/a | n/a | n/a | n/a | 50% | n/a | 55% | n/a | 57% | n/a | 59%
[6 empty] | Achieved | n/a | n/a | n/a | n/a | n/a | 53.18% | n/a | 56.04% | n/a | 57.85% | n/a | 42.68%
| Number of lawyers from the free legal system and ombudsmen institutes trained in HR, non-discrimination and principles of legal aid (Numărul de avocaţi din sistemul juridic gratuit şi institutele de mediatori instruiţi în drepturile omului, non-discriminării şi a principiilor de asistenţă juridică) |  |  | 1.8. | Yes | Target | 50 | 100 | 150 | 200 | 250 | 300 | 526 | 601 | 651 | 701 | 751 | 801
[6 empty] | Achieved | 51 | 102 | 152 | 244 | 294 | 426 | 524 | 602 | 627 | 702 | 751 | 801
| Number of PLWHA assisted by legal aid (consultancies offered by legal network) (Numărul PTH furnizate cu ajutor juridic (consultaţii oferite de către reţeaua juridică)) |  |  | 1.10. | Yes | Target | 10 | 20 | 30 | 40 | 55 | 70 | 212 | 242 | 272 | 302 | 332 | 362
[6 empty] | Achieved | 25 | 78 | 108 | 142 | 163 | 182 | 210 | 251 | 296 | 344 | 394 | 429
| Number of the PLWHA League members trained in languages, strategic planning, M&E etc.(Numărul de membri ai Ligii PTH instruiţi în limbi, planificare strategică, M&E, etc.)) |  |  | 1.11. | Yes | Target | 35 | 70 | 105 | 140 | 190 | 240 | 390 | 440 | 490 | 540 | 590 | 640
[6 empty] | Achieved |  | 78 |  |  |  | 340 | 411 | 542 | 608 | 712 | 741 | 780
| Table is automatically updated. No data or information is to be entered here. |  |  | Code | Directly Tied? |  | 0 | 0 | 0 | 0 | 0 | P1-P6 | P7 | P8 | P9 | P10 | P11 | P12
| Number of people living with HIV/AIDS reached with care and support services (Numărul persoanelor care trăiesc cu HIV / SIDA au primit suport social) |  |  | 1.7. | Yes | Target | 3250 | 3500 | 3750 | 4000 | 4375 | 4750 | 4832 | 5207 | 5357 | 5507 | 5657 | 5807
[6 empty] | Achieved | 2093 | 2817 | 3197 | 3717 | 3976 | 4296 | 4564 | 4853 | 5107 | 5327 | 5519 | 5704
| Number of IDUs on oppoid substitution therapy that receive at least 3 support services from NGOs working in DUs rehabilitation (Numărul de UDI care sunt în terapia de substituţie cu metadonă şi primesc cel puţin 3 servicii de suport din partea ONG-urilor care lucrează la reabilitarea UDI) |  |  | 1.5. | Yes | Target | 54 | 108 | 162 | 216 | 280 | 344 | 407 | 471 | 511 | 551 | 591 | 631
[6 empty] | Achieved | 61 | 131 | 180 | 225 | 284 | 322 | 368 | 437 | 462 | 481 | 500 | 534
| Number of medical (doctors and nurses) and non-medical staff (psychologists, social assistants, peer consultants) trained in HIV/AIDS (Numărul personalului medical (medici şi aistente medicale) şi non-medical (psihologi, asistenţi sociali, educatori de la egal la egal) instruiţi în HIV/SIDA) |  |  | 1.1. | Yes | Target | 25 | 150 | 225 | 400 | 500 | 625 | 1224 | 1410 | 1510 | 1610 | 1710 | 1810
[6 empty] | Achieved | 50 | 174 | 268 | 594 | 788 | 1099 | 1224 | 1395 | 1448 | 1608 | 1804 | 1898
Note on B30: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.
Note on B72: If data are not available, do not enter zeros; rather, leave the cells in the table blank.
Note on B73: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B79: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B94: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.
Menu

## Grant Detail
Dashboard: Moldova - HIV / AIDS
Country: | Moldova |  | Title of the Grant: |  | Reducing HIV-related burden in the Republic of Moldova
Component: | HIV / AIDS | Grant No. | MOL-809-G06-H | Start Date: |  | January 01, 2010 | Total Funding | 8430291
Round: | SSF (Round 8) | Phase: | Phase 1 | Principal Recipient: |  | PAS Center
Report Period: | P12 | from: | July 01, 2012 | to: |  | December 31, 2012 | Latest Rating: | A1
Local Fund Agent: | PwC (PricewaterhouseCoopers) |  |  | Fund Portfolio Manager: |  | Tatiana Vinichenko
Prepared by: | PAS Center |  |  | Report preparation date: |  | April, 2013
http://www.crwflags.com/fotw/flags/country.html
Menu

## Finance
Dashboard: Moldova - HIV / AIDS
SSF (Round 8) | Phase 1 |  |  |  | Report Period: |  | P12
Latest Rating: | A1 |  | PAS Center |  | From: |  | July 01, 2012
|  | Reducing HIV-related burden in the Republic of Moldova |  |  |  | To: | December 31, 2012
Financial Indicators
F1: Budget and disbursements by Global Fund - in (€) Report Period: P12 |  |  |  | F3: Disbursements and expenditures - in (€) Report Period: P12
Comments: | The cumulative disbursement rate is 96.27%. The variance is due to funds not used as a result of delays in opening of the Social Regional Centers for assistance of people infected and affected by HIV. (Rata cumulativă a disbursării este de 96.27%.Variația este cauzată de fondurile neutilizate urmare a întârzierilor în deschiderea Centrelor sociale regionale pentru asistența PTH.) |  |  | Comments:
F2: Budget and actual expenditures by Grant Objective - in (€) Report Period: P12 |  |  |  | F4: Latest PR reporting and disbursement cycle Report Period: P12
Comments: | The cumulative rate of absorbtion from disbursements is 99.38% and from budget - 95.68%.Variance between budget and expenditure is mainly due delays in opening of the Social Regional Centers for assistance of people infected and affected by HIV, which led to lower absorption of funds committed for running costs of the centers, and lower abortion of funds for grants to NGOs to ensure proper operations of the regional centers. Despite this it is important to mention that this fact did not influence the range or quality of services provided by NGOs to PLHIV and their families. (Rata cumulativă de absobţie din disbursare este de 99.38%, iar din buget este de 95.68%. Variaţia dintre buget și cheltuieli, este în mare parte determinată deschiderea cu întârziere a Centrelor sociale regionale pentru asistenţa PTH, care a dus la absorbția mai mică a fondurilor planificate pentru cheltuieli curente de funcţionare a centrelor și absorbţie mai mic a fondurilor planificate pentru grantarea ONG-urilor care suplinesc CSR cu servicii. Cu toate acestea, este important de menționat că acest fapt nu a influențat gama sau calitatea serviciilor oferite de ONG-uri pentru PTH și familiile lor.) |  |  | Comments: | The PUDR for Semester 2, 2012 has been submitted to TGF on August 03, 2012, and the version revised bz LFA on September 12, 2012. The disbursment reached PR on December 12, 2012 (82 days after the PUDR). (Actualizarea progresului şi Cererea de disbursare (PUDR) pentru Semestrul 1, 2012 a fost transmisă Fondului Global pe date de 03.08.2012, iar versiunea revizuită de Agentul Local al Fondului pe data de 12.09.12. Disbursarea ultimei tranşe din cadrul Perioadei 1 a fost făcută pe 04.12.2012 (82 zile de la PUDR).)
Last fund disbursement: Calendar days
[6 empty] | Expected (days) | Actual (days)
|  |  |  | Days taken to submit final PU/DR to LFA |  | 45 | 34
|  |  |  | Days taken for disbursement to reach PR |  | 45 | 82
|  |  |  | Days taken for disbursement to reach SRs |  | 20 | 20
Menu

## Management
Dashboard: Moldova - HIV / AIDS
SSF (Round 8) | Phase 1 |  |  |  |  | Report Period: |  | P12
Latest Rating: | A1 |  | PAS Center |  |  | From: |  | July 01, 2012
|  | Reducing HIV-related burden in the Republic of Moldova |  |  |  |  | To: | December 31, 2012
Management Indicators
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) Report Period: P12 |  |  |  | M2: Status of key PR management positions Report Period: P12
Comments: | All five conditions precedent and/or other special conditions have been fulfilled in strict accordance with their provisions and timeline. (Toate cele cinci condiții precedente și/sau alte condiții speciale au fost îndeplinite, în strictă conformitate cu prevederile contractuale.) |  |  | Comments: | Two full time positions and 11 part time. (Două poziţii cu normă plină şi 11 - parţială.)
M3: Contractual arrangements (SRs) Report Period: P12 |  |  |  | M4: Number of complete reports received on time Report Period: P12
Comments: | Four Sub-recipients (SRs) have been identified to implement different components within the program: Soros Foundation-Moldova (SFM); League of people living with HIV of Moldova; New Life, Moldovan Institute for Human Rights. One SR (SFM) has been earlier assessed by the governmental PR of GF grants as it acts as an SR since GF Round one. Two other SRs have been assessed (New Life and Moldovan Institute for Human Rights) by PAS Center the last one (League of people living with HIV of Moldova) by TGF Local Fund Agent. Four sub-grant agreements have been signe following the assessment. In September 2011, due to lack of capacity for adequate implementation of the grant portion contracted the sub-grant agreement with one of the SRs (League of people living with HIV) was terminated and the management of activities has been entrusted to an other SR ( SFM). Respectively three sub-recipients are currently receiving funds within the grant. (Patru Sub-Recipienţi (SR), au fost identificaţi pentru a implementa diferite componente în cadrul programului: Fundația Soros-Moldova (FSM), Liga persoanelor care trăiesc cu HIV din Moldova, Viaţa Nouă, Institutul pentru Drepturile Omului din Moldova. Un SR (SFM) a fost evaluată anterior de către PR guvernamental, deoarece activează în calitate de SR începănd cu Runda 1. Alţi doi SR au fost evaluaţi (Viaţa Nouă și Institutul pentru Drepturile Omului din Moldova) de către Centrul PAS iar ultimul (Liga persoanelor care trăiesc cu HIV din Republica Moldova) de către Agentul Local al Fondului Global. Urmare a evaluării au fost semnate patru acorduri de sub-grant. În septembrie 2011, din cauza lipsei de capacitate pentru implementarea adecvată a componentului de grant contractat acordul de sub-finantare cu unul dintre SR (Liga persoanelor care trăiesc cu HIV) a fost reziliat și gestionarea activităților a fost încredințată altui SR (SFM). Respectiv, la moment , primesc fonduri din cadrul grantului trei SR.) |  |  | Comments: | The SRs’ quarterly reports (financial report, activity report and performance framework) are due to the PR not later than 25 days after the close of each quarter and are generally submitted in time. The clearance period vary from one SR to an other subject to the completeness and consistence of the reports. For the SR SFM the Sub-subrecipients financial reports are due quarterly and can be submitted during the following quarter, the activity reports are due not later than 10 days from the end of each month and are generally submitted in time except one Ssr - NGO Master in Public Health – that is constantly late in reporting. During the reporting period reflected in this dashboard 22 reports from 23 due were submited in time. For the SR New Life the reports (financial, activity and indicators) are due not later than 15 days after the close of each quarter and are generally submitted in time. (Rapoartele trimestriale ale SR (raport financiar, raport de activitate și cadrul de performanță) urmează a fi transmise RP nu mai târziu de 25 de zile de la încheierea fiecărui trimestru. Rapoartele sunt de regulă prezentate la timp. Perioada de verificare şi aprobare variază de la un SR la altul în funcţie de exhaustivitatea și consistență rapoartelor. Pentru SR FSM rapoarte financiare ale Sub-subrecipienţilor (Ssr) urmează a fi transmise trimestrial și pot fi prezentate în trimestrul următor, rapoartele de activitate urmează a fi prezentate nu mai târziu de 10 zile de la sfârșitul fiecărei luni și sunt, în general, prezentate la timp cu excepția unui Ssr - ONG Master în Sănătatea Publică - care întârzie raportarea în mod constant . Pe parcursul perioadei de raportare reflectă în aces raport, 22 raporte din 23 planificate au fost transmise în termeni. Pentru SR Viaţa Nouă rapoartele (financiare, de activitate și indicatorii) urmează a fi prezentate nu mai târziu de 15 zile de la încheierea fiecărui trimestru și sunt, de regulă, prezentate la timp.)
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals |  |  |  | M6: Difference between current and safety stock Report Period: P12
Comments: | N/A |  |  | Comments: | N/A
|  |  |  | Component | Products | Stock level expressed in months of treatment for all current patients | Months of safety stock | Difference between current stock and safety stock
|  |  |  | HIV / AIDS | Please Select |  | 0
[5 empty] | Please Select |  | 0
[5 empty] | Please Select |  | 0
[5 empty] | Please Select |  | 0
* Includes only EFR category 4 and 5 (Health products and health equipment & Medicines and Pharmaceuticals)
Menu

## Programmatic
Dashboard: Moldova - HIV / AIDS
SSF (Round 8) | Phase 1 | [8 empty] | Report Period: |  | P12
Latest Rating: | A1 |  | PAS Center | [7 empty] | From: | July 01, 2012
|  | Reducing HIV-related burden in the Republic of Moldova | [8 empty] | To: | December 31, 2012 | [7 empty] | Raiting |  | Valor
Programmatic Indicators
Number of people living with HIV/AIDS reached with care and support services (Numărul persoanelor care trăiesc cu HIV / SIDA au primit suport social) |  |  |  | Number of IDUs on oppoid substitution therapy that receive at least 3 support services from NGOs working in DUs rehabilitation (Numărul de UDI care sunt în terapia de substituţie cu metadonă şi primesc cel puţin 3 servicii de suport din partea ONG-urilor care lucrează la reabilitarea UDI) |  |  |  | Number of medical (doctors and nurses) and non-medical staff (psychologists, social assistants, peer consultants) trained in HIV/AIDS (Numărul personalului medical (medici şi aistente medicale) şi non-medical (psihologi, asistenţi sociali, educatori de la egal la egal) instruiţi în HIV/SIDA)
Comment: P1 | The indicator is substantially met (98%). The main part of PLHIV have been reached by project. Currently the number of new PLHIV that can be covered with support services is mostly related to new people diagnosed with HIV. To mention that not every PLHIV will be covered with support due to refusal to receive psycho-social services, migration, etc. (Indicatorul este substanţial atins (98%). Cea mai mare parte a persoanelor HIV pozitive au fost acoperite cu serviciile proiectului. În prezent, numărul persoanelor HIV pozitive, care pot fi primar acoperite cu servicii de suport este în mare parte legată de oameni noi diagnosticaţi cu HIV. De menţionat că nu toate PTH vor fi acoperite cu suport din cauza refuzului servicilor psiho-sociale, migrației, etc.) |  |  | Comment: P2 | The indicator is achieved in proportion of 85%. Reason for variance: The number of PWID on OST covered with psycho-social support is directly dependent to the number of PWID enrolled in OST treatment (new cases) which is continuously decreasing. The result reported for a specific period reflect new OST patients (who initiated OST in the reporting period) covered with support services, as well as a small percentage of OST patients enrolled before the reporting period but not yet reached\covered with project services. Smaller the number of new entrances in OST Treatment – smaller the number of OTS patients that can be covered with psycho-support services. In 2012, 83 new clients were enrolled in the substitution therapy program, the number of OST patients covered with support services (primarily reached) being 97. (Indicatorul este atins în proporție de 85%. Cauza variaţiei: Numărul de CDI în TSO acoperiţi cu suport psiho-social este direct dependent de numărul de CDI înrolaţi în TSO (cazuri noi), care este în continuă scădere. Rezultatul raportat pentru o anumită perioadă reflecta pacienţii noi înrolaţi în TSO (care au inițiat TSO în perioada de raportare), acoperiţi cu servicii de suport, precum și un procent mic de pacienţi înrolaţi în OST înaintea perioadei de raportare, dar nu au fost încă acoperiţi cu servicii. Cu cît este mai mic numărul de noi înrolaţi în TSO – cu atît este mai mic număr de pacienți în TSO care pot fi acoperiţi cu servicii psiho-sociale. În anul 2012, 83 de pacienţi noi au fost înrolaţi în terapie de substituție, numărul de pacienţi în OST acoperiţi cu servicii de suport (atinşi primar) fiind 97.) |  |  | Comment: P3 | The indicator is overachieved. Reason for variance: the number of non-medical staff from NSRS’s MDTs trained is higher due to the organization of the trainings in partnership with ILO and sharing of costs as per MLSPF request. (Indicatorul este depășit. Cauza variaţiei: numărul de specialişti non-medicali, reprezentanţi ai SNR, instruiţi este mai mare datorită organizării cursurilor în parteneriat cu OIM și partajare a costurilor conform solicitării MMPSF.)
Indicators |  |  | Target (cumulative over program term) | Achieved (cumulative over program term) | 0% - 59% | 60% - 89% | > 90% | Comments |  |  |  |  | min | 0 | 30% | 60% | 90% | 100% |  | min | 0 | 20% | 40% | 60% | 80%
Number of people living with HIV/AIDS reached with care and support services (Numărul persoanelor care trăiesc cu HIV / SIDA au primit suport social) |  |  | 5807 | 5704 | 98.23% |  |  | During S6 a total 377 PLHIV were primarily reached with care and support services through four social regional centers working in this area and 10 territorial organizations. The beneficiaries are provided with the following services: psycho-social counseling and registration, medical consultations, distribution of informational materials and peer health counseling, referral to services provided by public institutions, self-support groups, etc. The indicator is substantially met. (în semestrul 6, 377 PTH au fost primari acoperiți cu servicii de îngrijire şi suport în cadrul a 4 Centre Sociale Regionale şi 10 organizaţii care lucrează în acest domeniu. Beneficiariilor le sunt oferite următoarele servicii: consiliere psiho-socială, consultaţii medicale, distribuţia materialelor informaţionale şi consiliere de la egal la egal, servicii de referinţă furnizate de către instituţiile publice, grupuri de auto-suport, etc. Indicatorul este substanţial atins.) |  |  |  |  | max | 30% | 60% | 90% | 100% | 200% |  | max | 20% | 40% | 60% | 80% | 100%
Number of IDUs on oppoid substitution therapy that receive at least 3 support services from NGOs working in DUs rehabilitation (Numărul de UDI care sunt în terapia de substituţie cu metadonă şi primesc cel puţin 3 servicii de suport din partea ONG-urilor care lucrează la reabilitarea UDI) |  |  | 631 | 534 | 84.63% |  |  | During S6 a total of 53 PWID on opioid substitution therapy (primarily reached) received at least 3 support services from the package (psychosocial support, self-support groups, peer to peer education, distributions of informational materials and food parcels) offered by NGOs working in PWUD rehabilitation. The indicator is achieved in proportion of 85%. Reason for variance: The number of PWID on OST covered with psycho-social support is directly dependent to the number of PWID enrolled in OST treatment (new cases) which is continuously decreasing. The result reported for a specific period reflect new OST patients (who initiated OST in the reporting period) covered with support services, as well as a small percentage of OST patients enrolled before the reporting period but not yet reached\covered with project services. Smaller the number of new entrances in OST Treatment – smaller the number of OTS patients that can be covered with psycho-support services. In 2012, 83 new clients were enrolled in the substitution therapy program, the number of OST patients covered with support services (primarily reached) being 97. (în timpul S5 un total de 53 CDI aflați în terapie de substituţie cu metadonă (primari atinși) au primit cel puţin 3 servicii de suport social din pachetul (sprijin psiho-social, grupuri de suport reciproc, educație de la egal la egal, distribuţia de materiale informaţionale şi pachete alimentare și igienice) oferite în cadrul centrelor de zi de ONG-uri care lucrează în domeniul reabilitării CDI. Indicatorul este atins în proporție de 85%. Motiv pentru variație: Numărul de CDI în TSO acoperiţi cu suport psiho-social este direct dependent de numărul de CDI înrolaţi în TSO (cazuri noi), care este în continuă scădere. Rezultatul raportat pentru o anumită perioadă reflecta pacienţii noi înrolaţi în TSO (care au inițiat TSO în perioada de raportare), acoperiţi cu servicii de suport, precum și un procent mic de pacienţi înrolaţi în OST înaintea perioadei de raportare, dar nu au fost încă acoperiţi cu servicii. Cu cît este mai mic numărul de noi înrolaţi în TSO – cu atît este mai mic număr de pacienți în TSO care pot fi acoperiţi cu servicii psiho-sociale. În anul 2012, 83 de pacienţi noi au fost înrolaţi în terapie de substituție, numărul de pacienţi în OST acoperiţi cu servicii de suport (atinşi primar) fiind 97.) | [5 empty] | de 0 a 0.3 | de 0.3 a 0.6 | de 0.6 a 0.9 | de 0.9 a 1 | de 1 a 2 | Rating | Valor | de 0 a 0.2 | de 0.2 a 0.4 | de 0.4 a 0.6 | de 0.6 a 0.8 | de 0.8 a 1
Number of medical (doctors and nurses) and non-medical staff (psychologists, social assistants, peer consultants) trained in HIV/AIDS (Numărul personalului medical (medici şi aistente medicale) şi non-medical (psihologi, asistenţi sociali, educatori de la egal la egal) instruiţi în HIV/SIDA) |  |  | 1810 | 1898 | 104.9% |  |  | A total of 290 persons were trained in S6, from them: 50 medical staff attended international trainings at Clinica Lavra in HIV infection and Clinic administration and management of HIV infection, 68 non-medical staff from MDT under National Social Reference System were trained in Protection and assistance to victims of human trafficking, domestic violence and people living with HIV within the National Reference System; 23 representatives of SRC were trained in HIV infection; 19 representatives of SRC were trained in Case management of people living with HIV; 52 medical specialists were trained in TB/HIV collaborative activities: ICF/IPT; 27 medical staff were trained HIV infection; 51 social assistants in most affected regions were trained in HIV/AIDS. The indicator is overachieved. Reason for variance: the number of non-medical staff from NSRS’s MDTs trained is higher due to the organization of the trainings in partnership with ILO and sharing of costs as per MLSPF request. (Un total de 290 persoane au participat lainstruiri în semestrul 6, dintre care: 50 lucrători medicali au fost instruiţi la training-urile internaţionale organizate la Clinica Lavra în managementul clinic al infecţiei HIV; 68 lucrători non-medicali din echipele multidisciplinare din cadrul Sistemului Naţional Social de Referinţă au fost instruiţi în protecţia şi asistenţa victimelor traficului uman, violenţa domestică şi PTH în cadrul Sistemului Naţional de Referire; 23 reprezentanţi au fost instruiţi în HIV/SIDA şi 19 în managementul de caz al persoanei care trăieşte cu HIV; 52 lucrători medicali au fost instruiţi în activităţi colaborative TB/HIV; 27 specialişti în asistenţă medicală primară au fost instruiţi în infecţia HIV; 51 asistenţi sociali din cele mai afectate regiuni au fost instruiţi în HIV/SIDA). Indicatorul este depășit.Cauza variaţiei: numărul de specialişti non-medicali - reprezentanţi ai SNR instruiţi este mai mare datorită organizării cursurilor în parteneriat cu OIM și partajare a costurilor conform solicitării MMPSF. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number of PLWHA receiving palliative care (Numărul de PTH care primesc îngrijiri paliative) |  |  | 64 | 103 | 160.9% |  |  | 27 HIV infected patients received palliative care services within the ARV Treatment facility during reported period (care of skin, hair, nails, eyes, mouth, pneumonia prophylactic treatment, symptomatic treatment, alimentation, etc.). The indicator is overachieved. Reason for variance: The number of beneficiaries provided with palliative care services is determined by the need of such services (patients’ medical condition) among PLHIV during a specific period. The need varies from one period to another, but there is no waiting list and all patients in need of palliative care services receive them within the Dermatological and Communicable Diseases Hospital. (27 de pacienţi infectaţi cu HIV au primit servicii de îngrijiri paliative în cadrul departamentului de tratament ARV în timpul perioadei raportate (îngrijire a pielii, părului, unghiilor, cavității bucale, ochilor, tratamentul profilactic al pneumoniei, tratamentul medicamentos simptomatic, alimentaţie, etc. Indicatorul este depășit.Cauza variaţiei: Numărul de beneficiari acoperiţi cu servicii de îngrijire paliativă este determinată de necesitatea acestui tip de servicii (condiţia medicală a pacienților) în randul persoanelor cu HIV pe parcursul unei anumite perioade. Necesitatea variază de la o perioadă la alta, însă nu există listă de așteptare și toți pacienții care au nevoie de servicii de îngrijire paliativă le primesc în cadrul Spitalulului Dermatologie şi Maladii Comunicabile.) | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number of PLWHA receiving food parcels to improve ARV treatment adherence (Numărul de PTH care primesc pachete alimentare pentru a îmbunătăți aderenţa la tratamentul ARV) |  |  | 1221 | 1611 | 131.9% |  |  | A total of 159 PLHIV received food parcels during S6 (primarily reached). Each quarter 840 PLHIV out of those on ARV treatment, selected based on socio-economic vulnerability, benefit of food parcels. The indicator is overachieved. Reason for variance: Food parcels distribution is subject to PLHIV socio-economic vulnerability determined quarterly based on a unique set of vulnerability criteria. A total of 840 food parcels are distributed quarterly for better adherence to treatment, in both civilian and penitentiary sectors, and about 10% of beneficiaries are new beneficiaries (primarily reached). (Un număr total de 159 PTH au primit pachete alimentre în timpul semestrului 6 (beneficiari primari). În fiecare trimestru 840 PTH din răndul celoraflaţi în tratament ARV, selectaţi în baza vulnerabilităţii socio-economice, beneficiază de pachete alimentare. Indicatorul este depășit.Cauza variaţiei: distribuția pachetelor alimentare se face în funcţie de vulnerabilitatea socio-economică a PTH evaluată trimestrial în baza unui set unic de criterii de vulnerabilitate. În total 840 de pachete alimentare sunt distribuite trimestrial pentru creşterea aderenţei la tratament, în ambele sectoare civil și penitenciar, aproximativ 10% din beneficiari fiind beneficiari noi (primar acoperiţi). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number of children infected and affected by HIV/AIDS who receive social support (Numărul de copii infectaţi şi afectaţi de HIV/SIDA care primesc suport social) |  |  | 452 | 509 | 112.6% |  |  | A total of 47 children received social support during S6 (primarily reached), from them 10 HIV positive children and 37 children with unknown status born from HIV positive mothers. Each quarter 230 children (all HIV infected children that can be reached and the majority of children born from HIV infected mother with unknown status) benefit of food parcels. At the same time each semester HIV positive children benefit of a set of stationary and clothing for school as part of social support program (95 HIV positive children received such support during reported period). The indicator is overachieved. Reason for variance: The number of children primarily reached with social support is determined by the number of children diagnosed with HIV and by the number of children born from HIV positive mothers immediately before and during the reported period. (un număr total de 47 copii au primit suport social în timpul semestrului 6 (beneficiari primari), dintre care 10 copiiHIV infectaţi și 37 de copii cu statut nedeterminat născuți din mame HIV pozitive. În fiecare trimestru, 230 de copii (toți copiii infectați cu HIV, care pot fi acoperiţi cu servicii, și majoritatea copiilor născuți din mame infectate cu HIV pozitive) beneficiază de pachete alimentare. În același timp, în fiecare semestru copii HIV pozitivi beneficiază de un set de haine şi rechizite pentru scoala ca parte a programului de suport social (95 de copii HIV infectaţi au primit acest suport pe parcursul perioadei de raportare). Indicatorul este depășit. Cauza variaţiei: Numărul de copii primar acoperiţi cu suport social este determinat de numărul de copii diagnosticati cu HIV și de numărul de copii născuți din mame HIV pozitive imediat înainte și în timpul perioadei de raportare. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Number and percentage of individuals currently on OST who have been on OST continuously at least 6 months for the past 12 months (Numărul şi procentul persoanelor aflate în tratamentul de substituție cu metadonă (TS) care au fost în TS continuu cel puțin 6 luni pe parcursul ultimelor 12 luni) |  |  | 59% | 42.68% | 72.34% |  |  | A total of 35 individuals out of 82 that initiated OST during P9-P10 have completing at least 6 months of continuous treatment on OST. Currently OST is provided in three sites: Republican Narcological Dispensary, Balti Municipal Hospital and the Department of Penitentiary Institutions (in 7 penitentiaries). The indicator is partially achieved (73%). Reason for variance: the rate of retention in treatment is determined by a series of factors, namely: seasonal migration of patients (both abroad and in country), emergency of seasonal illicit drugs on black market, low doses of methadone (below recommended 60mg minimal average dose), and concurrent use of illicit drugs, methadone distribution restricted to OST for all patients including for drug users in stable remission, repeated enrollment in treatment without prior psycho-social support to prepare the patient for the next attempt, misconceptions about OST in both medical and psych-social support teams, negative image of OST among PWID, etc. (un total de 35 de persoane din 82 care a initiat TSO în timpul Tr.9-Tr.10 (ianuarie+iunie 2012) au finalizat cel puţin 6 luni de tratament continuu. Actualmente TSO este oferită in trei site-uri: Dispensarul Republican de Narcologie, Spitalul Municipal Bălţi şi Departamentul Instituţiilor Penitenciare (în 7 penitenciare). Indicatoruleste atins parțial (73%). Cauza variaţiei: rata de retenție în tratament este determinat de o serie de factori, și anume: migrația sezonieră a pacienti (atât în străinătate cît și în țară), apariţia droguri ilicite de sezon pe piața neagră, doze mici de metadona (doze mai mici decît doza minimiă recomandată de 60mg), precum și utilizarea concomitentă a drogurilor ilicite, distribuție metadonei limitată la punctul de distribuţie pentru toti pacientii, inclusiv pentru consumatorii de droguri în remisie stabila, înrolare repetată în tratamentul fără suport psiho-social preventiv pentru a pregăti pacientul pentru următoarea încercare, conceptii gresite despre TSO în echipele medicale și echipele de asistență psiho-socială, imaginea negativă a TSO printre CDI, etc | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Number of lawyers from the free legal system and ombudsmen institutes trained in HR, non-discrimination and principles of legal aid (Numărul de avocaţi din sistemul juridic gratuit şi institutele de mediatori instruiţi în drepturile omului, non-discriminării şi a principiilor de asistenţă juridică) |  |  | 801 | 801 | 100% |  |  | A total of 99 lawyers and health care workers have been trained during reported period within 4 training courses on human rights, non-discrimination, confidentiality and reparation for moral prejudices of people living with HIV, confidentiality of personal data with regard to health care, etc. (un număr total de 99 de avocaţi au fost instruiţi în semestrul 6 în cadrul a 4 cursuri de instruire în drepturile omului, non-discriminare, confidenţialitate şi despăgubire a prejudiciile morale ale PTH). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Number of PLWHA assisted by legal aid (consultancies offered by legal network) (Numărul PTH furnizate cu ajutor juridic (consultaţii oferite de către reţeaua juridică)) |  |  | 362 | 429 | 118.5% |  |  | A total of 85 consultancies were offered remotely by traveling to project sites of 4 lawyers, during S6. They offered legal assistance related to issues of legal, civil (including disclosure of HIV status), administrative nature to all PLHIV in need. The indicator is overachieved. Reason for variance: The number of consultancies offered by project lawyers is determined by the request of legal support from PLHIV and can vary from one period to another. With the opening of Social Regional Centers (two during reported period) project lawyer provide services within the Centers facilities (with a specific periodicity) bringing this way services closer to the beneficiary and increasing their access to legal support. The increase in number of consultancies provided has no financial impact as the layers are fool day project consultants with fix remuneration. (pe parcursul semestrului 6 au fost oferite 85 de consultaţii în teren de către 4 avocaţi. Aceștea au oferit asistenţă juridică pe aspecte de natură legală, civilă (incluzând divulgarea statutului HIV) şi administrative ale tuturor PTH care au solicitat ajutor). Indicatorul este depăşit. Cauza variaţiei: Numărul de consultaţii oferite de către avocații proiectului este determinată de cererea de asistență juridică din partea PTH și poate varia de la o perioadă la alta. Odată cu deschiderea Centrelor Sociale Regionale (două în timpul perioadei de raportare) avocaţii prestează servicii în cadrul centrelor (cu o anumită periodicitate) aducînd astfel serviciile mai aproape de beneficiar și crescînd accesul la asistență juridică. Creșterea numărului de servicii de consultanţă juridică prestate nu are impact financiar deoarece avocaţii sunt angajaţi în proiect cu yi plină de lucru şi au remunerare fixă. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Number of the PLWHA League members trained in languages, strategic planning, M&E etc.(Numărul de membri ai Ligii PTH instruiţi în limbi, planificare strategică, M&E, etc.)) |  |  | 640 | 780 | 121.9% |  |  | 68 representatives of NGOs providing services to PLHIV were trained during S6: 5 participants attended English language course (elementary), 24 social workers and peer to peer consultants from NGO which implement psycho-social support project were trained in HIV; 19 social workers, peer to peer consultants and infectious disease specialists attended a training on Strengthening the collaboration of social workers and infectious disease specialist providing services to PLHIV; 20 representatives from NGO’s Providing Care and support for the PLHIV were trained in M&E. (68 de reprezentanţi ai ONG-urilor care prestează servicii PTH au fost instruiţi în semestrul 6: 5 persoane au urmat cursuri de limbă engleză (nivelul începător), 19 lucrători sociali, educatori de la egal la egal şi infecţionişti au participat la o instruire focusată pe consolidarea colaborării lucrătorilor sociali și infecţioniştilor în prestarea de serviciilor pentru PTH, 20 de reprezentanți din ONG-uri implicate în îngrijirea şi suport pentru PTH au fost instruiți în M&E. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Menu

## Recommendations
Dashboard: Moldova - HIV / AIDS
SSF (Round 8) | Phase 1 |  |  |  |  | Report Period: | P12
Latest Rating: | A1 |  | PAS Center |  |  | From: | July 01, 2012
|  |  | Reducing HIV-related burden in the Republic of Moldova |  |  | To: | December 31, 2012
Recommendations
Are all funds reaching implementation levels and being spent according to budget?
Financial |  | Summary Comments |  |  | Recommendations
F1 |  | The cumulative disbursement rate is 96.27%. The variance is due to funds not used as a result of delays in opening of the Social Regional Centers for assistance of people infected and affected by HIV. (Rata cumulativă a disbursării este de 96.27%.Variația este cauzată de fondurile neutilizate urmare a întârzierilor în deschiderea Centrelor sociale regionale pentru asistența PTH.)
F2 |  | The cumulative rate of absorbtion from disbursements is 99.38% and from budget - 95.68%.Variance between budget and expenditure is mainly due delays in opening of the Social Regional Centers for assistance of people infected and affected by HIV, which led to lower absorption of funds committed for running costs of the centers, and lower abortion of funds for grants to NGOs to ensure proper operations of the regional centers. Despite this it is important to mention that this fact did not influence the range or quality of services provided by NGOs to PLHIV and their families. (Rata cumulativă de absobţie din disbursare este de 99.38%, iar din buget este de 95.68%. Variaţia dintre buget și cheltuieli, este în mare parte determinată deschiderea cu întârziere a Centrelor sociale regionale pentru asistenţa PTH, care a dus la absorbția mai mică a fondurilor planificate pentru cheltuieli curente de funcţionare a centrelor și absorbţie mai mic a fondurilor planificate pentru grantarea ONG-urilor care suplinesc CSR cu servicii. Cu toate acestea, este important de menționat că acest fapt nu a influențat gama sau calitatea serviciilor oferite de ONG-uri pentru PTH și familiile lor.)
F3
F4 |  | The PUDR for Semester 2, 2012 has been submitted to TGF on August 03, 2012, and the version revised bz LFA on September 12, 2012. The disbursment reached PR on December 12, 2012 (82 days after the PUDR). (Actualizarea progresului şi Cererea de disbursare (PUDR) pentru Semestrul 1, 2012 a fost transmisă Fondului Global pe date de 03.08.2012, iar versiunea revizuită de Agentul Local al Fondului pe data de 12.09.12. Disbursarea ultimei tranşe din cadrul Perioadei 1 a fost făcută pe 04.12.2012 (82 zile de la PUDR).)
Are procurement and hiring on schedule?
Management |  | Summary Comments |  |  | Recommendations
M1 |  | All five conditions precedent and/or other special conditions have been fulfilled in strict accordance with their provisions and timeline. (Toate cele cinci condiții precedente și/sau alte condiții speciale au fost îndeplinite, în strictă conformitate cu prevederile contractuale.)
M2 |  | Two full time positions and 11 part time. (Două poziţii cu normă plină şi 11 - parţială.) | #DIV/0! | #DIV/0!
M3 |  | Four Sub-recipients (SRs) have been identified to implement different components within the program: Soros Foundation-Moldova (SFM); League of people living with HIV of Moldova; New Life, Moldovan Institute for Human Rights. One SR (SFM) has been earlier assessed by the governmental PR of GF grants as it acts as an SR since GF Round one. Two other SRs have been assessed (New Life and Moldovan Institute for Human Rights) by PAS Center the last one (League of people living with HIV of Moldova) by TGF Local Fund Agent. Four sub-grant agreements have been signe following the assessment. In September 2011, due to lack of capacity for adequate implementation of the grant portion contracted the sub-grant agreement with one of the SRs (League of people living with HIV) was terminated and the management of activities has been entrusted to an other SR ( SFM). Respectively three sub-recipients are currently receiving funds within the grant. (Patru Sub-Recipienţi (SR), au fost identificaţi pentru a implementa diferite componente în cadrul programului: Fundația Soros-Moldova (FSM), Liga persoanelor care trăiesc cu HIV din Moldova, Viaţa Nouă, Institutul pentru Drepturile Omului din Moldova. Un SR (SFM) a fost evaluată anterior de către PR guvernamental, deoarece activează în calitate de SR începănd cu Runda 1. Alţi doi SR au fost evaluaţi (Viaţa Nouă și Institutul pentru Drepturile Omului din Moldova) de către Centrul PAS iar ultimul (Liga persoanelor care trăiesc cu HIV din Republica Moldova) de către Agentul Local al Fondului Global. Urmare a evaluării au fost semnate patru acorduri de sub-grant. În septembrie 2011, din cauza lipsei de capacitate pentru implementarea adecvată a componentului de grant contractat acordul de sub-finantare cu unul dintre SR (Liga persoanelor care trăiesc cu HIV) a fost reziliat și gestionarea activităților a fost încredințată altui SR (SFM). Respectiv, la moment , primesc fonduri din cadrul grantului trei SR.)
M4 |  | The SRs’ quarterly reports (financial report, activity report and performance framework) are due to the PR not later than 25 days after the close of each quarter and are generally submitted in time. The clearance period vary from one SR to an other subject to the completeness and consistence of the reports. For the SR SFM the Sub-subrecipients financial reports are due quarterly and can be submitted during the following quarter, the activity reports are due not later than 10 days from the end of each month and are generally submitted in time except one Ssr - NGO Master in Public Health – that is constantly late in reporting. During the reporting period reflected in this dashboard 22 reports from 23 due were submited in time. For the SR New Life the reports (financial, activity and indicators) are due not later than 15 days after the close of each quarter and are generally submitted in time. (Rapoartele trimestriale ale SR (raport financiar, raport de activitate și cadrul de performanță) urmează a fi transmise RP nu mai târziu de 25 de zile de la încheierea fiecărui trimestru. Rapoartele sunt de regulă prezentate la timp. Perioada de verificare şi aprobare variază de la un SR la altul în funcţie de exhaustivitatea și consistență rapoartelor. Pentru SR FSM rapoarte financiare ale Sub-subrecipienţilor (Ssr) urmează a fi transmise trimestrial și pot fi prezentate în trimestrul următor, rapoartele de activitate urmează a fi prezentate nu mai târziu de 10 zile de la sfârșitul fiecărei luni și sunt, în general, prezentate la timp cu excepția unui Ssr - ONG Master în Sănătatea Publică - care întârzie raportarea în mod constant . Pe parcursul perioadei de raportare reflectă în aces raport, 22 raporte din 23 planificate au fost transmise în termeni. Pentru SR Viaţa Nouă rapoartele (financiare, de activitate și indicatorii) urmează a fi prezentate nu mai târziu de 15 zile de la încheierea fiecărui trimestru și sunt, de regulă, prezentate la timp.)
M5 |  | N/A
M6 |  | N/A
Are technical targets being achieved?
Programmatic |  | Summary Comments |  |  | Recommendations
P1 - trend |  | The indicator is substantially met (98%). The main part of PLHIV have been reached by project. Currently the number of new PLHIV that can be covered with support services is mostly related to new people diagnosed with HIV. To mention that not every PLHIV will be covered with support due to refusal to receive psycho-social services, migration, etc. (Indicatorul este substanţial atins (98%). Cea mai mare parte a persoanelor HIV pozitive au fost acoperite cu serviciile proiectului. În prezent, numărul persoanelor HIV pozitive, care pot fi primar acoperite cu servicii de suport este în mare parte legată de oameni noi diagnosticaţi cu HIV. De menţionat că nu toate PTH vor fi acoperite cu suport din cauza refuzului servicilor psiho-sociale, migrației, etc.)
P2 - trend |  | The indicator is achieved in proportion of 85%. Reason for variance: The number of PWID on OST covered with psycho-social support is directly dependent to the number of PWID enrolled in OST treatment (new cases) which is continuously decreasing. The result reported for a specific period reflect new OST patients (who initiated OST in the reporting period) covered with support services, as well as a small percentage of OST patients enrolled before the reporting period but not yet reached\covered with project services. Smaller the number of new entrances in OST Treatment – smaller the number of OTS patients that can be covered with psycho-support services. In 2012, 83 new clients were enrolled in the substitution therapy program, the number of OST patients covered with support services (primarily reached) being 97. (Indicatorul este atins în proporție de 85%. Cauza variaţiei: Numărul de CDI în TSO acoperiţi cu suport psiho-social este direct dependent de numărul de CDI înrolaţi în TSO (cazuri noi), care este în continuă scădere. Rezultatul raportat pentru o anumită perioadă reflecta pacienţii noi înrolaţi în TSO (care au inițiat TSO în perioada de raportare), acoperiţi cu servicii de suport, precum și un procent mic de pacienţi înrolaţi în OST înaintea perioadei de raportare, dar nu au fost încă acoperiţi cu servicii. Cu cît este mai mic numărul de noi înrolaţi în TSO – cu atît este mai mic număr de pacienți în TSO care pot fi acoperiţi cu servicii psiho-sociale. În anul 2012, 83 de pacienţi noi au fost înrolaţi în terapie de substituție, numărul de pacienţi în OST acoperiţi cu servicii de suport (atinşi primar) fiind 97.) |  |  | Implicarea tuturor structurilor de stat, internaţionale şi organizaţiilor nonguvernamentale vizate în realizarea recomandărilor Evaluării Serviciului de Terapie de Substituţie cu Opioide (TSO) in Moldova efectuate în luna Noiembrie 2012 (raportul se anexează) şi implementarea planului de acţiuni "Sporirea calităţii Programului Terapiei de Substituţie cu Opioide/Metadonă în Republica Moldova", elaborat in cadrul mesei rotunde din 08.02.13 (planul se anexeaxa). CNC va urmări progresul implementării planului de acţiuni. Extinderea serviciului TSO in vederea acoperirii lărgite cu serviciul respectiv în alte oraşe prin integrarea TSO în infrastructura existentă a serviciului narcologic. Dispensarul Narcologic va organiza şi coordona procesul.
P3 - trend |  | The indicator is overachieved. Reason for variance: the number of non-medical staff from NSRS’s MDTs trained is higher due to the organization of the trainings in partnership with ILO and sharing of costs as per MLSPF request. (Indicatorul este depășit. Cauza variaţiei: numărul de specialişti non-medicali, reprezentanţi ai SNR, instruiţi este mai mare datorită organizării cursurilor în parteneriat cu OIM și partajare a costurilor conform solicitării MMPSF.)
P1 |  | During S6 a total 377 PLHIV were primarily reached with care and support services through four social regional centers working in this area and 10 territorial organizations. The beneficiaries are provided with the following services: psycho-social counseling and registration, medical consultations, distribution of informational materials and peer health counseling, referral to services provided by public institutions, self-support groups, etc. The indicator is substantially met. (în semestrul 6, 377 PTH au fost primari acoperiți cu servicii de îngrijire şi suport în cadrul a 4 Centre Sociale Regionale şi 10 organizaţii care lucrează în acest domeniu. Beneficiariilor le sunt oferite următoarele servicii: consiliere psiho-socială, consultaţii medicale, distribuţia materialelor informaţionale şi consiliere de la egal la egal, servicii de referinţă furnizate de către instituţiile publice, grupuri de auto-suport, etc. Indicatorul este substanţial atins.)
P2 |  | During S6 a total of 53 PWID on opioid substitution therapy (primarily reached) received at least 3 support services from the package (psychosocial support, self-support groups, peer to peer education, distributions of informational materials and food parcels) offered by NGOs working in PWUD rehabilitation. The indicator is achieved in proportion of 85%. Reason for variance: The number of PWID on OST covered with psycho-social support is directly dependent to the number of PWID enrolled in OST treatment (new cases) which is continuously decreasing. The result reported for a specific period reflect new OST patients (who initiated OST in the reporting period) covered with support services, as well as a small percentage of OST patients enrolled before the reporting period but not yet reached\covered with project services. Smaller the number of new entrances in OST Treatment – smaller the number of OTS patients that can be covered with psycho-support services. In 2012, 83 new clients were enrolled in the substitution therapy program, the number of OST patients covered with support services (primarily reached) being 97. (în timpul S5 un total de 53 CDI aflați în terapie de substituţie cu metadonă (primari atinși) au primit cel puţin 3 servicii de suport social din pachetul (sprijin psiho-social, grupuri de suport reciproc, educație de la egal la egal, distribuţia de materiale informaţionale şi pachete alimentare și igienice) oferite în cadrul centrelor de zi de ONG-uri care lucrează în domeniul reabilitării CDI. Indicatorul este atins în proporție de 85%. Motiv pentru variație: Numărul de CDI în TSO acoperiţi cu suport psiho-social este direct dependent de numărul de CDI înrolaţi în TSO (cazuri noi), care este în continuă scădere. Rezultatul raportat pentru o anumită perioadă reflecta pacienţii noi înrolaţi în TSO (care au inițiat TSO în perioada de raportare), acoperiţi cu servicii de suport, precum și un procent mic de pacienţi înrolaţi în OST înaintea perioadei de raportare, dar nu au fost încă acoperiţi cu servicii. Cu cît este mai mic numărul de noi înrolaţi în TSO – cu atît este mai mic număr de pacienți în TSO care pot fi acoperiţi cu servicii psiho-sociale. În anul 2012, 83 de pacienţi noi au fost înrolaţi în terapie de substituție, numărul de pacienţi în OST acoperiţi cu servicii de suport (atinşi primar) fiind 97.)
P3 |  | A total of 290 persons were trained in S6, from them: 50 medical staff attended international trainings at Clinica Lavra in HIV infection and Clinic administration and management of HIV infection, 68 non-medical staff from MDT under National Social Reference System were trained in Protection and assistance to victims of human trafficking, domestic violence and people living with HIV within the National Reference System; 23 representatives of SRC were trained in HIV infection; 19 representatives of SRC were trained in Case management of people living with HIV; 52 medical specialists were trained in TB/HIV collaborative activities: ICF/IPT; 27 medical staff were trained HIV infection; 51 social assistants in most affected regions were trained in HIV/AIDS. The indicator is overachieved. Reason for variance: the number of non-medical staff from NSRS’s MDTs trained is higher due to the organization of the trainings in partnership with ILO and sharing of costs as per MLSPF request. (Un total de 290 persoane au participat lainstruiri în semestrul 6, dintre care: 50 lucrători medicali au fost instruiţi la training-urile internaţionale organizate la Clinica Lavra în managementul clinic al infecţiei HIV; 68 lucrători non-medicali din echipele multidisciplinare din cadrul Sistemului Naţional Social de Referinţă au fost instruiţi în protecţia şi asistenţa victimelor traficului uman, violenţa domestică şi PTH în cadrul Sistemului Naţional de Referire; 23 reprezentanţi au fost instruiţi în HIV/SIDA şi 19 în managementul de caz al persoanei care trăieşte cu HIV; 52 lucrători medicali au fost instruiţi în activităţi colaborative TB/HIV; 27 specialişti în asistenţă medicală primară au fost instruiţi în infecţia HIV; 51 asistenţi sociali din cele mai afectate regiuni au fost instruiţi în HIV/SIDA). Indicatorul este depășit.Cauza variaţiei: numărul de specialişti non-medicali - reprezentanţi ai SNR instruiţi este mai mare datorită organizării cursurilor în parteneriat cu OIM și partajare a costurilor conform solicitării MMPSF.
P4 |  | 27 HIV infected patients received palliative care services within the ARV Treatment facility during reported period (care of skin, hair, nails, eyes, mouth, pneumonia prophylactic treatment, symptomatic treatment, alimentation, etc.). The indicator is overachieved. Reason for variance: The number of beneficiaries provided with palliative care services is determined by the need of such services (patients’ medical condition) among PLHIV during a specific period. The need varies from one period to another, but there is no waiting list and all patients in need of palliative care services receive them within the Dermatological and Communicable Diseases Hospital. (27 de pacienţi infectaţi cu HIV au primit servicii de îngrijiri paliative în cadrul departamentului de tratament ARV în timpul perioadei raportate (îngrijire a pielii, părului, unghiilor, cavității bucale, ochilor, tratamentul profilactic al pneumoniei, tratamentul medicamentos simptomatic, alimentaţie, etc. Indicatorul este depășit.Cauza variaţiei: Numărul de beneficiari acoperiţi cu servicii de îngrijire paliativă este determinată de necesitatea acestui tip de servicii (condiţia medicală a pacienților) în randul persoanelor cu HIV pe parcursul unei anumite perioade. Necesitatea variază de la o perioadă la alta, însă nu există listă de așteptare și toți pacienții care au nevoie de servicii de îngrijire paliativă le primesc în cadrul Spitalulului Dermatologie şi Maladii Comunicabile.)
P5 |  | A total of 159 PLHIV received food parcels during S6 (primarily reached). Each quarter 840 PLHIV out of those on ARV treatment, selected based on socio-economic vulnerability, benefit of food parcels. The indicator is overachieved. Reason for variance: Food parcels distribution is subject to PLHIV socio-economic vulnerability determined quarterly based on a unique set of vulnerability criteria. A total of 840 food parcels are distributed quarterly for better adherence to treatment, in both civilian and penitentiary sectors, and about 10% of beneficiaries are new beneficiaries (primarily reached). (Un număr total de 159 PTH au primit pachete alimentre în timpul semestrului 6 (beneficiari primari). În fiecare trimestru 840 PTH din răndul celoraflaţi în tratament ARV, selectaţi în baza vulnerabilităţii socio-economice, beneficiază de pachete alimentare. Indicatorul este depășit.Cauza variaţiei: distribuția pachetelor alimentare se face în funcţie de vulnerabilitatea socio-economică a PTH evaluată trimestrial în baza unui set unic de criterii de vulnerabilitate. În total 840 de pachete alimentare sunt distribuite trimestrial pentru creşterea aderenţei la tratament, în ambele sectoare civil și penitenciar, aproximativ 10% din beneficiari fiind beneficiari noi (primar acoperiţi).
P6 |  | A total of 47 children received social support during S6 (primarily reached), from them 10 HIV positive children and 37 children with unknown status born from HIV positive mothers. Each quarter 230 children (all HIV infected children that can be reached and the majority of children born from HIV infected mother with unknown status) benefit of food parcels. At the same time each semester HIV positive children benefit of a set of stationary and clothing for school as part of social support program (95 HIV positive children received such support during reported period). The indicator is overachieved. Reason for variance: The number of children primarily reached with social support is determined by the number of children diagnosed with HIV and by the number of children born from HIV positive mothers immediately before and during the reported period. (un număr total de 47 copii au primit suport social în timpul semestrului 6 (beneficiari primari), dintre care 10 copiiHIV infectaţi și 37 de copii cu statut nedeterminat născuți din mame HIV pozitive. În fiecare trimestru, 230 de copii (toți copiii infectați cu HIV, care pot fi acoperiţi cu servicii, și majoritatea copiilor născuți din mame infectate cu HIV pozitive) beneficiază de pachete alimentare. În același timp, în fiecare semestru copii HIV pozitivi beneficiază de un set de haine şi rechizite pentru scoala ca parte a programului de suport social (95 de copii HIV infectaţi au primit acest suport pe parcursul perioadei de raportare). Indicatorul este depășit. Cauza variaţiei: Numărul de copii primar acoperiţi cu suport social este determinat de numărul de copii diagnosticati cu HIV și de numărul de copii născuți din mame HIV pozitive imediat înainte și în timpul perioadei de raportare.
P7 |  | A total of 35 individuals out of 82 that initiated OST during P9-P10 have completing at least 6 months of continuous treatment on OST. Currently OST is provided in three sites: Republican Narcological Dispensary, Balti Municipal Hospital and the Department of Penitentiary Institutions (in 7 penitentiaries). The indicator is partially achieved (73%). Reason for variance: the rate of retention in treatment is determined by a series of factors, namely: seasonal migration of patients (both abroad and in country), emergency of seasonal illicit drugs on black market, low doses of methadone (below recommended 60mg minimal average dose), and concurrent use of illicit drugs, methadone distribution restricted to OST for all patients including for drug users in stable remission, repeated enrollment in treatment without prior psycho-social support to prepare the patient for the next attempt, misconceptions about OST in both medical and psych-social support teams, negative image of OST among PWID, etc. (un total de 35 de persoane din 82 care a initiat TSO în timpul Tr.9-Tr.10 (ianuarie+iunie 2012) au finalizat cel puţin 6 luni de tratament continuu. Actualmente TSO este oferită in trei site-uri: Dispensarul Republican de Narcologie, Spitalul Municipal Bălţi şi Departamentul Instituţiilor Penitenciare (în 7 penitenciare). Indicatoruleste atins parțial (73%). Cauza variaţiei: rata de retenție în tratament este determinat de o serie de factori, și anume: migrația sezonieră a pacienti (atât în străinătate cît și în țară), apariţia droguri ilicite de sezon pe piața neagră, doze mici de metadona (doze mai mici decît doza minimiă recomandată de 60mg), precum și utilizarea concomitentă a drogurilor ilicite, distribuție metadonei limitată la punctul de distribuţie pentru toti pacientii, inclusiv pentru consumatorii de droguri în remisie stabila, înrolare repetată în tratamentul fără suport psiho-social preventiv pentru a pregăti pacientul pentru următoarea încercare, conceptii gresite despre TSO în echipele medicale și echipele de asistență psiho-socială, imaginea negativă a TSO printre CDI, etc |  |  | Modificarea protocoalelor clinice în conformitate cu recomandările OMS întru îmbunătăţirea calităţii acestuia şi sporirea aderenţei la TSO. Ajustarea actelor legislative pentru a permite în mod individual administrarea dozelor de medicamente opioide (metadonă) la domiciliu în cazul pacienţilor în remisiune stabilă. Monitorizarea sistematică a calităţii TSO şi nivelul de corespundere a acesteia standardelor internaţionale şi necesităţilor pacienţilor. Dispensarul Narcologic va organiza şi coordona procesul. UNODC va oferi suport tehnic.
P8 |  | A total of 99 lawyers and health care workers have been trained during reported period within 4 training courses on human rights, non-discrimination, confidentiality and reparation for moral prejudices of people living with HIV, confidentiality of personal data with regard to health care, etc. (un număr total de 99 de avocaţi au fost instruiţi în semestrul 6 în cadrul a 4 cursuri de instruire în drepturile omului, non-discriminare, confidenţialitate şi despăgubire a prejudiciile morale ale PTH).
P9 |  | A total of 85 consultancies were offered remotely by traveling to project sites of 4 lawyers, during S6. They offered legal assistance related to issues of legal, civil (including disclosure of HIV status), administrative nature to all PLHIV in need. The indicator is overachieved. Reason for variance: The number of consultancies offered by project lawyers is determined by the request of legal support from PLHIV and can vary from one period to another. With the opening of Social Regional Centers (two during reported period) project lawyer provide services within the Centers facilities (with a specific periodicity) bringing this way services closer to the beneficiary and increasing their access to legal support. The increase in number of consultancies provided has no financial impact as the layers are fool day project consultants with fix remuneration. (pe parcursul semestrului 6 au fost oferite 85 de consultaţii în teren de către 4 avocaţi. Aceștea au oferit asistenţă juridică pe aspecte de natură legală, civilă (incluzând divulgarea statutului HIV) şi administrative ale tuturor PTH care au solicitat ajutor). Indicatorul este depăşit. Cauza variaţiei: Numărul de consultaţii oferite de către avocații proiectului este determinată de cererea de asistență juridică din partea PTH și poate varia de la o perioadă la alta. Odată cu deschiderea Centrelor Sociale Regionale (două în timpul perioadei de raportare) avocaţii prestează servicii în cadrul centrelor (cu o anumită periodicitate) aducînd astfel serviciile mai aproape de beneficiar și crescînd accesul la asistență juridică. Creșterea numărului de servicii de consultanţă juridică prestate nu are impact financiar deoarece avocaţii sunt angajaţi în proiect cu yi plină de lucru şi au remunerare fixă.
P10 |  | 68 representatives of NGOs providing services to PLHIV were trained during S6: 5 participants attended English language course (elementary), 24 social workers and peer to peer consultants from NGO which implement psycho-social support project were trained in HIV; 19 social workers, peer to peer consultants and infectious disease specialists attended a training on Strengthening the collaboration of social workers and infectious disease specialist providing services to PLHIV; 20 representatives from NGO’s Providing Care and support for the PLHIV were trained in M&E. (68 de reprezentanţi ai ONG-urilor care prestează servicii PTH au fost instruiţi în semestrul 6: 5 persoane au urmat cursuri de limbă engleză (nivelul începător), 19 lucrători sociali, educatori de la egal la egal şi infecţionişti au participat la o instruire focusată pe consolidarea colaborării lucrătorilor sociali și infecţioniştilor în prestarea de serviciilor pentru PTH, 20 de reprezentanți din ONG-uri implicate în îngrijirea şi suport pentru PTH au fost instruiți în M&E.
Menu

## Actions
Dashboard: Moldova - HIV / AIDS
| SSF (Round 8) | Phase 1 |  |  |  | Report Period: |  | P12
| Latest Rating: | A1 |  | PAS Center |  | From: |  | July 01, 2012
|  |  | Reducing HIV-related burden in the Republic of Moldova |  |  |  | To: | December 31, 2012
Decisions and Actions
What is the overall status of this grant implementation?
Programul este implementat în conformitate cu planul de lucru şi prevederile contractuale. Rata cumulativă de absobţie din buget este de 95.68%, iar performanța medie a indicatorilor de 104.9%. Raiting-ul general acordate de Fondul Global grantului HIV implementate de Centrul PAS este A1.
| Key Recommendations from Oversight Group(s) |  |  |  | CCM Decision | Due Date | Person Responsible
Current Reporting Period | Implicarea tuturor structurilor de stat, internaţionale şi organizaţiilor nonguvernamentale vizate în realizarea recomandărilor Evaluării Serviciului de Terapie de Substituţie cu Opioide (TSO) in Moldova efectuate în luna Noiembrie 2012 (raportul se anexează) şi implementarea planului de acţiuni "Sporirea calităţii Programului Terapiei de Substituţie cu Opioide/Metadonă în Republica Moldova", elaborat in cadrul mesei rotunde din 08.02.13 (planul se anexeaxa). CNC va urmări progresul implementării planului de acţiuni.
Extinderea serviciului TSO in vederea acoperirii lărgite cu serviciul respectiv în alte oraşe prin integrarea TSO în infrastructura existentă a serviciului narcologic. Dispensarul Narcologic va organiza şi coordona procesul.
Modificarea protocoalelor clinice în conformitate cu recomandările OMS întru îmbunătăţirea calităţii acestuia şi sporirea aderenţei la TSO. Ajustarea actelor legislative pentru a permite în mod individual administrarea dozelor de medicamente opioide (metadonă) la domiciliu în cazul pacienţilor în remisiune stabilă. Monitorizarea sistematică a calităţii TSO şi nivelul de corespundere a acesteia standardelor internaţionale şi necesităţilor pacienţilor. Dispensarul Narcologic va organiza şi coordona procesul. UNODC va oferi suport tehnic.
Actions to Implement / Previous Period
What is the overall status of this grant implementation?
| CCM Decision |  |  |  | Action Taken | Date | Person Responsible
Previous Reporting Period
Menu

## Setup (hidden)
Dashboard: Moldova - HIV / AIDS
Set-up = List of validation for Grant Detail page
Component | Currency | Round | Phase | Period | Rating | LFA | Medicaments | Countries
Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select
HIV / AIDS | $ | Round 1 | Phase 1 | P1 | A1 | CA (Crown Agents) | Isoniazid | Afghanistan
MALARIA | € | Round 2 | Phase 2 | P2 | A2 | DEL (Deloitte) | Ethambutol | Albania
TB |  | Round 3 | RCC | P3 | B1 | DTT (DTT Emerging Markets) | Rifampicin | Algeria
HIVAIDS / TB |  | Round 4 |  | P4 | B2 | FIN (Finconsult) | Pyrazimamide | Angola
HSS |  | Round 5 |  | P5 | C | GT (Grant Thornton) | RDT | Argentina
|  | Round 6 |  | P6 |  | H-C (Hodar-Conseil) | NVP | Armenia
|  | Round 7 |  | P7 |  | KPMG (KPMG) | 3TC | Azerbaijan
|  | Round 8 |  | P8 |  | MSCI (MSCI) | D4T | Bangladesh
|  | Round 9 |  | P9 |  | PwC (PricewaterhouseCoopers) | AZT | Belarus
|  | Round 10 |  | P10 |  | STI (Swiss Tropical Institute), | DDI | Belize
|  |  |  | P11 |  | UNOPS | EFV | Benin
|  |  |  | P12 |  |  | AS/LF | Bhutan
[7 empty] | AS/AQ | Bolivia
[7 empty] | AS/MQ | Bosnia and Herzegovina
[7 empty] | Al/Lum | Botswana
Brazil
[7 empty] | TB nutri'l supplements | Bulgaria
[7 empty] | E-PAP | Burkina Faso
Burundi
Cambodia
Cameroon
Cape Verde
Central African Republic
Chad
Chile
China
China
Colombia
Comoros
Congo (Democratic Republic of the)
Congo (Republic of the)
Costa Rica
Cote d'Ivoire
Croatia
Cuba
Djibouti
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Ethiopia
Fiji
Gabon
Gambia
Georgia
Ghana
Global(LWF)
Guatemala
Guinea
Guinea-Bissau
Guyana
Haiti
Honduras
India
Indonesia
Iran (Islamic Republic of)
Iraq
Jamaica
Jordan
Kazakhstan
Kenya
Korea, Democratic Peoples Republic of
Kosovo (Serbia)
Kyrgyzstan
Lao PDR
Lesotho
Liberia
Macedonia, FYR
Madagascar
Malawi
Maldives
Mali
Mauritania
Mauritius
Moldova
Mongolia
Montenegro
Morocco
Mozambique
Multi-country Africa (West Africa Corridor Program)
Multi-country Africa(RMCC)
Multi-country Americas (Andean)
Multi-country Americas (CARICOM)
Multi-country Americas (CRN+)
Multi-country Americas (Meso)
Multi-country Americas (OECS)
Multi-country Americas (REDCA+)
Multi-country Western Pacific
Myanmar
Namibia
Nepal
Nicaragua
Niger
Nigeria
Pakistan
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Romania
Russian Federation
Rwanda
Sao Tome and Principe
Senegal
Serbia
Sierra Leone
Solomon Islands
Somalia
South Africa
Sri Lanka
Sudan
Suriname
Swaziland
Syrian Arab Republic
Tajikistan
Tanzania
Thailand
Timor-Leste
Togo
Tunisia
Turkey
Uganda
Ukraine
UN Theme Group on HIV/AIDS (West Bank and Gaza)
Uzbekistan
Viet Nam
Yemen
Zambia
Zanzibar (Tanzania)
Zimbabwe