## Menu
Dashboard: Moldova - TB
TB Round 9, Phase 1 | Grant No.: MOL-809-G05-T
V1.0
Finance
Programmatic
Management
Select the option you want to see:
Recommendations
Actions
Grant Detail
List of Indicators
Data Entry
Grant Information
Indicators
Reports

## List of Indicators
Dashboard: Moldova - TB
Financial information
Name: | Definition | Measurement | Data Sources
F1: Budget and disbursements by Global Fund | Cumulative budget: Sum of the grant budget from period one (quarter, trimester, or semester) of the current phase, up to and including the dashboard reporting period. Cumulative Disbursments by GF: Sum of all the funds transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to and including the dasboard reporting period. | Currency of the grant ($ or Euro) Cumulative – Figures refer to budget and disbursements for all the periods of the phase up to and including the dashboard reporting period | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F2: Budget and actual expenditures by Grant Objective | Cumulative Budget per Objective: Sum of the grant budget by Objective, from period one of the current phase up to and including the dashboard reporting period. Cumulative Expenditure per Objective: Sum of amounts spent by Objective directly by the PR plus the amounts transferred by the PR to all SRs from the beginning of the phase up to and including dashboard reporting period, by Objective | • Cumulative – Figures refer to budget, disbursements or expenditure for all the periods of the phase up to and including the dashboard reporting period. | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F3: Disbursements and expenditures | Disbursement by GF: Prior to this Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to but not including dashboard reporting period. Disbursement by GF: Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), during dashboard reporting period. PR disbursements and expenditure: Prior to this Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) up to but not including dashboard reporting period. PR disbursements and expenditure: Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) during dashboard reporting period. Disbursements to SRs: Prior to this Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), up to but not including dashboard reporting period. Disbursements to SRs:Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), in dashboard reporting period. SR expenditures: Prior to this Reporting period: The sum of all expenditures reported by the SRs, up to but not including dashboard reporting period. SR expenditures: Reporting period: The sum of all expenditures reported by the SRs, during dashboard reporting period. | Currency of the grant ($ or Euro) • Reporting period – Figures refer to budget, disbursements or expenditure for the reporting period to which the dashboard refers. • Prior to reporting period - Figures refer to the total budget, disbursements or expenditure for all the periods before but not including the current period. | PU/DR; PR data: SR reports to PR
F4: Latest PR reporting and disbursement cycle | Days taken to submit final PU/DR to LFA – This indicator measures the number of calendar days it took the PR to send a final Performance Update and Disbursement Request (PU/DR) to the LFA after the end of the period. A 'final' PU/DR would be one for which the LFA did not require any further clarifications from the PR. The expected value is 45 days from the end of the period, as defined in the Grant Agreement. The actual value is the number of calendar days from the end date of the period to the date on which the PR sent to the LFA the final PU/DR. Days taken for disbursement to reach PR – This indicator measures the number of calendar days it took the Global Fund to send the latest disbursement to the PR's account after receipt of the acceptable PU/DR by the LFA. The expected number is 45 days. The actual number is the number of days from the date of transmission by the PR to the LFA of the acceptable PU/DR to the date the disbursement is received by the PR at its bank. Days taken for disbursement to reach SRs – This indicator measures the average number of days for disbursements to be made to all the SRs. The expected value for this indicator will be set locally by the PR and SRs, preferably in the Grant Operations Manual. The actual value is the average of the number of days from the receipt of the funds from the GF by the PR to the date the funds are received by each SR. Different SRs coudl receive funds on different dates and this indicator is the average across all SRs for the latest disbursement. | Number of calendar days; it refers only to reporting period for which the latest disbursement was received and is not cumulative | PR, LFA, GF emails and records; bank notification document or the notice of receipt by the PR to GF; SR reports to PR based on bank records
Management Information
Name: | Definition | Measurement | Data Source
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) | Number of Conditions Precedent (CPs) and Time Bound Actions (TBAs ) fulfilled, or unfulfilled. Within the Unfulfilled category, we distinguish between those CPs and TBAs whose deadline has not passed and those for which the deadline has passed. | Number, cumulative to the dashboard reporting period. Number of fulfilled CPs and/or TBAs plus unfulfilled CPs and/or TBAs should equal the total number set by the Global Fund on the grant | PR records; Grant Performance Reports;
M2: Status of key PR management positions | Number of PR grant management positions planned currently filled or vacant. Full time equivalents of the managerial positions that are on the organizational chart (or otherwise planned) and directly responsible for ensuring grant implementation at the PR, and lead SRs (if necessary). This will include new hires, current staff who are assigned to work on the grant’s management, as well as any staff seconded from other divisions or partner organizations. | Number, in current reporting period | PR records
M3: Contractual arrangements (SRs) | Identified: Total number of potential SRs identified by the PR for the phase. Assessed: Total number of potential SRs assessed by the PR to determine whether they qualify to function as SRs for the grant. Approved: Total number of SRs that have been approved. Signed: Total number of SRs that have signed agreements/contracts with the PR under the grant. Receiving funding: Total number of SRs that are getting funds and/or supplies from the PR. Numbers of SRs Identified, Assessed, Approved, Signed and Receiving funds are cumulative for the phase, with the following exceptions: If an SR does not need new approval in Phase II, then approval in Phase I is counted. If an SR was signed in a previous Phase but is not working in the current Phase, that SR is no longer counted in Identified, Assessed, Approved. | Number, cumulative to the reporting period. A SR is an institution or program with its own workplan, budget and performance targets. | PR records; Sub-agreements/MOUs; CCM records
M4: Number of complete reports received on time | The total number of periodic reports with up-to-date financial, management and performance (programmatic) data received by the PR from SRs and by SRs from the SubSRs (SSRs) by the expected date. A 'complete' report is one that contains all the data that the PR requires for the PU/DR. The expected date would be set by the PR in the sub-agreements. | Number of reports received. The figure reflects only the period of reporting; it is not cumulative. | PR and SR records
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals | This indicator measures the budget approved for the current phase of the grant for purchase of health products and equipment and pharmaceuticals and medicines (categories 4 and 5 in the new Enhanced Financial Report), and the cumulative amounts of financial obligations and expenditures up to the dashboard reporting period. Budget approved: Total approved budget for purchases (categories 4 and 5) for the entire phase of the grant. It does not include the amounts for fees, management, operational costs, etc. Cumulative Obligations: Total of all order(s) placed and monies committed for these purchases by the PR up to and including the dashboard reporting period. Ideally, by the end of the Phase, budget should equal obligations. Cumulative expenditure: Total of actual Expenditures on category 4 and 5 up to and including the dashboard reporting period (whether paid by PR or authorized to be paid by another entity like GF or other). | Currency of the grant ($ or Euro) | Grant agreement approved budget (for categories 4 and 5 of Enhanced Finance Reporting in current phase); and PR financial data (for expenditures), and/or PSM unit (for orders placed and funding committed or obligated).
Note: Category 6 of the EFR will not be considered as part of the budget for pharmaceuticals. Category 6 has several expenditures that are difficult to disaggregate or quantify, such as warehousing costs, distribution costs (particularly when distibution is done by MOHs), and others that are related to operational costs of the PSM component.
M6: Difference between current and safety stock | This indicator is a snapshot of the difference between the current (or last month) stock level of a specific product (medicine in single, fixed-dose combination, bednets, diagnostic kits, etc.) of a particular dose, expressed in monthly needs (number of months of treatment available) for all patients in the program, and the safety or buffer stock (also expressed in months) as established by the disease program, warehouse system or essential drugs program, for the particular product and dosage. The table will show the difference in months in colors: • RED: when the difference is negative or 0, showing that months of existing stock are lower than or equal to what has been established as months of safety stock • YELLOW: when we have more than the level of safety stock (>0) but less than 3 months (+3). • GREEN: when the difference is between 3 and 18 months. • VIOLET: When the difference shows that the level above the safety stock is greater than or equal to 18 months indicating a potential overstock) problem. For a full description of how this indicator is calculated, please see the User’s Manual. | Number of months | PR records: Warehouse data.
Programmatic Indicators (from Performance Framework)
Indicator | Definition (from M&E Plan, June 2007) | Measurement | Data Source
Number of TB service staff and Primary Health Care (PHC) staff trained in DR-TB management | Indicator refers to trainings of TB doctors and nurses from in- and out-patient services and primary health care institutions covering both civilian and penitentiary sectors. | all persons who signed the list of participation at training | List of participants trained
Number of MDR-TB patients registered under DOTS plus program who are receiving incentives and enablers for improved treatment compliance | Each patient will receive at least three food packages per month. | new persons who received services during the reported period | Database
Number of volunteers, members of multidisciplinary teams, NGOs representatives and priests trained in TB community aspects | Targets refer to the number of persons/contacts trained, assuming that the same persons might attend more than one training. Volunteers from the NGO network, representatives of the NGOs and of the multidisciplinary teams of the community centres, including local public authorities, will be trained in DOT and TB community aspects. Priests will be trained through workshops on TB prevention and social involvement. | all persons who signed the list of participation at trening | List of participants trained
Number of DOT community centres renovated and functional | Number of rooms renovated, furnished and equipped to be used as location for community centers. | works accepting report | Ministry of Health Order
Number of new TB patients provided with DOTS plus program who are receiving incentives and enablers for improved treatment compliance | Numerator: Number of new TB patients provided with DOT by the community (community centres and NGOs). Denominator: Total number of new TB patients reported to the health authority in the same administrative area. Patient is considered "reached" if he/she receives at least 10 DOT interventions during 1 months. DOT intervention definition: visit to DOT centre by the patient or visit to the patient by DOT supporters for drug intake. | new persons who received services during the reported period | Database
Number of people (TB/HIV patients and their families) reached by peer support groups | Targets refer to number of patients with TB/HIV coinfection, drug users and their families, etc. reached by peer educators. The aim of this activity is to improve the adherence to TB treatment, prevent the defaults, inform the beneficiaries about the referral system in the country and to advocate for TB control problems among vulnerable population. The peer educators are the former TB patients, PLWHA, medical personnel and others, who have willingness and capacity to work in the area of TB. | new persons who received services during the reported period | Database
Number of TB patients registered under DOTS program who are receiving incentives and enablers to improve their treatment adherence | Support to treatment adherence (food and hygienic parcels) for TB patients. Patients will receive at least three food packages per month. The number represents 55% of all TB patients registered under DOTS program and need incentives during the reporting period | new persons who received services during the reported period | Database
Number of medical personnel trained in TB control, community involvement and methods of informational work with different groups of population | Targets refer to the trainings of TB doctors and nurses from the TB cabinets in rayons, family doctors and assistants from the Primary Health Care (PHC) institutions, NTP staff and M&E specialists from Phthisiopneumology Institute. The subjects of the trainings are: TB control and community involvement and methods of informational work with different groups of population. | all persons who signed the list of participation at trening | List of participants trained
Number of peer educators, journalists at national and district level and local stakeholders trained in TB and TB/HIV issues | Peer educators will be trained to carry out informational work on TB; journalists at national and district level will be trained in TB communications; and the local stakeholders (representatives of the civil society and NGOs, Local Public Administrations in rayons, personnel of the Centre of Preventive Medicine, hospitals' administrators, representatives of the PHC institutions and teaches from schools and colleges) will be trained in TB and TB/HIV issues. | all persons who signed the list of participation at trening | List of participants trained
Percentage of population with correct knowledge about TB (mode of transmission, symptoms, treatment and curability) | Numerator: Respondents who identified all the three main TB symptoms (coughs with smear lasting longer than 3 weeks, fatigue and fever lasting longer than 3 weeks) & respondents who spontaneously mentioned the air way during the cough as TB transmission route & respondents who stated that TB can be cured or can be cured if treated in time. Denominator: Surveyed respondents. | study | KAP survey
Indicator Number: Name (Perf Framework No.) | Definition | Measurement | Data Source
The indicators should be selected by the PRs and members of the CCM or the CCM Technical Committee, from the Performance Framework |  |  | Performance Framework
Menu

## Data Entry
Grant information
| Country: | Moldova |  | Title of the Grant: |  | Empowerment of people with TB and Communities in Moldova
| Grant No.: | MOL-809-G05-T |  | Component: |  | TB | Total Funding: | 4257180
| Principal Recipient: | PAS Center |  |  | Round: | Round 9 | Phase: | Phase 1
| Start Date (dd/Mmm/yy): | October 01, 2010 |  | Local Fund Agent: |  | PwC (PricewaterhouseCoopers)
| Latest Rating: | A2 |  | Fund Portfolio Manager: |  | Tatiana Vinichenko
Information reporting period
| Report Period: | P9 | From: | 2012-07-01 | To: | 2012-12-31 | Date of entry of information: |  | 2013-04-08
| Prepared by: |  | PAS Center
Information on indicators
Enter the data based on the colour-coded cells
| Financial Information: |  | Management Information: |  |  | Programmatic Information:
| Financial Information: | [8 empty] | Enter finance data in every orange cell like this.
| Currency of the grant |  | €
F1: Budget and disbursements by Global Fund
| Disbursement | [15 empty] | 1024001.535
| Reporting period | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12 | % Cumulative |  |  | 1881651.16
| Budget (in €) | 1024001.535 | 857649.625 | 341578.625 | 343592.625 | 499505.1875 | 359178.1875 | 340817.1875 | 317627 | 433470 |  |  |  | 89.94% |  |  | 2223229.785
| Disbursements by GF (in €) | 2566823 | 0 | 0 | 0 | 596434 | 0 | 803675 |  | 96126 | [6 empty] | 2566822.41
| Cumulative budget | 1024001.535 | 1881651.16 | 2223229.785 | 2566822.41 | 3066327.5975 | 3425505.785 | 3766322.9725 | 4083949.9725 | 4517419.9725 | 0 | 0 | 0 |  |  |  | 3066327.5975
| Cumulative disbursements | 2566823 | 2566823 | 2566823 | 2566823 | 3163257 | 3163257 | 3966932 | 3966932 | 4063058 | 0 | 0 | 0 |  |  |  | 3425505.785
|  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 89.94% | 0% | 0% | 0% |  |  |  | 3766322.9725
F2: Budget and actual expenditures by Grant Objective
| Grant Objective | P1: Cumulative Budget (in €); P2: Cumulative Expenditures (in €)
| Mobilize resources to support community-level partnerships | P1: 1217900; P2: 1033130.34
| Remove barriers to care for poor and other vulnerable communities | P1: 988790; P2: 905496.08
| Strengthen the health system and engage all available partners in TB control | P1: 409758; P2: 282666.52
| Advocacy, communication and social mobilization (ACSM) | P1: 123588; P2: 116664.29
| Integrate TB services on both sides of the prison walls | P1: 353400; P2: 252518.63
| Ensure universal access to diagnosis, treatment, care and support of drug-resistant tuberculosis | P1: 783054; P2: 687586.3
| Operational research in priority issues of TB and monitoring and evaluation | P1: 20745; P2: 17224.35
| Project management | P1: 620185; P2: 665661.34
| Total | P1: 4517420; P2: 3960947.85; P4: OK: Data match
| F3: Disbursements and expenditures | [15 empty] | 4083949.9725
4517419.9725
|  | P1: Prior to reporting period; P2: Current reporting period; P3: Total Spent and Disbursement (in €) |  |  | 0
| Disbursed by Global Fund | P1: 3966932; P2: 96126; P3: 4063058
| PR expenditure and disbursement | P1: 2910482; P2: 1050465.96; P3: 3960947.96
| Disbursed to SRs | P1: 1729139.88; P2: 348191; P3: 2077330.88
| SR expenditures | P1: 1521927.32; P2: 458920.52; P3: 1980847.84
F4: Latest PR reporting and disbursement cycle
Last fund disbursement: Number of calendar days
|  | Expected (days) | Actual (days)
| Days taken to submit final PU/DR to LFA | P1: 45; P2: 42
| Days taken for disbursement to reach PR | P1: 45; P2: 111
| Days taken for disbursement to reach SRs | P1: 20; P2: 5
| Management Information: | P6: Enter management data in every blue cell.
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs)
|  |  | Fulfilled | Not fulfilled, but within deadline | Not fulfilled, and past the deadline | Total
Conditions precedent (CPs) | bar: P2 to P5
| Time Bound Actions (TBAs) | P5: 0
M2: Status of key PR management positions
|  | Planned | Filled | Vacant
| PMU | P1: 10; P2: 10; P3: 0
M3: Contractual arrangements (SRs)
|  | Identified | Assessed | Approved | Signed | Receiving Funding
| SRs | P1: 3; P2: 2; P3: 3; P4: 3; P5: 3
M4: Number of complete reports received on time
|  | # Expected | # Received | Pending
| SSR to SR | P1: 14; P2: 14; P3: 0
| SRs to PR | P1: 3; P2: 3; P3: 0
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals
|  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
Budget Approved*
Obligations
Expenditures
| Budget Approved cumulative* | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Obligations cumulative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Expenditures cumulative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
* Includes only EFR category 4 and 5 (Health products and health equipment & Medicines and Pharmaceuticals)
M6: Difference between current and safety stock
| Component | Products | (1) Number of tablets per patient per day (Review country treatment guidelines) | (2 = 1 x 30) Monthly treatment (Tablets per patient x 30 days) | (3) Total patients in treatment | (4 = 2 x 3) Total # tab/pills required for all patients per month | (5) Current stock in central warehouse (that does not expire within the next 3 months) | (6 = 5 / 4) Stock level expressed in months of treatment for all current patients | (7) Level of safety stock (expressed in months and defined by country) | (8 = 6 - 7) Difference between current stock and safety stock
| TB | P1: Please Select
Please Select
Please Select
Please Select
| Programmatic Information: | P9: Enter performance data in every yellow cell.
| Programmatic indicators (Performance Framework ) |  |  | Code | Directly Tied? |  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
TOP 3 | Number of new TB patients provided with DOTS program who are receiving incentives and enablers for improved treatment compliance ( Numarul de pacienți noi înregistrați în programul DOTS care au beneficiat de stimulente pentru sporirea complianței la tratament) |  |  | 2.3 | Yes | Target | 268 | 536 | 804 | 1072 | 1372 | 1672 | 1972=100%; 65%=1281 | 2297 | 2597
[6 empty] | Achieved | 0 | 0 | 389 | 663 | 861 | 1133 | 1362 | 1585 | 1923
| Number of MDR-TB patients registered under DOTS plus program who are receiving incentives and enablers for improved treatment compliance (Numarul de pacienți înregistrați în programul DOTS Plus care au primit stimulente (pachete alimentare și pachete igienice) pentru sporirea complianței la tratament). |  |  | 1.2. | Yes | Target | 127 | 254 | 397 | 540 | 667 | 793 | 932 | 1063 | 1196
[6 empty] | Achieved | 153 | 304 | 474 | 633 | 728 | 850 | 962 | 1062 | 1206
| Number of medical personnel trained in TB control, community involvement and methods of informational work with different groups of population ( Numarul de lucrători medicali instruiți în controlul tuberculozei, implicarea comunității și metode de lucru informațional pe tuberculoză, pentru diferite grupuri de populație) |  |  | 4.1 | Yes | Target | 130 | 260 | 290 | 320 | 450 | 580 | 610 | 665 | 710
[6 empty] | Achieved | 0 | 15 | 457 | 733 | 1007 | 1326 | 1358 | 1406 | 1476
| Number of TB service staff and Primary Health Care (PHC) staff trained in DR-TB management (Numarul personalului din serviciul ftiziopneumologic si ingrijire medicala primara (AMP) instruiti in managementul TB-MDR) |  |  | 1.1. | Yes | Target | 100 | 208 | 308 | 416 | 471 | 524 | 579 | 679 | 679
[6 empty] | Achieved | 278 | 448 | 585 | 665 | 834 | 1082 | 1155 | 1236 | 1348
| Number of TB patients registered under DOTS program who are receiving incentives and enablers to improve their treatment adherence (Numarul de pacienți TB înregistrați în programul DOTS care au primit stimulente (pachete alimentare și pachete igienice) pentru sporirea complianței la tratament) |  |  | 3.2 | Yes | Target | 588 | 1176 | 1764 | 2352 | 2928 | 3504 | 4080 | 4656 | 5212
[6 empty] | Achieved | 0 | 825 | 1976 | 2935 | 3612 | 4460 | 5144 | 5890 | 6769
| Number of DOT community centres renovated and functional (Numarul de Centre Comunitate renovate si functionale) |  |  | 2.2 | Yes | Target | 0 | 5 | 5 | n/a | n/a | n/a | n/a | n/a | n/a
[6 empty] | Achieved | 0 | 0 | 10 | n/a | n/a | n/a | n/a | n/a | n/a
| Number of people (TB/HIV patients and their families) reached by peer support groups (Numarul de persoane (pacienți TB/HIV și familiile lor) care au fost instruiti de către grupurile de la egal la egal) |  |  | 3.1. | Yes | Target | n/a | n/a | n/a | n/a | 300 | 600 | 900 | 1200 | 1800
[6 empty] | Achieved | n/a | n/a | n/a | n/a | 305 | 623 | 896 | 1182 | 1867
| Number of volunteers, members of multidisciplinary teams, NGOs representatives and priests trained in TB community aspects (Numarul de voluntari, membri din echipele multidisciplinare, reprezentanti ai ONG-lor si preoți / lucrători ai bisericii ortodoxe instruiti în aspecte DOT și controlul tuberculozei la nivel de comunitate) |  |  | 2.1 | Yes | Target | 430 | 725 | 1030 | 1325 | 1380 | 1450 | 1480 | 1515 | 1570
[6 empty] | Achieved | 0 | 47 | 222 | 956 | 1442 | 1442 | 1616 | 1694 | 2380
| Number of peer educators, journalists at national and district level and local stakeholders trained in TB and TB/HIV issues (Numarul de educatori de la egal la egal, jurnaliști la nivel național și regional, persoane-cheie din republică instruiți in TB și TB/HIV) |  |  | 5.1. | Yes | Target | 75 | 180 | 230 | 310 | 385 | 480 | 530 | 600 | 680
[6 empty] | Achieved | 0 | 0 | 149 | 321 | 635 | 882 | 1251 | 1539 | 2142
| Percentage of population with correct knowledge about TB (mode of transmission, symptoms, treatment and curability) (Procentul populatiei cu cunostinte corecte (modul de transmitere, simptome, tratament si curabilitatea) |  |  | 7.1. | Yes | Target | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 43%
[6 empty] | Achieved | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 63%
| Table is automatically updated. No data or information is to be entered here. |  |  | Code | Directly Tied? |  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
| Number of new TB patients provided with DOTS program who are receiving incentives and enablers for improved treatment compliance ( Numarul de pacienți noi înregistrați în programul DOTS care au beneficiat de stimulente pentru sporirea complianței la tratament) |  |  | 2.3 | Yes | Target | 268 | 536 | 804 | 1072 | 1372 | 1672 | 1972=100%; 65%=1281 | 2297 | 2597 | 0 | 0 | 0
[6 empty] | Achieved | 0 | 0 | 389 | 663 | 861 | 1133 | 1362 | 1585 | 1923 | 0 | 0 | 0
| Number of MDR-TB patients registered under DOTS plus program who are receiving incentives and enablers for improved treatment compliance (Numarul de pacienți înregistrați în programul DOTS Plus care au primit stimulente (pachete alimentare și pachete igienice) pentru sporirea complianței la tratament). |  |  | 1.2. | Yes | Target | 127 | 254 | 397 | 540 | 667 | 793 | 932 | 1063 | 1196 | 0 | 0 | 0
[6 empty] | Achieved | 153 | 304 | 474 | 633 | 728 | 850 | 962 | 1062 | 1206 | 0 | 0 | 0
| Number of medical personnel trained in TB control, community involvement and methods of informational work with different groups of population ( Numarul de lucrători medicali instruiți în controlul tuberculozei, implicarea comunității și metode de lucru informațional pe tuberculoză, pentru diferite grupuri de populație) |  |  | 4.1 | Yes | Target | 130 | 260 | 290 | 320 | 450 | 580 | 610 | 665 | 710 | 0 | 0 | 0
[6 empty] | Achieved | 0 | 15 | 457 | 733 | 1007 | 1326 | 1358 | 1406 | 1476 | 0 | 0 | 0
Note on B30: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.
Note on B72: If data are not available, do not enter zeros; rather, leave the cells in the table blank.
Note on B73: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B79: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B94: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.
Menu

## Grant Detail
Dashboard: Moldova - TB
Country: | Moldova |  | Title of the Grant: |  | Empowerment of people with TB and Communities in Moldova
Component: | TB | Grant No. | MOL-809-G05-T | Start Date: |  | October 01, 2010 | Total Funding | 4257180
Round: | Round 9 | Phase: | Phase 1 | Principal Recipient: |  | PAS Center
Report Period: | P9 | from: | 2012-07-01 | to: |  | 2012-12-31 | Latest Rating: | A2
Local Fund Agent: | PwC (PricewaterhouseCoopers) |  |  | Fund Portfolio Manager: |  | Tatiana Vinichenko
Prepared by: | PAS Center |  |  | Report preparation date: |  | 2013-04-08
http://www.crwflags.com/fotw/flags/country.html
Menu

## Finance
Dashboard: Moldova - TB
Round 9 | Phase 1 |  |  |  | Report Period: |  | P9
Latest Rating: | A2 |  | PAS Center |  | From: |  | 2012-07-01
|  | Empowerment of people with TB and Communities in Moldova |  |  |  | To: | 2012-12-31
Financial Indicators
F1: Budget and disbursements by Global Fund - in (€) Report Period: P9 |  |  |  | F3: Disbursements and expenditures - in (€) Report Period: P9
Comments: | At the end of Phase 1 of Grant implementation, all unused funds were declared as savings and were not disbursed by the TGF (EUR 454,362.00). All activities included in the programme of the Phase 1 were implimented. La finalizarea fazei I de implimentare a Grantului, toate sursele financiare neutilizate au fost declarate ca economii si debursari din partea FG nu au fost efectuate ( EUR 454,362.00). Toate activitatile incluse in program pentru faza I au fost implementate. |  |  | Comments: | The variance between the disbursed funds from GF and PR expenditure and disbursements are mainly due to the use of funds on the PR's account, disbursed during the previous periods. The variance between the disbursed funds from PR and SRs expenditures are due to the use of funds on the SR's account, disbursed during the previous periods. The unsed funds on the SRs accounts at the end of the Phase 1 were declared savings and a request for reallocation in this regard was addressed to TGF. Diferența dintre suma debursata de la Fondul Global și suma cheltuită și debursată de către Recipientul Principal se explică prin faptul că in această perioadă s/au utilizat sumele disponibile în contul RP, sume formate din debursările perioadelor anterioare. Diferența dintre sumele debursate de către RP și cheltuielile subrecipienților este condiționată de disponibilitatea sumelor în contul SR, formate din debursările anterioare. Sumele neutilizate de către SR, inregistrate la sfirșitul Fazei 1, au fost declarate ca economii. In adresa FG s/a făcut o cerere de aprobare a realocării sumelor economisite de SR la activitățile prioritare, incluse în Faza 2 al Grantului.
F2: Budget and actual expenditures by Grant Objective - in (€) Report Period: P9 |  |  |  | F4: Latest PR reporting and disbursement cycle Report Period: P9
Comments: | The variance between budget and expenditures is mainly due to : 1.Objective # 1 Mobilization resources to support community level: a) small number of NGO were involved in TB area at the time of announcement of granting grants.Thus, the activity of providing grants under objective # 1 was completed after establishment, registration and involvement of new NGO in TB field, a procedure requiring a certain time; b) getting a cost-efficiency in utilization of funds projected for establishment, mantaining and running cost for Community Centers; Objective 2. Remove barriers to care for poor and other vulnerable communities: a)less requests to cover transportation of patients, due to close location of patients to the health units; b) getting cost- efficieny for organising monitoring visits, meetings projected for members of the National League of People Living with HIV, peer support groups; Objective 3. Strengthen the health system and engage all available partners in TB control: a)obtaining less cost for logistics issues related to trainings/ meetings, printing and issues of training and informational materials for PHC, for representative of orthodox church; Objective 5. Integrate TB services on both sides of the prison walls All activities were completed. Less cost were involved in implementation of the activities. Diferenţele dintre buget şi cheltuieli sunt formate din urmatoarele considerente: Obiectivul # 1 Mobilizarea resurselor pentru suportul comunităţii: a) un număr mic de ONG activau in domeniul TB, la etapa publicării anunţului de oferire a granturilor. Astfel, activitatea de acordare a granturilor a fost implimentată odată cu inregistrarea a noilor ONG, orientate spre a activa in TB; b)eficientizarea costurilor programate pentru crearea, dotarea, și menținerea activității Centrelor Comunitare; Obiectivul 2.Eliminarea barierilor pentru păturile vulnerabile a) costurile de transport pentru pacienți aflați în tratament au fost mai mici, din motiv că mai des pacienții își au locul de trai ori sunt arondați pentru primirea tratamentului la cea mai apropiată unitate sanitară; b) eficientizarea costurilor la organizarea vizitelor de monitorizare, intrunirilor pentru membrii Ligii persoanelor cu HIV, educatorilor de la egal la egal etc.; Obiectivul 3. Fortificarea sistemului de sănătate și implicarea tuturor partenerilor antrenați în controlul TB: a) obținerea costurilor mai mici pentru logistica trainingurilor/ întrunirilor, imprimare și editare a materialelor informaționale și cele pentru instruirea personalului medical din sistemul de medicinî primară, pentru reprezentanții bisericii ortodoxe; Obiectivul 5. Integrarea serviciilor de TB in sistemul penitenciar. Toate activitățile au fost realizate cu implicarea costurilor mai mici versus celor estimate în buget. |  |  | Comments: | The PR always makes the disbursements to SRs in the shortest period when the disbursement request is received and the report is presented. Perioada de debursează către SR este cit mai operativ posibil de la data depunerii cererii de debursare şi prezentare a raportului financiar.
Last fund disbursement: Calendar days
[6 empty] | Expected (days) | Actual (days)
|  |  |  | Days taken to submit final PU/DR to LFA |  | 45 | 42
|  |  |  | Days taken for disbursement to reach PR |  | 45 | 111
|  |  |  | Days taken for disbursement to reach SRs |  | 20 | 5
Menu

## Management
Dashboard: Moldova - TB
Round 9 | Phase 1 |  |  |  |  | Report Period: |  | P9
Latest Rating: | A2 |  | PAS Center |  |  | From: |  | 2012-07-01
|  | Empowerment of people with TB and Communities in Moldova |  |  |  |  | To: | 2012-12-31
Management Indicators
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) Report Period: P9 |  |  |  | M2: Status of key PR management positions Report Period: P9
Comments: | The only CP was fulfilled by PAS Center,received NO from GF. Centrul PAS a implementat cerinta inaintată în Fondul Global în CP, avînd NO de la FG. |  |  | Comments: | All key positions of the management department are filled in by the PR. Toate functiile sunt completate de RP.
M3: Contractual arrangements (SRs) Report Period: P9 |  |  |  | M4: Number of complete reports received on time Report Period: P9
Comments: | Soros Moldova Foundation was not assesed due to its proved experience in grants' implementation. Fundația Soros- Moldova nu a fost evaluată ținînd cont de semnificativa experiență în implementarea granturilor. |  |  | Comments: | For the reported period, July-December 2012, 14 SSRs were involved in TB related activities , from which two (NGO "Youth for the right to live" Balti and "Socio-Medical Programmes" from Bender) are acting as SSR for two SRs - Soros Foundation Moldova and NGO "AFI". Basically , the majority of NGO are implementing one grant, with exception of four NGOs which applied to Soros Foundation - Moldova and were granted with more then one grant, as follow: NGO "Speranta Terrei" - 4 grants, NGO "AFI" - 3 grants, NGO "Socio-Medical Programmes" - 2 grants and NGO "National Association of TB pacients SMIT" - 2 grants. In perioada de raportare, iulie- decembrie 2012, 14 sub- subrecipienți au realizat activități conexe programului de control al TB, din care 2 organizații( ONG Tineri pentru Dreptul la Viață și ONG Programel Medico - Social) sunt în calitate de subsub recipienți pentru doi SR: Fundația Soros - Moldova și ONG "AFI". Majoritatea ONG realizeaza a cîte un grant,e xcepție fiind 4 ONG care au aplicat către Fundația Soros - Moldova, și au fost aprobate pentru implementarea a mai mult de un grant cum ar fi: ONG Speranța Terret - 4 granturi, ONG AFI - 3 granturi, ONG Programme Medico- Sociale- 2 granturi și ONG SMIT - 2 granturi.
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals |  |  |  | M6: Difference between current and safety stock Report Period: P9
Comments: |  |  |  | Comments:
|  |  |  | Component | Products | Stock level expressed in months of treatment for all current patients | Months of safety stock | Difference between current stock and safety stock
|  |  |  | TB | Please Select |  | 0
[5 empty] | Please Select |  | 0
[5 empty] | Please Select |  | 0
[5 empty] | Please Select |  | 0
* Includes only EFR category 4 and 5 (Health products and health equipment & Medicines and Pharmaceuticals)
Menu

## Programmatic
Dashboard: Moldova - TB
Round 9 | Phase 1 | [8 empty] | Report Period: |  | P9
Latest Rating: | A2 |  | PAS Center | [7 empty] | From: | 2012-07-01
|  | Empowerment of people with TB and Communities in Moldova | [8 empty] | To: | 2012-12-31 | [7 empty] | Raiting |  | Valor
Programmatic Indicators
Number of new TB patients provided with DOTS program who are receiving incentives and enablers for improved treatment compliance ( Numarul de pacienți noi înregistrați în programul DOTS care au beneficiat de stimulente pentru sporirea complianței la tratament) |  |  |  | Number of MDR-TB patients registered under DOTS plus program who are receiving incentives and enablers for improved treatment compliance (Numarul de pacienți înregistrați în programul DOTS Plus care au primit stimulente (pachete alimentare și pachete igienice) pentru sporirea complianței la tratament). |  |  |  | Number of medical personnel trained in TB control, community involvement and methods of informational work with different groups of population ( Numarul de lucrători medicali instruiți în controlul tuberculozei, implicarea comunității și metode de lucru informațional pe tuberculoză, pentru diferite grupuri de populație)
Comment: P1 | A total number of 2790 new TB patients were included in treatment from the project beginning at the CC level (1442 TB patients in 2011 and 1348 during 2012). The cumulative number of patients to be covered at December 31, 2012 from the total number of 2790 is equal with 2092 TB patients (75%) should be covered with services during the period 2011 - December 2012. Cumulatively for the project life 69% of total number of TB patients covered with services provided by the community centers. De la inceputul proiectului, 2790 pacienți noi cu TB au fost incluși în tratament la nivel de Centre Comunitare (1442 pacienți cu TB în 2011 și 1348 pe parcursul 2012). Numărul total al pacienților acoperiți cu servicii de către Centrele Comunitare la 31 Decembrie 2012 trebuie sa fie 2092 din numărul total de 2790 de pacienți cu TB ( 75%). In perioada raportată pentru perioada derulării proiectului cumulativ au fost asistați cu servicii 69% din numărul total de pacienți cu TB. |  |  | Comment: P2 | Accomplished. Realizat |  |  | Comment: P3 | During providing trainings there were negotiated better prices. The obtained savings allowed to involve more persons in trainings. In procesul de organizare a cursurilor de instruire s-au obținut prețuri mai mici. Economiile obținute a permis extinderea numărului de persoane instruite.
Indicators |  |  | Target | Achieved | 0% - 59% | 60% - 89% | > 90% | Comments |  |  |  |  | min | 0 | 30% | 60% | 90% | 100% |  | min | 0 | 20% | 40% | 60% | 80%
Number of new TB patients provided with DOTS program who are receiving incentives and enablers for improved treatment compliance ( Numarul de pacienți noi înregistrați în programul DOTS care au beneficiat de stimulente pentru sporirea complianței la tratament) |  |  | 2597 | 1923 | 106% |  |  | 561 of new TB patients provided with DOT by the community in the last semester (community centres and NGOs) received at least 25 DOT interventions during 1 months. (visit to DOT centre by the patient or visit to the patient by DOT supporters for drug intake). 561 de pacienti noi cu TB au primit cel putin 25 de interventii DOT timp de o luna in ultimul semestru. ( visita DOT la centru de catre pacient/ pacientul visitat de DOT suporter). |  |  |  |  | max | 30% | 60% | 90% | 100% | 200% |  | max | 20% | 40% | 60% | 80% | 100%
Number of MDR-TB patients registered under DOTS plus program who are receiving incentives and enablers for improved treatment compliance (Numarul de pacienți înregistrați în programul DOTS Plus care au primit stimulente (pachete alimentare și pachete igienice) pentru sporirea complianței la tratament). |  |  | 1196 | 1206 | 100.8% |  |  | 244 patients in the last semester were provided with at least three food packages per month. (244 pacienti au primit cel putin trei pachete de produse alimentare pe luna in ultimul semestru de raportare). | [5 empty] | de 0 a 0.3 | de 0.3 a 0.6 | de 0.6 a 0.9 | de 0.9 a 1 | de 1 a 2 | Rating | Valor | de 0 a 0.2 | de 0.2 a 0.4 | de 0.4 a 0.6 | de 0.6 a 0.8 | de 0.8 a 1
Number of medical personnel trained in TB control, community involvement and methods of informational work with different groups of population ( Numarul de lucrători medicali instruiți în controlul tuberculozei, implicarea comunității și metode de lucru informațional pe tuberculoză, pentru diferite grupuri de populație) |  |  | 710 | 1476 | 207.9% |  |  | A total of 118 persons were trained during S4.Due to the fact that were negotiated better prices for training expenses, this allowed to involve more persons in trainings. (Un total de 118 de persoane au fost instruite în S4.Tinta a fost depasita pentru faptul că au fost negociate preţuri mai bune pentru cheltuielile de formare profesională, aceasta a permis de a implica mai multe persoane în formare. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number of TB service staff and Primary Health Care (PHC) staff trained in DR-TB management (Numarul personalului din serviciul ftiziopneumologic si ingrijire medicala primara (AMP) instruiti in managementul TB-MDR) |  |  | 679 | 1348 | 198.5% |  |  | A total of 193 persons were trained in the reporting semester. Ministry of Health in partnership with State Medical and Pharmaceutical University, requested PAS Center to increase the number of trained TB and PHC specialists, because of MDR-TB situation in the country is very severe. For this purpose, SMPU agreed to co-finance accommodation and transportation costs in order to train more TB and PHC workers, than initially planned by the project. At this stage, 1/5 from the total number of 6500 PHC specialist have been trained. (Un total de 193 de persoane in semestrul de raportare au fost instruite. Ministerul Sănătăţii, în parteneriat cu Universitatea de Stat de Medicină şi Farmacie, a solicitat Centrul PAS marirea numărul de specialiști in TB şi din AMP instruiți, tinind cont ca povara MDR-TB este esențială în ţară. În acest scop, USMF a fost de acord să co-finanţeze costurile de cazare şi de transport, în scopul de a instrui mai multi specialişti din domeniul TB şi din medicina primară, versus numărului iniţial planificat în proiect. La această etapă, 1/5 din numărul total de 6500 specialişti din medicina primară au fost instruiţi). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number of TB patients registered under DOTS program who are receiving incentives and enablers to improve their treatment adherence (Numarul de pacienți TB înregistrați în programul DOTS care au primit stimulente (pachete alimentare și pachete igienice) pentru sporirea complianței la tratament) |  |  | 5212 | 6769 | 129.9% |  |  | 1625 patients registered under DOTS program recieved at least three food packages per month. (1625 pacienti cu TB inregistrati in cadrul programului DOTS au primit cel putin trei pachete de produse alimentare pe luna). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number of DOT community centres renovated and functional (Numarul de Centre Comunitate renovate si functionale) |  |  | n/a | n/a | N/A |  |  | 10 DOT community centres were renovated.The multidisciplinary teams of the community centers were trained and re-trained in development of the workplans, in judicial and administrative issues. (10 DOT centre comunitare au fost renovate. Echipele multidisciplinare din centrele comunitare au fost instruite şi re-instruite în elaborarea planurilor de lucru, în probleme juridice şi administrative). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Number of people (TB/HIV patients and their families) reached by peer support groups (Numarul de persoane (pacienți TB/HIV și familiile lor) care au fost instruiti de către grupurile de la egal la egal) |  |  | 1800 | 1867 | 103.7% |  |  | During S4, 971 people (TB/HIV patients and their families) were reached by peer support groups. (În timpul S4, 971 de persoane (TB / HIV, pacienti si familiile acestora) au beneficiat de asistenţa din partea grupurilor de sprijin de la egal la egal). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Number of volunteers, members of multidisciplinary teams, NGOs representatives and priests trained in TB community aspects (Numarul de voluntari, membri din echipele multidisciplinare, reprezentanti ai ONG-lor si preoți / lucrători ai bisericii ortodoxe instruiti în aspecte DOT și controlul tuberculozei la nivel de comunitate) |  |  | 1570 | 2380 | 151.6% |  |  | A total of 764 persons were trained, from them: 49 people from multidisciplinary teams of the community center including participation of representatives of local public authorities; 112 volunteers trained from the NGOs network in TB community aspects and 603 of priests and church activists were involved in workshops on informational and social work on TB. ( 764 de persoane au fost instruite, din care: 49 de persoane din echipele multidisciplinare a centrelor comunitare, inclusiv reprezentanti ai autoritatilor publice locale ; 112 voluntari şi 603 de preoți și lucrători ai bisericii au participat la ateliere de lucru privind activităţile informaționale și sociale în controlul tuberculozei). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Number of peer educators, journalists at national and district level and local stakeholders trained in TB and TB/HIV issues (Numarul de educatori de la egal la egal, jurnaliști la nivel național și regional, persoane-cheie din republică instruiți in TB și TB/HIV) |  |  | 680 | 2142 | 315% |  |  | A total of 891 persons were trained in the last reported semester, from them: 168 of peer educators trained to carry out informational work on TB; 16 of journalists at national and district level trained on TB communications and 707 of local stakeholders attending worshops on TB and TB/HIV. Un total de 891 de persoane in semestrul de raportare au fost instruite, din care: 168 de educatori de la egal la egal au fost instruiți pentru realizarea lucrului informațional despre tuberculoză; 16 jurnalisti de nivel national si raional instruiti cu privire la comunicarea în TB şi 707 de persoane-cheie din republică au participat la ateliere de lucru privind TB și TB/HIV. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Percentage of population with correct knowledge about TB (mode of transmission, symptoms, treatment and curability) (Procentul populatiei cu cunostinte corecte (modul de transmitere, simptome, tratament si curabilitatea) |  |  | 0.43 | 0.63 | N/A |  |  | 63 % of population with correct knowledge about TB (mode of transmission, symptoms, treatment and curability). (63% din populatie detine cunostinte corecte despre TB - caile de transmitere, simptomele, tratamentul si vindecarea). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Menu

## Recommendations
Dashboard: Moldova - TB
Round 9 | Phase 1 |  |  |  |  | Report Period: | P9
Latest Rating: | A2 |  | PAS Center |  |  | From: | 2012-07-01
|  |  | Empowerment of people with TB and Communities in Moldova |  |  | To: | 2012-12-31
Recommendations
Are all funds reaching implementation levels and being spent according to budget?
Financial |  | Summary Comments |  |  | Recommendations
F1 |  | At the end of Phase 1 of Grant implementation, all unused funds were declared as savings and were not disbursed by the TGF (EUR 454,362.00). All activities included in the programme of the Phase 1 were implimented. La finalizarea fazei I de implimentare a Grantului, toate sursele financiare neutilizate au fost declarate ca economii si debursari din partea FG nu au fost efectuate ( EUR 454,362.00). Toate activitatile incluse in program pentru faza I au fost implementate. |  |  | N/A
F2 |  | The variance between budget and expenditures is mainly due to : 1.Objective # 1 Mobilization resources to support community level: a) small number of NGO were involved in TB area at the time of announcement of granting grants.Thus, the activity of providing grants under objective # 1 was completed after establishment, registration and involvement of new NGO in TB field, a procedure requiring a certain time; b) getting a cost-efficiency in utilization of funds projected for establishment, mantaining and running cost for Community Centers; Objective 2. Remove barriers to care for poor and other vulnerable communities: a)less requests to cover transportation of patients, due to close location of patients to the health units; b) getting cost- efficieny for organising monitoring visits, meetings projected for members of the National League of People Living with HIV, peer support groups; Objective 3. Strengthen the health system and engage all available partners in TB control: a)obtaining less cost for logistics issues related to trainings/ meetings, printing and issues of training and informational materials for PHC, for representative of orthodox church; Objective 5. Integrate TB services on both sides of the prison walls All activities were completed. Less cost were involved in implementation of the activities. Diferenţele dintre buget şi cheltuieli sunt formate din urmatoarele considerente: Obiectivul # 1 Mobilizarea resurselor pentru suportul comunităţii: a) un număr mic de ONG activau in domeniul TB, la etapa publicării anunţului de oferire a granturilor. Astfel, activitatea de acordare a granturilor a fost implimentată odată cu inregistrarea a noilor ONG, orientate spre a activa in TB; b)eficientizarea costurilor programate pentru crearea, dotarea, și menținerea activității Centrelor Comunitare; Obiectivul 2.Eliminarea barierilor pentru păturile vulnerabile a) costurile de transport pentru pacienți aflați în tratament au fost mai mici, din motiv că mai des pacienții își au locul de trai ori sunt arondați pentru primirea tratamentului la cea mai apropiată unitate sanitară; b) eficientizarea costurilor la organizarea vizitelor de monitorizare, intrunirilor pentru membrii Ligii persoanelor cu HIV, educatorilor de la egal la egal etc.; Obiectivul 3. Fortificarea sistemului de sănătate și implicarea tuturor partenerilor antrenați în controlul TB: a) obținerea costurilor mai mici pentru logistica trainingurilor/ întrunirilor, imprimare și editare a materialelor informaționale și cele pentru instruirea personalului medical din sistemul de medicinî primară, pentru reprezentanții bisericii ortodoxe; Obiectivul 5. Integrarea serviciilor de TB in sistemul penitenciar. Toate activitățile au fost realizate cu implicarea costurilor mai mici versus celor estimate în buget. |  |  | Fortificarea activitatilor de antrenare a ONG in controlul TB.
F3 |  | The variance between the disbursed funds from GF and PR expenditure and disbursements are mainly due to the use of funds on the PR's account, disbursed during the previous periods. The variance between the disbursed funds from PR and SRs expenditures are due to the use of funds on the SR's account, disbursed during the previous periods. The unsed funds on the SRs accounts at the end of the Phase 1 were declared savings and a request for reallocation in this regard was addressed to TGF. Diferența dintre suma debursata de la Fondul Global și suma cheltuită și debursată de către Recipientul Principal se explică prin faptul că in această perioadă s/au utilizat sumele disponibile în contul RP, sume formate din debursările perioadelor anterioare. Diferența dintre sumele debursate de către RP și cheltuielile subrecipienților este condiționată de disponibilitatea sumelor în contul SR, formate din debursările anterioare. Sumele neutilizate de către SR, inregistrate la sfirșitul Fazei 1, au fost declarate ca economii. In adresa FG s/a făcut o cerere de aprobare a realocării sumelor economisite de SR la activitățile prioritare, incluse în Faza 2 al Grantului.
F4 |  | The PR always makes the disbursements to SRs in the shortest period when the disbursement request is received and the report is presented. Perioada de debursează către SR este cit mai operativ posibil de la data depunerii cererii de debursare şi prezentare a raportului financiar.
Are procurement and hiring on schedule?
Management |  | Summary Comments |  |  | Recommendations
M1 |  | The only CP was fulfilled by PAS Center,received NO from GF. Centrul PAS a implementat cerinta inaintată în Fondul Global în CP, avînd NO de la FG.
M2 |  | All key positions of the management department are filled in by the PR. Toate functiile sunt completate de RP. | #DIV/0! | #DIV/0!
M3 |  | Soros Moldova Foundation was not assesed due to its proved experience in grants' implementation. Fundația Soros- Moldova nu a fost evaluată ținînd cont de semnificativa experiență în implementarea granturilor.
M4 |  | For the reported period, July-December 2012, 14 SSRs were involved in TB related activities , from which two (NGO "Youth for the right to live" Balti and "Socio-Medical Programmes" from Bender) are acting as SSR for two SRs - Soros Foundation Moldova and NGO "AFI". Basically , the majority of NGO are implementing one grant, with exception of four NGOs which applied to Soros Foundation - Moldova and were granted with more then one grant, as follow: NGO "Speranta Terrei" - 4 grants, NGO "AFI" - 3 grants, NGO "Socio-Medical Programmes" - 2 grants and NGO "National Association of TB pacients SMIT" - 2 grants. In perioada de raportare, iulie- decembrie 2012, 14 sub- subrecipienți au realizat activități conexe programului de control al TB, din care 2 organizații( ONG Tineri pentru Dreptul la Viață și ONG Programel Medico - Social) sunt în calitate de subsub recipienți pentru doi SR: Fundația Soros - Moldova și ONG "AFI". Majoritatea ONG realizeaza a cîte un grant,e xcepție fiind 4 ONG care au aplicat către Fundația Soros - Moldova, și au fost aprobate pentru implementarea a mai mult de un grant cum ar fi: ONG Speranța Terret - 4 granturi, ONG AFI - 3 granturi, ONG Programme Medico- Sociale- 2 granturi și ONG SMIT - 2 granturi.
M5
M6
Are technical targets being achieved?
Programmatic |  | Summary Comments |  |  | Recommendations
P1 - trend |  | A total number of 2790 new TB patients were included in treatment from the project beginning at the CC level (1442 TB patients in 2011 and 1348 during 2012). The cumulative number of patients to be covered at December 31, 2012 from the total number of 2790 is equal with 2092 TB patients (75%) should be covered with services during the period 2011 - December 2012. Cumulatively for the project life 69% of total number of TB patients covered with services provided by the community centers. De la inceputul proiectului, 2790 pacienți noi cu TB au fost incluși în tratament la nivel de Centre Comunitare (1442 pacienți cu TB în 2011 și 1348 pe parcursul 2012). Numărul total al pacienților acoperiți cu servicii de către Centrele Comunitare la 31 Decembrie 2012 trebuie sa fie 2092 din numărul total de 2790 de pacienți cu TB ( 75%). In perioada raportată pentru perioada derulării proiectului cumulativ au fost asistați cu servicii 69% din numărul total de pacienți cu TB. |  |  | Raportul final de evaluare al PNCT al OMS de considerat la elaborarea planului de actiuni pentru fortificarea programului de control al tuberculozei, inclusiv cresterea rolului Centrelor Comunitare cit si altor actori din comunitate/ societatea civila in controlul Tuberculozei.
P2 - trend |  | Accomplished. Realizat
P3 - trend |  | During providing trainings there were negotiated better prices. The obtained savings allowed to involve more persons in trainings. In procesul de organizare a cursurilor de instruire s-au obținut prețuri mai mici. Economiile obținute a permis extinderea numărului de persoane instruite.
P1 |  | 561 of new TB patients provided with DOT by the community in the last semester (community centres and NGOs) received at least 25 DOT interventions during 1 months. (visit to DOT centre by the patient or visit to the patient by DOT supporters for drug intake). 561 de pacienti noi cu TB au primit cel putin 25 de interventii DOT timp de o luna in ultimul semestru. ( visita DOT la centru de catre pacient/ pacientul visitat de DOT suporter).
P2 |  | 244 patients in the last semester were provided with at least three food packages per month. (244 pacienti au primit cel putin trei pachete de produse alimentare pe luna in ultimul semestru de raportare).
P3 |  | A total of 118 persons were trained during S4.Due to the fact that were negotiated better prices for training expenses, this allowed to involve more persons in trainings. (Un total de 118 de persoane au fost instruite în S4.Tinta a fost depasita pentru faptul că au fost negociate preţuri mai bune pentru cheltuielile de formare profesională, aceasta a permis de a implica mai multe persoane în formare.
P4 |  | A total of 193 persons were trained in the reporting semester. Ministry of Health in partnership with State Medical and Pharmaceutical University, requested PAS Center to increase the number of trained TB and PHC specialists, because of MDR-TB situation in the country is very severe. For this purpose, SMPU agreed to co-finance accommodation and transportation costs in order to train more TB and PHC workers, than initially planned by the project. At this stage, 1/5 from the total number of 6500 PHC specialist have been trained. (Un total de 193 de persoane in semestrul de raportare au fost instruite. Ministerul Sănătăţii, în parteneriat cu Universitatea de Stat de Medicină şi Farmacie, a solicitat Centrul PAS marirea numărul de specialiști in TB şi din AMP instruiți, tinind cont ca povara MDR-TB este esențială în ţară. În acest scop, USMF a fost de acord să co-finanţeze costurile de cazare şi de transport, în scopul de a instrui mai multi specialişti din domeniul TB şi din medicina primară, versus numărului iniţial planificat în proiect. La această etapă, 1/5 din numărul total de 6500 specialişti din medicina primară au fost instruiţi).
P5 |  | 1625 patients registered under DOTS program recieved at least three food packages per month. (1625 pacienti cu TB inregistrati in cadrul programului DOTS au primit cel putin trei pachete de produse alimentare pe luna).
P6 |  | 10 DOT community centres were renovated.The multidisciplinary teams of the community centers were trained and re-trained in development of the workplans, in judicial and administrative issues. (10 DOT centre comunitare au fost renovate. Echipele multidisciplinare din centrele comunitare au fost instruite şi re-instruite în elaborarea planurilor de lucru, în probleme juridice şi administrative).
P7 |  | During S4, 971 people (TB/HIV patients and their families) were reached by peer support groups. (În timpul S4, 971 de persoane (TB / HIV, pacienti si familiile acestora) au beneficiat de asistenţa din partea grupurilor de sprijin de la egal la egal).
P8 |  | A total of 764 persons were trained, from them: 49 people from multidisciplinary teams of the community center including participation of representatives of local public authorities; 112 volunteers trained from the NGOs network in TB community aspects and 603 of priests and church activists were involved in workshops on informational and social work on TB. ( 764 de persoane au fost instruite, din care: 49 de persoane din echipele multidisciplinare a centrelor comunitare, inclusiv reprezentanti ai autoritatilor publice locale ; 112 voluntari şi 603 de preoți și lucrători ai bisericii au participat la ateliere de lucru privind activităţile informaționale și sociale în controlul tuberculozei).
P9 |  | A total of 891 persons were trained in the last reported semester, from them: 168 of peer educators trained to carry out informational work on TB; 16 of journalists at national and district level trained on TB communications and 707 of local stakeholders attending worshops on TB and TB/HIV. Un total de 891 de persoane in semestrul de raportare au fost instruite, din care: 168 de educatori de la egal la egal au fost instruiți pentru realizarea lucrului informațional despre tuberculoză; 16 jurnalisti de nivel national si raional instruiti cu privire la comunicarea în TB şi 707 de persoane-cheie din republică au participat la ateliere de lucru privind TB și TB/HIV.
P10 |  | 63 % of population with correct knowledge about TB (mode of transmission, symptoms, treatment and curability). (63% din populatie detine cunostinte corecte despre TB - caile de transmitere, simptomele, tratamentul si vindecarea).
Menu

## Actions
Dashboard: Moldova - TB
| Round 9 | Phase 1 |  |  |  | Report Period: |  | P9
| Latest Rating: | A2 |  | PAS Center |  | From: |  | 2012-07-01
|  |  | Empowerment of people with TB and Communities in Moldova |  |  |  | To: | 2012-12-31
Decisions and Actions
What is the overall status of this grant implementation?
| Key Recommendations from Oversight Group(s) |  |  |  | CCM Decision | Due Date | Person Responsible
Current Reporting Period
Actions to Implement / Previous Period
What is the overall status of this grant implementation?
| CCM Decision |  |  |  | Action Taken | Date | Person Responsible
Previous Reporting Period
Menu

## Setup (hidden)
Dashboard: Moldova - TB
Set-up = List of validation for Grant Detail page
Component | Currency | Round | Phase | Period | Rating | LFA | Medicaments | Countries
Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select
HIV / AIDS | $ | Round 1 | Phase 1 | P1 | A1 | CA (Crown Agents) | Isoniazid | Afghanistan
MALARIA | € | Round 2 | Phase 2 | P2 | A2 | DEL (Deloitte) | Ethambutol | Albania
TB |  | Round 3 | RCC | P3 | B1 | DTT (DTT Emerging Markets) | Rifampicin | Algeria
HIVAIDS / TB |  | Round 4 |  | P4 | B2 | FIN (Finconsult) | Pyrazimamide | Angola
HSS |  | Round 5 |  | P5 | C | GT (Grant Thornton) | RDT | Argentina
|  | Round 6 |  | P6 |  | H-C (Hodar-Conseil) | NVP | Armenia
|  | Round 7 |  | P7 |  | KPMG (KPMG) | 3TC | Azerbaijan
|  | Round 8 |  | P8 |  | MSCI (MSCI) | D4T | Bangladesh
|  | Round 9 |  | P9 |  | PwC (PricewaterhouseCoopers) | AZT | Belarus
|  | Round 10 |  | P10 |  | STI (Swiss Tropical Institute), | DDI | Belize
|  |  |  | P11 |  | UNOPS | EFV | Benin
|  |  |  | P12 |  |  | AS/LF | Bhutan
[7 empty] | AS/AQ | Bolivia
[7 empty] | AS/MQ | Bosnia and Herzegovina
[7 empty] | Al/Lum | Botswana
Brazil
[7 empty] | TB nutri'l supplements | Bulgaria
[7 empty] | E-PAP | Burkina Faso
Burundi
Cambodia
Cameroon
Cape Verde
Central African Republic
Chad
Chile
China
China
Colombia
Comoros
Congo (Democratic Republic of the)
Congo (Republic of the)
Costa Rica
Cote d'Ivoire
Croatia
Cuba
Djibouti
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Ethiopia
Fiji
Gabon
Gambia
Georgia
Ghana
Global(LWF)
Guatemala
Guinea
Guinea-Bissau
Guyana
Haiti
Honduras
India
Indonesia
Iran (Islamic Republic of)
Iraq
Jamaica
Jordan
Kazakhstan
Kenya
Korea, Democratic Peoples Republic of
Kosovo (Serbia)
Kyrgyzstan
Lao PDR
Lesotho
Liberia
Macedonia, FYR
Madagascar
Malawi
Maldives
Mali
Mauritania
Mauritius
Moldova
Mongolia
Montenegro
Morocco
Mozambique
Multi-country Africa (West Africa Corridor Program)
Multi-country Africa(RMCC)
Multi-country Americas (Andean)
Multi-country Americas (CARICOM)
Multi-country Americas (CRN+)
Multi-country Americas (Meso)
Multi-country Americas (OECS)
Multi-country Americas (REDCA+)
Multi-country Western Pacific
Myanmar
Namibia
Nepal
Nicaragua
Niger
Nigeria
Pakistan
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Romania
Russian Federation
Rwanda
Sao Tome and Principe
Senegal
Serbia
Sierra Leone
Solomon Islands
Somalia
South Africa
Sri Lanka
Sudan
Suriname
Swaziland
Syrian Arab Republic
Tajikistan
Tanzania
Thailand
Timor-Leste
Togo
Tunisia
Turkey
Uganda
Ukraine
UN Theme Group on HIV/AIDS (West Bank and Gaza)
Uzbekistan
Viet Nam
Yemen
Zambia
Zanzibar (Tanzania)
Zimbabwe