## Menu
Dashboard: Moldova - HIV / AIDS
HIV / AIDS SSF (Round 8), Piriod 2 | Grant No.: MOL-H-PAS
V1.0
Finance
Programmatic
Management
Select the option you want to see:
Recommendations
Actions
Grant Detail
List of Indicators
Data Entry
Grant Information
Indicators
Reports

## List of Indicators
Dashboard: Moldova - HIV / AIDS
Financial information
Name: | Definition | Measurement | Data Sources
F1: Budget and disbursements by Global Fund | Cumulative budget: Sum of the grant budget from period one (quarter, trimester, or semester) of the current phase, up to and including the dashboard reporting period. Cumulative Disbursments by GF: Sum of all the funds transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to and including the dasboard reporting period. | Currency of the grant ($ or Euro) Cumulative – Figures refer to budget and disbursements for all the periods of the phase up to and including the dashboard reporting period | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F2: Budget and actual expenditures by Grant Objective | Cumulative Budget per Objective: Sum of the grant budget by Objective, from period one of the current phase up to and including the dashboard reporting period. Cumulative Expenditure per Objective: Sum of amounts spent by Objective directly by the PR plus the amounts transferred by the PR to all SRs from the beginning of the phase up to and including dashboard reporting period, by Objective | • Cumulative – Figures refer to budget, disbursements or expenditure for all the periods of the phase up to and including the dashboard reporting period. | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F3: Disbursements and expenditures | Disbursement by GF: Prior to this Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to but not including dashboard reporting period. Disbursement by GF: Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), during dashboard reporting period. PR disbursements and expenditure: Prior to this Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) up to but not including dashboard reporting period. PR disbursements and expenditure: Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) during dashboard reporting period. Disbursements to SRs: Prior to this Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), up to but not including dashboard reporting period. Disbursements to SRs:Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), in dashboard reporting period. SR expenditures: Prior to this Reporting period: The sum of all expenditures reported by the SRs, up to but not including dashboard reporting period. SR expenditures: Reporting period: The sum of all expenditures reported by the SRs, during dashboard reporting period. | Currency of the grant ($ or Euro) • Reporting period – Figures refer to budget, disbursements or expenditure for the reporting period to which the dashboard refers. • Prior to reporting period - Figures refer to the total budget, disbursements or expenditure for all the periods before but not including the current period. | PU/DR; PR data: SR reports to PR
F4: Latest PR reporting and disbursement cycle | Days taken to submit final PU/DR to LFA – This indicator measures the number of calendar days it took the PR to send a final Performance Update and Disbursement Request (PU/DR) to the LFA after the end of the period. A 'final' PU/DR would be one for which the LFA did not require any further clarifications from the PR. The expected value is 45 days from the end of the period, as defined in the Grant Agreement. The actual value is the number of calendar days from the end date of the period to the date on which the PR sent to the LFA the final PU/DR. Days taken for disbursement to reach PR – This indicator measures the number of calendar days it took the Global Fund to send the latest disbursement to the PR's account after receipt of the acceptable PU/DR by the LFA. The expected number is 45 days. The actual number is the number of days from the date of transmission by the PR to the LFA of the acceptable PU/DR to the date the disbursement is received by the PR at its bank. Days taken for disbursement to reach SRs – This indicator measures the average number of days for disbursements to be made to all the SRs. The expected value for this indicator will be set locally by the PR and SRs, preferably in the Grant Operations Manual. The actual value is the average of the number of days from the receipt of the funds from the GF by the PR to the date the funds are received by each SR. Different SRs coudl receive funds on different dates and this indicator is the average across all SRs for the latest disbursement. | Number of calendar days; it refers only to reporting period for which the latest disbursement was received and is not cumulative | PR, LFA, GF emails and records; bank notification document or the notice of receipt by the PR to GF; SR reports to PR based on bank records
Management Information
Name: | Definition | Measurement | Data Source
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) | Number of Conditions Precedent (CPs) and Time Bound Actions (TBAs ) fulfilled, or unfulfilled. Within the Unfulfilled category, we distinguish between those CPs and TBAs whose deadline has not passed and those for which the deadline has passed. | Number, cumulative to the dashboard reporting period. Number of fulfilled CPs and/or TBAs plus unfulfilled CPs and/or TBAs should equal the total number set by the Global Fund on the grant | PR records; Grant Performance Reports;
M2: Status of key PR management positions | Number of PR grant management positions planned currently filled or vacant. Full time equivalents of the managerial positions that are on the organizational chart (or otherwise planned) and directly responsible for ensuring grant implementation at the PR, and lead SRs (if necessary). This will include new hires, current staff who are assigned to work on the grant’s management, as well as any staff seconded from other divisions or partner organizations. | Number, in current reporting period | PR records
M3: Contractual arrangements (SRs) | Identified: Total number of potential SRs identified by the PR for the phase. Assessed: Total number of potential SRs assessed by the PR to determine whether they qualify to function as SRs for the grant. Approved: Total number of SRs that have been approved. Signed: Total number of SRs that have signed agreements/contracts with the PR under the grant. Receiving funding: Total number of SRs that are getting funds and/or supplies from the PR. Numbers of SRs Identified, Assessed, Approved, Signed and Receiving funds are cumulative for the phase, with the following exceptions: If an SR does not need new approval in Phase II, then approval in Phase I is counted. If an SR was signed in a previous Phase but is not working in the current Phase, that SR is no longer counted in Identified, Assessed, Approved. | Number, cumulative to the reporting period. A SR is an institution or program with its own workplan, budget and performance targets. | PR records; Sub-agreements/MOUs; CCM records
M4: Number of complete reports received on time | The total number of periodic reports with up-to-date financial, management and performance (programmatic) data received by the PR from SRs and by SRs from the SubSRs (SSRs) by the expected date. A 'complete' report is one that contains all the data that the PR requires for the PU/DR. The expected date would be set by the PR in the sub-agreements. | Number of reports received. The figure reflects only the period of reporting; it is not cumulative. | PR and SR records
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals | This indicator measures the budget approved for the current phase of the grant for purchase of health products and equipment and pharmaceuticals and medicines (categories 4 and 5 in the new Enhanced Financial Report), and the cumulative amounts of financial obligations and expenditures up to the dashboard reporting period. Budget approved: Total approved budget for purchases (categories 4 and 5) for the entire phase of the grant. It does not include the amounts for fees, management, operational costs, etc. Cumulative Obligations: Total of all order(s) placed and monies committed for these purchases by the PR up to and including the dashboard reporting period. Ideally, by the end of the Phase, budget should equal obligations. Cumulative expenditure: Total of actual Expenditures on category 4 and 5 up to and including the dashboard reporting period (whether paid by PR or authorized to be paid by another entity like GF or other). | Currency of the grant ($ or Euro) | Grant agreement approved budget (for categories 4 and 5 of Enhanced Finance Reporting in current phase); and PR financial data (for expenditures), and/or PSM unit (for orders placed and funding committed or obligated).
Note: Category 6 of the EFR will not be considered as part of the budget for pharmaceuticals. Category 6 has several expenditures that are difficult to disaggregate or quantify, such as warehousing costs, distribution costs (particularly when distibution is done by MOHs), and others that are related to operational costs of the PSM component.
M6: Difference between current and safety stock | This indicator is a snapshot of the difference between the current (or last month) stock level of a specific product (medicine in single, fixed-dose combination, bednets, diagnostic kits, etc.) of a particular dose, expressed in monthly needs (number of months of treatment available) for all patients in the program, and the safety or buffer stock (also expressed in months) as established by the disease program, warehouse system or essential drugs program, for the particular product and dosage. The table will show the difference in months in colors: • RED: when the difference is negative or 0, showing that months of existing stock are lower than or equal to what has been established as months of safety stock • YELLOW: when we have more than the level of safety stock (>0) but less than 3 months (+3). • GREEN: when the difference is between 3 and 18 months. • VIOLET: When the difference shows that the level above the safety stock is greater than or equal to 18 months indicating a potential overstock) problem. For a full description of how this indicator is calculated, please see the User’s Manual. | Number of months | PR records: Warehouse data.
Programmatic Indicators (from Performance Framework)
Indicator | Definition (from M&E Plan, September 2009) | Measurement | Data Source
Number of medical (doctors and nurses) and non-medical staff (psychologists, social assistants, peer consultants) trained in HIV/AIDS | Indicator refers to training of ART and MDT medical specialists, infectious diseases and PHC specialists, social assistants and MDT non-medical specialists. This is a composite indicator, related activities: 3.1.1., 3.1.2., 3.1.4. & 3.1.5 | A person is considered trained if he/she has attended the course not less than 80% and signed the list of participation at training (people signed the list of attendance twice a day along the course). | Training records (daily attendance lists signed by trainees)
Number of PLHIV receiving food parcels to improve ARV treatment adherence | Patients on ART treatment will receive quarterly incentives (food parcels) for better adherence to treatment, in both civilian and penitentiary sectors. A PLHIV is considered "reached" if s/he has received a food package per quarter at least one quarter. Quarterly will be distributed 800 food parcels based on the socio-economic vulnerability criteria. Targets for this indicator are annual and have been calculated based on an estimated quarterly increase by 10% in the number of new beneficiaries. Related activity: 4.1.1 | New persons who received a food package per quarter at least quart. | Register of people reached and SR program reports
Number of people living with HIV/AIDS reached with care and support services | The beneficiaries are provided with the following services: psycho-social counseling and support, medical counseling and refferal, distribution of information materials, peer counseling, self-support groups and food support, etc. The beneficiary is considered "reached" if s/he has received at least one of the listed services. Related activity 4.1.2,4.1.3 & 4.4.1-4.4.3. Target include baseline. | The beneficiaries are provided with the following services: psycho-social counseling and support, medical counseling and referral, distribution of information materials and peer counseling. The beneficiary is considered "reached" if he/she has received at least one of the listed services. | Register of people reached and SR program reports
Number of children infected and affected by HIV/AIDS who receive social support | The social support includes food parcels and clothing and school supplies for HIV infected children and food support for children born from HIV positive mothers with unknown status. Quarterly will be distributed 230 food parcels. Targets for this indicator are annual and have been calculated based on an estimated quarterly increase by 10% in number of new born to HIV positive mothers. It is a composite indicator, related activities: 4.3.1.& 4.3.2. | A child is considered "reached" if she/he has received a social support (food parcels and clothing and school supplies for HIV infected children and food support for children born from HIV positive mothers with unknown status) per quarter at least quart. | Register of people reached and SR program reports
Number of Injecting drug users on oppoid substitution therapy that receive at least 3 support services from NGOs working in DUs rehabilitation | The beneficiary is considered "reached" if s/he has received at least three of the services listed (psycho-social support, self-support groups, peer to peer education, distributions of information materials, food support,etc.). Related activity 4.2.1-4.2.3 Target include baseline. | The beneficiary is considered "reached" if he/she has received at least three of the services listed (psycho-social support, self-support groups, peer to peer education, distributions of information materials, food support, etc.). | Register of people reached and SR program reports
Number and percentage of individuals currently on OST who have been on OST continuously at least 6 months for the past 12 months | Numerator: number of individuals completing at least 6 months of continuous treatment on OST that initiated treatment 6-12 months prior to the end of the reporting period. Denominator: total number of individuals that initiated treatment 6-12 months prior to the end of reporting period. The indicator is linked to percentage and absolute numbers will be provided when reporting results. The targets refer to the patient cohort (both new and repeated cases) that initiated treatment in the first 6 months of the last 12 months period. NOTE: PAS Center is responsible for data collection and validation. | Determine the number of people who initiated OST (first or repeated) in the first six months of the last 12 months and evaluated how many of these people remained in OST at least 6 months continuously. 6 months cohort based evaluations. | OST centers administrative records (RND, Balti municipal hospital and DPI)
Number of human rights strategic litigation cases for PLHIV initiated | Indicator refers to cases of PLHIV rights violation initiated for strategic litigation in order to change the existing practices. Related activity 5.2.2-5.2.4 | Total number of human rights strategic litigation cases registered in the register | List of human rights strategic litigation cases
Number of PLHIV assisted by legal aid (consultancies offered by legal network) | The indicator refers to legal assistance provided remotely to PLHIV on issues of legal, civil (including disclosure of HIV status), administrative nature. Related activity 5.2.1&5.2.4 | Person is considered "reached" if he/she receives at least one consultation offered by legal network. | List of PLHIV assisted by legal aid
Number of members of the civil society trained in services provision to PLHIV | Indicator refers to training of members of the civil society in services provision to PLHIV. Related activities: 5.3.9. | A person is considered trained if he/she has attended the course not less than 80% and signed the list of participation at training (people signed the list of attendance twice a day along the course). | Training records (daily attendance lists signed by trainees)
Indicator Number: Name (Perf Framework No.) | Definition | Measurement | Data Source
The indicators should be selected by the PRs and members of the CCM or the CCM Technical Committee, from the Performance Framework |  |  | Performance Framework
Menu

## Data Entry
Grant information
| Country: | Moldova |  | Title of the Grant: |  | Reducing HIV-related burden in the Republic of Moldova
| Grant No.: | MOL-H-PAS |  | Component: |  | HIV / AIDS | Total Funding: | EUR 12057410
| Principal Recipient: | PAS Center |  |  | Round: | SSF (Round 8) | Phase: | Piriod 2
| Start Date (dd/Mmm/yy): | January 01, 2010 |  | Local Fund Agent: |  | PwC (PricewaterhouseCoopers)
| Latest Rating: | A2 |  | Fund Portfolio Manager: |  | Tatiana Vinichenko
Information reporting period
| Report Period: | P7 | From: | January 01, 2013 | To: | June 30, 2013 | Date of entry of information: |  | September 01, 2013
| Prepared by: |  | PAS Center
Information on indicators
Enter the data based on the colour-coded cells
| Financial Information: |  | Management Information: |  |  | Programmatic Information:
| Financial Information: | [8 empty] | Enter finance data in every orange cell like this.
| Currency of the grant |  | €
F1: Budget and disbursements by Global Fund
| Disbursement | [15 empty] | 0
| Reporting period |  |  |  |  | P1-P12 (Q1.2010-Q4.2012) | P13 (Q1.2013) | P14 (Q2.2013) | [5 empty] | % Cumulative |  |  | 0
| Budget (in €) |  |  |  |  | 8116137 | 470112.82 | 506932.17 | [5 empty] | 116.2% |  |  | 0
| Disbursements by GF (in €) |  |  |  |  | 8116137 | 2449445.91 | [9 empty] | 0
| Cumulative budget |  |  |  |  | 8116137 | 8586249.82 | 9093181.99 | [8 empty] | 8116137
| Cumulative disbursements |  |  |  |  | 8116137 | 10565582.91 | 10565582.91 | [8 empty] | 8586249.82
|  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 9093181.99
F2: Budget and actual expenditures by Grant Objective
| Grant Objective | Cumulative Budget (in €) | Cumulative Expenditures (in €)
| Improve performance of GFATM Round VI through improved infrastructure | 1046390.57 | 1068207.5667
| Improve quality of Life of PLWH | 5818038.33 | 5862071.5186
| Strengthen the National League of PLWH | 791501.52 | 790769.5847
| Planning and administration | 1437251.5718 | 1445842.8046
| Total | 9093181.9918 | 9166891.4747 |  | OK: Data match
| F3: Disbursements and expenditures | [15 empty] | 0
0
|  | Prior to reporting period | Current reporting period | Total Spent and Disbursement (in €) | [11 empty] | 0
| Disbursed by Global Fund | 8116137 | 2449445.91 | 10565582.91
| PR expenditure and disbursement | 8127337 | 1039564.1018 | 9166901.1018
| Disbursed to SRs | 4855420 | 609614.6794 | 5465034.6794
| SR expenditures | 4794075 | 625352.21 | 5419427.21
F4: Latest PR reporting and disbursement cycle
Last fund disbursement: Number of calendar days
|  | Expected (days) | Actual (days)
| Days taken to submit final PU/DR to LFA | 45 | 43
| Days taken for disbursement to reach PR | 45 | 83
| Days taken for disbursement to reach SRs | 20 | 5
| Management Information: | [5 empty] | Enter management data in every blue cell.
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs)
|  |  | Fulfilled | Not fulfilled, but within deadline | Not fulfilled, and past the deadline | Total
| Conditions precedent (CPs) |  | 2 |  |  | 2
| Time Bound Actions (TBAs) |  |  |  |  | 0
M2: Status of key PR management positions
|  | Planned | Filled | Vacant
| PMU | 14 | 14 | 0
M3: Contractual arrangements (SRs)
|  | Identified | Assessed | Approved | Signed | Receiving Funding
| SRs | 4 | 4 | 4 | 2 | 2
M4: Number of complete reports received on time
|  | # Expected | # Received | Pending
| SSR to SR | 18 | 17 | 1
| SRs to PR | 2 | 2 | 0
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals
|  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
Budget Approved*
Obligations
Expenditures
| Budget Approved cumulative* | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Obligations cumulative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Expenditures cumulative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
* Includes only EFR category 4 and 5 (Health products and health equipment & Medicines and Pharmaceuticals)
M6: Difference between current and safety stock
| Component | Products | (1) Number of tablets per patient per day (Review country treatment guidelines) | (2 = 1 x 30) Monthly treatment (Tablets per patient x 30 days) | (3) Total patients in treatment | (4 = 2 x 3) Total # tab/pills required for all patients per month | (5) Current stock in central warehouse (that does not expire within the next 3 months) | (6 = 5 / 4) Stock level expressed in months of treatment for all current patients | (7) Level of safety stock (expressed in months and defined by country) | (8 = 6 - 7) Difference between current stock and safety stock
| HIV / AIDS | P1: Please Select
Please Select
Please Select
Please Select
| Programmatic Information: | P9: Enter performance data in every yellow cell.
| Programmatic indicators (Performance Framework ) |  |  | Code | Directly Tied? |  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12 | P13 | P14
TOP 3 | Number of people living with HIV/AIDS reached with care and support services (Numărul persoanelor care trăiesc cu HIV/SIDA şi au primit suport social) |  |  | 4.2 | Yes | Target | 3250 | 3500 | 3750 | 4000 | 4375 | 4750 | 4832 | 5207 | 5357 | 5507 | 5657 | 5807 | 5947 | 6087
[6 empty] | Achieved | 2093 | 2817 | 3197 | 3717 | 3976 | 4296 | 4564 | 4853 | 5107 | 5327 | 5519 | 5704 | 5874 | 6085
| Number of children infected and affected by HIV/AIDS who receive social support (Numărul de copii infectaţi şi afectaţi de HIV/SIDA care primesc suport social) |  |  | 4.3 | Yes | Target | 95 | 125 | 155 | 185 | 216 | 248 | 352 | 372 | 392 | 412 | 432 | 452 | 230 | 244
[6 empty] | Achieved | 91 | 133 | 195 | 236 | 298 | 332 | 363 | 395 | 395 | 462 | 482 | 509 | 229 | 264
| Number of Injecting drug users on opioid substitution therapy that receive at least 3 support services from NGOs working in DUs rehabilitation (Numărul de CDI care sunt în terapia de substituţie cu metadonă şi primesc cel puţin 3 servicii de suport din partea ONG-urilor care lucrează la reabilitarea CDI) |  |  | 4.4 | Yes | Target | 54 | 108 | 162 | 216 | 280 | 344 | 407 | 471 | 511 | 551 | 591 | 631 | 651 | 671
[6 empty] | Achieved | 61 | 131 | 180 | 225 | 284 | 322 | 368 | 437 | 462 | 481 | 500 | 534 | 554 | 579
| Number of medical (doctors and nurses) and non-medical staff (psychologists, social assistants, peer consultants) trained in HIV/AIDS (Numărul personalului medical (medici şi asistente medicale) şi non-medical (psihologi, asistenţi sociali, educatori de la egal la egal) instruiţi în HIV/SIDA) |  |  | 3.1 | Yes | Target | 25 | 150 | 225 | 400 | 500 | 625 | 1224 | 1410 | 1510 | 1610 | 1710 | 1810 | 50 | 90
[6 empty] | Achieved | 50 | 174 | 268 | 594 | 788 | 1099 | 1224 | 1395 | 1448 | 1608 | 1804 | 1898 | 24 | 129
| Number of PLHIV receiving food parcels to improve ARV treatment adherence (Numărul de PTH care primesc pachete alimentare pentru a îmbunătăți aderenţa la tratamentul ARV) |  |  | 4.1 | Yes | Target | 108 | 216 | 324 | 432 | 573 | 715 | 1011 | 1061 | 1101 | 1141 | 1181 | 1221 | 800 | 880
[6 empty] | Achieved | 108 | 269 | 462 | 588 | 803 | 961 | 1134 | 1257 | 1257 | 1452 | 1554 | 1611 | 800 | 842
| Number and percentage of individuals currently on OST who have been on OST continuously at least 6 months for the past 12 months (Numărul şi procentul persoanelor aflate în tratamentul de substituție cu metadonă (TSO) care au fost în TSO continuu cel puțin 6 luni pe parcursul ultimelor 12 luni) |  |  | 4.5 |  | Target | n/a | n/a | n/a | n/a | n/a | 50% | n/a | 55% | n/a | 57% | n/a | 59% | n/a | 60%
[6 empty] | Achieved | n/a | n/a | n/a | n/a | n/a | 53.18% | n/a | 56.04% | n/a | 57.85% | n/a | 42.68% | n/a | 44.61%
| Number of human rights strategic litigation cases for PLWH initiated (Numărul de cazuri de încălcare a drepturilor PTH inițiate pentru litigare strategică) |  |  | 5.1 | Yes | Target | 5 | 10 | 15 | 20 | 25 | 30 | 35 | 40 | 45 | 50 | 55 | 60 | 5 | 10
[6 empty] | Achieved | 8 | 15 | 24 | 29 | 34 | 39 | 44 | 50 | 55 | 60 | 65 | 70 | 5 | 11
| Number of PLHIV assisted by legal aid (consultancies offered by legal network) (Numărul de PTH care au beneficiat de asistență juridică) |  |  | 5.2 | Yes | Target | 10 | 20 | 30 | 40 | 55 | 70 | 212 | 242 | 272 | 302 | 332 | 362 | 35 | 70
[6 empty] | Achieved | 25 | 78 | 108 | 142 | 163 | 182 | 210 | 251 | 296 | 344 | 394 | 429 | 52 | 104
| Number of members of the civil society trained in services provision to PLHIV (Numărul de membri ai societăţii civile instruiţi în furnizarea de servicii pentru PTH) |  |  | 5.3 | Yes | Target | 35 | 70 | 105 | 140 | 190 | 240 | 390 | 440 | 490 | 540 | 590 | 640 | 0 | 25
[6 empty] | Achieved |  | 78 |  |  |  | 340 | 411 | 542 | 608 | 712 | 741 | 780 | 0 | 30
| Table is automatically updated. No data or information is to be entered here. |  |  | Code | Directly Tied? |  | 0 | 0 | 0 | 0 | P1-P12 (Q1.2010-Q4.2012) | P13 (Q1.2013) | P14 (Q2.2013) | 0 | 0 | 0 | 0 | 0 | P13 | P14
| Number of people living with HIV/AIDS reached with care and support services (Numărul persoanelor care trăiesc cu HIV/SIDA şi au primit suport social) |  |  | 4.2 | Yes | Target | 3250 | 3500 | 3750 | 4000 | 4375 | 4750 | 4832 | 5207 | 5357 | 5507 | 5657 | 5807 | 5947 | 6087
[6 empty] | Achieved | 2093 | 2817 | 3197 | 3717 | 3976 | 4296 | 4564 | 4853 | 5107 | 5327 | 5519 | 5704 | 5874 | 6085
| Number of children infected and affected by HIV/AIDS who receive social support (Numărul de copii infectaţi şi afectaţi de HIV/SIDA care primesc suport social) |  |  | 4.3 | Yes | Target | 95 | 125 | 155 | 185 | 216 | 248 | 352 | 372 | 392 | 412 | 432 | 452 | 230 | 244
[6 empty] | Achieved | 91 | 133 | 195 | 236 | 298 | 332 | 363 | 395 | 395 | 462 | 482 | 509 | 229 | 264
| Number of Injecting drug users on opioid substitution therapy that receive at least 3 support services from NGOs working in DUs rehabilitation (Numărul de CDI care sunt în terapia de substituţie cu metadonă şi primesc cel puţin 3 servicii de suport din partea ONG-urilor care lucrează la reabilitarea CDI) |  |  | 4.4 | Yes | Target | 54 | 108 | 162 | 216 | 280 | 344 | 407 | 471 | 511 | 551 | 591 | 631 | 651 | 671
[6 empty] | Achieved | 61 | 131 | 180 | 225 | 284 | 322 | 368 | 437 | 462 | 481 | 500 | 534 | 554 | 579
Note on B30: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.
Note on B72: If data are not available, do not enter zeros; rather, leave the cells in the table blank.
Note on B73: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B79: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B94: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.
Menu

## Grant Detail
Dashboard: Moldova - HIV / AIDS
Country: | Moldova |  | Title of the Grant: |  | Reducing HIV-related burden in the Republic of Moldova
Component: | HIV / AIDS | Grant No. | MOL-H-PAS | Start Date: |  | January 01, 2010 | Total Funding | EUR 12057410
Round: | SSF (Round 8) | Phase: | Piriod 2 | Principal Recipient: |  | PAS Center
Report Period: | P7 | from: | January 01, 2013 | to: |  | June 30, 2013 | Latest Rating: | A2
Local Fund Agent: | PwC (PricewaterhouseCoopers) |  |  | Fund Portfolio Manager: |  | Tatiana Vinichenko
Prepared by: | PAS Center |  |  | Report preparation date: |  | September 01, 2013
http://www.crwflags.com/fotw/flags/country.html
Menu

## Finance
Dashboard: Moldova - HIV / AIDS
SSF (Round 8) | Piriod 2 |  |  |  | Report Period: |  | P7
Latest Rating: | A2 |  | PAS Center |  | From: |  | January 01, 2013
|  | Reducing HIV-related burden in the Republic of Moldova |  |  |  | To: | June 30, 2013
Financial Indicators
F1: Budget and disbursements by Global Fund - in (€) Report Period: P7 |  |  |  | F3: Disbursements and expenditures - in (€) Report Period: P7
Comments: | The cumulative disbursement rate is 116%. The variance is due shift at TGF level from semiannual do annual disbursements. Respectively the cumulative disbursement includes the budget for semester 2, 2013 and the buffer for Q1, 2014. (Rata cumulativă a disbursării este de 116%. Variația este cauzată de trecerea Fondul Global de la disbursări semestriale la disbursări anuale. Respectiv disbursarea cumulativă include bugetul pentru semestrul 2, 2013 şi un un buffer pentru Tr.1, 2014). |  |  | Comments: | The PR cash outflow rate for the reported period is 106,4% (Actual 1,039,564/Budget 977,045) from the semiannual budget. The variance for the reporting period is over expenditure of EUR 62,519 mainly due to advance payments to SRs and implementers and payments afferent to commitments from Period 1 (EUR 38,425). (Rata de absorbţie pentru perioada raportată este de 106,4% (Actual 1,039,564/Budget 977,045 budget) din bugetul semianual. Variaţia dintre buget și cheltuieli pentru perioada raportată constituie o supra cheltuială de 62,519 Euro fiind în mare parte determinată de plăţi în avans către SR şi alţi implementatori şi de plăţile aferente angajamentelor din Perioada 1 (EUR 38,425).
F2: Budget and actual expenditures by Grant Objective - in (€) Report Period: P7 |  |  |  | F4: Latest PR reporting and disbursement cycle Report Period: P7
Comments: | The cumulative rate of absorption from budget as of June 2013 is 100,81% (Actual 9,166,890/Budget 9,093,180). The cumulative variance at the end of the reporting period is an under-expenditure of EUR 73,719 mainly due to advance payments to SRs and implementers and payments afferent to commitments from Period 1 (EUR 38,425). (Rata cumulativă de absorbţie din buget la 30 iunie 2013 este de 100,81% (Actual 9,166,890/Budget 9,093,180). Variaţia cumulativă la finalul perioadei raportate constituie o supra cheltuială de 73,719 Euro fiind în mare parte determinată de plăţi în avans către SR şi alţi implementatori şi de plăţile aferente angajamentelor din Perioada 1 (EUR 38,425). |  |  | Comments: | The PU for Semester 1, 2013 has been submitted to LFA in due terms (45 days after the end of reported period), on September 12, 2013. The disbursement requested with the previous PU/DR for S2, 2012 (submitted on February 15, 2013) reached the PR on 08 May, 2013 (83 days after the PU/DR) and include the budget for semester 2, 2013 and the buffer for Q1, 2014. (Actualizarea progresului pentru Semestrul şi a fost remisa Agentului Local al Fondului in termenii stabiliți (45 de zile după finisarea perioadei raportate) pe data de 12 septembrie 2013. Disbursarea solicitată cu precedenta Actualizare de progres (PU/DR) pentru Semestrul 2, 2012 a fost primită de PR pe data de 08 mai 2013 (83 zile de la PU/DR). Disbursarea include bugetul pentru semestrul 2, 2013 și un buffer pentru Tr.1, 2014.)
Last fund disbursement: Calendar days
[6 empty] | Expected (days) | Actual (days)
|  |  |  | Days taken to submit final PU/DR to LFA |  | 45 | 43
|  |  |  | Days taken for disbursement to reach PR |  | 45 | 83
|  |  |  | Days taken for disbursement to reach SRs |  | 20 | 5
Menu

## Management
Dashboard: Moldova - HIV / AIDS
SSF (Round 8) | Piriod 2 |  |  |  |  | Report Period: |  | P7
Latest Rating: | A2 |  | PAS Center |  |  | From: |  | January 01, 2013
|  | Reducing HIV-related burden in the Republic of Moldova |  |  |  |  | To: | June 30, 2013
Management Indicators
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) Report Period: P7 |  |  |  | M2: Status of key PR management positions Report Period: P7
Comments: | The two special conditions have been fulfilled in strict accordance with their provisions. (Cele două condiții speciale au fost îndeplinite, în strictă conformitate cu prevederile contractuale.) |  |  | Comments: | Two full time positions and 12 part time. (Două poziţii cu normă plină şi 11 - parţială.)
M3: Contractual arrangements (SRs) Report Period: P7 |  |  |  | M4: Number of complete reports received on time Report Period: P7
Comments: | Four Sub-recipients (SRs) have been identified initialy (2010) to implement different components within the program: Soros Foundation-Moldova (SFM); League of people living with HIV of Moldova; New Life, Moldovan Institute for Human Rights. One SR (SFM) has been earlier assessed by the governmental PR of GF grants as it acts as an SR since GF Round one. Two other SRs have been assessed (New Life and Moldovan Institute for Human Rights) by PAS Center the last one (League of people living with HIV of Moldova) by TGF Local Fund Agent. Four sub-grant agreements have been signe following the assessment. In September 2011, due to lack of capacity for adequate implementation of the grant portion contracted the sub-grant agreement with one of the SRs (League of people living with HIV) was terminated and the management of activities has been entrusted to an other SR ( SFM). Respectively three sub-recipients continued to receive funds till the end of Period one (December 31, 2012). During renewal one SR component has been reorganised and starting with Period two (2013) there are two SRs that receiv funds within the grant. (Patru Sub-Recipienţi (SR), au fost identificaţi inițial (2010) pentru a implementa diferite componente în cadrul programului: Fundația Soros-Moldova (FSM), Liga persoanelor care trăiesc cu HIV din Moldova, Viaţa Nouă, Institutul pentru Drepturile Omului din Moldova. Un SR (SFM) a fost evaluată anterior de către PR guvernamental, deoarece activează în calitate de SR începănd cu Runda 1. Alţi doi SR au fost evaluaţi (Viaţa Nouă și Institutul pentru Drepturile Omului din Moldova) de către Centrul PAS iar ultimul (Liga persoanelor care trăiesc cu HIV din Republica Moldova) de către Agentul Local al Fondului Global. Urmare a evaluării au fost semnate patru acorduri de sub-grant. În septembrie 2011, din cauza lipsei de capacitate pentru implementarea adecvată a componentului de grant contractat acordul de sub-finantare cu unul dintre SR (Liga persoanelor care trăiesc cu HIV) a fost reziliat și gestionarea activităților a fost încredințată altui SR (SFM). Respectiv trei SR au primit fonduri pînă la finele Perioadei unu (31 decembrie 2012). La etapa de reînoire a grantului, componentul implementat de unul dintre acesti SR a fost reorganizat și începănd cu Perioada 2 (2013) doi SR primesc resurse din cadrul grantului trei SR. |  |  | Comments: | The SRs’ quarterly reports (financial report, activity report and performance framework) are due to the PR not later than 25 days after the close of each quarter and are generally submitted in time. The clearance period vary from one SR to an other subject to the completeness and consistence of the reports. For the SR SFM the Sub-subrecipients financial reports are due quarterly and can be submitted during the following quarter, the activity reports are due not later than 10 days from the end of each month and are generally submitted in time except one Ssr - NGO Master in Public Health – that is constantly late in reporting. During the reporting period reflected in this dashboard 15 reports from 16 due were submited in time. For the SR New Life the reports (financial, activity and indicators) are due not later than 15 days after the close of each quarter and are generally submitted in time. (Rapoartele trimestriale ale SR (raport financiar, raport de activitate și cadrul de performanță) urmează a fi transmise RP nu mai târziu de 25 de zile de la încheierea fiecărui trimestru. Rapoartele sunt de regulă prezentate la timp. Perioada de verificare şi aprobare variază de la un SR la altul în funcţie de exhaustivitatea și consistență rapoartelor. Pentru SR FSM rapoarte financiare ale Sub-subrecipienţilor (Ssr) urmează a fi transmise trimestrial și pot fi prezentate în trimestrul următor, rapoartele de activitate urmează a fi prezentate nu mai târziu de 10 zile de la sfârșitul fiecărei luni și sunt, în general, prezentate la timp cu excepția unui Ssr - ONG Master în Sănătatea Publică - care întârzie raportarea în mod constant . Pe parcursul perioadei de raportare reflectă în aces raport, 15 raporte din 16 planificate au fost transmise în termeni. Pentru SR Viaţa Nouă rapoartele (financiare, de activitate și indicatorii) urmează a fi prezentate nu mai târziu de 15 zile de la încheierea fiecărui trimestru și sunt, de regulă, prezentate la timp.)
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals |  |  |  | M6: Difference between current and safety stock Report Period: P7
Comments: | N/A |  |  | Comments: | N/A
|  |  |  | Component | Products | Stock level expressed in months of treatment for all current patients | Months of safety stock | Difference between current stock and safety stock
|  |  |  | HIV / AIDS | Please Select |  | 0
[5 empty] | Please Select |  | 0
[5 empty] | Please Select |  | 0
[5 empty] | Please Select |  | 0
* Includes only EFR category 4 and 5 (Health products and health equipment & Medicines and Pharmaceuticals)
Menu

## Programmatic
Dashboard: Moldova - HIV / AIDS
SSF (Round 8) | Piriod 2 | [8 empty] | Report Period: |  | P7
Latest Rating: | A2 |  | PAS Center | [7 empty] | From: | January 01, 2013
|  | Reducing HIV-related burden in the Republic of Moldova | [8 empty] | To: | June 30, 2013 | [7 empty] | Raiting |  | Valor
Programmatic Indicators
Number of people living with HIV/AIDS reached with care and support services (Numărul persoanelor care trăiesc cu HIV/SIDA şi au primit suport social) |  |  |  | Number of children infected and affected by HIV/AIDS who receive social support (Numărul de copii infectaţi şi afectaţi de HIV/SIDA care primesc suport social) |  |  |  | Number of Injecting drug users on opioid substitution therapy that receive at least 3 support services from NGOs working in DUs rehabilitation (Numărul de CDI care sunt în terapia de substituţie cu metadonă şi primesc cel puţin 3 servicii de suport din partea ONG-urilor care lucrează la reabilitarea CDI)
Comment: P1 | During S7 a total 381 PLHIV were primarily reached with care and support services through four regional social centers providing assistance to PLHIV and 10 territorial organizations that ensures outreach to PLHIV and their families. The beneficiaries are provided with the following services: psycho-social counseling and support, medical counseling and referral, distribution of information materials, peer counseling, self-support groups and food support, etc. The indicator is achieved. (Pe parcursul semestrului 7, un total de 381 PTH au fost primar acoperiți cu servicii de îngrijire şi suport în cadrul celor patru Centre Sociale Regionale şi a 10 organizaţii teritoriale care prestează servicii PTH şi membrilor familiilor lor. Beneficiarilor le sunt prestate următoarele servicii: suport şi consiliere psiho-socială, consiliere medicală şi referire, diseminarea materialelor informaţionale, consiliere de la egal la egal, activităţi in grup şi suport alimentar, etc. Indicatorul este atins). |  |  | Comment: P2 | A total of 264 children received social support during S7 (primarily reached) out of them 99 infected and 165 affected by HIV. Each quarter 230 children (all HIV infected children that can be reached and the majority of children born from HIV infected mother with unknown status) benefit of food parcels. At the same time each semester HIV positive children benefit of a set of stationary and clothing for school as part of social support program. During reported period the number of HIV positive children that benefited of clothing and school supplies was 99, exceeding by four the planned number of 95. This fact has determined the need to reallocate additional budget (from savings under other budget lines targeted at PLHIV support) in order to cover four additional sets of clothing and school supplies. The indicator is overachieved. Reason for variance: The number of children primarily reached with social support is determined by the number of children diagnosed with HIV that are reached and by the number of children born from HIV positive mothers immediately before and during the reported period. (Pe parcursul semestrului 7, in total 264 copii au beneficiat de suport social (acoperiţi primar), dintre care 99 copii HIV infectaţi și 165 copii cu statut nedeterminat născuți din mame HIV pozitive (afectaţi). În acelaşi timp, în fiecare trimestru, 230 copii (toți copiii infectați cu HIV, care pot fi acoperiţi cu servicii, și majoritatea copiilor născuți din mame infectate cu HIV) beneficiază de un set de haine şi rechizite școlare ca parte a programului de acordare a suportului social. Pe parcursul perioadei de raportare, numărul de copii HIV infectaţi care au primit un set de haine şi rechizite școlare a crescut la 99, depăşind cu patru unităţi numărul planificat de 95. Acest fapt a determinat necesitatea realocării unui buget adiţional (din economiile obţinute in cadrul altor linii bugetare orientate către suportul PTH) pentru a acoperi patru seturi suplimentare de îmbrăcăminte şi rechizite şcolare. Indicatorul este depășit. Cauza variaţiei: Numărul de copii primar acoperiţi cu suport social este determinat de numărul de copii diagnosticaţi cu HIV și numărul copiilor născuți din mame HIV pozitive imediat înainte și în perioada de raportate). |  |  | Comment: P3 | During S7 a total of 45 PWIDs on opioid substitution therapy (primarily reached) received at least 3 support services from the package (psycho-social support, self-support groups, peer to peer education, distributions of information materials, food support, etc.) offered by NGOs working in PWUDs rehabilitation. The number of PWIDs on OST covered with psycho-social support is directly dependent to the number of PWIDs enrolled in OST treatment (new patients) which is continuously decreasing. During S1, 2013, 48 new clients versus 50 planned were enrolled in the substitution therapy program, the number of OST patients covered with support services (primarily reached) being 45 versus 40 planned. The indicator is achieved in proportion of 86%. Reason for variance: The target for the period 7 (40 persons primarily reached) has been exceeded (45 people reached). The underachievement of the cumulative target for the reported period (over program term) is determined by the variation between targets settled and results registered for period one of grant implementation caused by continuously decreasing enrolment of new patients in OST. As the number of OST patients that can be covered with psycho-support services is directly tied to new patients enrolled in OST, the enrolment dynamics in period one has determined and directly impacted the achievement of targets for this indicator and is affecting the results for the reported period as the target is cumulative over program term. (Pe parcursul semestrului 7 un total de 45 CDI aflați în terapia de substituţie cu metadonă (primar acoperiţi) au primit cel puţin 3 servicii de suport social din pachetul serviciilor (sprijin psiho-social, grupuri de suport reciproc, educație de la egal la egal, diseminarea materialelor informaţionale şi distribuirea pachetelor alimentare) oferite în cadrul centrelor de zi de către ONG-urile care lucrează în domeniul reabilitării CDI. Numărul de CDI aflaţi în TSO, acoperiţi cu suport psiho-social este direct dependent de numărul de CDI înrolaţi în TSO (cazuri noi), cifra care este în continuă scădere. În timpul S1, 2013, 48 beneficiari noi versus 50 planificați au fost înrolați în terapia de substituție, numărul de pacienți în TSO acoperiți cu servicii de sprijin (primari acoperiţi) fiind de 45 faţă de 40 planificați. Indicatorul este atins în proporție de 86%. Cauza variației: Ținta pentru perioada 7 (40 persoane noi primar acoperite) a fost depășită (45 persoane acoperite). Neatingerea țintei cumulative pentru perioada raportată (pe toata perioada grantului) este determinată de variația între ținta stabilită și rezultatele înregistrate pentru Perioada 1 de implementare a grantului cauzată de scăderea continua a pacienților înrolați în TSO. Numărul de pacienți în TSO care pot fi acoperiți cu servicii de suport psiho-social este direct proporţional cu numărul pacienților noi înrolați în TSO, dinamica înrolării în Perioada 1 a determinat și a afectat direct atingerea țintei pentru acest indicator și afectează rezultatul pentru perioada raportată deoarece ținta propusa se calculează cumulativ pentru toată perioada grantului).
Indicators |  |  | Target (cumulative over program term) | Achieved (cumulative over program term) | 0% - 59% | 60% - 89% | > 90% | Comments |  |  |  |  | min | 0 | 30% | 60% | 90% | 100% |  | min | 0 | 20% | 40% | 60% | 80%
Number of people living with HIV/AIDS reached with care and support services (Numărul persoanelor care trăiesc cu HIV/SIDA şi au primit suport social) |  |  | 6087 | 6085 | 99.97% |  |  | During S7 a total 381 PLHIV were primarily reached with care and support services through four regional social centers providing assistance to PLHIV and 10 territorial organizations that ensures outreach to PLHIV and their families. The beneficiaries are provided with the following services: psycho-social counseling and support, medical counseling and referral, distribution of information materials, peer counseling, self-support groups and food support, etc. The indicator is achieved. (Pe parcursul semestrului 7, un total de 381 PTH au fost primar acoperiți cu servicii de îngrijire şi suport în cadrul celor patru Centre Sociale Regionale şi a 10 organizaţii teritoriale care prestează servicii PTH şi membrilor familiilor lor. Beneficiarilor le sunt prestate următoarele servicii: suport şi consiliere psiho-socială, consiliere medicală şi referire, diseminarea materialelor informaţionale, consiliere de la egal la egal, activităţi in grup şi suport alimentar, etc. Indicatorul este atins). |  |  |  |  | max | 30% | 60% | 90% | 100% | 200% |  | max | 20% | 40% | 60% | 80% | 100%
Number of children infected and affected by HIV/AIDS who receive social support (Numărul de copii infectaţi şi afectaţi de HIV/SIDA care primesc suport social) |  |  | 244 | 264 | 108.2% |  |  | A total of 264 children received social support during S7 (primarily reached) out of them 99 infected and 165 affected by HIV. Each quarter 230 children (all HIV infected children that can be reached and the majority of children born from HIV infected mother with unknown status) benefit of food parcels. At the same time each semester HIV positive children benefit of a set of stationary and clothing for school as part of social support program. During reported period the number of HIV positive children that benefited of clothing and school supplies was 99, exceeding by four the planned number of 95. This fact has determined the need to reallocate additional budget (from savings under other budget lines targeted at PLHIV support) in order to cover four additional sets of clothing and school supplies. The indicator is overachieved. Reason for variance: The number of children primarily reached with social support is determined by the number of children diagnosed with HIV that are reached and by the number of children born from HIV positive mothers immediately before and during the reported period. (Pe parcursul semestrului 7, in total 264 copii au beneficiat de suport social (acoperiţi primar), dintre care 99 copii HIV infectaţi și 165 copii cu statut nedeterminat născuți din mame HIV pozitive (afectaţi). În acelaşi timp, în fiecare trimestru, 230 copii (toți copiii infectați cu HIV, care pot fi acoperiţi cu servicii, și majoritatea copiilor născuți din mame infectate cu HIV) beneficiază de un set de haine şi rechizite școlare ca parte a programului de acordare a suportului social. Pe parcursul perioadei de raportare, numărul de copii HIV infectaţi care au primit un set de haine şi rechizite școlare a crescut la 99, depăşind cu patru unităţi numărul planificat de 95. Acest fapt a determinat necesitatea realocării unui buget adiţional (din economiile obţinute in cadrul altor linii bugetare orientate către suportul PTH) pentru a acoperi patru seturi suplimentare de îmbrăcăminte şi rechizite şcolare. Indicatorul este depășit. Cauza variaţiei: Numărul de copii primar acoperiţi cu suport social este determinat de numărul de copii diagnosticaţi cu HIV și numărul copiilor născuți din mame HIV pozitive imediat înainte și în perioada de raportate). | [5 empty] | de 0 a 0.3 | de 0.3 a 0.6 | de 0.6 a 0.9 | de 0.9 a 1 | de 1 a 2 | Rating | Valor | de 0 a 0.2 | de 0.2 a 0.4 | de 0.4 a 0.6 | de 0.6 a 0.8 | de 0.8 a 1
Number of Injecting drug users on opioid substitution therapy that receive at least 3 support services from NGOs working in DUs rehabilitation (Numărul de CDI care sunt în terapia de substituţie cu metadonă şi primesc cel puţin 3 servicii de suport din partea ONG-urilor care lucrează la reabilitarea CDI) |  |  | 671 | 579 | 86.29% |  |  | During S7 a total of 45 PWIDs on opioid substitution therapy (primarily reached) received at least 3 support services from the package (psycho-social support, self-support groups, peer to peer education, distributions of information materials, food support, etc.) offered by NGOs working in PWUDs rehabilitation. The number of PWIDs on OST covered with psycho-social support is directly dependent to the number of PWIDs enrolled in OST treatment (new patients) which is continuously decreasing. During S1, 2013, 48 new clients versus 50 planned were enrolled in the substitution therapy program, the number of OST patients covered with support services (primarily reached) being 45 versus 40 planned. The indicator is achieved in proportion of 86%. Reason for variance: The target for the period 7 (40 persons primarily reached) has been exceeded (45 people reached). The underachievement of the cumulative target for the reported period (over program term) is determined by the variation between targets settled and results registered for period one of grant implementation caused by continuously decreasing enrolment of new patients in OST. As the number of OST patients that can be covered with psycho-support services is directly tied to new patients enrolled in OST, the enrolment dynamics in period one has determined and directly impacted the achievement of targets for this indicator and is affecting the results for the reported period as the target is cumulative over program term. (Pe parcursul semestrului 7 un total de 45 CDI aflați în terapia de substituţie cu metadonă (primar acoperiţi) au primit cel puţin 3 servicii de suport social din pachetul serviciilor (sprijin psiho-social, grupuri de suport reciproc, educație de la egal la egal, diseminarea materialelor informaţionale şi distribuirea pachetelor alimentare) oferite în cadrul centrelor de zi de către ONG-urile care lucrează în domeniul reabilitării CDI. Numărul de CDI aflaţi în TSO, acoperiţi cu suport psiho-social este direct dependent de numărul de CDI înrolaţi în TSO (cazuri noi), cifra care este în continuă scădere. În timpul S1, 2013, 48 beneficiari noi versus 50 planificați au fost înrolați în terapia de substituție, numărul de pacienți în TSO acoperiți cu servicii de sprijin (primari acoperiţi) fiind de 45 faţă de 40 planificați. Indicatorul este atins în proporție de 86%. Cauza variației: Ținta pentru perioada 7 (40 persoane noi primar acoperite) a fost depășită (45 persoane acoperite). Neatingerea țintei cumulative pentru perioada raportată (pe toata perioada grantului) este determinată de variația între ținta stabilită și rezultatele înregistrate pentru Perioada 1 de implementare a grantului cauzată de scăderea continua a pacienților înrolați în TSO. Numărul de pacienți în TSO care pot fi acoperiți cu servicii de suport psiho-social este direct proporţional cu numărul pacienților noi înrolați în TSO, dinamica înrolării în Perioada 1 a determinat și a afectat direct atingerea țintei pentru acest indicator și afectează rezultatul pentru perioada raportată deoarece ținta propusa se calculează cumulativ pentru toată perioada grantului). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number of medical (doctors and nurses) and non-medical staff (psychologists, social assistants, peer consultants) trained in HIV/AIDS (Numărul personalului medical (medici şi asistente medicale) şi non-medical (psihologi, asistenţi sociali, educatori de la egal la egal) instruiţi în HIV/SIDA) |  |  | 90 | 129 | 143.3% |  |  | A total of 129 persons trained in S7, from them: 15 medical staff were trained in international training in Clinica Lavra in ART and Opportunistic infection in HIV infected patients, 41 non-medical staff from social regional centers, territorial organizations and NRS MDTs participated in regional workshops targeted at strengthening collaboration and building sustainable referral systems to specialized HIV services; 73 infectious diseases specialists were trained in the reformed and reorganized system of medical service provision to PLHIV. The indicator is overachieved. Reason for variance: due to the fact that the three trainings for infectious diseases specialists planned under budget line 3.1.4 were directly related to the reform and reorganization of the HIV medical service provision system, all three events planned for year 2013 (two in S1 and one in S2) have been organized during reported period; the approach to the events under budget line 3.1.2 has been changed with TGF approval (two three days national events initially planned for Year 2013, one per semester, have been replaced with three two days regional events, two in S1, 2013 and one in S2, 2013) and two events for central and north regions organized during reported period. (In total 129 persoane au fost instruite in semestrul 7, dintre care: 15 lucrători medicali au participat la trainingul internaţional organizat la Clinica Lavra privind ARV si infecțiile oportuniste la pacienții HIV infectați; 41 lucrători non-medicali din centrele social regionale, organizațiile teritoriale și EMD au participat la întrunirea regională în contextul colaborării și referirii persoanelor care trăiesc cu HIV la serviciile specializate; 73 specialişti în boli infecţioase au fost instruiţi privind reformarea si reorganizarea sistemului in prestarea serviciilor medicale PTH. Indicatorul este depășit. Cauza variaţiei: datorită faptului că trei instruiri pentru specialiştii în boli infecţioase planificate în cadrul liniei bugetare 3. 1. 4, au fost direct legate de reforma si de reorganizarea sistemului in furnizarea serviciilor medicale PTH, toate aceste trei evenimente planificate pentru anul 2013 (două în S1 şi unul în S2) au fost desfăşurate pe parcursul perioadei raportate; durata organizării evenimentelor din cadrul liniei bugetare 3. 1. 2 a fost modificat cu aprobarea FG (două evenimente naţionale a cate trei zile iniţial planificate pentru anul 2013, unul per semestru, au fost înlocuite cu trei evenimente regionale a cate doua zile, două în S1, şi unul in S2, 2013); in perioada raportata au fost organizate si două evenimente pentru regiunile centrale şi de nord). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number of PLHIV receiving food parcels to improve ARV treatment adherence (Numărul de PTH care primesc pachete alimentare pentru a îmbunătăți aderenţa la tratamentul ARV) |  |  | 880 | 842 | 95.68% |  |  | A total of 842 PLHIV received food parcels during S7 (primarily reached). Each quarter 800 PLHIV out of those on ARV treatment, selected based on socio-economic vulnerability, benefit of food parcels. A total of 800 food parcels are distributed quarterly to adult patient on ARV for better adherence to treatment, in both civilian and penitentiary sectors. The indicator is substantially achieved. (Un număr total de 842 PTH au primit pachete alimentare pe parcursul semestrului 7 (beneficiari primar acoperiţi). În fiecare trimestru 800 PTH din rândul celor aflaţi în tratamentul ARV, selectaţi în baza vulnerabilităţii socio-economice, beneficiază de pachete alimentare. În total 800 de pachete alimentare sunt distribuite trimestrial pacienţilor adulţi aflaţi in ARV în scopul creşterii aderenţei la tratament, atât in sectorul civil cat și penitenciar. Indicatorul este acoperit in mare măsură). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number and percentage of individuals currently on OST who have been on OST continuously at least 6 months for the past 12 months (Numărul şi procentul persoanelor aflate în tratamentul de substituție cu metadonă (TSO) care au fost în TSO continuu cel puțin 6 luni pe parcursul ultimelor 12 luni) |  |  | 60% | 44.61% | 74.35% |  |  | A total of 58 individuals out of 130 that initiated OST during P11-P12 have completing at least 6 months of continuous treatment on OST. Currently OST is provided in three sites: Republican Narcological Dispensary, Balti Municipal Hospital and the Department of Penitentiary Institutions (in 12 penitentiary institutions: #1 Taraclia, #3 Leova, #4 Cricova, #6 Soroca, #7 Rusca, #9 Pruncul, #11 Balti, #15 Cricova, #16 Pruncul, #17 Rezina, #18 Branesti, #13 Chisinau). The indicator is partially achieved (74%). Reason for variance: the rate of retention in treatment is determined by a series of factors, namely: seasonal migration of patients (both abroad and in country), emergency of seasonal illicit drugs on black market, low doses of methadone (below recommended 60mg minimal average dose), and concurrent use of illicit drugs, methadone distribution restricted to OST for all patients including for drug users in stable remission, repeated enrollment in treatment without prior psycho-social support to prepare the patient for the next attempt, misconceptions about OST in both medical and psych-social support teams, negative image of OST among PWID, etc. Un număr total de 58 de persoane din 130 care au iniţiat TSO în semestrul 2, 2012 au finalizat cel puţin 6 luni de tratament TSO continuu. Actualmente TSO este distribuita in trei site-uri: Dispensarul Republican de Narcologie, Spitalul Municipal Bălţi şi Departamentul Instituţiilor Penitenciare (în 12institutii penitenciare: #1 Taraclia, #3 Leova, #4 Cricova, #6 Soroca, #7 Rusca, #9 Pruncul, #11 Bălti, #15 Cricova, #16 Pruncul, #17 Rezina, #18 Brăneşti, #13 Chişinău). Indicatorul este atins parțial (74%). Cauza variaţiei: rata de retenție în tratament este determinata de o serie de factori, și anume: migrația sezonieră a pacienţilor (atât peste hotare cât și în interiorul țarii), apariţia drogurilor ilicite sezoniere pe piața neagră, doze mici de metadonă (mai puţin decât doza minimă recomandată de 60mg), precum și utilizarea concomitentă a drogurilor ilicite, distribuția metadonei limitată la site-urile OST, inclusiv pentru consumatorii de droguri în remisie stabila, înrolare repetată în tratament fără suport psiho-social preventiv pentru a pregăti pacientul pentru următoarea încercare, concepţii greşite despre TSO în atât în echipele medicale cat și cele de asistență psiho-socială, imaginea negativă a TSO printre CDI, etc). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Number of human rights strategic litigation cases for PLWH initiated (Numărul de cazuri de încălcare a drepturilor PTH inițiate pentru litigare strategică) |  |  | 10 | 11 | 110% |  |  | 11 litigation cases have been initiated during S7. The cases were related to disclosure of confidential medical information related to HIV status, unethical and unprofessional behavior of medical staff, refusal to offer medical services, adoption of children by HIV positive persons, inhuman/ degrading treatment of detained PLHIV, etc. The indicator is overachieved. Reason for variance: The increase in number of cased initiated is determined by the type of cases handled during reported period and has no financial impact as the layers are fool day project consultants with fix remuneration. (Pe parcursul semestrului 7, au fost inițiate 11 litigii. Cazurile au fost legate de divulgarea informației medicale confidențiale legate de statutul HIV, comportament neetic și neprofesional al personalului medical, refuzul de a acorda servicii medicale, problema adopției copiilor de către persoane HIV pozitive, tratament inuman/degradat față de deținuții HIV pozitivi, etc. Indicatorul este depăşit. Cauza variaţiei: Numărul de litigii inițiate este determinat de tipul cazurilor soluţionate în perioada de raportare și nu are impact financiar deoarece avocaţii sunt angajaţi în proiect cu zi plină de munca şi au remunerare fixă). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Number of PLHIV assisted by legal aid (consultancies offered by legal network) (Numărul de PTH care au beneficiat de asistență juridică) |  |  | 70 | 104 | 148.6% |  |  | A total of 104 consultancies were offered remotely by traveling to project sites of 4 lawyers, during S7; they offered legal assistance related to issues of legal, civil (including disclosure of HIV status), administrative nature to all PLHIV in need. The indicator is overachieved. Reason for variance: The number of consultancies offered by project lawyers is determined by the request of legal support from PLHIV and can vary from one period to another. With the opening of Social Regional Centers project lawyer provide services within the Centers facilities (with a specific periodicity) bringing this way services closer to the beneficiary and increasing their access to legal support. The increase in number of consultancies provided has no financial impact as the layers are fool day project consultants with fix remuneration. (Pe parcursul semestrului 7 au fost prestate 104 consultații în teren de către 4 avocaţi. Ei au oferit asistenţă juridică pe aspecte de natură legală, civilă (inclusiv divulgarea statutului HIV) şi administrative ale tuturor PTH care au solicitat asistenta juridica. Indicatorul este depăşit. Cauza variaţiei: Numărul de consultaţii oferite de către avocații proiectului este determinat de cererea de asistență juridică din partea PTH și poate varia de la o perioadă la alta. Odată cu deschiderea Centrelor Sociale Regionale avocaţii prestează servicii în cadrul centrelor (cu o anumită periodicitate) aducând astfel serviciile mai aproape de beneficiar și crescând accesul la asistența juridică. Creșterea numărului de servicii de consultanţă juridică prestate nu are impact financiar deoarece avocaţii sunt angajaţi în proiect cu zi plină de lucru şi au remunerare fixă). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Number of members of the civil society trained in services provision to PLHIV (Numărul de membri ai societăţii civile instruiţi în furnizarea de servicii pentru PTH) |  |  | 25 | 30 | 120% |  |  | A total number of 30 representatives of organizations that provide services to PLHIV and key populations were trained in organizational management and leadership. The indicator is overachieved. Reason for variance: The number of people interested in the training course was higher than planned and due to the fact that the costs for the selected venue allowed the number of trainees was increased to 30 instead of 25 planned. (Un număr total de 30 reprezentanţi ai organizaţiilor care prestează servicii PTH şi populaţiilor cheie au fost instruiţi în managementul organizaţional si liderism. Indicatorul este depăşit. Motivul pentru variaţie: numărul persoanelor interesate in audierea cursului a fost mai mare decât cel planificat şi datorită faptului că costurile de desfăşurare a al evenimentului au permis, numărul participanţilor a fost crescut la 30 in loc de cei 25 planificaţi). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Menu

## Recommendations
Dashboard: Moldova - HIV / AIDS
SSF (Round 8) | Piriod 2 |  |  |  |  | Report Period: | P7
Latest Rating: | A2 |  | PAS Center |  |  | From: | January 01, 2013
|  |  | Reducing HIV-related burden in the Republic of Moldova |  |  | To: | June 30, 2013
Recommendations
Are all funds reaching implementation levels and being spent according to budget?
Financial |  | Summary Comments |  |  | Recommendations
F1 |  | The cumulative disbursement rate is 116%. The variance is due shift at TGF level from semiannual do annual disbursements. Respectively the cumulative disbursement includes the budget for semester 2, 2013 and the buffer for Q1, 2014. (Rata cumulativă a disbursării este de 116%. Variația este cauzată de trecerea Fondul Global de la disbursări semestriale la disbursări anuale. Respectiv disbursarea cumulativă include bugetul pentru semestrul 2, 2013 şi un un buffer pentru Tr.1, 2014).
F2 |  | The cumulative rate of absorption from budget as of June 2013 is 100,81% (Actual 9,166,890/Budget 9,093,180). The cumulative variance at the end of the reporting period is an under-expenditure of EUR 73,719 mainly due to advance payments to SRs and implementers and payments afferent to commitments from Period 1 (EUR 38,425). (Rata cumulativă de absorbţie din buget la 30 iunie 2013 este de 100,81% (Actual 9,166,890/Budget 9,093,180). Variaţia cumulativă la finalul perioadei raportate constituie o supra cheltuială de 73,719 Euro fiind în mare parte determinată de plăţi în avans către SR şi alţi implementatori şi de plăţile aferente angajamentelor din Perioada 1 (EUR 38,425).
F3 |  | The PR cash outflow rate for the reported period is 106,4% (Actual 1,039,564/Budget 977,045) from the semiannual budget. The variance for the reporting period is over expenditure of EUR 62,519 mainly due to advance payments to SRs and implementers and payments afferent to commitments from Period 1 (EUR 38,425). (Rata de absorbţie pentru perioada raportată este de 106,4% (Actual 1,039,564/Budget 977,045 budget) din bugetul semianual. Variaţia dintre buget și cheltuieli pentru perioada raportată constituie o supra cheltuială de 62,519 Euro fiind în mare parte determinată de plăţi în avans către SR şi alţi implementatori şi de plăţile aferente angajamentelor din Perioada 1 (EUR 38,425).
F4 |  | The PU for Semester 1, 2013 has been submitted to LFA in due terms (45 days after the end of reported period), on September 12, 2013. The disbursement requested with the previous PU/DR for S2, 2012 (submitted on February 15, 2013) reached the PR on 08 May, 2013 (83 days after the PU/DR) and include the budget for semester 2, 2013 and the buffer for Q1, 2014. (Actualizarea progresului pentru Semestrul şi a fost remisa Agentului Local al Fondului in termenii stabiliți (45 de zile după finisarea perioadei raportate) pe data de 12 septembrie 2013. Disbursarea solicitată cu precedenta Actualizare de progres (PU/DR) pentru Semestrul 2, 2012 a fost primită de PR pe data de 08 mai 2013 (83 zile de la PU/DR). Disbursarea include bugetul pentru semestrul 2, 2013 și un buffer pentru Tr.1, 2014.)
Are procurement and hiring on schedule?
Management |  | Summary Comments |  |  | Recommendations
M1 |  | The two special conditions have been fulfilled in strict accordance with their provisions. (Cele două condiții speciale au fost îndeplinite, în strictă conformitate cu prevederile contractuale.)
M2 |  | Two full time positions and 12 part time. (Două poziţii cu normă plină şi 11 - parţială.) | #DIV/0! | #DIV/0!
M3 |  | Four Sub-recipients (SRs) have been identified initialy (2010) to implement different components within the program: Soros Foundation-Moldova (SFM); League of people living with HIV of Moldova; New Life, Moldovan Institute for Human Rights. One SR (SFM) has been earlier assessed by the governmental PR of GF grants as it acts as an SR since GF Round one. Two other SRs have been assessed (New Life and Moldovan Institute for Human Rights) by PAS Center the last one (League of people living with HIV of Moldova) by TGF Local Fund Agent. Four sub-grant agreements have been signe following the assessment. In September 2011, due to lack of capacity for adequate implementation of the grant portion contracted the sub-grant agreement with one of the SRs (League of people living with HIV) was terminated and the management of activities has been entrusted to an other SR ( SFM). Respectively three sub-recipients continued to receive funds till the end of Period one (December 31, 2012). During renewal one SR component has been reorganised and starting with Period two (2013) there are two SRs that receiv funds within the grant. (Patru Sub-Recipienţi (SR), au fost identificaţi inițial (2010) pentru a implementa diferite componente în cadrul programului: Fundația Soros-Moldova (FSM), Liga persoanelor care trăiesc cu HIV din Moldova, Viaţa Nouă, Institutul pentru Drepturile Omului din Moldova. Un SR (SFM) a fost evaluată anterior de către PR guvernamental, deoarece activează în calitate de SR începănd cu Runda 1. Alţi doi SR au fost evaluaţi (Viaţa Nouă și Institutul pentru Drepturile Omului din Moldova) de către Centrul PAS iar ultimul (Liga persoanelor care trăiesc cu HIV din Republica Moldova) de către Agentul Local al Fondului Global. Urmare a evaluării au fost semnate patru acorduri de sub-grant. În septembrie 2011, din cauza lipsei de capacitate pentru implementarea adecvată a componentului de grant contractat acordul de sub-finantare cu unul dintre SR (Liga persoanelor care trăiesc cu HIV) a fost reziliat și gestionarea activităților a fost încredințată altui SR (SFM). Respectiv trei SR au primit fonduri pînă la finele Perioadei unu (31 decembrie 2012). La etapa de reînoire a grantului, componentul implementat de unul dintre acesti SR a fost reorganizat și începănd cu Perioada 2 (2013) doi SR primesc resurse din cadrul grantului trei SR.
M4 |  | The SRs’ quarterly reports (financial report, activity report and performance framework) are due to the PR not later than 25 days after the close of each quarter and are generally submitted in time. The clearance period vary from one SR to an other subject to the completeness and consistence of the reports. For the SR SFM the Sub-subrecipients financial reports are due quarterly and can be submitted during the following quarter, the activity reports are due not later than 10 days from the end of each month and are generally submitted in time except one Ssr - NGO Master in Public Health – that is constantly late in reporting. During the reporting period reflected in this dashboard 15 reports from 16 due were submited in time. For the SR New Life the reports (financial, activity and indicators) are due not later than 15 days after the close of each quarter and are generally submitted in time. (Rapoartele trimestriale ale SR (raport financiar, raport de activitate și cadrul de performanță) urmează a fi transmise RP nu mai târziu de 25 de zile de la încheierea fiecărui trimestru. Rapoartele sunt de regulă prezentate la timp. Perioada de verificare şi aprobare variază de la un SR la altul în funcţie de exhaustivitatea și consistență rapoartelor. Pentru SR FSM rapoarte financiare ale Sub-subrecipienţilor (Ssr) urmează a fi transmise trimestrial și pot fi prezentate în trimestrul următor, rapoartele de activitate urmează a fi prezentate nu mai târziu de 10 zile de la sfârșitul fiecărei luni și sunt, în general, prezentate la timp cu excepția unui Ssr - ONG Master în Sănătatea Publică - care întârzie raportarea în mod constant . Pe parcursul perioadei de raportare reflectă în aces raport, 15 raporte din 16 planificate au fost transmise în termeni. Pentru SR Viaţa Nouă rapoartele (financiare, de activitate și indicatorii) urmează a fi prezentate nu mai târziu de 15 zile de la încheierea fiecărui trimestru și sunt, de regulă, prezentate la timp.)
M5 |  | N/A
M6 |  | N/A
Are technical targets being achieved?
Programmatic |  | Summary Comments |  |  | Recommendations
P1 - trend |  | During S7 a total 381 PLHIV were primarily reached with care and support services through four regional social centers providing assistance to PLHIV and 10 territorial organizations that ensures outreach to PLHIV and their families. The beneficiaries are provided with the following services: psycho-social counseling and support, medical counseling and referral, distribution of information materials, peer counseling, self-support groups and food support, etc. The indicator is achieved. (Pe parcursul semestrului 7, un total de 381 PTH au fost primar acoperiți cu servicii de îngrijire şi suport în cadrul celor patru Centre Sociale Regionale şi a 10 organizaţii teritoriale care prestează servicii PTH şi membrilor familiilor lor. Beneficiarilor le sunt prestate următoarele servicii: suport şi consiliere psiho-socială, consiliere medicală şi referire, diseminarea materialelor informaţionale, consiliere de la egal la egal, activităţi in grup şi suport alimentar, etc. Indicatorul este atins).
P2 - trend |  | A total of 264 children received social support during S7 (primarily reached) out of them 99 infected and 165 affected by HIV. Each quarter 230 children (all HIV infected children that can be reached and the majority of children born from HIV infected mother with unknown status) benefit of food parcels. At the same time each semester HIV positive children benefit of a set of stationary and clothing for school as part of social support program. During reported period the number of HIV positive children that benefited of clothing and school supplies was 99, exceeding by four the planned number of 95. This fact has determined the need to reallocate additional budget (from savings under other budget lines targeted at PLHIV support) in order to cover four additional sets of clothing and school supplies. The indicator is overachieved. Reason for variance: The number of children primarily reached with social support is determined by the number of children diagnosed with HIV that are reached and by the number of children born from HIV positive mothers immediately before and during the reported period. (Pe parcursul semestrului 7, in total 264 copii au beneficiat de suport social (acoperiţi primar), dintre care 99 copii HIV infectaţi și 165 copii cu statut nedeterminat născuți din mame HIV pozitive (afectaţi). În acelaşi timp, în fiecare trimestru, 230 copii (toți copiii infectați cu HIV, care pot fi acoperiţi cu servicii, și majoritatea copiilor născuți din mame infectate cu HIV) beneficiază de un set de haine şi rechizite școlare ca parte a programului de acordare a suportului social. Pe parcursul perioadei de raportare, numărul de copii HIV infectaţi care au primit un set de haine şi rechizite școlare a crescut la 99, depăşind cu patru unităţi numărul planificat de 95. Acest fapt a determinat necesitatea realocării unui buget adiţional (din economiile obţinute in cadrul altor linii bugetare orientate către suportul PTH) pentru a acoperi patru seturi suplimentare de îmbrăcăminte şi rechizite şcolare. Indicatorul este depășit. Cauza variaţiei: Numărul de copii primar acoperiţi cu suport social este determinat de numărul de copii diagnosticaţi cu HIV și numărul copiilor născuți din mame HIV pozitive imediat înainte și în perioada de raportate).
P3 - trend |  | During S7 a total of 45 PWIDs on opioid substitution therapy (primarily reached) received at least 3 support services from the package (psycho-social support, self-support groups, peer to peer education, distributions of information materials, food support, etc.) offered by NGOs working in PWUDs rehabilitation. The number of PWIDs on OST covered with psycho-social support is directly dependent to the number of PWIDs enrolled in OST treatment (new patients) which is continuously decreasing. During S1, 2013, 48 new clients versus 50 planned were enrolled in the substitution therapy program, the number of OST patients covered with support services (primarily reached) being 45 versus 40 planned. The indicator is achieved in proportion of 86%. Reason for variance: The target for the period 7 (40 persons primarily reached) has been exceeded (45 people reached). The underachievement of the cumulative target for the reported period (over program term) is determined by the variation between targets settled and results registered for period one of grant implementation caused by continuously decreasing enrolment of new patients in OST. As the number of OST patients that can be covered with psycho-support services is directly tied to new patients enrolled in OST, the enrolment dynamics in period one has determined and directly impacted the achievement of targets for this indicator and is affecting the results for the reported period as the target is cumulative over program term. (Pe parcursul semestrului 7 un total de 45 CDI aflați în terapia de substituţie cu metadonă (primar acoperiţi) au primit cel puţin 3 servicii de suport social din pachetul serviciilor (sprijin psiho-social, grupuri de suport reciproc, educație de la egal la egal, diseminarea materialelor informaţionale şi distribuirea pachetelor alimentare) oferite în cadrul centrelor de zi de către ONG-urile care lucrează în domeniul reabilitării CDI. Numărul de CDI aflaţi în TSO, acoperiţi cu suport psiho-social este direct dependent de numărul de CDI înrolaţi în TSO (cazuri noi), cifra care este în continuă scădere. În timpul S1, 2013, 48 beneficiari noi versus 50 planificați au fost înrolați în terapia de substituție, numărul de pacienți în TSO acoperiți cu servicii de sprijin (primari acoperiţi) fiind de 45 faţă de 40 planificați. Indicatorul este atins în proporție de 86%. Cauza variației: Ținta pentru perioada 7 (40 persoane noi primar acoperite) a fost depășită (45 persoane acoperite). Neatingerea țintei cumulative pentru perioada raportată (pe toata perioada grantului) este determinată de variația între ținta stabilită și rezultatele înregistrate pentru Perioada 1 de implementare a grantului cauzată de scăderea continua a pacienților înrolați în TSO. Numărul de pacienți în TSO care pot fi acoperiți cu servicii de suport psiho-social este direct proporţional cu numărul pacienților noi înrolați în TSO, dinamica înrolării în Perioada 1 a determinat și a afectat direct atingerea țintei pentru acest indicator și afectează rezultatul pentru perioada raportată deoarece ținta propusa se calculează cumulativ pentru toată perioada grantului).
P1 |  | During S7 a total 381 PLHIV were primarily reached with care and support services through four regional social centers providing assistance to PLHIV and 10 territorial organizations that ensures outreach to PLHIV and their families. The beneficiaries are provided with the following services: psycho-social counseling and support, medical counseling and referral, distribution of information materials, peer counseling, self-support groups and food support, etc. The indicator is achieved. (Pe parcursul semestrului 7, un total de 381 PTH au fost primar acoperiți cu servicii de îngrijire şi suport în cadrul celor patru Centre Sociale Regionale şi a 10 organizaţii teritoriale care prestează servicii PTH şi membrilor familiilor lor. Beneficiarilor le sunt prestate următoarele servicii: suport şi consiliere psiho-socială, consiliere medicală şi referire, diseminarea materialelor informaţionale, consiliere de la egal la egal, activităţi in grup şi suport alimentar, etc. Indicatorul este atins).
P2 |  | A total of 264 children received social support during S7 (primarily reached) out of them 99 infected and 165 affected by HIV. Each quarter 230 children (all HIV infected children that can be reached and the majority of children born from HIV infected mother with unknown status) benefit of food parcels. At the same time each semester HIV positive children benefit of a set of stationary and clothing for school as part of social support program. During reported period the number of HIV positive children that benefited of clothing and school supplies was 99, exceeding by four the planned number of 95. This fact has determined the need to reallocate additional budget (from savings under other budget lines targeted at PLHIV support) in order to cover four additional sets of clothing and school supplies. The indicator is overachieved. Reason for variance: The number of children primarily reached with social support is determined by the number of children diagnosed with HIV that are reached and by the number of children born from HIV positive mothers immediately before and during the reported period. (Pe parcursul semestrului 7, in total 264 copii au beneficiat de suport social (acoperiţi primar), dintre care 99 copii HIV infectaţi și 165 copii cu statut nedeterminat născuți din mame HIV pozitive (afectaţi). În acelaşi timp, în fiecare trimestru, 230 copii (toți copiii infectați cu HIV, care pot fi acoperiţi cu servicii, și majoritatea copiilor născuți din mame infectate cu HIV) beneficiază de un set de haine şi rechizite școlare ca parte a programului de acordare a suportului social. Pe parcursul perioadei de raportare, numărul de copii HIV infectaţi care au primit un set de haine şi rechizite școlare a crescut la 99, depăşind cu patru unităţi numărul planificat de 95. Acest fapt a determinat necesitatea realocării unui buget adiţional (din economiile obţinute in cadrul altor linii bugetare orientate către suportul PTH) pentru a acoperi patru seturi suplimentare de îmbrăcăminte şi rechizite şcolare. Indicatorul este depășit. Cauza variaţiei: Numărul de copii primar acoperiţi cu suport social este determinat de numărul de copii diagnosticaţi cu HIV și numărul copiilor născuți din mame HIV pozitive imediat înainte și în perioada de raportate).
P3 |  | During S7 a total of 45 PWIDs on opioid substitution therapy (primarily reached) received at least 3 support services from the package (psycho-social support, self-support groups, peer to peer education, distributions of information materials, food support, etc.) offered by NGOs working in PWUDs rehabilitation. The number of PWIDs on OST covered with psycho-social support is directly dependent to the number of PWIDs enrolled in OST treatment (new patients) which is continuously decreasing. During S1, 2013, 48 new clients versus 50 planned were enrolled in the substitution therapy program, the number of OST patients covered with support services (primarily reached) being 45 versus 40 planned. The indicator is achieved in proportion of 86%. Reason for variance: The target for the period 7 (40 persons primarily reached) has been exceeded (45 people reached). The underachievement of the cumulative target for the reported period (over program term) is determined by the variation between targets settled and results registered for period one of grant implementation caused by continuously decreasing enrolment of new patients in OST. As the number of OST patients that can be covered with psycho-support services is directly tied to new patients enrolled in OST, the enrolment dynamics in period one has determined and directly impacted the achievement of targets for this indicator and is affecting the results for the reported period as the target is cumulative over program term. (Pe parcursul semestrului 7 un total de 45 CDI aflați în terapia de substituţie cu metadonă (primar acoperiţi) au primit cel puţin 3 servicii de suport social din pachetul serviciilor (sprijin psiho-social, grupuri de suport reciproc, educație de la egal la egal, diseminarea materialelor informaţionale şi distribuirea pachetelor alimentare) oferite în cadrul centrelor de zi de către ONG-urile care lucrează în domeniul reabilitării CDI. Numărul de CDI aflaţi în TSO, acoperiţi cu suport psiho-social este direct dependent de numărul de CDI înrolaţi în TSO (cazuri noi), cifra care este în continuă scădere. În timpul S1, 2013, 48 beneficiari noi versus 50 planificați au fost înrolați în terapia de substituție, numărul de pacienți în TSO acoperiți cu servicii de sprijin (primari acoperiţi) fiind de 45 faţă de 40 planificați. Indicatorul este atins în proporție de 86%. Cauza variației: Ținta pentru perioada 7 (40 persoane noi primar acoperite) a fost depășită (45 persoane acoperite). Neatingerea țintei cumulative pentru perioada raportată (pe toata perioada grantului) este determinată de variația între ținta stabilită și rezultatele înregistrate pentru Perioada 1 de implementare a grantului cauzată de scăderea continua a pacienților înrolați în TSO. Numărul de pacienți în TSO care pot fi acoperiți cu servicii de suport psiho-social este direct proporţional cu numărul pacienților noi înrolați în TSO, dinamica înrolării în Perioada 1 a determinat și a afectat direct atingerea țintei pentru acest indicator și afectează rezultatul pentru perioada raportată deoarece ținta propusa se calculează cumulativ pentru toată perioada grantului).
P4 |  | A total of 129 persons trained in S7, from them: 15 medical staff were trained in international training in Clinica Lavra in ART and Opportunistic infection in HIV infected patients, 41 non-medical staff from social regional centers, territorial organizations and NRS MDTs participated in regional workshops targeted at strengthening collaboration and building sustainable referral systems to specialized HIV services; 73 infectious diseases specialists were trained in the reformed and reorganized system of medical service provision to PLHIV. The indicator is overachieved. Reason for variance: due to the fact that the three trainings for infectious diseases specialists planned under budget line 3.1.4 were directly related to the reform and reorganization of the HIV medical service provision system, all three events planned for year 2013 (two in S1 and one in S2) have been organized during reported period; the approach to the events under budget line 3.1.2 has been changed with TGF approval (two three days national events initially planned for Year 2013, one per semester, have been replaced with three two days regional events, two in S1, 2013 and one in S2, 2013) and two events for central and north regions organized during reported period. (In total 129 persoane au fost instruite in semestrul 7, dintre care: 15 lucrători medicali au participat la trainingul internaţional organizat la Clinica Lavra privind ARV si infecțiile oportuniste la pacienții HIV infectați; 41 lucrători non-medicali din centrele social regionale, organizațiile teritoriale și EMD au participat la întrunirea regională în contextul colaborării și referirii persoanelor care trăiesc cu HIV la serviciile specializate; 73 specialişti în boli infecţioase au fost instruiţi privind reformarea si reorganizarea sistemului in prestarea serviciilor medicale PTH. Indicatorul este depășit. Cauza variaţiei: datorită faptului că trei instruiri pentru specialiştii în boli infecţioase planificate în cadrul liniei bugetare 3. 1. 4, au fost direct legate de reforma si de reorganizarea sistemului in furnizarea serviciilor medicale PTH, toate aceste trei evenimente planificate pentru anul 2013 (două în S1 şi unul în S2) au fost desfăşurate pe parcursul perioadei raportate; durata organizării evenimentelor din cadrul liniei bugetare 3. 1. 2 a fost modificat cu aprobarea FG (două evenimente naţionale a cate trei zile iniţial planificate pentru anul 2013, unul per semestru, au fost înlocuite cu trei evenimente regionale a cate doua zile, două în S1, şi unul in S2, 2013); in perioada raportata au fost organizate si două evenimente pentru regiunile centrale şi de nord).
P5 |  | A total of 842 PLHIV received food parcels during S7 (primarily reached). Each quarter 800 PLHIV out of those on ARV treatment, selected based on socio-economic vulnerability, benefit of food parcels. A total of 800 food parcels are distributed quarterly to adult patient on ARV for better adherence to treatment, in both civilian and penitentiary sectors. The indicator is substantially achieved. (Un număr total de 842 PTH au primit pachete alimentare pe parcursul semestrului 7 (beneficiari primar acoperiţi). În fiecare trimestru 800 PTH din rândul celor aflaţi în tratamentul ARV, selectaţi în baza vulnerabilităţii socio-economice, beneficiază de pachete alimentare. În total 800 de pachete alimentare sunt distribuite trimestrial pacienţilor adulţi aflaţi in ARV în scopul creşterii aderenţei la tratament, atât in sectorul civil cat și penitenciar. Indicatorul este acoperit in mare măsură).
P6 |  | A total of 58 individuals out of 130 that initiated OST during P11-P12 have completing at least 6 months of continuous treatment on OST. Currently OST is provided in three sites: Republican Narcological Dispensary, Balti Municipal Hospital and the Department of Penitentiary Institutions (in 12 penitentiary institutions: #1 Taraclia, #3 Leova, #4 Cricova, #6 Soroca, #7 Rusca, #9 Pruncul, #11 Balti, #15 Cricova, #16 Pruncul, #17 Rezina, #18 Branesti, #13 Chisinau). The indicator is partially achieved (74%). Reason for variance: the rate of retention in treatment is determined by a series of factors, namely: seasonal migration of patients (both abroad and in country), emergency of seasonal illicit drugs on black market, low doses of methadone (below recommended 60mg minimal average dose), and concurrent use of illicit drugs, methadone distribution restricted to OST for all patients including for drug users in stable remission, repeated enrollment in treatment without prior psycho-social support to prepare the patient for the next attempt, misconceptions about OST in both medical and psych-social support teams, negative image of OST among PWID, etc. Un număr total de 58 de persoane din 130 care au iniţiat TSO în semestrul 2, 2012 au finalizat cel puţin 6 luni de tratament TSO continuu. Actualmente TSO este distribuita in trei site-uri: Dispensarul Republican de Narcologie, Spitalul Municipal Bălţi şi Departamentul Instituţiilor Penitenciare (în 12institutii penitenciare: #1 Taraclia, #3 Leova, #4 Cricova, #6 Soroca, #7 Rusca, #9 Pruncul, #11 Bălti, #15 Cricova, #16 Pruncul, #17 Rezina, #18 Brăneşti, #13 Chişinău). Indicatorul este atins parțial (74%). Cauza variaţiei: rata de retenție în tratament este determinata de o serie de factori, și anume: migrația sezonieră a pacienţilor (atât peste hotare cât și în interiorul țarii), apariţia drogurilor ilicite sezoniere pe piața neagră, doze mici de metadonă (mai puţin decât doza minimă recomandată de 60mg), precum și utilizarea concomitentă a drogurilor ilicite, distribuția metadonei limitată la site-urile OST, inclusiv pentru consumatorii de droguri în remisie stabila, înrolare repetată în tratament fără suport psiho-social preventiv pentru a pregăti pacientul pentru următoarea încercare, concepţii greşite despre TSO în atât în echipele medicale cat și cele de asistență psiho-socială, imaginea negativă a TSO printre CDI, etc).
P7 |  | 11 litigation cases have been initiated during S7. The cases were related to disclosure of confidential medical information related to HIV status, unethical and unprofessional behavior of medical staff, refusal to offer medical services, adoption of children by HIV positive persons, inhuman/ degrading treatment of detained PLHIV, etc. The indicator is overachieved. Reason for variance: The increase in number of cased initiated is determined by the type of cases handled during reported period and has no financial impact as the layers are fool day project consultants with fix remuneration. (Pe parcursul semestrului 7, au fost inițiate 11 litigii. Cazurile au fost legate de divulgarea informației medicale confidențiale legate de statutul HIV, comportament neetic și neprofesional al personalului medical, refuzul de a acorda servicii medicale, problema adopției copiilor de către persoane HIV pozitive, tratament inuman/degradat față de deținuții HIV pozitivi, etc. Indicatorul este depăşit. Cauza variaţiei: Numărul de litigii inițiate este determinat de tipul cazurilor soluţionate în perioada de raportare și nu are impact financiar deoarece avocaţii sunt angajaţi în proiect cu zi plină de munca şi au remunerare fixă).
P8 |  | A total of 104 consultancies were offered remotely by traveling to project sites of 4 lawyers, during S7; they offered legal assistance related to issues of legal, civil (including disclosure of HIV status), administrative nature to all PLHIV in need. The indicator is overachieved. Reason for variance: The number of consultancies offered by project lawyers is determined by the request of legal support from PLHIV and can vary from one period to another. With the opening of Social Regional Centers project lawyer provide services within the Centers facilities (with a specific periodicity) bringing this way services closer to the beneficiary and increasing their access to legal support. The increase in number of consultancies provided has no financial impact as the layers are fool day project consultants with fix remuneration. (Pe parcursul semestrului 7 au fost prestate 104 consultații în teren de către 4 avocaţi. Ei au oferit asistenţă juridică pe aspecte de natură legală, civilă (inclusiv divulgarea statutului HIV) şi administrative ale tuturor PTH care au solicitat asistenta juridica. Indicatorul este depăşit. Cauza variaţiei: Numărul de consultaţii oferite de către avocații proiectului este determinat de cererea de asistență juridică din partea PTH și poate varia de la o perioadă la alta. Odată cu deschiderea Centrelor Sociale Regionale avocaţii prestează servicii în cadrul centrelor (cu o anumită periodicitate) aducând astfel serviciile mai aproape de beneficiar și crescând accesul la asistența juridică. Creșterea numărului de servicii de consultanţă juridică prestate nu are impact financiar deoarece avocaţii sunt angajaţi în proiect cu zi plină de lucru şi au remunerare fixă).
P9 |  | A total number of 30 representatives of organizations that provide services to PLHIV and key populations were trained in organizational management and leadership. The indicator is overachieved. Reason for variance: The number of people interested in the training course was higher than planned and due to the fact that the costs for the selected venue allowed the number of trainees was increased to 30 instead of 25 planned. (Un număr total de 30 reprezentanţi ai organizaţiilor care prestează servicii PTH şi populaţiilor cheie au fost instruiţi în managementul organizaţional si liderism. Indicatorul este depăşit. Motivul pentru variaţie: numărul persoanelor interesate in audierea cursului a fost mai mare decât cel planificat şi datorită faptului că costurile de desfăşurare a al evenimentului au permis, numărul participanţilor a fost crescut la 30 in loc de cei 25 planificaţi).
P10
Menu

## Actions
Dashboard: Moldova - HIV / AIDS
| SSF (Round 8) | Piriod 2 |  |  |  | Report Period: |  | P7
| Latest Rating: | A2 |  | PAS Center |  | From: |  | January 01, 2013
|  |  | Reducing HIV-related burden in the Republic of Moldova |  |  |  | To: | June 30, 2013
Decisions and Actions
What is the overall status of this grant implementation?
Programul este implementat în conformitate cu planul de lucru şi prevederile contractuale. Rata cumulativă de absobţie din buget este de 95.68%, iar performanța medie a indicatorilor de 104.9%. Raiting-ul general acordate de Fondul Global grantului HIV implementate de Centrul PAS este A1.
| Key Recommendations from Oversight Group(s) |  |  |  | CCM Decision | Due Date | Person Responsible
Current Reporting Period
Actions to Implement / Previous Period
What is the overall status of this grant implementation?
| CCM Decision |  |  |  | Action Taken | Date | Person Responsible
Previous Reporting Period
Menu

## Setup (hidden)
Dashboard: Moldova - HIV / AIDS
Set-up = List of validation for Grant Detail page
Component | Currency | Round | Phase | Period | Rating | LFA | Medicaments | Countries
Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select
HIV / AIDS | $ | Round 1 | Phase 1 | P1 | A1 | CA (Crown Agents) | Isoniazid | Afghanistan
MALARIA | € | Round 2 | Phase 2 | P2 | A2 | DEL (Deloitte) | Ethambutol | Albania
TB |  | Round 3 | RCC | P3 | B1 | DTT (DTT Emerging Markets) | Rifampicin | Algeria
HIVAIDS / TB |  | Round 4 |  | P4 | B2 | FIN (Finconsult) | Pyrazimamide | Angola
HSS |  | Round 5 |  | P5 | C | GT (Grant Thornton) | RDT | Argentina
|  | Round 6 |  | P6 |  | H-C (Hodar-Conseil) | NVP | Armenia
|  | Round 7 |  | P7 |  | KPMG (KPMG) | 3TC | Azerbaijan
|  | Round 8 |  | P8 |  | MSCI (MSCI) | D4T | Bangladesh
|  | Round 9 |  | P9 |  | PwC (PricewaterhouseCoopers) | AZT | Belarus
|  | Round 10 |  | P10 |  | STI (Swiss Tropical Institute), | DDI | Belize
|  |  |  | P11 |  | UNOPS | EFV | Benin
|  |  |  | P12 |  |  | AS/LF | Bhutan
[7 empty] | AS/AQ | Bolivia
[7 empty] | AS/MQ | Bosnia and Herzegovina
[7 empty] | Al/Lum | Botswana
Brazil
[7 empty] | TB nutri'l supplements | Bulgaria
[7 empty] | E-PAP | Burkina Faso
Burundi
Cambodia
Cameroon
Cape Verde
Central African Republic
Chad
Chile
China
China
Colombia
Comoros
Congo (Democratic Republic of the)
Congo (Republic of the)
Costa Rica
Cote d'Ivoire
Croatia
Cuba
Djibouti
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Ethiopia
Fiji
Gabon
Gambia
Georgia
Ghana
Global(LWF)
Guatemala
Guinea
Guinea-Bissau
Guyana
Haiti
Honduras
India
Indonesia
Iran (Islamic Republic of)
Iraq
Jamaica
Jordan
Kazakhstan
Kenya
Korea, Democratic Peoples Republic of
Kosovo (Serbia)
Kyrgyzstan
Lao PDR
Lesotho
Liberia
Macedonia, FYR
Madagascar
Malawi
Maldives
Mali
Mauritania
Mauritius
Moldova
Mongolia
Montenegro
Morocco
Mozambique
Multi-country Africa (West Africa Corridor Program)
Multi-country Africa(RMCC)
Multi-country Americas (Andean)
Multi-country Americas (CARICOM)
Multi-country Americas (CRN+)
Multi-country Americas (Meso)
Multi-country Americas (OECS)
Multi-country Americas (REDCA+)
Multi-country Western Pacific
Myanmar
Namibia
Nepal
Nicaragua
Niger
Nigeria
Pakistan
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Romania
Russian Federation
Rwanda
Sao Tome and Principe
Senegal
Serbia
Sierra Leone
Solomon Islands
Somalia
South Africa
Sri Lanka
Sudan
Suriname
Swaziland
Syrian Arab Republic
Tajikistan
Tanzania
Thailand
Timor-Leste
Togo
Tunisia
Turkey
Uganda
Ukraine
UN Theme Group on HIV/AIDS (West Bank and Gaza)
Uzbekistan
Viet Nam
Yemen
Zambia
Zanzibar (Tanzania)
Zimbabwe