## Meniu
Dashboard: Moldova - TB
TB Round 9, Phase 2 | Grant No.(Nr. Grantului): MOL-T-PAS
V1.0
Finance
Programmatic
Management
Select the option you want to see:
Recommendations
Actions
Grant Detail
List of Indicators
Data Entry
Grant Information
Indicators
Reports

## Lista Indicatorilor
Dashboard: Moldova - TB
Financial information
Name: | Definition | Measurement | Data Sources
F1: Budget and disbursements by Global Fund (Bugetul și debursările de către Fondul Global) | Cumulative budget: Sum of the grant budget from period one (quarter, trimester, or semester) of the current phase, up to and including the dashboard reporting period. Cumulative Disbursments by GF: Sum of all the funds transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to and including the dasboard reporting period. | Currency of the grant ($ or Euro) Cumulative – Figures refer to budget and disbursements for all the periods of the phase up to and including the dashboard reporting period | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F2: Budget and actual expenditures by Grant Objective (Bugetul și cheltuielile actuale după Obiectivele Grantului) | Cumulative Budget per Objective: Sum of the grant budget by Objective, from period one of the current phase up to and including the dashboard reporting period. Cumulative Expenditure per Objective: Sum of amounts spent by Objective directly by the PR plus the amounts transferred by the PR to all SRs from the beginning of the phase up to and including dashboard reporting period, by Objective | • Cumulative – Figures refer to budget, disbursements or expenditure for all the periods of the phase up to and including the dashboard reporting period. | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F3:Disbursements and expenditures (Debursări și cheltuieli) | Disbursement by GF: Prior to this Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to but not including dashboard reporting period. Disbursement by GF: Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), during dashboard reporting period. PR disbursements and expenditure: Prior to this Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) up to but not including dashboard reporting period. PR disbursements and expenditure: Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) during dashboard reporting period. Disbursements to SRs: Prior to this Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), up to but not including dashboard reporting period. Disbursements to SRs:Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), in dashboard reporting period. SR expenditures: Prior to this Reporting period: The sum of all expenditures reported by the SRs, up to but not including dashboard reporting period. SR expenditures: Reporting period: The sum of all expenditures reported by the SRs, during dashboard reporting period. | Currency of the grant ($ or Euro) • Reporting period – Figures refer to budget, disbursements or expenditure for the reporting period to which the dashboard refers. • Prior to reporting period - Figures refer to the total budget, disbursements or expenditure for all the periods before but not including the current period. | PU/DR; PR data: SR reports to PR
F4: Latest PR reporting and disbursement cycle (Ultima perioadă de raportare și debursare a RP) | Days taken to submit final PU/DR to LFA – This indicator measures the number of calendar days it took the PR to send a final Performance Update and Disbursement Request (PU/DR) to the LFA after the end of the period. A 'final' PU/DR would be one for which the LFA did not require any further clarifications from the PR. The expected value is 45 days from the end of the period, as defined in the Grant Agreement. The actual value is the number of calendar days from the end date of the period to the date on which the PR sent to the LFA the final PU/DR. Days taken for disbursement to reach PR – This indicator measures the number of calendar days it took the Global Fund to send the latest disbursement to the PR's account after receipt of the acceptable PU/DR by the LFA. The expected number is 45 days. The actual number is the number of days from the date of transmission by the PR to the LFA of the acceptable PU/DR to the date the disbursement is received by the PR at its bank. Days taken for disbursement to reach SRs – This indicator measures the average number of days for disbursements to be made to all the SRs. The expected value for this indicator will be set locally by the PR and SRs, preferably in the Grant Operations Manual. The actual value is the average of the number of days from the receipt of the funds from the GF by the PR to the date the funds are received by each SR. Different SRs coudl receive funds on different dates and this indicator is the average across all SRs for the latest disbursement. | Number of calendar days; it refers only to reporting period for which the latest disbursement was received and is not cumulative | PR, LFA, GF emails and records; bank notification document or the notice of receipt by the PR to GF; SR reports to PR based on bank records
Management Information
Name: | Definition | Measurement | Data Source
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) (Statutul Condițiilor Precedente și a Acțiunilor Prestabilite în Timp) | Number of Conditions Precedent (CPs) and Time Bound Actions (TBAs ) fulfilled, or unfulfilled. Within the Unfulfilled category, we distinguish between those CPs and TBAs whose deadline has not passed and those for which the deadline has passed. | Number, cumulative to the dashboard reporting period. Number of fulfilled CPs and/or TBAs plus unfulfilled CPs and/or TBAs should equal the total number set by the Global Fund on the grant | PR records; Grant Performance Reports;
M2: Status of key PR management positions (Statutul pozițiilor cheie a RP) | Number of PR grant management positions planned currently filled or vacant. Full time equivalents of the managerial positions that are on the organizational chart (or otherwise planned) and directly responsible for ensuring grant implementation at the PR, and lead SRs (if necessary). This will include new hires, current staff who are assigned to work on the grant’s management, as well as any staff seconded from other divisions or partner organizations. | Number, in current reporting period | PR records
M3: Contractual arrangements (SRs) (Aranjamente contractuale (SR)) | Identified: Total number of potential SRs identified by the PR for the phase. Assessed: Total number of potential SRs assessed by the PR to determine whether they qualify to function as SRs for the grant. Approved: Total number of SRs that have been approved. Signed: Total number of SRs that have signed agreements/contracts with the PR under the grant. Receiving funding: Total number of SRs that are getting funds and/or supplies from the PR. Numbers of SRs Identified, Assessed, Approved, Signed and Receiving funds are cumulative for the phase, with the following exceptions: If an SR does not need new approval in Phase II, then approval in Phase I is counted. If an SR was signed in a previous Phase but is not working in the current Phase, that SR is no longer counted in Identified, Assessed, Approved. | Number, cumulative to the reporting period. A SR is an institution or program with its own workplan, budget and performance targets. | PR records; Sub-agreements/MOUs; CCM records
M4: Number of complete reports received on time (Numărul rapoartelor complete recepționate la timp) | The total number of periodic reports with up-to-date financial, management and performance (programmatic) data received by the PR from SRs and by SRs from the SubSRs (SSRs) by the expected date. A 'complete' report is one that contains all the data that the PR requires for the PU/DR. The expected date would be set by the PR in the sub-agreements. | Number of reports received. The figure reflects only the period of reporting; it is not cumulative. | PR and SR records
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals (Bugetul și Procurarea produselor medicale, echipamentului medical, medicamentelor și produselor farmaceutice ) | This indicator measures the budget approved for the current phase of the grant for purchase of health products and equipment and pharmaceuticals and medicines (categories 4 and 5 in the new Enhanced Financial Report), and the cumulative amounts of financial obligations and expenditures up to the dashboard reporting period. Budget approved: Total approved budget for purchases (categories 4 and 5) for the entire phase of the grant. It does not include the amounts for fees, management, operational costs, etc. Cumulative Obligations: Total of all order(s) placed and monies committed for these purchases by the PR up to and including the dashboard reporting period. Ideally, by the end of the Phase, budget should equal obligations. Cumulative expenditure: Total of actual Expenditures on category 4 and 5 up to and including the dashboard reporting period (whether paid by PR or authorized to be paid by another entity like GF or other). | Currency of the grant ($ or Euro) | Grant agreement approved budget (for categories 4 and 5 of Enhanced Finance Reporting in current phase); and PR financial data (for expenditures), and/or PSM unit (for orders placed and funding committed or obligated).
Note: Category 6 of the EFR will not be considered as part of the budget for pharmaceuticals. Category 6 has several expenditures that are difficult to disaggregate or quantify, such as warehousing costs, distribution costs (particularly when distibution is done by MOHs), and others that are related to operational costs of the PSM component.
M6: Difference between current and safety stock (Diferență între stocul curent și stocul de siguranță) | This indicator is a snapshot of the difference between the current (or last month) stock level of a specific product (medicine in single, fixed-dose combination, bednets, diagnostic kits, etc.) of a particular dose, expressed in monthly needs (number of months of treatment available) for all patients in the program, and the safety or buffer stock (also expressed in months) as established by the disease program, warehouse system or essential drugs program, for the particular product and dosage. The table will show the difference in months in colors: • RED: when the difference is negative or 0, showing that months of existing stock are lower than or equal to what has been established as months of safety stock • YELLOW: when we have more than the level of safety stock (>0) but less than 3 months (+3). • GREEN: when the difference is between 3 and 18 months. • VIOLET: When the difference shows that the level above the safety stock is greater than or equal to 18 months indicating a potential overstock) problem. For a full description of how this indicator is calculated, please see the User’s Manual. | Number of months | PR records: Warehouse data.
Programmatic Indicators (from Performance Framework) // Indicatori programatici
Indicator | Definiție (din planul M&E,pentru perioada 2) | Measurement | Data Source (Sursa datelor)
The default rate among New TB Cases in Community Centers | Numerator: Number of default cases among new smear-positive pulmonary TB patients registered for tratment in a given year in community TB centers. Denominator: Total number of new cases registered for treatment in the same specified period in community TB centers. Actual absolute figures for numerator and deniminator will be provided with the report. | Numerator: Number of default cases among new smear-positive pulmonary TB patients registered for tratment in a given year in community TB centers. Denominator: Total number of new cases registered for treatment in the same specified period in community TB centers. Actual absolute figures for numerator and deniminator will be provided with the report. | Program reports
Number of volunteers, members of multidisciplinary teams and NGOs representatives trained in TB community aspects | Targets refer to the number of persons/contacts trained, assuming that the same persons might attend more than one training. Volunteers from the NGO network, representatives of the NGOs and of the multidisciplinary teams of the community centres, including local public authorities, will be trained in DOT and TB community aspects.Composite indicator, related activities 2.2.4; 2.3.2; 2.3.3 | All persons who attended the course not less than 80% and signed the list of participation at training | Training records and SR reports
Number of new TB patients in ambulatory phases provided with DOT support by the community |  | Patient is considered "reached" if he/she receives at least 25 DOT interventions during 1 month. | TB patient register and SR reports
Number of people (TB,TB/HIV patients and their families) reached by peer support groups | Targets refer to number of patients with TB,TB/HIV coinfection, drug users and their families, etc. reached by peer educators. The aim of this activity is to improve the adherence to TB treatment, prevent the defaults, inform the beneficiaries about the referral system in the country and to advocate for TB control problems among vulnerable population. The peer educators are the former TB patients, PLWHA, medical personnel and others, who have willingness and capacity to work in the area of TB.Related activity: 2.4.2 | New persons who received services during the reported period | Register of people reached and SR reports
Number of peer educators, journalists at national and district level and local stakeholders trained in TB and TB/HIV issues | Peer educators will be trained to carry out informational work on TB; journalists at national and district level will be trained in TB communications; and the local stakeholders (representatives of the civil society and NGOs, Local Public Administrations in rayons, personnel of the Centre of Preventive Medicine, hospitals' administrators, representatives of the PHC institutions and teaches from schools and colleges) will be trained in TB and TB/HIV issues. Composite indicator, related activities 2.5.1; 2.6.4 & 2.6.7. | All persons who attended the course not less than 80% and signed the list of participation at training | Training records
Number of TB service staff trained in DR-TB management | Indicator refers to trainings of TB service staff from in- and out-patient treatment delivery sites, covering both civilian and penitentiary sectors.Related activiti: 3,3,2 | All persons who attended the course not less than 80% and signed the list of participation at training | Training records
Number and percentage of MDR-TB patients registered under DOTS program who are receiving incentives and enablers for improved treatment compliance | Each patient will receive at least four food packages per month. Related activity: 3,2,4 Numerator:Number of patients with MDR TB in ambulatory phase received incentives and enablers for improved treatment compliance Denominator Total Number of patients with MDR TB in ambulatory phase under treatment | All patients who receive at least three food packages per month. | TB patient register and SR reports
Number of TB patients registered under DOTS program who are receiving incentives and enablers to improve their treatment adherence | Support to treatment adherence (food and hygienic parcels) for TB patients. Patients will receive at least four food packages per month. Related activity: 3,1,1 Numerator: Number of TB patients in ambulatory phase received incentives and enablers for improved treatment compliance Denominator Total Number of TB patients in ambulatory phase under treatment | All patients who receive at least three food packages per month. | TB patient register and SR reports
Percentage of released prison inmates on TB treatment supported through the TB treatment follow-up program | Numerator: Number of released prison inmates on TB treatment supported through the TB treatment follow-up program during a given time period. Denominator: Total number of released prison inmates on TB treatment during the same time period. Because the denominator may vary the targets are set in percentage and absolute numbers will be reported with each Progress Update. All inmates participating in the treatment follow-up program will be provided with financial incentives upon completion of their treatment. When needed, the beneficiaries will be also provided with legal support/processing of legal papers/identification documents. Actual absolute figures for numerator and deniminator will be provided with the report. | All inmates participating in the treatment follow-up program | SR reports
Number of PHC staff trained in TB case management, community TB care issues and methods of informational work with different groups of population | Training program of PHC staff (doctors and nurses) will be continued to strengthen their involvement in TB control, with priority attention to TB case detection, strengthening referrals and cooperation with specialized TB service, TB case management in out-patient settings (including MDR-TB cases), community TB care and adherence support, defaulter tracing and contacts' investigation, in conditions of revised TB care delivery model. Related activity 3.4.1 | All persons who attended the course not less than 80% and signed the list of participation at training | Training records and SR reports
Indicator Number: Name (Perf Framework No.) | Definition | Measurement | Data Source
The indicators should be selected by the PRs and members of the CCM or the CCM Technical Committee, from the Performance Framework |  |  | Performance Framework
Menu

## Introducerea datelor
Grant information (Informație despre Grant)
| Country (Țara): | Moldova |  | Title of the Grant (Numele Grantului): |  | Empowerment of people with TB and Communities in Moldova
| Grant No.(Nr. Grantului): | MOL-T-PAS |  | Component(Componenta): |  | TB | Suma totală: | 7434590.72
| Principal Recipient (Recipientul Principal): | PAS Center |  |  | Round (Runda): | Round 9 | Faza: | Phase 2
| Start Date (dd/Mmm/yy)(Data Demarării (zz/ll/aa): | January 01, 2010 |  | Local Fund Agent(Agentul Local): |  | PwC (PricewaterhouseCoopers)
| Latest Rating (Ultimul Rating): | A1 |  | Fund Portfolio Manager: |  | Tatiana Vinichenko
Information reporting period (Informația despre perioada raportată)
| Report Period(Perioada de Raportare): | P11 | From(De la): | 2013-01-01 | To(Pînă la): | 2013-06-30 | Date of entry of information (Data de introducere a informației): |  | 2013-09-01
| Prepared by(Pregătit de către): |  | PAS Center
Information on indicators (Informația despre indicatori)
Enter the data based on the colour-coded cells (Introduceți datele bazîndu-vă de celulele codificate prin culoare)
| Financial Information(Informația Financiară): |  | Management Information(Informația pe Management): |  |  | Programmatic Information (Informația Programatică):
| Financial Information: | [5 empty] | Enter finance data in every orange cell like this. |  |  | (Introduceți datele financiare în celulele colorate în oranj)
| Currency of the grant (Valuta Grantului) |  | €
F1: Budget and disbursements by Global Fund (Bugetul și debursările de către Fondul Global)
| Disbursement | [14 empty] | 0
| Reporting period (Perioada Raportată) | [8 empty] | P1-P9 | P10 | P11 | P12 | P13 | % Cumulative | 0
| Buget (in €) | [8 empty] | 4063058 | 303817.76 | 327052.76 |  |  | 118.3% | 0
| Debursări de către FG (in €) | [8 empty] | 4063058 | 303818 | 1188387 |  |  |  | 0
| Cumulative budget (Buget Cumulativ) | [8 empty] | 4063058 | 4366875.76 | 4693928.52 |  | 0 |  | 0
| Cumulative disbursements (Debursări cumulative) | [8 empty] | 4063058 | 4366876 | 5555263 |  | 0 |  | 0
|  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 118.3% | 0% |  |  | 0
F2: Budget and actual expenditures by Grant Objective (Bugetul și cheltuielile actuale după Obiectivele Grantului)
| Grant Objective (Obiectivele Grantului) | Bugetul Cumulativ (in €) | Cheltuielile Cumulative (in €)
| Mobilize resources to support community-level partnerships | 1217344.5 | 1188085.1605
| Remove barriers to care for poor and other vulnerable communities | 1087111.7 | 1012944.597
| Strengthen the health system and engage all available partners in TB control | 342054 | 304286.8453
| Advocacy, communication and social mobilization (ACSM) | 141888 | 129552.6781
| Integrate TB services on both sides of the prison walls | 342209 | 330546.9587
| Ensure universal access to diagnosis, treatment, care and support of drug-resistant tuberculosis | 818318.89 | 784916.3105
| Operational research in priority issues of TB and monitoring and evaluation | 19227 | 18666.42
| Project management | 725776.4 | 808977.2834
| Total | 4693929.49 | 4577976.2534 |  | OK: Datele coincid
| F3:Disbursements and expenditures (Debursări și cheltuieli) | [14 empty] | 0
4063058
|  | Către perioada de raportare | Perioada de raportare curentă | Total Cheltuit și debursat (in €)
| Disbursed by Global Fund (Debursat de către Fondul Global) | 4063058 | 1492205 | 5555263
| PR expenditure and disbursement (Cheltuielile și debursările RP ) | 3960947.86 | 617028.3945 | 4577976.2545
| Disbursed to SRs (Debursări către SR) | 2077330.71 | 279964.81 | 2357295.52
| SR expenditures (Cheltuielile SR) | 1980847.15 | 338962 | 2319809.15
F4: Latest PR reporting and disbursement cycle (Ultima perioadă de raportare și debursare a RP)
Last fund disbursement: Number of calendar days (Ultima debursare a surselor: Număr de zile calendaristice)
|  | Expected (days)Preconizat (zile) | Actual (days) Actual (zile)
| Days taken to submit final PU/DR to LFA (Zile necesare pentru remiterea PU/DR final către ALF) | 45 | 44
| Days taken for disbursement to reach PR (Zile necesare pentru debursare către RP) | 45 | 99
| Days taken for disbursement to reach SRs (Zile necesare pentru debursare către SR) | 20 | 5
| Management Information: (Informația pe Management) |  |  |  | Enter management data in every blue cell. |  | (Întroduceți datele pentru management în celulele albastre)
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) (Statutul Condițiilor Precedente și a Acțiunilor Prestabilite în Timp)
|  |  | Fulfilled (Finisate) | Not fulfilled, but within deadline (Ne finisate, dar realizarea în conformitate cu planul) | Not fulfilled, and past the deadline (Ne finisate, și au depășit planul de realizare) | Total
| Conditions precedent (CPs) (Condiții Precedente (CP)) |  | 1 | 2 |  | 3
| Time Bound Actions (TBAs) (Acțiuni Prestabilite în Timp (TBA)) |  |  |  |  | 0
M2: Status of key PR management positions (Statutul pozițiilor cheie a RP)
|  | Planned (Planificate) | Filled (Completate) | Vacant (Vacante)
| PMU | 14 | 14 | 0
M3: Contractual arrangements (SRs) (Aranjamente contractuale (SR))
|  | Identified (Identificați) | Assessed (Evaluați) | Approved (Aprobați) | Signed (Contracte semnate) | Receiving Funding (Au recepționat surse)
| SRs | 3 | 2 | 3 | 3 | 3
M4: Number of complete reports received on time (Numărul rapoartelor complete recepționate la timp)
|  | # Expected (Planificat) | # Received (Recepționat) | Pending (În așteptare)
| SSR to SR | 8 | 8 | 0
| SRs to PR | 3 | 3 | 0
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals (Bugetul și Procurarea produselor medicale, echipamentului medical, medicamentelor și produselor farmaceutice )
|  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12 | P13
Budget Approved* (Buget Aprobat*)
Obligations (Obligațiuni)
Expenditures (Cheltuieli)
Budget Approved cumulative* (Buget Aprobat cumulativ*)
Obligations cumulative (Obligațiuni cumulative)
Expenditures cumulative (Cheltuieli cumulative)
* Includes only EFR category 4 and 5 (Health products and health equipment & Medicines and Pharmaceuticals) (* Include numai EFR categoriile 4 și 5 (Produse medicale și Echipamente medicale & Medicamente și Produse farmaceutice))
M6: Difference between current and safety stock (Diferență între stocul curent și stocul de siguranță)
| Component (Componenta) | Produsul | (1) Numărul de pastile per pacient per zi (În conformitate cu ghidurile d etratament al țării) | (2 = 1 x 30) Tratamentul per lună (Pastile per pacient x 30 zile) | (3) Total pacienți în tratament | (4 = 2 x 3) # Total pastile necesare pentru toți pacienții per lună | (5) Stocul Curent în depozitul central (nu expiră în următoarele 3 luni) | (6 = 5 / 4) Stocul exprimat în luni de treatament pentru toți pacienții curenți | (7) Nivelul stocului de siguranță (exprimat în luni și prestabilit de țară) | (8 = 6 - 7) Diferența între stocul curent și stocul de siguranță
| TB | P1: Please Select
Please Select
Please Select
Please Select
| Programmatic Information (Informația Programatică): | P9: Enter performance data in every yellow cell.
| Indicatori de Program (Performance Framework ) |  |  | Code / codul | Direct rezulta din activitatea FG? |  | P10 | P11 | P12 | P13 | P14 | P15 |  |  |  |  | P17
TOP 3 | Number of TB patients registered under DOTS program who are receiving incentives and enablers to improve their treatment adherence (Numarul de pacienți înregistrați în programul DOTS care au beneficiat de stimulente pentru sporirea complianței la tratament) | P3: 3.3; P4: Yes; P5: Target; P6: 562; P7: 1125
[6 empty] | Achieved | 341 | 1237
| Number and percentage of MDR-TB patients registered under DOTS program who are receiving incentives and enablers for improved treatment compliance (Numarul și procentul de pacienți înregistrați în programul DOTS Plus care au primit stimulente pentru sporirea complianței la tratament) | P3: 3.2; P4: Yes; P5: Target // Ținta; P6: 142; P7: 285
[6 empty] | Achieved // Realizat | 63 | 288
| Number of volunteers, members of multidisciplinary teams and NGOs representatives trained in TB community aspects(Numarul de voluntari, membri din echipele multidisciplinare, reprezentanti ai ONG-lor insruiti în aspecte DOT și controlul tuberculozei la nivel de comunitate) | P3: 2.2; P4: Yes; P5: Target // Ținta; P6: 40; P7: 80
[6 empty] | Achieved // Realizat | 23 | 85
| The default rate among New TB Cases in Community Centers (Rata abandonurilor cazurilor noi de TB în cadrul centrelor comunitare) | P3: 2.1; P4: Yes; P5: Target // Ținta; P6: n/a; P7: n/a
[6 empty] | Achieved // Realizat | n/a | n/a
| Number of new TB patients in ambulatory phases provided with DOT support by the community (Numărul pacienților noi cu TB aflați în faza de ambulator care au beneficiat de suportul DOT în cadrul centrelor comunitare) | P3: 2.3; P4: Yes; P5: Target // Ținta; P6: 168; P7: 337
[6 empty] | Achieved // Realizat | 151 | 313
| Number of people (TB,TB/HIV patients and their families) reached by peer support groups (Numarul de persoane (pacienți TB,TB/HIV și familiile lor) care au fost instruiti de către grupurile de la egal la egal) | P3: 2.4; P4: Yes; P5: Target // Ținta; P6: 100; P7: 200
[6 empty] | Achieved // Realizat | 40 | 200
| Number of peer educators, journalists at national and district level and local stakeholders trained in TB and TB/HIV issues (Numarul de educatori de la egal la egal, jurnaliști la nivel național și regional, persoane-cheie din republică instruiți in TB și TB/HIV) | P3: 2.5; P4: Yes; P5: Target // Ținta; P6: 60; P7: 135
[6 empty] | Achieved // Realizat | 509 | 758
| Number of TB service staff trained in DR-TB management (Numarul de personal din serviciu TB instruiti in managementul TB-MDR) | P3: 3.1; P4: Yes; P5: Target // Ținta; P6: 0; P7: 25
[6 empty] | Achieved // Realizat | 0 | 115
| Percentage of released prison inmates on TB treatment supported through the TB treatment follow-up program (Procentul de deţinuţi înrolați în tratamentul TB și susţinuți prin programul tratamentului TB de follow-up) | P3: 3.4; P4: Yes; P5: Target // Ținta; P6: n/a; P7: 95%
[6 empty] | Achieved // Realizat | n/a | 100%
| Number of PHC staff trained in TB case management, community TB care issues and methods of informational work with different groups of population (Numărul de lucrători medicali instruiți în managementul de caz, probleme de îngrijire comunitară, lucru informaţional cu diferite grupuri de populaţie) | P3: 3.5; P4: Yes; P5: Target // Ținta; P6: 25; P7: 50
[6 empty] | Achieved // Realizat | 0 | 24
| Tabelul este în mod automat reînnoit. Nu necesită introducerea datelor și/sau informației. |  |  | Code | Direct rezulta din activitatea FG? |  | P10 | P11 | P12 | P13 | P14 | P15
| Number of TB patients registered under DOTS program who are receiving incentives and enablers to improve their treatment adherence (Numarul de pacienți înregistrați în programul DOTS care au beneficiat de stimulente pentru sporirea complianței la tratament) |  |  | 3.3 | Yes | Target | 562 | 1125 | 0 | 0 | 0 | 0
[6 empty] | Achieved | 341 | 1237 | 0 | 0 | 0 | 0
| Number and percentage of MDR-TB patients registered under DOTS program who are receiving incentives and enablers for improved treatment compliance (Numarul și procentul de pacienți înregistrați în programul DOTS Plus care au primit stimulente pentru sporirea complianței la tratament) |  |  | 3.2 | Yes | Target | 142 | 285 | 0 | 0 | 0 | 0
[6 empty] | Achieved | 63 | 288 | 0 | 0 | 0 | 0
| Number of volunteers, members of multidisciplinary teams and NGOs representatives trained in TB community aspects(Numarul de voluntari, membri din echipele multidisciplinare, reprezentanti ai ONG-lor insruiti în aspecte DOT și controlul tuberculozei la nivel de comunitate) |  |  | 2.2 | Yes | Target | 40 | 80 | 0 | 0 | 0 | 0
[6 empty] | Achieved | 23 | 85 | 0 | 0 | 0 | 0
Menu
Note on B30: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.
Note on B72: If data are not available, do not enter zeros; rather, leave the cells in the table blank.
Note on B73: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B79: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B94: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.

## Detalii despre Grant
Dashboard: Moldova - TB
Country: | Moldova |  | Title of the Grant: |  | Empowerment of people with TB and Communities in Moldova
Component: | TB | Grant No. | MOL-T-PAS | Start Date: |  | January 01, 2010 | Total Funding | 7434590.72
Round: | Round 9 | Phase: | Phase 2 | Principal Recipient: |  | PAS Center
Report Period: | P11 | from: | 2013-01-01 | to: |  | 2013-06-30 | Latest Rating: | A1
Local Fund Agent: | PwC (PricewaterhouseCoopers) |  |  | Fund Portfolio Manager: |  | Tatiana Vinichenko
Prepared by: | PAS Center |  |  | Report preparation date: |  | 2013-09-01
http://www.crwflags.com/fotw/flags/country.html
Menu

## Financiar
Dashboard: Moldova - TB
Round 9 | Phase 2 |  |  |  | Report Period(Perioada de Raportare): |  | P11
Latest Rating (Ultimul Rating): | A1 |  | PAS Center |  | From(De la): |  | 2013-01-01
|  | Empowerment of people with TB and Communities in Moldova |  |  |  | To(Pînă la): | 2013-06-30
Financial Indicators
F1: Budget and disbursements by Global Fund (Bugetul și debursările de către Fondul Global) - in (€) Report Period(Perioada de Raportare): P11 |  |  |  | F3:Disbursements and expenditures (Debursări și cheltuieli) - in (€) Report Period(Perioada de Raportare): P11
Comments: | Cumulative disbursements is more than cumulative budget (first semester 2013), due to the fact that disbursement includes the budget for the second semester of 2013 and for the first quarter of 2014 (buffer period). Suma debursarilor este mai mare decit suma bugetata, deoarece suma bugetata reflecta bugetul pina la 30 iunie 2013, iar in debursari este inclus si bugetul pentru semestrul 2, 2013 si perioada de buffer din 2014 (1 ianuarie-31 martie). |  |  | Comments: | The variance between the disbursement and expenditures of the PR for the current period is due to: 1. Disbursement includes the budget for the second semester of 2013 and for the first quarter of 2014 (buffer period); 2. Commitments from semester 1 and Period 1of the grant - EURO 142,669. The expenditures of the SRs are in a bigger amount than the disbursed amount, due to the use of funds on the SR's account, disbursed during the previous periods. Variatia dintre suma disbursata si suma cheltuita este formata din motiv ca: 1. In debursari este inclus si bugetul pentru semstrul 2, 2013 si perioada de buffer din 2014 (1 ianuarie-31 martie); 2. Sumele angajate din perioada 1 al grantului si semestrul 1 2013, care vor fi cheltuite pina la sfirsitul anului 2013. Diferența dintre sumele debursate de către RP și cheltuielile subrecipienților este condiționată de disponibilitatea sumelor în contul SR, formate din debursările anterioare.
F2: Budget and actual expenditures by Grant Objective (Bugetul și cheltuielile actuale după Obiectivele Grantului) - in (€) Report Period(Perioada de Raportare): P11 |  |  |  | F4: Latest PR reporting and disbursement cycle (Ultima perioadă de raportare și debursare a RP) Report Period(Perioada de Raportare): P11
Comments: | All expenditures were done according to the planned budget and in line with the project activities. Some of funds from period 1 were saved due to a cost-efficiency in utilization of funds. Toate cheltuielile au fost efectuate conform bugetului si, cu scopul de a atinge obiectivele proiectului. A fost posibil de economisit anumite fonduri din Perioada 1 datorita eficientizarii costurilor programate. |  |  | Comments: | The PR always makes the disbursements to SRs in the shortest period when the disbursement request is received and the report is presented. Perioada de debursare către SR este cit mai operativ posibil de la data depunerii cererii de debursare şi prezentare a raportului financiar.
Last fund disbursement: Calendar days
[6 empty] | Expected (days) | Actual (days)
|  |  |  | Days taken to submit final PU/DR to LFA (Zile necesare pentru remiterea PU/DR final către ALF) |  | 45 | 44
|  |  |  | Days taken for disbursement to reach PR (Zile necesare pentru debursare către RP) |  | 45 | 99
|  |  |  | Days taken for disbursement to reach SRs (Zile necesare pentru debursare către SR) |  | 20 | 5
Menu

## Management
Dashboard: Moldova - TB
Round 9 | Phase 2 |  |  |  |  | Report Period(Perioada de Raportare): |  | P11
Latest Rating (Ultimul Rating): | A1 |  | PAS Center |  |  | From(De la): |  | 2013-01-01
|  | Empowerment of people with TB and Communities in Moldova |  |  |  |  | To(Pînă la): | 2013-06-30
Management Indicators
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) (Statutul Condițiilor Precedente și a Acțiunilor Prestabilite în Timp) Report Period(Perioada de Raportare): P11 |  |  |  | M2: Status of key PR management positions (Statutul pozițiilor cheie a RP) Report Period(Perioada de Raportare): P11
Comments: | One Condition Precedent (CP), prior to grant agreement signing, was fulfilled by PAS Center, received NO from GF. The other two CP are on implimentation stage: review of the NTP in written form by 15th august 2013 and present of the strategic plan for out-patient care to improve compliance and reduce treatment default by 15th august 2013. The mission of the WHO were held in February, 2013. The final draft of the report was prepared and shared for comments. The final version of the report is expected by end of September 2013. Based on the key findings and recommendations discussed with the MoH, NTP and partners, at the end of the mission, there was developed the strategic plan for improving treatment compliace and reducing treatment defaulting. The updated final version of the Plan was sent to the Ministry of Health for approval ( letter of TB Institute # 01-2/799 dated July 18, 2013). The PR prior to extension of the grant agreement, presented to TGF information note on progress of implimentation of two CP and are pending to be approved. Centrul PAS a implementat cerinta inaintată de Fondul Global vizavi de conditii precedente( CP), inainte de semnarea acordului de grant, avînd NO de la FG. Celelalte doua CP, inaintate de catre FG sunt la etapa de implimentare: raportul de evaluare a Programului National de Control al Tuberculozei ( PNCT) si planul strategic pentru imbunatatirea aderentei la tratament si micsorarea abandonului la tratamentul in conditii de ambulatoriu. Misiunea OMS a fost organizata in Februarie 2013. Proiectul de raport a fost expediat pentru comentarii partenerilor. Varianta finala a raportului este programata pentru sfirsit de Septembrie 2013. In baza recomandarilor misiunii OMS identificate si prezentate Ministerului Sanatatii si PNCT, a fost elaborat planul strategic pentru imbunatatirea aderentei la tratament si micsorarea abandonului la tratamentul in conditii de ambulatoriu. Planul a fost prezentat MS spre aprobare ( scrisoarea IFP # 01-2/799 Iulie 18, 2013). PR a prezentat o nota de informare in termenul stabilit in accordul cu FG, inainte de semnarea acordului de prelungire a grantului, si sint in asteptarea aprobarii. |  |  | Comments: | All key positions of the management department are filled in by the PR. Toate functiile sunt completate de RP.
M3: Contractual arrangements (SRs) (Aranjamente contractuale (SR)) Report Period(Perioada de Raportare): P11 |  |  |  | M4: Number of complete reports received on time (Numărul rapoartelor complete recepționate la timp) Report Period(Perioada de Raportare): P11
Comments: | Soros Moldova Foundation was not assessed due to its proved experience in grants' implementation. Fundația Soros-Moldova nu a fost evaluată ținînd cont de semnificativa experiență în implementarea granturilor. |  |  | Comments: | For the reported period, January-June 2013, 8 SSRs were involved in TB related activities, from which one ("Socio-Medical Programs" from Bender) is acting as SSR for two SRs - Soros Foundation Moldova and NGO "AFI". Basically , the majority of NGO are implementing one grant, with exception of two NGOs which applied to Soros Foundation - Moldova and were granted with more than one grant, as follow: NGO "AFI" - 3 grants, and NGO "National Association of TB patients SMIT" - 2 grants. In perioada de raportare, ianuarie-iunie 2013, 8 sub-subrecipienți au realizat activități conexe programului de control al TB, din care o organizație (ONG Programe Medico - Sociale) este în calitate de subsub recipient pentru doi SR: Fundația Soros - Moldova și ONG "AFI". Majoritatea ONG realizeaza a cîte un grant, excepție fiind 2 ONG care au aplicat către Fundația Soros - Moldova, și au fost aprobate pentru implementarea a mai mult de un grant cum ar fi: ONG AFI - 3 granturi și ONG SMIT - 2 granturi.
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals (Bugetul și Procurarea produselor medicale, echipamentului medical, medicamentelor și produselor farmaceutice ) |  |  |  | M6: Difference between current and safety stock (Diferență între stocul curent și stocul de siguranță) Report Period(Perioada de Raportare): P11
Comments: |  |  |  | Comments:
|  |  |  | Component | Products | Stock level expressed in months of treatment for all current patients | Months of safety stock | Difference between current stock and safety stock
|  |  |  | TB | Please Select |  | 0
[5 empty] | Please Select |  | 0
[5 empty] | Please Select |  | 0
[5 empty] | Please Select |  | 0
* Includes only EFR category 4 and 5 (Health products and health equipment & Medicines and Pharmaceuticals) (* Include numai EFR categoriile 4 și 5 (Produse medicale și Echipamente medicale & Medicamente și Produse farmaceutice))
Menu

## Programatic
Dashboard: Moldova - TB
Round 9 | Phase 2 | [8 empty] | Report Period(Perioada de Raportare): |  | P11
Latest Rating (Ultimul Rating): | A1 |  | PAS Center | [7 empty] | From(De la): | 2013-01-01
|  | Empowerment of people with TB and Communities in Moldova | [8 empty] | To(Pînă la): | 2013-06-30 | [7 empty] | Raiting |  | Valor
Programmatic Indicators
Number of TB patients registered under DOTS program who are receiving incentives and enablers to improve their treatment adherence (Numărul pacienților noi înregistrați în programul DOTS, care au beneficiat de suport motivațional pentru a spori aderența la tratament ) |  |  |  | Number and percentage of MDR-TB patients registered under DOTS program who are receiving incentives and enablers for improved treatment compliance (Numărul de pacienți cu MDRTB înregistrați în tratamentul DOTS Plus care au beneficiat de suport motivațional pentru a spori aderența la tratament) |  |  |  | Number of volunteers, members of multidisciplinary teams and NGOs representatives trained in TB community aspects(Numarul de voluntari, membri din echipele multidisciplinare, reprezentanti ai ONG-lor insruiti în aspecte DOT și controlul tuberculozei la nivel de comunitate)
Comment: P1 | During S5, 1237 TB patients registered under DOTS program received incentives for improved treatment compliance from the total number of 2085 TB patients in ambulatory phase under treatment.The indicator is overachieved. (Pe parcursul semestrului5, 1237 pacienți cu TB înregistrați în programul DOTS au primit suport motivational pentru îmbunătățirea aderentei la tratamentul din numărul total de 2085 pacienţi cu TB în faza de ambulator. Indicatorul este supra îndeplinit). |  |  | Comment: P2 | During the first half of 2013, 288 MDR-TB patients were received incentives for improved treatment compliance from the total number of 335 patients with MDR-TB in ambulatory phase under treatment. The indicator is achieved. (În prima jumatate a anului 2013, 288 de pacienţi MDR-TB au primit suport motivational pentru îmbunătățirea aderentei tratamentului din numărul total de 335 pacienţi MDR-TB în faza de ambulator. Indicatorul este realizat). |  |  | Comment: P3 | A total of 85 persons were trained, from them: 29 people from multidisciplinary teams of the community center; 23 people from NGOs in DOT and TB community aspects and 33 volunteers trained from the NGOs network in TB community aspects. (Un total de 85 de persoane au fost instruiţi, dintre care: 29 de persoane din echipele multidisciplinare din centrul comunitar; 23 de persoane din ONG-uri şi 33 voluntari din reţeaua de ONG-uri).
Indicators |  |  | Target | Achieved | 0% - 59% | 60% - 89% | > 90% | Comments |  |  |  |  | min | 0 | 30% | 60% | 90% | 100% |  | min | 0 | 20% | 40% | 60% | 80%
Number of TB patients registered under DOTS program who are receiving incentives and enablers to improve their treatment adherence (Numărul pacienților noi înregistrați în programul DOTS, care au beneficiat de suport motivațional pentru a spori aderența la tratament ) |  |  | 1125 | 1237 | 110% |  |  | During S5, 1237 TB patients registered under DOTS program received incentives for improved treatment compliance from the total number of 2085 TB patients in ambulatory phase under treatment.The indicator is overachieved. (Pe parcursul semestrului5, 1237 pacienți cu TB înregistrați în programul DOTS au primit suport motivational pentru îmbunătățirea aderentei la tratamentul din numărul total de 2085 pacienţi cu TB în faza de ambulator. Indicatorul este supra îndeplinit). |  |  |  |  | max | 30% | 60% | 90% | 100% | 200% |  | max | 20% | 40% | 60% | 80% | 100%
Number and percentage of MDR-TB patients registered under DOTS program who are receiving incentives and enablers for improved treatment compliance ( Numărul de pacienți cu MDRTB înregistrați în tratamentul DOTS Plus care au beneficiat de suport motivațional pentru a spori aderența la tratament) |  |  | 285 | 288 | 101.1% |  |  | During the first half of 2013, 288 MDR-TB patients were received incentives for improved treatment compliance from the total number of 335 patients with MDR-TB in ambulatory phase under treatment. The indicator is achieved. (În prima jumatate a anului 2013, 288 de pacienţi MDR-TB au primit suport motivational pentru îmbunătățirea aderentei tratamentului din numărul total de 335 pacienţi MDR-TB în faza de ambulator. Indicatorul este realizat). | [5 empty] | de 0 a 0.3 | de 0.3 a 0.6 | de 0.6 a 0.9 | de 0.9 a 1 | de 1 a 2 | Rating | Valor | de 0 a 0.2 | de 0.2 a 0.4 | de 0.4 a 0.6 | de 0.6 a 0.8 | de 0.8 a 1
Number of volunteers, members of multidisciplinary teams and NGOs representatives trained in TB community aspects (Numarul de voluntari, membri din echipele multidisciplinare, reprezentanti ai ONG-lor insruiti în aspecte DOT și controlul tuberculozei la nivel de comunitate) |  |  | 80 | 85 | 106.2% |  |  | A total of 85 persons were trained, from them: 29 people from multidisciplinary teams of the community center; 23 people from NGOs in DOT and TB community aspects and 33 volunteers trained from the NGOs network in TB community aspects. (Un total de 85 de persoane au fost instruiţi, dintre care: 29 de persoane din echipele multidisciplinare din centrul comunitar; 23 de persoane din ONG-uri şi 33 voluntari din reţeaua de ONG-uri). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
The default rate among New TB Cases in Community Centers (Rata abandonurilor cazurilor noi de TB în cadrul centrelor comunitare) |  |  | n/a | n/a | 0% |  |  | The indicator will be reported on the next reported period. (Indicatorul va fi raportat în următoarea perioadă de raportare). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number of new TB patients in ambulatory phases provided with DOT support by the community (Numărul pacienților noi cu TB aflați în faza de ambulator care au beneficiat de suportul DOT în cadrul centrelor comunitare) |  |  | 337 | 313 | 92.88% |  |  | 313 of new TB patients provided with DOT by the community (community centers and NGOs) received at least 25 DOT interventions during 1 month (visit to DOT center by the patient or visit to the patient by DOT supporters for drug intake). The indicator is achieved in proportion of 93%. Reason for variance: AO AFI included and registered all the new TB patients provided in lists by Community Centers. (313 pacienţi noi cu TB au fost acoperiți cu servicii de către centrele comunitate, primind cel puţin 25 intervenţii DOT pe parcursul la o luna (vizite la centrul de DOT de către pacient sau vizite la pacient de suporterii DOT pentru administrarea medicamentelor). Indicatorul este realizat în proporţie de 93%. Motivul pentru variaţie este explicat prin faptul că toți pacienții noi raportați au fost incluși în listele centrelor comunitare). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number of people (TB,TB/HIV patients and their families) reached by peer support groups (Numarul de persoane (pacienți TB,TB/HIV și familiile lor) care au fost instruiti de către grupurile de la egal la egal) |  |  | 200 | 200 | 100% |  |  | During S5, 200 people (TB/HIV patients and their families) were reached by peer support groups. The indicator is achieved. (În timpul S5, 200 de persoane (TB/HIV pacienţii şi familiile lor) au beneficiat de suport de la egal la egal. Indicatorul este atins). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Number of peer educators, journalists at national and district level and local stakeholders trained in TB and TB/HIV issues (Numarul de educatori de la egal la egal, jurnaliști la nivel național și regional, persoane-cheie din republică instruiți in TB și TB/HIV) |  |  | 135 | 758 | 561.5% |  |  | A total of 758 persons were trained, from them: 587 of local stakeholders attending workshops on TB and TB/HIV and 171 of peer educators trained to carry out informational work on TB; The planned indicator is overachieved because of number of requests addressed to the PAS Center from different organizations and institutions during and after public awareness campaign in March- May 2013. Keeping in mind that community and decision makers involvement in TB control is one of the most important goal of the project, PAS Center organized 2 additional round tables in Chisinau on request of and in collaboration with Center of Public Health Chisinau, another 1 in Chisinau in collaboration with NGO "Viata Noua" and 2 in Balti, on the request of the department of education. All additional round tables were organized in the framework of existing budget. At the same time it is necessary to mention that such round tables attracted attention of many people - local leaders and managers - and we cannot limit the number of participants. E.g. - the Center of Public Health Chisinau decided to organize 1 round table - for chiefs of all municipal educational institutions (high schools, gymnasiums etc.). This event was very successful and the head of the Department of education from Chisinau asked to organize the similar round table for managers of kindergartens. As a result of these meetings in most part of educational institutions of Chisinau were organized viewing of short documentaries on TB, informational sessions for parents other informational activities. (Un total de 758 persoane au fost instruite, dintre care: 587 reprezentanți ai autorităților locale au participat la atelier de lucru în TB și TB/HIV și 171 educători de la egal la egal instruiți să efectueze lucrul informațional pe TB; Indicatorii au fost supraîndepliniți din cauza numărului de solicitări adresate Centrului PAS din partea a mai multor organizații și instituții pe parcursul și după campaniea de sensibilizare a opiniei publice din martie-mai 2013. Ţinând cont că comunitatea şi implicarea factorilor de decizie în controlul TB este unul dintre cel mai important obiectiv al proiectului, Centrul PAS a organizat 2 mese rotunde suplimentare la Chişinău la cererea şi în colaborare cu centrul de sănătate publică din Chisinau, un alt eveniment organizat în Chişinău în colaborare cu ONG "Viata Noua" şi 2 în Balt, la solicitarea Departamentului de educaţie. Toate mesele rotunde suplimentare au fost organizate în cadrul bugetului existent. În acelaşi timp, este necesar să se menţioneze că aceste mese rotunde a atras atenţia multor oameni - liderii locali şi manageri - astfel nefiind posibil de a limita numărul de participanţi. Centrul de sănătate publică din Chişinău a decis să organizeze o masă rotunda - pentru şefii din toate instituţiile de învăţământ municipale (licee, gimnazii etc.). Acest eveniment a avut un mare succes. Seful Departamentului de educaţie din Chişinău a cerut permisiunea pentru organizarea unei mese rotunde similare pentru managerii de gradinite. Ca urmare a acestor întâlniri în cea mai mare parte a instituţiilor de învăţămînt din Chişinău au fost organizate vizualizari scurte a filmului documentar despre TB, sesiuni de informare pentru parinti precum și alte activităţi informative. | [5 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
Number of TB service staff trained in DR-TB management (Numarul de personal din serviciu TB instruiti in managementul TB-MDR) |  |  | 25 | 115 | 460% |  |  | A total of 115 ( 24+91) TB service staff trained in DR-TB management. The 3 days training was splited into two events with approval of the GF due to request of director of WHO Collaborating Center for TB and Lung Diseases to do one common event in Moldova on DRTB management. Thus two days training on DRTB management at ambulatory level was attended by 25 participants covering all matters related to management of DRTB at ambulatory level. One day was dedicated for organization of the conference on DRTB management. By the executive order of MoH was approved the list with 80 participants at the conference. Since the venue for the conference was the TB Institute, organized with participation of the international experts in TB, the administration requested to allow participation of more specialists from the TB institute to use the opportunity to communicate directly with experts. (Un total de 115 (24+91) persoane din serviciu TB au fost instruiți în managementul TB-MDR. Cursul de 3 zile a fost separat în 2 evenimente cu aprobarea FG în baza cererii directorul Centrului de colaborare OMS pentru TB şi boli pulmonare pentru a face un eveniment comun în Moldova pe DR-TB management. Astfel două zile de formare pe management DR-TB la nivel de ambulator, au participat 25 de participanţi care acoperă toate aspectele legate de gestionarea a DR-TB la nivel de ambulator. O zi a fost dedicată pentru organizarea conferinţei DR-TB management. Ordinul MS a aprobat lista cu 80 de participanţi la conferinţă. Conferința a avut loc la Institutul de TB, cu participarea unor experti internationali în TB, administraţia a solicitat să se permită participarea a mai mulți specialisi de la Institutul de TB ca să folosească ocazia pentru a comunica direct cu experţii. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Percentage of released prison inmates on TB treatment supported through the TB treatment follow-up program (Procentul de deţinuţi înrolați în tratamentul TB și susţinuți prin programul tratamentului TB de follow-up) |  |  | 0.95 | 1 | 105.3% |  |  | During the first half of 2013, 12 eligible prison inmates on TB treatment were released. All of them were supported through the TB follow up program. (In prima jumatate anului 2013, au fost eliberați 12 deţinuţi aflați în tratamentul TB. Toți aceștia au fost susţinuți prin programul tratamentului TB de follow-up). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Number of PHC staff trained in TB case management, community TB care issues and methods of informational work with different groups of population (Numărul de lucrători medicali instruiți în managementul de caz, probleme de îngrijire comunitară, lucru informaţional cu diferite grupuri de populaţie) |  |  | 24 | 50 | 48% |  |  | The events are projected to be organized in partnership with the State Medical and Pharmaceutical University and Medical College. The schedule of the continue education courses at the University were preponderantly programmed for the autumn period. The SR had to organize new tenders for selection companies for logistic issues ( office suppliers, for food delivery etc. ) required for trainings programme planned for the second period of the grant( 2013-2015), which took time at the beginning of the year from the logistic aspect . Thereby the SR did not succeed to interfere one training course with the continue education programme of the Medical Colleges. The training course is transferred for the fall,2013. (Instruirile sunt planificate să fie organizate în parteneriat cu Universitatea de Stat de Medicină și Farmaceutică și cu Colegiul de Medicină. Orarul cursurilor de educare continuă la universitate sunt preponderent programate pentru perioada de toamnă. Tot odata[ SR a avut de organizat tendere noi pentru selectarea companiei de logistică (rechizite, servicii de livrare a alimentației etc), o solicitare pentru organizarea instruirilor planificate pentru perioada a doua a grantului (2013-2015). Tenderul a avut loc la inceputul anului în programul de educare continua în cadrul Colegiului de Medicină. Instruirile sunt transferate pentru toamnă, 2013). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Menu

## Recomandari
Dashboard: Moldova - TB
Round 9 | Phase 2 |  |  |  |  | Report Period(Perioada de Raportare): | P11
Latest Rating (Ultimul Rating): | A1 |  | PAS Center |  |  | From(De la): | 2013-01-01
|  |  | Empowerment of people with TB and Communities in Moldova |  |  | To(Pînă la): | 2013-06-30
Recommendations
Are all funds reaching implementation levels and being spent according to budget?
Financial |  | Summary Comments |  |  | Recommendations
F1 |  | Cumulative disbursements is more than cumulative budget (first semester 2013), due to the fact that disbursement includes the budget for the second semester of 2013 and for the first quarter of 2014 (buffer period). Suma debursarilor este mai mare decit suma bugetata, deoarece suma bugetata reflecta bugetul pina la 30 iunie 2013, iar in debursari este inclus si bugetul pentru semestrul 2, 2013 si perioada de buffer din 2014 (1 ianuarie-31 martie).
F2 |  | All expenditures were done according to the planned budget and in line with the project activities. Some of funds from period 1 were saved due to a cost-efficiency in utilization of funds. Toate cheltuielile au fost efectuate conform bugetului si, cu scopul de a atinge obiectivele proiectului. A fost posibil de economisit anumite fonduri din Perioada 1 datorita eficientizarii costurilor programate.
F3 |  | The variance between the disbursement and expenditures of the PR for the current period is due to: 1. Disbursement includes the budget for the second semester of 2013 and for the first quarter of 2014 (buffer period); 2. Commitments from semester 1 and Period 1of the grant - EURO 142,669. The expenditures of the SRs are in a bigger amount than the disbursed amount, due to the use of funds on the SR's account, disbursed during the previous periods. Variatia dintre suma disbursata si suma cheltuita este formata din motiv ca: 1. In debursari este inclus si bugetul pentru semstrul 2, 2013 si perioada de buffer din 2014 (1 ianuarie-31 martie); 2. Sumele angajate din perioada 1 al grantului si semestrul 1 2013, care vor fi cheltuite pina la sfirsitul anului 2013. Diferența dintre sumele debursate de către RP și cheltuielile subrecipienților este condiționată de disponibilitatea sumelor în contul SR, formate din debursările anterioare.
F4 |  | The PR always makes the disbursements to SRs in the shortest period when the disbursement request is received and the report is presented. Perioada de debursare către SR este cit mai operativ posibil de la data depunerii cererii de debursare şi prezentare a raportului financiar.
Are procurement and hiring on schedule?
Management |  | Summary Comments |  |  | Recommendations
M1 |  | One Condition Precedent (CP), prior to grant agreement signing, was fulfilled by PAS Center, received NO from GF. The other two CP are on implimentation stage: review of the NTP in written form by 15th august 2013 and present of the strategic plan for out-patient care to improve compliance and reduce treatment default by 15th august 2013. The mission of the WHO were held in February, 2013. The final draft of the report was prepared and shared for comments. The final version of the report is expected by end of September 2013. Based on the key findings and recommendations discussed with the MoH, NTP and partners, at the end of the mission, there was developed the strategic plan for improving treatment compliace and reducing treatment defaulting. The updated final version of the Plan was sent to the Ministry of Health for approval ( letter of TB Institute # 01-2/799 dated July 18, 2013). The PR prior to extension of the grant agreement, presented to TGF information note on progress of implimentation of two CP and are pending to be approved. Centrul PAS a implementat cerinta inaintată de Fondul Global vizavi de conditii precedente( CP), inainte de semnarea acordului de grant, avînd NO de la FG. Celelalte doua CP, inaintate de catre FG sunt la etapa de implimentare: raportul de evaluare a Programului National de Control al Tuberculozei ( PNCT) si planul strategic pentru imbunatatirea aderentei la tratament si micsorarea abandonului la tratamentul in conditii de ambulatoriu. Misiunea OMS a fost organizata in Februarie 2013. Proiectul de raport a fost expediat pentru comentarii partenerilor. Varianta finala a raportului este programata pentru sfirsit de Septembrie 2013. In baza recomandarilor misiunii OMS identificate si prezentate Ministerului Sanatatii si PNCT, a fost elaborat planul strategic pentru imbunatatirea aderentei la tratament si micsorarea abandonului la tratamentul in conditii de ambulatoriu. Planul a fost prezentat MS spre aprobare ( scrisoarea IFP # 01-2/799 Iulie 18, 2013). PR a prezentat o nota de informare in termenul stabilit in accordul cu FG, inainte de semnarea acordului de prelungire a grantului, si sint in asteptarea aprobarii.
M2 |  | All key positions of the management department are filled in by the PR. Toate functiile sunt completate de RP. | #DIV/0! | #DIV/0!
M3 |  | Soros Moldova Foundation was not assessed due to its proved experience in grants' implementation. Fundația Soros-Moldova nu a fost evaluată ținînd cont de semnificativa experiență în implementarea granturilor.
M4 |  | For the reported period, January-June 2013, 8 SSRs were involved in TB related activities, from which one ("Socio-Medical Programs" from Bender) is acting as SSR for two SRs - Soros Foundation Moldova and NGO "AFI". Basically , the majority of NGO are implementing one grant, with exception of two NGOs which applied to Soros Foundation - Moldova and were granted with more than one grant, as follow: NGO "AFI" - 3 grants, and NGO "National Association of TB patients SMIT" - 2 grants. In perioada de raportare, ianuarie-iunie 2013, 8 sub-subrecipienți au realizat activități conexe programului de control al TB, din care o organizație (ONG Programe Medico - Sociale) este în calitate de subsub recipient pentru doi SR: Fundația Soros - Moldova și ONG "AFI". Majoritatea ONG realizeaza a cîte un grant, excepție fiind 2 ONG care au aplicat către Fundația Soros - Moldova, și au fost aprobate pentru implementarea a mai mult de un grant cum ar fi: ONG AFI - 3 granturi și ONG SMIT - 2 granturi.
M5
M6
Are technical targets being achieved?
Programmatic |  | Summary Comments |  |  | Recommendations
P1 - trend |  | During S5, 1237 TB patients registered under DOTS program received incentives for improved treatment compliance from the total number of 2085 TB patients in ambulatory phase under treatment.The indicator is overachieved. (Pe parcursul semestrului5, 1237 pacienți cu TB înregistrați în programul DOTS au primit suport motivational pentru îmbunătățirea aderentei la tratamentul din numărul total de 2085 pacienţi cu TB în faza de ambulator. Indicatorul este supra îndeplinit).
P2 - trend |  | During the first half of 2013, 288 MDR-TB patients were received incentives for improved treatment compliance from the total number of 335 patients with MDR-TB in ambulatory phase under treatment. The indicator is achieved. (În prima jumatate a anului 2013, 288 de pacienţi MDR-TB au primit suport motivational pentru îmbunătățirea aderentei tratamentului din numărul total de 335 pacienţi MDR-TB în faza de ambulator. Indicatorul este realizat).
P3 - trend |  | A total of 85 persons were trained, from them: 29 people from multidisciplinary teams of the community center; 23 people from NGOs in DOT and TB community aspects and 33 volunteers trained from the NGOs network in TB community aspects. (Un total de 85 de persoane au fost instruiţi, dintre care: 29 de persoane din echipele multidisciplinare din centrul comunitar; 23 de persoane din ONG-uri şi 33 voluntari din reţeaua de ONG-uri).
P1 |  | During S5, 1237 TB patients registered under DOTS program received incentives for improved treatment compliance from the total number of 2085 TB patients in ambulatory phase under treatment.The indicator is overachieved. (Pe parcursul semestrului5, 1237 pacienți cu TB înregistrați în programul DOTS au primit suport motivational pentru îmbunătățirea aderentei la tratamentul din numărul total de 2085 pacienţi cu TB în faza de ambulator. Indicatorul este supra îndeplinit).
P2 |  | During the first half of 2013, 288 MDR-TB patients were received incentives for improved treatment compliance from the total number of 335 patients with MDR-TB in ambulatory phase under treatment. The indicator is achieved. (În prima jumatate a anului 2013, 288 de pacienţi MDR-TB au primit suport motivational pentru îmbunătățirea aderentei tratamentului din numărul total de 335 pacienţi MDR-TB în faza de ambulator. Indicatorul este realizat).
P3 |  | A total of 85 persons were trained, from them: 29 people from multidisciplinary teams of the community center; 23 people from NGOs in DOT and TB community aspects and 33 volunteers trained from the NGOs network in TB community aspects. (Un total de 85 de persoane au fost instruiţi, dintre care: 29 de persoane din echipele multidisciplinare din centrul comunitar; 23 de persoane din ONG-uri şi 33 voluntari din reţeaua de ONG-uri).
P4 |  | The indicator will be reported on the next reported period. (Indicatorul va fi raportat în următoarea perioadă de raportare).
P5 |  | 313 of new TB patients provided with DOT by the community (community centers and NGOs) received at least 25 DOT interventions during 1 month (visit to DOT center by the patient or visit to the patient by DOT supporters for drug intake). The indicator is achieved in proportion of 93%. Reason for variance: AO AFI included and registered all the new TB patients provided in lists by Community Centers. (313 pacienţi noi cu TB au fost acoperiți cu servicii de către centrele comunitate, primind cel puţin 25 intervenţii DOT pe parcursul la o luna (vizite la centrul de DOT de către pacient sau vizite la pacient de suporterii DOT pentru administrarea medicamentelor). Indicatorul este realizat în proporţie de 93%. Motivul pentru variaţie este explicat prin faptul că toți pacienții noi raportați au fost incluși în listele centrelor comunitare).
P6 |  | During S5, 200 people (TB/HIV patients and their families) were reached by peer support groups. The indicator is achieved. (În timpul S5, 200 de persoane (TB/HIV pacienţii şi familiile lor) au beneficiat de suport de la egal la egal. Indicatorul este atins).
P7 |  | A total of 758 persons were trained, from them: 587 of local stakeholders attending workshops on TB and TB/HIV and 171 of peer educators trained to carry out informational work on TB; The planned indicator is overachieved because of number of requests addressed to the PAS Center from different organizations and institutions during and after public awareness campaign in March- May 2013. Keeping in mind that community and decision makers involvement in TB control is one of the most important goal of the project, PAS Center organized 2 additional round tables in Chisinau on request of and in collaboration with Center of Public Health Chisinau, another 1 in Chisinau in collaboration with NGO "Viata Noua" and 2 in Balti, on the request of the department of education. All additional round tables were organized in the framework of existing budget. At the same time it is necessary to mention that such round tables attracted attention of many people - local leaders and managers - and we cannot limit the number of participants. E.g. - the Center of Public Health Chisinau decided to organize 1 round table - for chiefs of all municipal educational institutions (high schools, gymnasiums etc.). This event was very successful and the head of the Department of education from Chisinau asked to organize the similar round table for managers of kindergartens. As a result of these meetings in most part of educational institutions of Chisinau were organized viewing of short documentaries on TB, informational sessions for parents other informational activities. (Un total de 758 persoane au fost instruite, dintre care: 587 reprezentanți ai autorităților locale au participat la atelier de lucru în TB și TB/HIV și 171 educători de la egal la egal instruiți să efectueze lucrul informațional pe TB; Indicatorii au fost supraîndepliniți din cauza numărului de solicitări adresate Centrului PAS din partea a mai multor organizații și instituții pe parcursul și după campaniea de sensibilizare a opiniei publice din martie-mai 2013. Ţinând cont că comunitatea şi implicarea factorilor de decizie în controlul TB este unul dintre cel mai important obiectiv al proiectului, Centrul PAS a organizat 2 mese rotunde suplimentare la Chişinău la cererea şi în colaborare cu centrul de sănătate publică din Chisinau, un alt eveniment organizat în Chişinău în colaborare cu ONG "Viata Noua" şi 2 în Balt, la solicitarea Departamentului de educaţie. Toate mesele rotunde suplimentare au fost organizate în cadrul bugetului existent. În acelaşi timp, este necesar să se menţioneze că aceste mese rotunde a atras atenţia multor oameni - liderii locali şi manageri - astfel nefiind posibil de a limita numărul de participanţi. Centrul de sănătate publică din Chişinău a decis să organizeze o masă rotunda - pentru şefii din toate instituţiile de învăţământ municipale (licee, gimnazii etc.). Acest eveniment a avut un mare succes. Seful Departamentului de educaţie din Chişinău a cerut permisiunea pentru organizarea unei mese rotunde similare pentru managerii de gradinite. Ca urmare a acestor întâlniri în cea mai mare parte a instituţiilor de învăţămînt din Chişinău au fost organizate vizualizari scurte a filmului documentar despre TB, sesiuni de informare pentru parinti precum și alte activităţi informative.
P8 |  | A total of 115 ( 24+91) TB service staff trained in DR-TB management. The 3 days training was splited into two events with approval of the GF due to request of director of WHO Collaborating Center for TB and Lung Diseases to do one common event in Moldova on DRTB management. Thus two days training on DRTB management at ambulatory level was attended by 25 participants covering all matters related to management of DRTB at ambulatory level. One day was dedicated for organization of the conference on DRTB management. By the executive order of MoH was approved the list with 80 participants at the conference. Since the venue for the conference was the TB Institute, organized with participation of the international experts in TB, the administration requested to allow participation of more specialists from the TB institute to use the opportunity to communicate directly with experts. (Un total de 115 (24+91) persoane din serviciu TB au fost instruiți în managementul TB-MDR. Cursul de 3 zile a fost separat în 2 evenimente cu aprobarea FG în baza cererii directorul Centrului de colaborare OMS pentru TB şi boli pulmonare pentru a face un eveniment comun în Moldova pe DR-TB management. Astfel două zile de formare pe management DR-TB la nivel de ambulator, au participat 25 de participanţi care acoperă toate aspectele legate de gestionarea a DR-TB la nivel de ambulator. O zi a fost dedicată pentru organizarea conferinţei DR-TB management. Ordinul MS a aprobat lista cu 80 de participanţi la conferinţă. Conferința a avut loc la Institutul de TB, cu participarea unor experti internationali în TB, administraţia a solicitat să se permită participarea a mai mulți specialisi de la Institutul de TB ca să folosească ocazia pentru a comunica direct cu experţii.
P9 |  | During the first half of 2013, 12 eligible prison inmates on TB treatment were released. All of them were supported through the TB follow up program. (In prima jumatate anului 2013, au fost eliberați 12 deţinuţi aflați în tratamentul TB. Toți aceștia au fost susţinuți prin programul tratamentului TB de follow-up).
P10 |  | The events are projected to be organized in partnership with the State Medical and Pharmaceutical University and Medical College. The schedule of the continue education courses at the University were preponderantly programmed for the autumn period. The SR had to organize new tenders for selection companies for logistic issues ( office suppliers, for food delivery etc. ) required for trainings programme planned for the second period of the grant( 2013-2015), which took time at the beginning of the year from the logistic aspect . Thereby the SR did not succeed to interfere one training course with the continue education programme of the Medical Colleges. The training course is transferred for the fall,2013. (Instruirile sunt planificate să fie organizate în parteneriat cu Universitatea de Stat de Medicină și Farmaceutică și cu Colegiul de Medicină. Orarul cursurilor de educare continuă la universitate sunt preponderent programate pentru perioada de toamnă. Tot odata[ SR a avut de organizat tendere noi pentru selectarea companiei de logistică (rechizite, servicii de livrare a alimentației etc), o solicitare pentru organizarea instruirilor planificate pentru perioada a doua a grantului (2013-2015). Tenderul a avut loc la inceputul anului în programul de educare continua în cadrul Colegiului de Medicină. Instruirile sunt transferate pentru toamnă, 2013).
Menu

## Actions
Dashboard: Moldova - TB
| Round 9 | Phase 2 |  |  |  | Report Period(Perioada de Raportare): |  | P11
| Latest Rating (Ultimul Rating): | A1 |  | PAS Center |  | From(De la): |  | 2013-01-01
|  |  | Empowerment of people with TB and Communities in Moldova |  |  |  | To(Pînă la): | 2013-06-30
Decisions and Actions
What is the overall status of this grant implementation?
| Key Recommendations from Oversight Group(s) |  |  |  | CCM Decision | Due Date | Person Responsible
Current Reporting Period
Actions to Implement / Previous Period
What is the overall status of this grant implementation?
| CCM Decision |  |  |  | Action Taken | Date | Person Responsible
Previous Reporting Period
#REF!
Menu

## Setup (hidden)
Dashboard: Moldova - TB
Set-up = List of validation for Grant Detail page
Component | Currency | Round | Phase | Period | Rating | LFA | Medicaments | Countries
Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select
HIV / AIDS | $ | Round 1 | Phase 1 | P1 | A1 | CA (Crown Agents) | Isoniazid | Afghanistan
MALARIA | € | Round 2 | Phase 2 | P2 | A2 | DEL (Deloitte) | Ethambutol | Albania
TB |  | Round 3 | RCC | P3 | B1 | DTT (DTT Emerging Markets) | Rifampicin | Algeria
HIVAIDS / TB |  | Round 4 |  | P4 | B2 | FIN (Finconsult) | Pyrazimamide | Angola
HSS |  | Round 5 |  | P5 | C | GT (Grant Thornton) | RDT | Argentina
|  | Round 6 |  | P6 |  | H-C (Hodar-Conseil) | NVP | Armenia
|  | Round 7 |  | P7 |  | KPMG (KPMG) | 3TC | Azerbaijan
|  | Round 8 |  | P8 |  | MSCI (MSCI) | D4T | Bangladesh
|  | Round 9 |  | P9 |  | PwC (PricewaterhouseCoopers) | AZT | Belarus
|  | Round 10 |  | P10 |  | STI (Swiss Tropical Institute), | DDI | Belize
|  |  |  | P11 |  | UNOPS | EFV | Benin
|  |  |  | P12 |  |  | AS/LF | Bhutan
[7 empty] | AS/AQ | Bolivia
[7 empty] | AS/MQ | Bosnia and Herzegovina
[7 empty] | Al/Lum | Botswana
Brazil
[7 empty] | TB nutri'l supplements | Bulgaria
[7 empty] | E-PAP | Burkina Faso
Burundi
Cambodia
Cameroon
Cape Verde
Central African Republic
Chad
Chile
China
China
Colombia
Comoros
Congo (Democratic Republic of the)
Congo (Republic of the)
Costa Rica
Cote d'Ivoire
Croatia
Cuba
Djibouti
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Ethiopia
Fiji
Gabon
Gambia
Georgia
Ghana
Global(LWF)
Guatemala
Guinea
Guinea-Bissau
Guyana
Haiti
Honduras
India
Indonesia
Iran (Islamic Republic of)
Iraq
Jamaica
Jordan
Kazakhstan
Kenya
Korea, Democratic Peoples Republic of
Kosovo (Serbia)
Kyrgyzstan
Lao PDR
Lesotho
Liberia
Macedonia, FYR
Madagascar
Malawi
Maldives
Mali
Mauritania
Mauritius
Moldova
Mongolia
Montenegro
Morocco
Mozambique
Multi-country Africa (West Africa Corridor Program)
Multi-country Africa(RMCC)
Multi-country Americas (Andean)
Multi-country Americas (CARICOM)
Multi-country Americas (CRN+)
Multi-country Americas (Meso)
Multi-country Americas (OECS)
Multi-country Americas (REDCA+)
Multi-country Western Pacific
Myanmar
Namibia
Nepal
Nicaragua
Niger
Nigeria
Pakistan
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Romania
Russian Federation
Rwanda
Sao Tome and Principe
Senegal
Serbia
Sierra Leone
Solomon Islands
Somalia
South Africa
Sri Lanka
Sudan
Suriname
Swaziland
Syrian Arab Republic
Tajikistan
Tanzania
Thailand
Timor-Leste
Togo
Tunisia
Turkey
Uganda
Ukraine
UN Theme Group on HIV/AIDS (West Bank and Gaza)
Uzbekistan
Viet Nam
Yemen
Zambia
Zanzibar (Tanzania)
Zimbabwe