## Meniu
Dashboard: Moldova - TB
TB Round 9, Phase 2 | Grant No.(Nr. Grantului): MOL-T-PAS
V1.0
Finance
Programmatic
Management
Select the option you want to see:
Recommendations
Actions
Grant Detail
List of Indicators
Data Entry
Grant Information
Indicators
Reports

## Lista Indicatorilor
Dashboard: Moldova - TB
Financial information
Name: | Definition | Measurement | Data Sources
F1: Budget and disbursements by Global Fund (Bugetul și debursările de către Fondul Global) | Cumulative budget: Sum of the grant budget from period one (quarter, trimester, or semester) of the current phase, up to and including the dashboard reporting period. Cumulative Disbursments by GF: Sum of all the funds transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to and including the dasboard reporting period. | Currency of the grant ($ or Euro) Cumulative – Figures refer to budget and disbursements for all the periods of the phase up to and including the dashboard reporting period | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F2: Budget and actual expenditures by Grant Objective (Bugetul și cheltuielile actuale după Obiectivele Grantului) | Cumulative Budget per Objective: Sum of the grant budget by Objective, from period one of the current phase up to and including the dashboard reporting period. Cumulative Expenditure per Objective: Sum of amounts spent by Objective directly by the PR plus the amounts transferred by the PR to all SRs from the beginning of the phase up to and including dashboard reporting period, by Objective | • Cumulative – Figures refer to budget, disbursements or expenditure for all the periods of the phase up to and including the dashboard reporting period. | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F3:Disbursements and expenditures (Debursări și cheltuieli) | Disbursement by GF: Prior to this Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to but not including dashboard reporting period. Disbursement by GF: Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), during dashboard reporting period. PR disbursements and expenditure: Prior to this Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) up to but not including dashboard reporting period. PR disbursements and expenditure: Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) during dashboard reporting period. Disbursements to SRs: Prior to this Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), up to but not including dashboard reporting period. Disbursements to SRs:Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), in dashboard reporting period. SR expenditures: Prior to this Reporting period: The sum of all expenditures reported by the SRs, up to but not including dashboard reporting period. SR expenditures: Reporting period: The sum of all expenditures reported by the SRs, during dashboard reporting period. | Currency of the grant ($ or Euro) • Reporting period – Figures refer to budget, disbursements or expenditure for the reporting period to which the dashboard refers. • Prior to reporting period - Figures refer to the total budget, disbursements or expenditure for all the periods before but not including the current period. | PU/DR; PR data: SR reports to PR
F4: Latest PR reporting and disbursement cycle (Ultima perioadă de raportare și debursare a RP) | Days taken to submit final PU/DR to LFA – This indicator measures the number of calendar days it took the PR to send a final Performance Update and Disbursement Request (PU/DR) to the LFA after the end of the period. A 'final' PU/DR would be one for which the LFA did not require any further clarifications from the PR. The expected value is 45 days from the end of the period, as defined in the Grant Agreement. The actual value is the number of calendar days from the end date of the period to the date on which the PR sent to the LFA the final PU/DR. Days taken for disbursement to reach PR – This indicator measures the number of calendar days it took the Global Fund to send the latest disbursement to the PR's account after receipt of the acceptable PU/DR by the LFA. The expected number is 45 days. The actual number is the number of days from the date of transmission by the PR to the LFA of the acceptable PU/DR to the date the disbursement is received by the PR at its bank. Days taken for disbursement to reach SRs – This indicator measures the average number of days for disbursements to be made to all the SRs. The expected value for this indicator will be set locally by the PR and SRs, preferably in the Grant Operations Manual. The actual value is the average of the number of days from the receipt of the funds from the GF by the PR to the date the funds are received by each SR. Different SRs coudl receive funds on different dates and this indicator is the average across all SRs for the latest disbursement. | Number of calendar days; it refers only to reporting period for which the latest disbursement was received and is not cumulative | PR, LFA, GF emails and records; bank notification document or the notice of receipt by the PR to GF; SR reports to PR based on bank records
Management Information
Name: | Definition | Measurement | Data Source
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) (Statutul Condițiilor Precedente și a Acțiunilor Prestabilite în Timp) | Number of Conditions Precedent (CPs) and Time Bound Actions (TBAs ) fulfilled, or unfulfilled. Within the Unfulfilled category, we distinguish between those CPs and TBAs whose deadline has not passed and those for which the deadline has passed. | Number, cumulative to the dashboard reporting period. Number of fulfilled CPs and/or TBAs plus unfulfilled CPs and/or TBAs should equal the total number set by the Global Fund on the grant | PR records; Grant Performance Reports;
M2: Status of key PR management positions (Statutul pozițiilor cheie a RP) | Number of PR grant management positions planned currently filled or vacant. Full time equivalents of the managerial positions that are on the organizational chart (or otherwise planned) and directly responsible for ensuring grant implementation at the PR, and lead SRs (if necessary). This will include new hires, current staff who are assigned to work on the grant’s management, as well as any staff seconded from other divisions or partner organizations. | Number, in current reporting period | PR records
M3: Contractual arrangements (SRs) (Aranjamente contractuale (SR)) | Identified: Total number of potential SRs identified by the PR for the phase. Assessed: Total number of potential SRs assessed by the PR to determine whether they qualify to function as SRs for the grant. Approved: Total number of SRs that have been approved. Signed: Total number of SRs that have signed agreements/contracts with the PR under the grant. Receiving funding: Total number of SRs that are getting funds and/or supplies from the PR. Numbers of SRs Identified, Assessed, Approved, Signed and Receiving funds are cumulative for the phase, with the following exceptions: If an SR does not need new approval in Phase II, then approval in Phase I is counted. If an SR was signed in a previous Phase but is not working in the current Phase, that SR is no longer counted in Identified, Assessed, Approved. | Number, cumulative to the reporting period. A SR is an institution or program with its own workplan, budget and performance targets. | PR records; Sub-agreements/MOUs; CCM records
M4: Number of complete reports received on time (Numărul rapoartelor complete recepționate la timp) | The total number of periodic reports with up-to-date financial, management and performance (programmatic) data received by the PR from SRs and by SRs from the SubSRs (SSRs) by the expected date. A 'complete' report is one that contains all the data that the PR requires for the PU/DR. The expected date would be set by the PR in the sub-agreements. | Number of reports received. The figure reflects only the period of reporting; it is not cumulative. | PR and SR records
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals (Bugetul și Procurarea produselor medicale, echipamentului medical, medicamentelor și produselor farmaceutice ) | This indicator measures the budget approved for the current phase of the grant for purchase of health products and equipment and pharmaceuticals and medicines (categories 4 and 5 in the new Enhanced Financial Report), and the cumulative amounts of financial obligations and expenditures up to the dashboard reporting period. Budget approved: Total approved budget for purchases (categories 4 and 5) for the entire phase of the grant. It does not include the amounts for fees, management, operational costs, etc. Cumulative Obligations: Total of all order(s) placed and monies committed for these purchases by the PR up to and including the dashboard reporting period. Ideally, by the end of the Phase, budget should equal obligations. Cumulative expenditure: Total of actual Expenditures on category 4 and 5 up to and including the dashboard reporting period (whether paid by PR or authorized to be paid by another entity like GF or other). | Currency of the grant ($ or Euro) | Grant agreement approved budget (for categories 4 and 5 of Enhanced Finance Reporting in current phase); and PR financial data (for expenditures), and/or PSM unit (for orders placed and funding committed or obligated).
Note: Category 6 of the EFR will not be considered as part of the budget for pharmaceuticals. Category 6 has several expenditures that are difficult to disaggregate or quantify, such as warehousing costs, distribution costs (particularly when distibution is done by MOHs), and others that are related to operational costs of the PSM component.
M6: Difference between current and safety stock (Diferență între stocul curent și stocul de siguranță) | This indicator is a snapshot of the difference between the current (or last month) stock level of a specific product (medicine in single, fixed-dose combination, bednets, diagnostic kits, etc.) of a particular dose, expressed in monthly needs (number of months of treatment available) for all patients in the program, and the safety or buffer stock (also expressed in months) as established by the disease program, warehouse system or essential drugs program, for the particular product and dosage. The table will show the difference in months in colors: • RED: when the difference is negative or 0, showing that months of existing stock are lower than or equal to what has been established as months of safety stock • YELLOW: when we have more than the level of safety stock (>0) but less than 3 months (+3). • GREEN: when the difference is between 3 and 18 months. • VIOLET: When the difference shows that the level above the safety stock is greater than or equal to 18 months indicating a potential overstock) problem. For a full description of how this indicator is calculated, please see the User’s Manual. | Number of months | PR records: Warehouse data.
Programmatic Indicators (from Performance Framework) // Indicatori programatici
Indicator | Definiție (din planul M&E,pentru perioada 2) | Measurement | Data Source (Sursa datelor)
The default rate among New TB Cases in Community Centers | Numerator: Number of default cases among new smear-positive pulmonary TB patients registered for tratment in a given year in community TB centers. Denominator: Total number of new cases registered for treatment in the same specified period in community TB centers. Actual absolute figures for numerator and deniminator will be provided with the report. | Numerator: Number of default cases among new smear-positive pulmonary TB patients registered for tratment in a given year in community TB centers. Denominator: Total number of new cases registered for treatment in the same specified period in community TB centers. Actual absolute figures for numerator and deniminator will be provided with the report. | Program reports
Number of volunteers, members of multidisciplinary teams and NGOs representatives trained in TB community aspects | Targets refer to the number of persons/contacts trained, assuming that the same persons might attend more than one training. Volunteers from the NGO network, representatives of the NGOs and of the multidisciplinary teams of the community centres, including local public authorities, will be trained in DOT and TB community aspects.Composite indicator, related activities 2.2.4; 2.3.2; 2.3.3 | All persons who attended the course not less than 80% and signed the list of participation at training | Training records and SR reports
Number of new TB patients in ambulatory phases provided with DOT support by the community |  | Patient is considered "reached" if he/she receives at least 25 DOT interventions during 1 month. | TB patient register and SR reports
Number of people (TB,TB/HIV patients and their families) reached by peer support groups | Targets refer to number of patients with TB,TB/HIV coinfection, drug users and their families, etc. reached by peer educators. The aim of this activity is to improve the adherence to TB treatment, prevent the defaults, inform the beneficiaries about the referral system in the country and to advocate for TB control problems among vulnerable population. The peer educators are the former TB patients, PLWHA, medical personnel and others, who have willingness and capacity to work in the area of TB.Related activity: 2.4.2 | New persons who received services during the reported period | Register of people reached and SR reports
Number of peer educators, journalists at national and district level and local stakeholders trained in TB and TB/HIV issues | Peer educators will be trained to carry out informational work on TB; journalists at national and district level will be trained in TB communications; and the local stakeholders (representatives of the civil society and NGOs, Local Public Administrations in rayons, personnel of the Centre of Preventive Medicine, hospitals' administrators, representatives of the PHC institutions and teaches from schools and colleges) will be trained in TB and TB/HIV issues. Composite indicator, related activities 2.5.1; 2.6.4 & 2.6.7. | All persons who attended the course not less than 80% and signed the list of participation at training | Training records
Number of TB service staff trained in DR-TB management | Indicator refers to trainings of TB service staff from in- and out-patient treatment delivery sites, covering both civilian and penitentiary sectors.Related activiti: 3,3,2 | All persons who attended the course not less than 80% and signed the list of participation at training | Training records
Number and percentage of MDR-TB patients registered under DOTS program who are receiving incentives and enablers for improved treatment compliance | Each patient will receive at least four food packages per month. Related activity: 3,2,4 Numerator:Number of patients with MDR TB in ambulatory phase received incentives and enablers for improved treatment compliance Denominator Total Number of patients with MDR TB in ambulatory phase under treatment | All patients who receive at least three food packages per month. | TB patient register and SR reports
Number of TB patients registered under DOTS program who are receiving incentives and enablers to improve their treatment adherence | Support to treatment adherence (food and hygienic parcels) for TB patients. Patients will receive at least four food packages per month. Related activity: 3,1,1 Numerator: Number of TB patients in ambulatory phase received incentives and enablers for improved treatment compliance Denominator Total Number of TB patients in ambulatory phase under treatment | All patients who receive at least three food packages per month. | TB patient register and SR reports
Percentage of released prison inmates on TB treatment supported through the TB treatment follow-up program | Numerator: Number of released prison inmates on TB treatment supported through the TB treatment follow-up program during a given time period. Denominator: Total number of released prison inmates on TB treatment during the same time period. Because the denominator may vary the targets are set in percentage and absolute numbers will be reported with each Progress Update. All inmates participating in the treatment follow-up program will be provided with financial incentives upon completion of their treatment. When needed, the beneficiaries will be also provided with legal support/processing of legal papers/identification documents. Actual absolute figures for numerator and deniminator will be provided with the report. | All inmates participating in the treatment follow-up program | SR reports
Number of PHC staff trained in TB case management, community TB care issues and methods of informational work with different groups of population | Training program of PHC staff (doctors and nurses) will be continued to strengthen their involvement in TB control, with priority attention to TB case detection, strengthening referrals and cooperation with specialized TB service, TB case management in out-patient settings (including MDR-TB cases), community TB care and adherence support, defaulter tracing and contacts' investigation, in conditions of revised TB care delivery model. Related activity 3.4.1 | All persons who attended the course not less than 80% and signed the list of participation at training | Training records and SR reports
Indicator Number: Name (Perf Framework No.) | Definition | Measurement | Data Source
The indicators should be selected by the PRs and members of the CCM or the CCM Technical Committee, from the Performance Framework |  |  | Performance Framework
Menu

## Introducerea datelor
Grant information (Informație despre Grant)
| Country (Țara): | Moldova |  | Title of the Grant (Numele Grantului): |  | Empowerment of people with TB and Communities in Moldova
| Grant No.(Nr. Grantului): | MOL-T-PAS |  | Component(Componenta): |  | TB | Suma totală: | 7434590.72
| Principal Recipient (Recipientul Principal): | PAS Center |  |  | Round (Runda): | Round 9 | Faza: | Phase 2
| Start Date (dd/Mmm/yy)(Data Demarării (zz/ll/aa): | January 01, 2010 |  | Local Fund Agent(Agentul Local): |  | PwC (PricewaterhouseCoopers)
| Latest Rating (Ultimul Rating): | A2 |  | Fund Portfolio Manager: |  | Tatiana Vinichenko
Information reporting period (Informația despre perioada raportată)
| Report Period(Perioada de Raportare): | P10 | From(De la): | 2014-01-01 | To(Pînă la): | 2014-06-30 | Date of entry of information (Data de introducere a informației): |  | 2014-09-23
| Prepared by(Pregătit de către): |  | PAS Center
Information on indicators (Informația despre indicatori)
Enter the data based on the colour-coded cells (Introduceți datele bazîndu-vă de celulele codificate prin culoare)
| Financial Information(Informația Financiară): |  |  | Management Information(Informația pe Management): |  |  | Programmatic Information (Informația Programatică):
| Financial Information: | [5 empty] | Enter finance data in every orange cell like this.
| Currency of the grant (Valuta Grantului) |  | €
F1: Budget and disbursements by Global Fund (Bugetul și debursările de către Fondul Global)
| Disbursement | [14 empty] | 0
| Reporting period (Perioada Raportată) | [5 empty] | Phase One | P7 | P8 | P9 | P10 | P11 | P12 |  | % Cumulative | 0
| Buget (in €) | [5 empty] | 4063058 | 303817.76 | 327052.76 | 587460.52 | 654470.92 |  |  |  | 114.2% | 0
| Debursări de către FG (in €) | [5 empty] | 4063058 | 303818 | 1188387 | 1222219 | 0 |  |  |  |  | 0
| Cumulative budget (Buget Cumulativ) |  |  |  |  | 0 | 4063058 | 4366875.76 | 4693928.52 | 5281390.04 | 5935860.96 |  | 0 | 0 |  | 0
| Cumulative disbursements (Debursări cumulative) | [5 empty] | 4063058 | 4366876 | 5555263 | 6777482 | 6777482 |  |  |  |  | 4063058
|  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 114.2% | 0% | 0% |  |  | 4366875.76
F2: Budget and actual expenditures by Grant Objective (Bugetul și cheltuielile actuale după Obiectivele Grantului)
| Grant Objective (Obiectivele Grantului) | Bugetul Cumulativ (in €) | Cheltuielile Cumulative (in €)
| Strengthen community involvement and foster partnerships for effective TB control | 1909544.5 | 1933545.4862
| Ensure successful TB case management through patient support and strengthening health system capacities | 1843562.83 | 1646586.7181
| Integrate TB services on both sides of the prison walls | 342209 | 340362.6137
| Strengthen the health system and engage all available partners in TB control | 102080 | 106798.33
| Ensure universal access to diagnosis, treatment, care and support of drug-resistant tuberculosis | 707986.42 | 671331.6
| Operational research in priority issues of TB and monitoring and evaluation | 19227 | 18754.98
| Project management | 1011251.25 | 1111298.582
| Total | 5935861 | 5828678.3099 |  | OK: Datele coincid
| F3:Disbursements and expenditures (Debursări și cheltuieli) | [14 empty] | 4693928.52
5281390.04
|  | Către perioada de raportare | Perioada de raportare curentă | Total Cheltuit și debursat (in €)
| Disbursed by Global Fund (Debursat de către Fondul Global) | 6777481.9 | 0 | 6777481.9
| PR expenditure and disbursement (Cheltuielile și debursările RP ) | 5250145.53 | 632433.2599 | 5882578.7899
| Disbursed to SRs (Debursări către SR) | 2737382.59 | 358205.25 | 3095587.84
| SR expenditures (Cheltuielile SR) | 2683482.1 | 316902.35 | 3000384.45
F4: Latest PR reporting and disbursement cycle (Ultima perioadă de raportare și debursare a RP)
Last fund disbursement: Number of calendar days (Ultima debursare a surselor: Număr de zile calendaristice)
|  | Expected (days)Preconizat (zile) | Actual (days) Actual (zile)
| Days taken to submit final PU/DR to LFA (Zile necesare pentru remiterea PU/DR final către ALF) | 45 | 42
| Days taken for disbursement to reach PR (Zile necesare pentru debursare către RP) | 45 | 45
| Days taken for disbursement to reach SRs (Zile necesare pentru debursare către SR) | 20 | 5
| Management Information: (Informația pe Management) |  |  |  | Enter management data in every blue cell. |  | (Întroduceți datele pentru management în celulele albastre)
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) (Statutul Condițiilor Precedente și a Acțiunilor Prestabilite în Timp)
|  |  | Fulfilled (Finisate) | Not fulfilled, but within deadline (Ne finisate, dar realizarea în conformitate cu planul) | Not fulfilled, and past the deadline (Ne finisate, și au depășit planul de realizare) | Total
| Conditions precedent (CPs) (Condiții Precedente (CP)) |  | 3 | 0 |  | 3
| Time Bound Actions (TBAs) (Acțiuni Prestabilite în Timp (TBA)) |  |  |  |  | 0
M2: Status of key PR management positions (Statutul pozițiilor cheie a RP)
|  | Planned (Planificate) | Filled (Completate) | Vacant (Vacante)
| PMU | 14 | 14 | 0
M3: Contractual arrangements (SRs) (Aranjamente contractuale (SR))
|  | Identified (Identificați) | Assessed (Evaluați) | Approved (Aprobați) | Signed (Contracte semnate) | Receiving Funding (Au recepționat surse)
| SRs | 3 | 2 | 3 | 3 | 3
M4: Number of complete reports received on time (Numărul rapoartelor complete recepționate la timp)
|  | # Expected (Planificat) | # Received (Recepționat) | Pending (În așteptare)
| SSR to SR | 8 | 8 | 0
| SRs to PR | 3 | 3 | 0
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals (Bugetul și Procurarea produselor medicale, echipamentului medical, medicamentelor și produselor farmaceutice )
|  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12 | P13
Budget Approved* (Buget Aprobat*)
Obligations (Obligațiuni)
Expenditures (Cheltuieli)
Budget Approved cumulative* (Buget Aprobat cumulativ*)
Obligations cumulative (Obligațiuni cumulative)
Expenditures cumulative (Cheltuieli cumulative)
* Includes only EFR category 4 and 5 (Health products and health equipment & Medicines and Pharmaceuticals) (* Include numai EFR categoriile 4 și 5 (Produse medicale și Echipamente medicale & Medicamente și Produse farmaceutice))
M6: Difference between current and safety stock (Diferență între stocul curent și stocul de siguranță)
| Component (Componenta) | Produsul | (1) Numărul de pastile per pacient per zi (În conformitate cu ghidurile d etratament al țării) | (2 = 1 x 30) Tratamentul per lună (Pastile per pacient x 30 zile) | (3) Total pacienți în tratament | (4 = 2 x 3) # Total pastile necesare pentru toți pacienții per lună | (5) Stocul Curent în depozitul central (nu expiră în următoarele 3 luni) | (6 = 5 / 4) Stocul exprimat în luni de treatament pentru toți pacienții curenți | (7) Nivelul stocului de siguranță (exprimat în luni și prestabilit de țară) | (8 = 6 - 7) Diferența între stocul curent și stocul de siguranță
| TB | P1: Please Select
Please Select
Please Select
Please Select
| Programmatic Information (Informația Programatică): | P9: Enter performance data in every yellow cell.
| Indicatori de Program (Performance Framework ) |  |  | Code / codul | Direct rezulta din activitatea FG? |  | P5 | P6 | P7 | P8 | P9 | P10 |  |  |  |  | P17
TOP 3 | Number of TB patients registered under DOTS program who are receiving incentives and enablers to improve their treatment adherence (Numarul de pacienți înregistrați în programul DOTS care au beneficiat de stimulente pentru sporirea complianței la tratament) |  |  | 3.3 | Yes | Target | 562 | 1125 | 562 | 1125 | 552 | 1105
[6 empty] | Achieved | 341 | 1237 | 555 | 1003 | 441 | 991
| Number and percentage of MDR-TB patients registered under DOTS program who are receiving incentives and enablers for improved treatment compliance (Numarul și procentul de pacienți înregistrați în programul DOTS Plus care au primit stimulente pentru sporirea complianței la tratament) |  |  | 3.2 | Yes | Target // Ținta | 142 | 285 | 142 | 285 | 140 | 280
[6 empty] | Achieved // Realizat | 63 | 288 | 152 | 290 | 137 | 283
| Number of volunteers, members of multidisciplinary teams and NGOs representatives trained in TB community aspects(Numarul de voluntari, membri din echipele multidisciplinare, reprezentanti ai ONG-lor insruiti în aspecte DOT și controlul tuberculozei la nivel de comunitate) |  |  | 2.2 | Yes | Target // Ținta | 40 | 80 | 15 | 55 | 40 | 80
[6 empty] | Achieved // Realizat | 23 | 85 | 15 | 69 | 40 | 85
| The default rate among New TB Cases in Community Centers (Rata abandonurilor cazurilor noi de TB în cadrul centrelor comunitare) |  |  | 2.1 | Yes | Target // Ținta | n/a | n/a | n/a | 10% | n/a | n/a
[6 empty] | Achieved // Realizat | n/a | n/a | n/a | 4.82% | n/a | n/a
| Number of new TB patients in ambulatory phases provided with DOT support by the community (Numărul pacienților noi cu TB aflați în faza de ambulator care au beneficiat de suportul DOT în cadrul centrelor comunitare) |  |  | 2.3 | Yes | Target // Ținta | 168 | 337 | 168 | 337 | 165 | 331
[6 empty] | Achieved // Realizat | 151 | 313 | 190 | 351 | 210 | 457
| Number of people (TB,TB/HIV patients and their families) reached by peer support groups (Numarul de persoane (pacienți TB,TB/HIV și familiile lor) care au fost instruiti de către grupurile de la egal la egal) |  |  | 2.4 | Yes | Target // Ținta | 100 | 200 | 100 | 200 | 100 | 200
[6 empty] | Achieved // Realizat | 40 | 200 | 102 | 202 | 100 | 199
| Number of peer educators, journalists at national and district level and local stakeholders trained in TB and TB/HIV issues (Numarul de educatori de la egal la egal, jurnaliști la nivel național și regional, persoane-cheie din republică instruiți in TB și TB/HIV) |  |  | 2.5 | Yes | Target // Ținta | 60 | 135 | 50 | 150 | 60 | 135
[6 empty] | Achieved // Realizat | 509 | 758 | 80 | 176 | 125 | 150
| Number of TB service staff trained in DR-TB management (Numarul de personal din serviciu TB instruiti in managementul TB-MDR) |  |  | 3.1 | Yes | Target // Ținta | 0 | 25 | 0 | 25 | 0 | 25
[6 empty] | Achieved // Realizat | 0 | 115 | 0 | 52 | 0 | 24
| Percentage of released prison inmates on TB treatment supported through the TB treatment follow-up program (Procentul de deţinuţi înrolați în tratamentul TB și susţinuți prin programul tratamentului TB de follow-up) |  |  | 3.4 | Yes | Target // Ținta | n/a | 95% | n/a | 95% | n/a | 95%
[6 empty] | Achieved // Realizat | n/a | 100% | n/a | 100% | n/a | 100%
| Number of PHC staff trained in TB case management, community TB care issues and methods of informational work with different groups of population (Numărul de lucrători medicali instruiți în managementul de caz, probleme de îngrijire comunitară, lucru informaţional cu diferite grupuri de populaţie) |  |  | 3.5 | Yes | Target // Ținta | 25 | 50 | 25 | 75 | 25 | 25
[6 empty] | Achieved // Realizat | 0 | 24 | 0 | 104 | 26 | 52
| Tabelul este în mod automat reînnoit. Nu necesită introducerea datelor și/sau informației. |  |  | Code | Direct rezulta din activitatea FG? |  | P5 | P6 | P7 | P8 | P9 | P10
| Number of TB patients registered under DOTS program who are receiving incentives and enablers to improve their treatment adherence (Numarul de pacienți înregistrați în programul DOTS care au beneficiat de stimulente pentru sporirea complianței la tratament) |  |  | 3.3 | Yes | Target | 562 | 1125 | 562 | 1125 | 552 | 1105
[6 empty] | Achieved | 341 | 1237 | 555 | 1003 | 441 | 991
| Number and percentage of MDR-TB patients registered under DOTS program who are receiving incentives and enablers for improved treatment compliance (Numarul și procentul de pacienți înregistrați în programul DOTS Plus care au primit stimulente pentru sporirea complianței la tratament) |  |  | 3.2 | Yes | Target | 142 | 285 | 142 | 285 | 140 | 280
[6 empty] | Achieved | 63 | 288 | 152 | 290 | 137 | 283
| Number of volunteers, members of multidisciplinary teams and NGOs representatives trained in TB community aspects(Numarul de voluntari, membri din echipele multidisciplinare, reprezentanti ai ONG-lor insruiti în aspecte DOT și controlul tuberculozei la nivel de comunitate) |  |  | 2.2 | Yes | Target | 40 | 80 | 15 | 55 | 40 | 80
[6 empty] | Achieved | 23 | 85 | 15 | 69 | 40 | 85
Menu
Note on B30: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.
Note on B72: If data are not available, do not enter zeros; rather, leave the cells in the table blank.
Note on B73: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B79: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B94: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.

## Detalii despre Grant
Dashboard: Moldova - TB
Country: | Moldova |  | Title of the Grant: |  | Empowerment of people with TB and Communities in Moldova
Component: | TB | Grant No. | MOL-T-PAS | Start Date: |  | January 01, 2010 | Total Funding | 7434590.72
Round: | Round 9 | Phase: | Phase 2 | Principal Recipient: |  | PAS Center
Report Period: | P10 | from: | 2014-01-01 | to: |  | 2014-06-30 | Latest Rating: | A2
Local Fund Agent: | PwC (PricewaterhouseCoopers) |  |  | Fund Portfolio Manager: |  | Tatiana Vinichenko
Prepared by: | PAS Center |  |  | Report preparation date: |  | 2014-09-23
http://www.crwflags.com/fotw/flags/country.html
Menu

## Financiar
Dashboard: Moldova - TB
Round 9 | Phase 2 |  |  |  | Report Period(Perioada de Raportare): |  | P10
Latest Rating (Ultimul Rating): | A2 |  | PAS Center |  | From(De la): |  | 2014-01-01
|  | Empowerment of people with TB and Communities in Moldova |  |  |  | To(Pînă la): | 2014-06-30
Financial Indicators
F1: Budget and disbursements by Global Fund (Bugetul și debursările de către Fondul Global) - in (€) Report Period(Perioada de Raportare): P10 |  |  |  | F3:Disbursements and expenditures (Debursări și cheltuieli) - in (€) Report Period(Perioada de Raportare): P10
Comments: | Cumulative disbursements is more than cumulative budget, due to the fact that disbursement includes the budget for 2014 and value for the first quarter of 2015 ( 01.01.2015-31.03.2015), as buffer stock . As per June 30, 2014 the total disbursement value by the GF to the PR was 6.777.482,00 Euro versus the planned budget of 5.935.861,00. The disbursement rate is 114%. Suma debursarilor este mai mare decât suma bugetată, deoarece suma bugetată include perioada de până la 30 iunie 2014, iar in debursari este inclus bugetul pentru întreg anul 2014 și suma pentru trimestrul I, 2015, în calitate de buffer. Astfel la 30 iunie 2014, suma totală debursată de FG catre RP a fost de 6.777.482,00 Euro versus bugetul de 5.935.861,00 Euro. Rata debursarii cumulative este de 114%. |  |  | Comments: | The variance between the disbursement and expenditures of the PR for the current period is due to: 1. Disbursement includes the budget for 2014 and buffer period for 2015 (Q1); 2. Commitments from the semester 1, 2014 - EUR 164,928.00. The expenditures of the SRs are closed to the disbursement value. The difference is explaiend by the commitments of the semester 1, 2014. Variatia dintre suma disbursata si suma cheltuita este formata din motiv ca: 1. In debursari este inclus si bugetul pentru 2014 și perioada de buffer - trim. 1, 2015; 2. Sumele angajate din semestrul 1, 2014 - EUR 164,928.00. Diferența dintre sumele debursate de către RP și cheltuielile subrecipienților sunt mici. Diferenta este explicata prin sumele angate pentru activitatile din semestrul 1, 2014.
F2: Budget and actual expenditures by Grant Objective (Bugetul și cheltuielile actuale după Obiectivele Grantului) - in (€) Report Period(Perioada de Raportare): P10 |  |  |  | F4: Latest PR reporting and disbursement cycle (Ultima perioadă de raportare și debursare a RP) Report Period(Perioada de Raportare): P10
Comments: | Almost all payments were done according to the planned budget and in line with the project activities. For the objective 1 "Strengthen community involvement and foster parnerships for effective TB control", the cumulative expenditure is higher due to approval by TGF of additional budget in value of 74,000.00 Euro, to increase the number of grants for 2013 and 2014, based on the reallocated savings from 2012 and 2013. The difference of value for the Project management is due to the interest income on bank account used for the office loan (as per TGF approval). As for the remaining objectives, due to commitments the cumulative expenditures is less then cumulative budget. Toate cheltuielile au fost efectuate conform bugetului și, cu scopul de a atinge obiectivele proiectului. Pentru obiectivul 1 "Strengthen community involvement and foster parnerships for effective TB control " cheltuielile cumulative sunt mai mari datorită aprobării realocării sumei de 74,000.00 Euro pentru linia de grant din 2013 și 2014, conform aprobării FG, fiind considerate economiile anului 2012 și 2013. Diferența de valori pentru Managementul de Proiect este condiționată de venitul din dobândă, cumulată în cont, pentru acoperirea împrumutului, conform aprobării FG. La celelalte obiective, datorită sumelor angajate, cheltuielele cumulative sunt mai mici decit bugetul planificat. |  |  | Comments: | The PR always makes the disbursements to SRs in the shortest period when the disbursement request is received and the report is presented. Perioada de debursare către SR este cit mai operativ posibil de la data depunerii cererii de debursare şi prezentare a raportului financiar.
Last fund disbursement: Calendar days
[6 empty] | Expected (days) | Actual (days)
|  |  |  | Days taken to submit final PU/DR to LFA (Zile necesare pentru remiterea PU/DR final către ALF) |  | 45 | 42
|  |  |  | Days taken for disbursement to reach PR (Zile necesare pentru debursare către RP) |  | 45 | 45
|  |  |  | Days taken for disbursement to reach SRs (Zile necesare pentru debursare către SR) |  | 20 | 5
Menu

## Management
Dashboard: Moldova - TB
Round 9 | Phase 2 |  |  |  |  | Report Period(Perioada de Raportare): |  | P10
Latest Rating (Ultimul Rating): | A2 |  | PAS Center |  |  | From(De la): |  | 2014-01-01
|  | Empowerment of people with TB and Communities in Moldova |  |  |  |  | To(Pînă la): | 2014-06-30
Management Indicators
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) (Statutul Condițiilor Precedente și a Acțiunilor Prestabilite în Timp) Report Period(Perioada de Raportare): P10 |  |  |  | M2: Status of key PR management positions (Statutul pozițiilor cheie a RP) Report Period(Perioada de Raportare): P10
Comments: | One Condition Precedent (CP), prior to grant agreement signing, was fulfilled by PAS Center, received NO from GF.The other two CP, prior to extension of the grant agreement: review of the NTP in written form by 15th august 2013 and present of the strategic plan for out-patient care to improve compliance and reduce treatment default by 15th august 2013, were completed. The final report English version was published and shared by the WHO in 2013. The MoH approved the plan for out- patient care to imrpove compliance and reduce treatment default on 27/09/2013 ( Order #1051). Centrul PAS a implementat cerinta inaintată de Fondul Global vizavi de conditii precedente( CP), inainte de semnarea acordului de grant, avînd NO de la FG. Celelalte doua conditii precedente pentru extinderea acordului de grant și anume: raportul de evaluare a Programului National de Control al Tuberculozei ( PNCT) si planul strategic pentru imbunatatirea aderentei la tratament si micsorarea abandonului la tratamentul in conditii de ambulatoriu au fost indeplinite. Raportul, versiunea Engleză, a fost publicat și distributi instituțiilor relevante de către OMS în 2013. Planul strategic menționat a fost aprobat de cître Ministerul Sănătății la 27/09/2013 , ordinul # 1051. |  |  | Comments: | All key positions of the management department are filled in by the PR. Toate functiile sunt completate de RP.
M3: Contractual arrangements (SRs) (Aranjamente contractuale (SR)) Report Period(Perioada de Raportare): P10 |  |  |  | M4: Number of complete reports received on time (Numărul rapoartelor complete recepționate la timp) Report Period(Perioada de Raportare): P10
Comments: | Soros Moldova Foundation was not assessed due to its proved experience in grants' implementation. Fundația Soros-Moldova nu a fost evaluată ținînd cont de semnificativa experiență în implementarea granturilor. |  |  | Comments: | For the reported period, January-June 2014, 8 SSRs were involved in TB related activities. Basically, the majority of NGO are implementing one grant, with exception of two NGOs which applied to Soros Foundation - Moldova and were granted with more than one grant, as follow: NGO "AFI" - 2 grants, and NGO "National Association of TB patients SMIT" - 3 grants. In perioada de raportare, ianuarie-iunie 2014, 8 sub-subrecipienți au realizat activități conexe programului de control al TB. Majoritatea ONG-urilor realizează a câte un grant, excepție fiind 2 ONG care au aplicat către Fundația Soros - Moldova, și au fost aprobate pentru implementarea a mai mult de un grant cum ar fi: ONG AFI - 2 granturi și ONG SMIT - 3 granturi.
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals (Bugetul și Procurarea produselor medicale, echipamentului medical, medicamentelor și produselor farmaceutice ) |  |  |  | M6: Difference between current and safety stock (Diferență între stocul curent și stocul de siguranță) Report Period(Perioada de Raportare): P10
Comments: |  |  |  | Comments:
|  |  |  | Component | Products | Stock level expressed in months of treatment for all current patients | Months of safety stock | Difference between current stock and safety stock
|  |  |  | TB | Please Select |  | 0
[5 empty] | Please Select |  | 0
[5 empty] | Please Select |  | 0
[5 empty] | Please Select |  | 0
* Includes only EFR category 4 and 5 (Health products and health equipment & Medicines and Pharmaceuticals) (* Include numai EFR categoriile 4 și 5 (Produse medicale și Echipamente medicale & Medicamente și Produse farmaceutice))
Menu

## Programatic
Dashboard: Moldova - TB
Round 9 | Phase 2 | [8 empty] | Report Period(Perioada de Raportare): |  | P10
Latest Rating (Ultimul Rating): | A2 |  | PAS Center | [7 empty] | From(De la): | 2014-01-01
|  | Empowerment of people with TB and Communities in Moldova | [8 empty] | To(Pînă la): | 2014-06-30 | [7 empty] | Raiting |  | Valor
Programmatic Indicators
Number of TB patients registered under DOTS program who are receiving incentives and enablers to improve their treatment adherence (Numărul pacienților noi înregistrați în programul DOTS, care au beneficiat de suport motivațional pentru a spori aderența la tratament ) |  |  |  | Number and percentage of MDR-TB patients registered under DOTS program who are receiving incentives and enablers for improved treatment compliance (Numărul de pacienți cu MDRTB înregistrați în tratamentul DOTS Plus care au beneficiat de suport motivațional pentru a spori aderența la tratament) |  |  |  | Number of volunteers, members of multidisciplinary teams and NGOs representatives trained in TB community aspects(Numarul de voluntari, membri din echipele multidisciplinare, reprezentanti ai ONG-lor insruiti în aspecte DOT și controlul tuberculozei la nivel de comunitate)
Comment: P1 | During the first half of the 2014, 991 TB patients registered under DOTS program received incentives for improved treatment compliance. The indicator is achieved at 89.%. Reason: Currently, in the country there are two sources of funding incentives’ support: CNAM and GF. The value of incentives offered through the CNAM is more consistent. Since the criteria described in the MoH regulation on providing incentives from the CNAM funds is not expressive, the SR AFI informed territorial TB coordinators from the TB health facilities to provide the list of sensitive TB patients that were not covered by the CNAM. Majority of TB coordinators register patients in the list for provision incentives with higher value, event the total sun approved by the CNAM does not predict to cover all needs. Also the TB doctors are focused on absorption the budget provided by the CNAM. After a long period of communication between PR, SR and public authorities on the issues related to the provision of incentives there were drafted and presented by the NTP the model of providing incentives by combining provision from two sources as follow: to start with CNAM funds during first 2-3 months and continue support with GF funds. The presented estimation to the RP was with unclear multiplication factors in the estimation formula. No explanations were presented to unclear multiplication factors to several PR requests to the MoH and NTP, up to date. Nevertheless the PR presented the estimation of the NTP/ MoH to the GF which also raised the same questions to the estimation formula. It expected to have final clarifications from the NTP of the estimation on the new drafted model for provision incentives programm from both sources. Also it is expected to have a decision of the NTP and CNAM on the possibility to revise the MoH order on providing incentives from different sources. In primul semestru al 2014, 991 pacienți cu TB înregistrați în programul DOTS au primit suport motivational pentru îmbunătățirea aderentei la tratament. Indicatorul este atins in proportie de 89,%. Motivul variației: În prezent, în ţară există două surse de finanţare a suportului motivational: CNAM şi FG. Valorea pachetului oferit din sursele CNAM este mai consistentă. Din motiv că criteriile descrise în regulamentul MS cu privire la oferirea suportului motivational nu sunt exprese, SR AFI a informat coordonatori TB teritoriali din institutiile medico- sanitare de a prezenta lista de pacienţii cu TB sensibilă care nu au fost acoperiţi de CNAM pentru a oferi suport motivaţional din sursele FG. Majoritatea Coordonatorilor TB inscriu pacientii in listele pentru suport motivaţional de la CNAM, cu o valoare mai mare .. Deasemenea TB Coordonatorii incearca sa absorbe sumele acordate de CNAM. Dupa o perioada esenţială de comunicare intre RP, SR si autorităţile publice despre problemele mecanismului de oferire a suportului motivaţional, NTP a elaborat şi a prezentat un model de oferire a suportului care prevede: acordarea suportului iniţial din sursele CNAM ( 2-3 luni) şi ulterior de al GF, pe durata tratamentului. Estimarea prezentatăp conţine factori în formulă de multiplicare neclari. Clarificări vizavi de incertitudinile din formula de estimare abordate de RP nu au fost prezentate pînp la data curentă. Necatînd la acest fapt estimarea a fost prezentat la FG. La rindul său FG a ridicat aceleaşi intrebări, nefiind posibil fără ele examinarea documentului şi aprobarea noului model de suport. Se asteaptă ca NTP să ofere clarificări vizavi de estimarea pentru noul model al suportului motivaţional din ambele surse de finanţare. Deasemenea se asteaptă sa fie luată decizia finală de NTP şi CNAM privind posibilitatea de a modifica Ordinul MS pentru acordarea de stimulente din diferite surse. |  |  | Comment: P2 | During the firs half of 2014, 283 MDR-TB patients were received incentives for improved treatment compliance . The indicator is achieved. În prima jumatate anului 2014, 283 de pacienţi MDR-TB au primit stimulente pentru îmbunătățirea respectării tratamentului. Indicatorul este atins. |  |  | Comment: P3 | A total of 85 persons were trained, from them: 28 people from multidisciplinary teams of the community center; 25 people from NGOs in DOT and TB community aspects and 32 volunteers trained from the NGOs network in TB community aspects. The indicator is overachieved in proportion of 106%. 85 de persoane au fost instruite pe parcusul semestrului 1, 2014, dintre care: 28 de persoane din echipele multidisciplinare din centrul comunitar; 25 persoane din ONG-uri care activează în aspecte comunitare, DOT şi TB şi 32 voluntari din reţeaua de ONG-uri. Indicatorul este supraindeplinit în proporţie de 106%.
Indicators |  |  | Target | Achieved | 0% - 59% | 60% - 89% | > 90% | Comments |  |  |  |  | min | 0 | 30% | 60% | 90% | 100% |  | min | 0 | 20% | 40% | 60% | 80%
Number of TB patients registered under DOTS program who are receiving incentives and enablers to improve their treatment adherence (Numarul de pacienți înregistrați în programul DOTS care au beneficiat de stimulente pentru sporirea complianței la tratament) |  |  | 1105 | 991 | 89.2% |  |  | During the first half of the 2014, 991 TB patients registered under DOTS program received incentives for improved treatment compliance. The indicator is achieved at 89.%. Reason: Currently, in the country there are two sources of funding incentives’ support: CNAM and GF. The value of incentives offered through the CNAM is more consistent. Since the criteria described in the MoH regulation on providing incentives from the CNAM funds is not expressive, the SR AFI informed territorial TB coordinators from the TB health facilities to provide the list of sensitive TB patients that were not covered by the CNAM. Majority of TB coordinators register patients in the list for provision incentives with higher value, event the total sun approved by the CNAM does not predict to cover all needs. Also the TB doctors are focused on absorption the budget provided by the CNAM. After a long period of communication between PR, SR and public authorities on the issues related to the provision of incentives there were drafted and presented by the NTP the model of providing incentives by combining provision from two sources as follow: to start with CNAM funds during first 2-3 months and continue support with GF funds. The presented estimation to the RP was with unclear multiplication factors in the estimation formula. No explanations were presented to unclear multiplication factors to several PR requests to the MoH and NTP, up to date. Nevertheless the PR presented the estimation of the NTP/ MoH to the GF which also raised the same questions to the estimation formula. It expected to have final clarifications from the NTP of the estimation on the new drafted model for provision incentives programm from both sources. Also it is expected to have a decision of the NTP and CNAM on the possibility to revise the MoH order on providing incentives from different sources. In primul semestru al 2014, 991 pacienți cu TB înregistrați în programul DOTS au primit suport motivational pentru îmbunătățirea aderentei la tratament. Indicatorul este atins in proportie de 89,%. Motivul variației: În prezent, în ţară există două surse de finanţare a suportului motivational: CNAM şi FG. Valorea pachetului oferit din sursele CNAM este mai consistentă. Din motiv că criteriile descrise în regulamentul MS cu privire la oferirea suportului motivational nu sunt exprese, SR AFI a informat coordonatori TB teritoriali din institutiile medico- sanitare de a prezenta lista de pacienţii cu TB sensibilă care nu au fost acoperiţi de CNAM pentru a oferi suport motivaţional din sursele FG. Majoritatea Coordonatorilor TB inscriu pacientii in listele pentru suport motivaţional de la CNAM, cu o valoare mai mare .. Deasemenea TB Coordonatorii incearca sa absorbe sumele acordate de CNAM. Dupa o perioada esenţială de comunicare intre RP, SR si autorităţile publice despre problemele mecanismului de oferire a suportului motivaţional, NTP a elaborat şi a prezentat un model de oferire a suportului care prevede: acordarea suportului iniţial din sursele CNAM ( 2-3 luni) şi ulterior de al GF, pe durata tratamentului. Estimarea prezentatăp conţine factori în formulă de multiplicare neclari. Clarificări vizavi de incertitudinile din formula de estimare abordate de RP nu au fost prezentate pînp la data curentă. Necatînd la acest fapt estimarea a fost prezentat la FG. La rindul său FG a ridicat aceleaşi intrebări, nefiind posibil fără ele examinarea documentului şi aprobarea noului model de suport. Se asteaptă ca NTP să ofere clarificări vizavi de estimarea pentru noul model al suportului motivaţional din ambele surse de finanţare. Deasemenea se asteaptă sa fie luată decizia finală de NTP şi CNAM privind posibilitatea de a modifica Ordinul MS pentru acordarea de stimulente din diferite surse. |  |  |  |  | max | 30% | 60% | 90% | 100% | 200% |  | max | 20% | 40% | 60% | 80% | 100%
Number and percentage of MDR-TB patients registered under DOTS program who are receiving incentives and enablers for improved treatment compliance (Numarul și procentul de pacienți înregistrați în programul DOTS Plus care au primit stimulente pentru sporirea complianței la tratament) |  |  | 280 | 283 | 101.1% |  |  | During the firs half of 2014, 283 MDR-TB patients were received incentives for improved treatment compliance . The indicator is achieved. În prima jumatate anului 2014, 283 de pacienţi MDR-TB au primit stimulente pentru îmbunătățirea respectării tratamentului. Indicatorul este atins. | [5 empty] | de 0 a 0.3 | de 0.3 a 0.6 | de 0.6 a 0.9 | de 0.9 a 1 | de 1 a 2 | Rating | Valor | de 0 a 0.2 | de 0.2 a 0.4 | de 0.4 a 0.6 | de 0.6 a 0.8 | de 0.8 a 1
Number of volunteers, members of multidisciplinary teams and NGOs representatives trained in TB community aspects(Numarul de voluntari, membri din echipele multidisciplinare, reprezentanti ai ONG-lor insruiti în aspecte DOT și controlul tuberculozei la nivel de comunitate) |  |  | 80 | 85 | 106.2% |  |  | A total of 85 persons were trained, from them: 28 people from multidisciplinary teams of the community center; 25 people from NGOs in DOT and TB community aspects and 32 volunteers trained from the NGOs network in TB community aspects. The indicator is overachieved in proportion of 106%. 85 de persoane au fost instruite pe parcusul semestrului 1, 2014, dintre care: 28 de persoane din echipele multidisciplinare din centrul comunitar; 25 persoane din ONG-uri care activează în aspecte comunitare, DOT şi TB şi 32 voluntari din reţeaua de ONG-uri. Indicatorul este supraindeplinit în proporţie de 106%. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
The default rate among New TB Cases in Community Centers (Rata abandonurilor cazurilor noi de TB în cadrul centrelor comunitare) |  |  | n/a | n/a | n/a |  |  | n/a | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number of new TB patients in ambulatory phases provided with DOT support by the community (Numărul pacienților noi cu TB aflați în faza de ambulator care au beneficiat de suportul DOT în cadrul centrelor comunitare) |  |  | 331 | 457 | 138.1% |  |  | 457 of new TB patients provided with DOT by the community (community centers and NGOs) received at least 25 DOT interventions during 1 month (visit to DOT center by the patient or visit to the patient by DOT supporters for drug intake). The indicator is overachieved in proportion of 138%. Reason for variance: AO AFI included and registered all the new TB patients provided in lists by Community Centers. 457 pacienţi noi cu TB au fost acoperiți cu servicii de comunitate (centre comunitare şi ONG-uri) ei au primit cel puţin 25 intervenţii DOT pe parcursul la o luna (vizite la centrul de DOT de către pacient sau vizite la pacient de suporterii DOT pentru consumul de medicamente). Indicatorul este realizat în proporţie de 138%. Motivul pentru variaţii: AO AFI au înclus şi înregistrat toţi pacienţii noi de TB prevăzuți în listele centrelor comunitare). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number of people (TB,TB/HIV patients and their families) reached by peer support groups (Numarul de persoane (pacienți TB,TB/HIV și familiile lor) care au fost instruiti de către grupurile de la egal la egal) |  |  | 200 | 199 | 99.5% |  |  | During the first semester of the 2014, 199 people (TB/HIV patients and their families) were reached by peer support groups. The indicator is achieved. În primul semestru al 2014, 199 de persoane (TB/HIV pacienţii şi familiile lor) au beneficiat de suport de la egal la egal. Indicatorul este atins | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Number of peer educators, journalists at national and district level and local stakeholders trained in TB and TB/HIV issues (Numarul de educatori de la egal la egal, jurnaliști la nivel național și regional, persoane-cheie din republică instruiți in TB și TB/HIV) |  |  | 135 | 150 | 111.1% |  |  | A total of 150 persons were trained, from them: 55 of local stakeholders attending workshops on TB and TB/HIV and 75 of peer educators trained to carry out informational work on TB and 20 journalists at national and district level trained; The indicator is achieved. Reason for variance: The number of journalists to attend the training course were increased based on the request within the establised budget. 150 persoane au fost instruite, din ei: 55 reprezentanți ai autorităților locale au participat la atelier de lucru în TB și TB/HIV şi 75 educători de la egal la egal instruiți să efectueze lucrul informațional pe TB şi 20 jurnalişti; Indicatorul este atins. Motivul variației este numărul de jurnaliști, aprobat să fie majorat, în limitele bugetului existent. | [5 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
Number of TB service staff trained in DR-TB management (Numarul de personal din serviciu TB instruiti in managementul TB-MDR) |  |  | 25 | 24 | 96% |  |  | A total of 24 TB service staff trained in DR-TB management. The indicator is achieved. 24 persoane din serviciu TB au fost instruite în managementul TB-MDR. Indicatorul este atins. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Percentage of released prison inmates on TB treatment supported through the TB treatment follow-up program (Procentul de deţinuţi înrolați în tratamentul TB și susţinuți prin programul tratamentului TB de follow-up) |  |  | 95% | 100% | 105.3% |  |  | During the first half of 2014, 16 eligible prison inmates on TB treatment were released. All of them were supported through the TB follow up program. In prima jumatate a 2014, au fost eliberați 16 deţinuţi aflați în tratamentul TB. Toți aceștia au fost susţinuți prin programul tratamentului TB de follow-up. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Number of PHC staff trained in TB case management, community TB care issues and methods of informational work with different groups of population (Numărul de lucrători medicali instruiți în managementul de caz, probleme de îngrijire comunitară, lucru informaţional cu diferite grupuri de populaţie) |  |  | 50 | 52 | 104% |  |  | During S7, a total of 52 medical staff were trained. The indicator is achieved. Pe parcursul S7, au fost instruiţi 52 lucrători medicali. Indicatorul este atins. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Menu

## Recomandari
Dashboard: Moldova - TB
Round 9 | Phase 2 |  |  |  |  | Report Period(Perioada de Raportare): | P10
Latest Rating (Ultimul Rating): | A2 |  | PAS Center |  |  | From(De la): | 2014-01-01
|  |  | Empowerment of people with TB and Communities in Moldova |  |  | To(Pînă la): | 2014-06-30
Recommendations
Are all funds reaching implementation levels and being spent according to budget?
Financial |  | Summary Comments |  |  | Recommendations
F1 |  | Cumulative disbursements is more than cumulative budget, due to the fact that disbursement includes the budget for 2014 and value for the first quarter of 2015 ( 01.01.2015-31.03.2015), as buffer stock . As per June 30, 2014 the total disbursement value by the GF to the PR was 6.777.482,00 Euro versus the planned budget of 5.935.861,00. The disbursement rate is 114%. Suma debursarilor este mai mare decât suma bugetată, deoarece suma bugetată include perioada de până la 30 iunie 2014, iar in debursari este inclus bugetul pentru întreg anul 2014 și suma pentru trimestrul I, 2015, în calitate de buffer. Astfel la 30 iunie 2014, suma totală debursată de FG catre RP a fost de 6.777.482,00 Euro versus bugetul de 5.935.861,00 Euro. Rata debursarii cumulative este de 114%.
F2 |  | Almost all payments were done according to the planned budget and in line with the project activities. For the objective 1 "Strengthen community involvement and foster parnerships for effective TB control", the cumulative expenditure is higher due to approval by TGF of additional budget in value of 74,000.00 Euro, to increase the number of grants for 2013 and 2014, based on the reallocated savings from 2012 and 2013. The difference of value for the Project management is due to the interest income on bank account used for the office loan (as per TGF approval). As for the remaining objectives, due to commitments the cumulative expenditures is less then cumulative budget. Toate cheltuielile au fost efectuate conform bugetului și, cu scopul de a atinge obiectivele proiectului. Pentru obiectivul 1 "Strengthen community involvement and foster parnerships for effective TB control " cheltuielile cumulative sunt mai mari datorită aprobării realocării sumei de 74,000.00 Euro pentru linia de grant din 2013 și 2014, conform aprobării FG, fiind considerate economiile anului 2012 și 2013. Diferența de valori pentru Managementul de Proiect este condiționată de venitul din dobândă, cumulată în cont, pentru acoperirea împrumutului, conform aprobării FG. La celelalte obiective, datorită sumelor angajate, cheltuielele cumulative sunt mai mici decit bugetul planificat.
F3 |  | The variance between the disbursement and expenditures of the PR for the current period is due to: 1. Disbursement includes the budget for 2014 and buffer period for 2015 (Q1); 2. Commitments from the semester 1, 2014 - EUR 164,928.00. The expenditures of the SRs are closed to the disbursement value. The difference is explaiend by the commitments of the semester 1, 2014. Variatia dintre suma disbursata si suma cheltuita este formata din motiv ca: 1. In debursari este inclus si bugetul pentru 2014 și perioada de buffer - trim. 1, 2015; 2. Sumele angajate din semestrul 1, 2014 - EUR 164,928.00. Diferența dintre sumele debursate de către RP și cheltuielile subrecipienților sunt mici. Diferenta este explicata prin sumele angate pentru activitatile din semestrul 1, 2014.
F4 |  | The PR always makes the disbursements to SRs in the shortest period when the disbursement request is received and the report is presented. Perioada de debursare către SR este cit mai operativ posibil de la data depunerii cererii de debursare şi prezentare a raportului financiar.
Are procurement and hiring on schedule?
Management |  | Summary Comments |  |  | Recommendations
M1 |  | One Condition Precedent (CP), prior to grant agreement signing, was fulfilled by PAS Center, received NO from GF.The other two CP, prior to extension of the grant agreement: review of the NTP in written form by 15th august 2013 and present of the strategic plan for out-patient care to improve compliance and reduce treatment default by 15th august 2013, were completed. The final report English version was published and shared by the WHO in 2013. The MoH approved the plan for out- patient care to imrpove compliance and reduce treatment default on 27/09/2013 ( Order #1051). Centrul PAS a implementat cerinta inaintată de Fondul Global vizavi de conditii precedente( CP), inainte de semnarea acordului de grant, avînd NO de la FG. Celelalte doua conditii precedente pentru extinderea acordului de grant și anume: raportul de evaluare a Programului National de Control al Tuberculozei ( PNCT) si planul strategic pentru imbunatatirea aderentei la tratament si micsorarea abandonului la tratamentul in conditii de ambulatoriu au fost indeplinite. Raportul, versiunea Engleză, a fost publicat și distributi instituțiilor relevante de către OMS în 2013. Planul strategic menționat a fost aprobat de cître Ministerul Sănătății la 27/09/2013 , ordinul # 1051.
M2 |  | All key positions of the management department are filled in by the PR. Toate functiile sunt completate de RP. | #DIV/0! | #DIV/0!
M3 |  | Soros Moldova Foundation was not assessed due to its proved experience in grants' implementation. Fundația Soros-Moldova nu a fost evaluată ținînd cont de semnificativa experiență în implementarea granturilor.
M4 |  | For the reported period, January-June 2014, 8 SSRs were involved in TB related activities. Basically, the majority of NGO are implementing one grant, with exception of two NGOs which applied to Soros Foundation - Moldova and were granted with more than one grant, as follow: NGO "AFI" - 2 grants, and NGO "National Association of TB patients SMIT" - 3 grants. In perioada de raportare, ianuarie-iunie 2014, 8 sub-subrecipienți au realizat activități conexe programului de control al TB. Majoritatea ONG-urilor realizează a câte un grant, excepție fiind 2 ONG care au aplicat către Fundația Soros - Moldova, și au fost aprobate pentru implementarea a mai mult de un grant cum ar fi: ONG AFI - 2 granturi și ONG SMIT - 3 granturi.
M5
M6
Are technical targets being achieved?
Programmatic |  | Summary Comments |  |  | Recommendations
P1 - trend |  | During the first half of the 2014, 991 TB patients registered under DOTS program received incentives for improved treatment compliance. The indicator is achieved at 89.%. Reason: Currently, in the country there are two sources of funding incentives’ support: CNAM and GF. The value of incentives offered through the CNAM is more consistent. Since the criteria described in the MoH regulation on providing incentives from the CNAM funds is not expressive, the SR AFI informed territorial TB coordinators from the TB health facilities to provide the list of sensitive TB patients that were not covered by the CNAM. Majority of TB coordinators register patients in the list for provision incentives with higher value, event the total sun approved by the CNAM does not predict to cover all needs. Also the TB doctors are focused on absorption the budget provided by the CNAM. After a long period of communication between PR, SR and public authorities on the issues related to the provision of incentives there were drafted and presented by the NTP the model of providing incentives by combining provision from two sources as follow: to start with CNAM funds during first 2-3 months and continue support with GF funds. The presented estimation to the RP was with unclear multiplication factors in the estimation formula. No explanations were presented to unclear multiplication factors to several PR requests to the MoH and NTP, up to date. Nevertheless the PR presented the estimation of the NTP/ MoH to the GF which also raised the same questions to the estimation formula. It expected to have final clarifications from the NTP of the estimation on the new drafted model for provision incentives programm from both sources. Also it is expected to have a decision of the NTP and CNAM on the possibility to revise the MoH order on providing incentives from different sources. In primul semestru al 2014, 991 pacienți cu TB înregistrați în programul DOTS au primit suport motivational pentru îmbunătățirea aderentei la tratament. Indicatorul este atins in proportie de 89,%. Motivul variației: În prezent, în ţară există două surse de finanţare a suportului motivational: CNAM şi FG. Valorea pachetului oferit din sursele CNAM este mai consistentă. Din motiv că criteriile descrise în regulamentul MS cu privire la oferirea suportului motivational nu sunt exprese, SR AFI a informat coordonatori TB teritoriali din institutiile medico- sanitare de a prezenta lista de pacienţii cu TB sensibilă care nu au fost acoperiţi de CNAM pentru a oferi suport motivaţional din sursele FG. Majoritatea Coordonatorilor TB inscriu pacientii in listele pentru suport motivaţional de la CNAM, cu o valoare mai mare .. Deasemenea TB Coordonatorii incearca sa absorbe sumele acordate de CNAM. Dupa o perioada esenţială de comunicare intre RP, SR si autorităţile publice despre problemele mecanismului de oferire a suportului motivaţional, NTP a elaborat şi a prezentat un model de oferire a suportului care prevede: acordarea suportului iniţial din sursele CNAM ( 2-3 luni) şi ulterior de al GF, pe durata tratamentului. Estimarea prezentatăp conţine factori în formulă de multiplicare neclari. Clarificări vizavi de incertitudinile din formula de estimare abordate de RP nu au fost prezentate pînp la data curentă. Necatînd la acest fapt estimarea a fost prezentat la FG. La rindul său FG a ridicat aceleaşi intrebări, nefiind posibil fără ele examinarea documentului şi aprobarea noului model de suport. Se asteaptă ca NTP să ofere clarificări vizavi de estimarea pentru noul model al suportului motivaţional din ambele surse de finanţare. Deasemenea se asteaptă sa fie luată decizia finală de NTP şi CNAM privind posibilitatea de a modifica Ordinul MS pentru acordarea de stimulente din diferite surse.
P2 - trend |  | During the firs half of 2014, 283 MDR-TB patients were received incentives for improved treatment compliance . The indicator is achieved. În prima jumatate anului 2014, 283 de pacienţi MDR-TB au primit stimulente pentru îmbunătățirea respectării tratamentului. Indicatorul este atins.
P3 - trend |  | A total of 85 persons were trained, from them: 28 people from multidisciplinary teams of the community center; 25 people from NGOs in DOT and TB community aspects and 32 volunteers trained from the NGOs network in TB community aspects. The indicator is overachieved in proportion of 106%. 85 de persoane au fost instruite pe parcusul semestrului 1, 2014, dintre care: 28 de persoane din echipele multidisciplinare din centrul comunitar; 25 persoane din ONG-uri care activează în aspecte comunitare, DOT şi TB şi 32 voluntari din reţeaua de ONG-uri. Indicatorul este supraindeplinit în proporţie de 106%.
P1 |  | During the first half of the 2014, 991 TB patients registered under DOTS program received incentives for improved treatment compliance. The indicator is achieved at 89.%. Reason: Currently, in the country there are two sources of funding incentives’ support: CNAM and GF. The value of incentives offered through the CNAM is more consistent. Since the criteria described in the MoH regulation on providing incentives from the CNAM funds is not expressive, the SR AFI informed territorial TB coordinators from the TB health facilities to provide the list of sensitive TB patients that were not covered by the CNAM. Majority of TB coordinators register patients in the list for provision incentives with higher value, event the total sun approved by the CNAM does not predict to cover all needs. Also the TB doctors are focused on absorption the budget provided by the CNAM. After a long period of communication between PR, SR and public authorities on the issues related to the provision of incentives there were drafted and presented by the NTP the model of providing incentives by combining provision from two sources as follow: to start with CNAM funds during first 2-3 months and continue support with GF funds. The presented estimation to the RP was with unclear multiplication factors in the estimation formula. No explanations were presented to unclear multiplication factors to several PR requests to the MoH and NTP, up to date. Nevertheless the PR presented the estimation of the NTP/ MoH to the GF which also raised the same questions to the estimation formula. It expected to have final clarifications from the NTP of the estimation on the new drafted model for provision incentives programm from both sources. Also it is expected to have a decision of the NTP and CNAM on the possibility to revise the MoH order on providing incentives from different sources. In primul semestru al 2014, 991 pacienți cu TB înregistrați în programul DOTS au primit suport motivational pentru îmbunătățirea aderentei la tratament. Indicatorul este atins in proportie de 89,%. Motivul variației: În prezent, în ţară există două surse de finanţare a suportului motivational: CNAM şi FG. Valorea pachetului oferit din sursele CNAM este mai consistentă. Din motiv că criteriile descrise în regulamentul MS cu privire la oferirea suportului motivational nu sunt exprese, SR AFI a informat coordonatori TB teritoriali din institutiile medico- sanitare de a prezenta lista de pacienţii cu TB sensibilă care nu au fost acoperiţi de CNAM pentru a oferi suport motivaţional din sursele FG. Majoritatea Coordonatorilor TB inscriu pacientii in listele pentru suport motivaţional de la CNAM, cu o valoare mai mare .. Deasemenea TB Coordonatorii incearca sa absorbe sumele acordate de CNAM. Dupa o perioada esenţială de comunicare intre RP, SR si autorităţile publice despre problemele mecanismului de oferire a suportului motivaţional, NTP a elaborat şi a prezentat un model de oferire a suportului care prevede: acordarea suportului iniţial din sursele CNAM ( 2-3 luni) şi ulterior de al GF, pe durata tratamentului. Estimarea prezentatăp conţine factori în formulă de multiplicare neclari. Clarificări vizavi de incertitudinile din formula de estimare abordate de RP nu au fost prezentate pînp la data curentă. Necatînd la acest fapt estimarea a fost prezentat la FG. La rindul său FG a ridicat aceleaşi intrebări, nefiind posibil fără ele examinarea documentului şi aprobarea noului model de suport. Se asteaptă ca NTP să ofere clarificări vizavi de estimarea pentru noul model al suportului motivaţional din ambele surse de finanţare. Deasemenea se asteaptă sa fie luată decizia finală de NTP şi CNAM privind posibilitatea de a modifica Ordinul MS pentru acordarea de stimulente din diferite surse.
P2 |  | During the firs half of 2014, 283 MDR-TB patients were received incentives for improved treatment compliance . The indicator is achieved. În prima jumatate anului 2014, 283 de pacienţi MDR-TB au primit stimulente pentru îmbunătățirea respectării tratamentului. Indicatorul este atins.
P3 |  | A total of 85 persons were trained, from them: 28 people from multidisciplinary teams of the community center; 25 people from NGOs in DOT and TB community aspects and 32 volunteers trained from the NGOs network in TB community aspects. The indicator is overachieved in proportion of 106%. 85 de persoane au fost instruite pe parcusul semestrului 1, 2014, dintre care: 28 de persoane din echipele multidisciplinare din centrul comunitar; 25 persoane din ONG-uri care activează în aspecte comunitare, DOT şi TB şi 32 voluntari din reţeaua de ONG-uri. Indicatorul este supraindeplinit în proporţie de 106%.
P4 |  | n/a
P5 |  | 457 of new TB patients provided with DOT by the community (community centers and NGOs) received at least 25 DOT interventions during 1 month (visit to DOT center by the patient or visit to the patient by DOT supporters for drug intake). The indicator is overachieved in proportion of 138%. Reason for variance: AO AFI included and registered all the new TB patients provided in lists by Community Centers. 457 pacienţi noi cu TB au fost acoperiți cu servicii de comunitate (centre comunitare şi ONG-uri) ei au primit cel puţin 25 intervenţii DOT pe parcursul la o luna (vizite la centrul de DOT de către pacient sau vizite la pacient de suporterii DOT pentru consumul de medicamente). Indicatorul este realizat în proporţie de 138%. Motivul pentru variaţii: AO AFI au înclus şi înregistrat toţi pacienţii noi de TB prevăzuți în listele centrelor comunitare).
P6 |  | During the first semester of the 2014, 199 people (TB/HIV patients and their families) were reached by peer support groups. The indicator is achieved. În primul semestru al 2014, 199 de persoane (TB/HIV pacienţii şi familiile lor) au beneficiat de suport de la egal la egal. Indicatorul este atins
P7 |  | A total of 150 persons were trained, from them: 55 of local stakeholders attending workshops on TB and TB/HIV and 75 of peer educators trained to carry out informational work on TB and 20 journalists at national and district level trained; The indicator is achieved. Reason for variance: The number of journalists to attend the training course were increased based on the request within the establised budget. 150 persoane au fost instruite, din ei: 55 reprezentanți ai autorităților locale au participat la atelier de lucru în TB și TB/HIV şi 75 educători de la egal la egal instruiți să efectueze lucrul informațional pe TB şi 20 jurnalişti; Indicatorul este atins. Motivul variației este numărul de jurnaliști, aprobat să fie majorat, în limitele bugetului existent.
P8 |  | A total of 24 TB service staff trained in DR-TB management. The indicator is achieved. 24 persoane din serviciu TB au fost instruite în managementul TB-MDR. Indicatorul este atins.
P9 |  | During the first half of 2014, 16 eligible prison inmates on TB treatment were released. All of them were supported through the TB follow up program. In prima jumatate a 2014, au fost eliberați 16 deţinuţi aflați în tratamentul TB. Toți aceștia au fost susţinuți prin programul tratamentului TB de follow-up.
P10 |  | During S7, a total of 52 medical staff were trained. The indicator is achieved. Pe parcursul S7, au fost instruiţi 52 lucrători medicali. Indicatorul este atins.
Menu

## Actions
Dashboard: Moldova - TB
| Round 9 | Phase 2 |  |  |  | Report Period(Perioada de Raportare): |  | P10
| Latest Rating (Ultimul Rating): | A2 |  | PAS Center |  | From(De la): |  | 2014-01-01
|  |  | Empowerment of people with TB and Communities in Moldova |  |  |  | To(Pînă la): | 2014-06-30
Decisions and Actions
What is the overall status of this grant implementation?
| Key Recommendations from Oversight Group(s) |  |  |  | CCM Decision | Due Date | Person Responsible
Current Reporting Period
Actions to Implement / Previous Period
What is the overall status of this grant implementation?
| CCM Decision |  |  |  | Action Taken | Date | Person Responsible
Previous Reporting Period
#REF!
Menu

## Setup (hidden)
Dashboard: Moldova - TB
Set-up = List of validation for Grant Detail page
Component | Currency | Round | Phase | Period | Rating | LFA | Medicaments | Countries
Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select
HIV / AIDS | $ | Round 1 | Phase 1 | P1 | A1 | CA (Crown Agents) | Isoniazid | Afghanistan
MALARIA | € | Round 2 | Phase 2 | P2 | A2 | DEL (Deloitte) | Ethambutol | Albania
TB |  | Round 3 | RCC | P3 | B1 | DTT (DTT Emerging Markets) | Rifampicin | Algeria
HIVAIDS / TB |  | Round 4 |  | P4 | B2 | FIN (Finconsult) | Pyrazimamide | Angola
HSS |  | Round 5 |  | P5 | C | GT (Grant Thornton) | RDT | Argentina
|  | Round 6 |  | P6 |  | H-C (Hodar-Conseil) | NVP | Armenia
|  | Round 7 |  | P7 |  | KPMG (KPMG) | 3TC | Azerbaijan
|  | Round 8 |  | P8 |  | MSCI (MSCI) | D4T | Bangladesh
|  | Round 9 |  | P9 |  | PwC (PricewaterhouseCoopers) | AZT | Belarus
|  | Round 10 |  | P10 |  | STI (Swiss Tropical Institute), | DDI | Belize
|  |  |  | P11 |  | UNOPS | EFV | Benin
|  |  |  | P12 |  |  | AS/LF | Bhutan
[7 empty] | AS/AQ | Bolivia
[7 empty] | AS/MQ | Bosnia and Herzegovina
[7 empty] | Al/Lum | Botswana
Brazil
[7 empty] | TB nutri'l supplements | Bulgaria
[7 empty] | E-PAP | Burkina Faso
Burundi
Cambodia
Cameroon
Cape Verde
Central African Republic
Chad
Chile
China
China
Colombia
Comoros
Congo (Democratic Republic of the)
Congo (Republic of the)
Costa Rica
Cote d'Ivoire
Croatia
Cuba
Djibouti
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Ethiopia
Fiji
Gabon
Gambia
Georgia
Ghana
Global(LWF)
Guatemala
Guinea
Guinea-Bissau
Guyana
Haiti
Honduras
India
Indonesia
Iran (Islamic Republic of)
Iraq
Jamaica
Jordan
Kazakhstan
Kenya
Korea, Democratic Peoples Republic of
Kosovo (Serbia)
Kyrgyzstan
Lao PDR
Lesotho
Liberia
Macedonia, FYR
Madagascar
Malawi
Maldives
Mali
Mauritania
Mauritius
Moldova
Mongolia
Montenegro
Morocco
Mozambique
Multi-country Africa (West Africa Corridor Program)
Multi-country Africa(RMCC)
Multi-country Americas (Andean)
Multi-country Americas (CARICOM)
Multi-country Americas (CRN+)
Multi-country Americas (Meso)
Multi-country Americas (OECS)
Multi-country Americas (REDCA+)
Multi-country Western Pacific
Myanmar
Namibia
Nepal
Nicaragua
Niger
Nigeria
Pakistan
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Romania
Russian Federation
Rwanda
Sao Tome and Principe
Senegal
Serbia
Sierra Leone
Solomon Islands
Somalia
South Africa
Sri Lanka
Sudan
Suriname
Swaziland
Syrian Arab Republic
Tajikistan
Tanzania
Thailand
Timor-Leste
Togo
Tunisia
Turkey
Uganda
Ukraine
UN Theme Group on HIV/AIDS (West Bank and Gaza)
Uzbekistan
Viet Nam
Yemen
Zambia
Zanzibar (Tanzania)
Zimbabwe