## Menu
Dashboard: Moldova - HIV / AIDS
HIV / AIDS NFM, | Grant No. [Nr. Grantului]: MDA-H-PAS
V1.0
Finance
Programmatic
Management
Select the option you want to see:
Recommendations
Actions
Grant Detail
List of Indicators
Data Entry
Grant Information
Indicators
Reports

## List of Indicators
Dashboard: Moldova - HIV / AIDS
Financial information
Name: | Definition | Measurement | Data Sources
F1: Budget and disbursements by Global Fund [Bugetul și debursările de către Fondul Global] | Cumulative budget: Sum of the grant budget from period one (quarter, trimester, or semester) of the current phase, up to and including the dashboard reporting period. Cumulative Disbursments by GF: Sum of all the funds transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to and including the dasboard reporting period. | Currency of the grant ($ or Euro) Cumulative – Figures refer to budget and disbursements for all the periods of the phase up to and including the dashboard reporting period | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F2: Budget and actual expenditures by Grant Objective [Bugetul și cheltuielile actuale după Obiectivele Grantului] | Cumulative Budget per Objective: Sum of the grant budget by Objective, from period one of the current phase up to and including the dashboard reporting period. Cumulative Expenditure per Objective: Sum of amounts spent by Objective directly by the PR plus the amounts transferred by the PR to all SRs from the beginning of the phase up to and including dashboard reporting period, by Objective | • Cumulative – Figures refer to budget, disbursements or expenditure for all the periods of the phase up to and including the dashboard reporting period. | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F3: Disbursements and expenditures [Debursări și cheltuieli] | Disbursement by GF: Prior to this Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to but not including dashboard reporting period. Disbursement by GF: Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), during dashboard reporting period. PR disbursements and expenditure: Prior to this Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) up to but not including dashboard reporting period. PR disbursements and expenditure: Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) during dashboard reporting period. Disbursements to SRs: Prior to this Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), up to but not including dashboard reporting period. Disbursements to SRs:Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), in dashboard reporting period. SR expenditures: Prior to this Reporting period: The sum of all expenditures reported by the SRs, up to but not including dashboard reporting period. SR expenditures: Reporting period: The sum of all expenditures reported by the SRs, during dashboard reporting period. | Currency of the grant ($ or Euro) • Reporting period – Figures refer to budget, disbursements or expenditure for the reporting period to which the dashboard refers. • Prior to reporting period - Figures refer to the total budget, disbursements or expenditure for all the periods before but not including the current period. | PU/DR; PR data: SR reports to PR
F4: Latest PR reporting and disbursement cycle [Ultima perioadă de raportare și debursare a RP] | Days taken to submit final PU/DR to LFA – This indicator measures the number of calendar days it took the PR to send a final Performance Update and Disbursement Request (PU/DR) to the LFA after the end of the period. A 'final' PU/DR would be one for which the LFA did not require any further clarifications from the PR. The expected value is 45 days from the end of the period, as defined in the Grant Agreement. The actual value is the number of calendar days from the end date of the period to the date on which the PR sent to the LFA the final PU/DR. Days taken for disbursement to reach PR – This indicator measures the number of calendar days it took the Global Fund to send the latest disbursement to the PR's account after receipt of the acceptable PU/DR by the LFA. The expected number is 45 days. The actual number is the number of days from the date of transmission by the PR to the LFA of the acceptable PU/DR to the date the disbursement is received by the PR at its bank. Days taken for disbursement to reach SRs – This indicator measures the average number of days for disbursements to be made to all the SRs. The expected value for this indicator will be set locally by the PR and SRs, preferably in the Grant Operations Manual. The actual value is the average of the number of days from the receipt of the funds from the GF by the PR to the date the funds are received by each SR. Different SRs coudl receive funds on different dates and this indicator is the average across all SRs for the latest disbursement. | Number of calendar days; it refers only to reporting period for which the latest disbursement was received and is not cumulative | PR, LFA, GF emails and records; bank notification document or the notice of receipt by the PR to GF; SR reports to PR based on bank records
Management Information
Name: | Definition | Measurement | Data Source
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) [Statutul Condițiilor Precedente și a Acțiunilor Prestabilite în Timp] | Number of Conditions Precedent (CPs) and Time Bound Actions (TBAs ) fulfilled, or unfulfilled. Within the Unfulfilled category, we distinguish between those CPs and TBAs whose deadline has not passed and those for which the deadline has passed. | Number, cumulative to the dashboard reporting period. Number of fulfilled CPs and/or TBAs plus unfulfilled CPs and/or TBAs should equal the total number set by the Global Fund on the grant | PR records; Grant Performance Reports;
M2: Status of key PR management positions | Number of PR grant management positions planned currently filled or vacant. Full time equivalents of the managerial positions that are on the organizational chart (or otherwise planned) and directly responsible for ensuring grant implementation at the PR, and lead SRs (if necessary). This will include new hires, current staff who are assigned to work on the grant’s management, as well as any staff seconded from other divisions or partner organizations. | Number, in current reporting period | PR records
M3: Contractual arrangements (SRs) | Identified: Total number of potential SRs identified by the PR for the phase. Assessed: Total number of potential SRs assessed by the PR to determine whether they qualify to function as SRs for the grant. Approved: Total number of SRs that have been approved. Signed: Total number of SRs that have signed agreements/contracts with the PR under the grant. Receiving funding: Total number of SRs that are getting funds and/or supplies from the PR. Numbers of SRs Identified, Assessed, Approved, Signed and Receiving funds are cumulative for the phase, with the following exceptions: If an SR does not need new approval in Phase II, then approval in Phase I is counted. If an SR was signed in a previous Phase but is not working in the current Phase, that SR is no longer counted in Identified, Assessed, Approved. | Number, cumulative to the reporting period. A SR is an institution or program with its own workplan, budget and performance targets. | PR records; Sub-agreements/MOUs; CCM records
M4: Number of complete reports received on time | The total number of periodic reports with up-to-date financial, management and performance (programmatic) data received by the PR from SRs and by SRs from the SubSRs (SSRs) by the expected date. A 'complete' report is one that contains all the data that the PR requires for the PU/DR. The expected date would be set by the PR in the sub-agreements. | Number of reports received. The figure reflects only the period of reporting; it is not cumulative. | PR and SR records
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals | This indicator measures the budget approved for the current phase of the grant for purchase of health products and equipment and pharmaceuticals and medicines (categories 4 and 5 in the new Enhanced Financial Report), and the cumulative amounts of financial obligations and expenditures up to the dashboard reporting period. Budget approved: Total approved budget for purchases (categories 4 and 5) for the entire phase of the grant. It does not include the amounts for fees, management, operational costs, etc. Cumulative Obligations: Total of all order(s) placed and monies committed for these purchases by the PR up to and including the dashboard reporting period. Ideally, by the end of the Phase, budget should equal obligations. Cumulative expenditure: Total of actual Expenditures on category 4 and 5 up to and including the dashboard reporting period (whether paid by PR or authorized to be paid by another entity like GF or other). | Currency of the grant ($ or Euro) | Grant agreement approved budget (for categories 4 and 5 of Enhanced Finance Reporting in current phase); and PR financial data (for expenditures), and/or PSM unit (for orders placed and funding committed or obligated).
Note: Category 6 of the EFR will not be considered as part of the budget for pharmaceuticals. Category 6 has several expenditures that are difficult to disaggregate or quantify, such as warehousing costs, distribution costs (particularly when distibution is done by MOHs), and others that are related to operational costs of the PSM component.
M6: Difference between current and safety stock | This indicator is a snapshot of the difference between the current (or last month) stock level of a specific product (medicine in single, fixed-dose combination, bednets, diagnostic kits, etc.) of a particular dose, expressed in monthly needs (number of months of treatment available) for all patients in the program, and the safety or buffer stock (also expressed in months) as established by the disease program, warehouse system or essential drugs program, for the particular product and dosage. The table will show the difference in months in colors: • RED: when the difference is negative or 0, showing that months of existing stock are lower than or equal to what has been established as months of safety stock • YELLOW: when we have more than the level of safety stock (>0) but less than 3 months (+3). • GREEN: when the difference is between 3 and 18 months. • VIOLET: When the difference shows that the level above the safety stock is greater than or equal to 18 months indicating a potential overstock) problem. For a full description of how this indicator is calculated, please see the User’s Manual. | Number of months | PR records: Warehouse data.
Programmatic Indicators (from Performance Framework) [Indicatorii programatici]
Indicator | Definition (from M&E Plan, 2014) [Definiție (din planul M&E,2014] | Measurement | Data Source [sursa de date]
Percentage of PWID reached with HIV prevention programs - defined package of services | Numerator: Number of PWID who have received a defined package of HIV prevention services. Denominator: Estimated number of PWID in the targeted area. Package of service: needle exchange, condom distribution, specialist consultation (psychologist, social assistant, medical), distribution of informational material, peer to peer concelling, VCT etc. The beneficiary is considered "reached" if he/she received at least two services from the package listed above, one of which is the needle exchange. Note: The estimated number of PWIDs for the sites currently covered and planned for coverage (currently 24, plus planned Cantemir, Leova, Cahul, UTA Gagauzia = 28 site) is 25,310 (the total estimated number of PWIDs in RM is 30,200). There are currently 7 projects (including 1 in Tiraspol, Transdniester region) that cover both civilian (5 projects) and penitentiary sectors (2 projects) covering 24 sites. The 5 projects in civil sector are regional and cover from two to six rayons. The penitentiary sector's projects cover 11 penitentiary institutions from the right bank (Pruncul, Rusca, Cricova - 2 penitentiaries, Branesti, Soroca, Leova, Balti,Taraclia, etc.) and 3 penitentiaries from the left bank (Grigoriopol, Glinoe village and Tiraspol). The numbers of project planned for NFM period is 8 and will cover 28 sites. | The beneficiary is considered "reached" if he/she received at least two services from the package listed below, one of which is the needle exchange. Package of service: (needle exchange, condom distribution, specialist consultation (psychologist, social assistant, medical), distribution of informational material, peer to peer counseling, VCT etc.) in the reporting period. The baseline value (39.4%) is for the covered sites [24]. The targets are cumulative annually. Absolute values will be reported semiannually and percentage will be reported annually. Targets are cumulative annually. | Numerator: Administrative records; Denominator: Estimated population size [28 sites].
Percentage of individuals receiving Opioid Substitution Therapy who received treatment for at least 6 months | Numerator: number of individuals completing at least 6 months of continuous treatment on OST that initiated treatment 6-12 months prior to the end of the reporting period. Denominator: total number of individuals that initiated treatment 6-12 months prior to the end of reporting period. The targets refer to the patient cohort (both new and repeated cases) that initiated treatment in the first 6 months of the last 12 months period. The indicator is linked to percentage and absolute numbers will be provided when reporting results. There are curently 3 OST sites [Republican Narcological Dispensary, Balti Municipal Hospital and the Department of Penitentiary Institutions (12 penitentiary institutions: #1 Taraclia, #3 Leova, #4 Cricova, #6 Soroca, #7 Rusca, #9 Pruncul, #11 Balti, #15 Cricova, #16 Pruncul, #17 Rezina, #18 Branesti, #13 Chisinau)]. At the same tyme adherence supprot is provided through daily centers in Chisinau, Balti, Cahul and one mobile unit for penitenciary system. For funding period the scale up of OST to 5 new sites is planned. | Determine the number of people who initiated OST (naïve or retreatment) in the first six months of the last 12 months and evaluate how many of these people remained in OST at least 6 months continuously. 6 months cohort based evaluations. Targets are not cumulative. | OST sites administrative records (RND, Balti municipal hospital and DPI and 5 new sites to be open in 2015)
Number of drug users reached with drug substitution therapy | The indicator refers to new beneficiaries from both civilian and penitentiary sectors enrolled in opioide substitution therapy. Additionally the number of daily patients on OST will be reported when reported enrolment [at the end of year 2013 a total number of 337 patients were on treatment]. There are curently 3 OST sites [Republican Narcological Dispensary, Balti Municipal Hospital and the Department of Penitentiary Institutions (12 penitentiary institutions: #1 Taraclia, #3 Leova, #4 Cricova, #6 Soroca, #7 Rusca, #9 Pruncul, #11 Balti, #15 Cricova, #16 Pruncul, #17 Rezina, #18 Branesti, #13 Chisinau)]. For funding period the scale up of OST to 5 new sites is planned. | Determine the number of drug users enrolled in drug substitution therapy. The targets are cumulative annually. | Patient records, OST registers.
Percentage of sex workers reached with HIV prevention programs defined package of services | Numerator: Number of sex workers who have received a defined package of HIV prevention services. Denomenator: Estimated number of sex workers in the targeted area. Package of service: condom distribution, distribution of informational materials, specialist consultation (psychologist, social assistant, medical), STI management, VCT, peer to peer counseling, distribution of syringes and distribution of disinfectants. The beneficiary is considered "reached" if he/she received at least two services from the package listed above, one of which is the condom. Absolute values will be reported semiannually and percentage will be reported annually. Data source: Numerator: Administrative records; Denominator: Estimated population size [5]. The estimated number of SWs in the sites currently covered and planned for coverage (5 site) is 6,382 (the total estimated number of SWs in RM is 12,000). There are currently 3 projects provide prevention activities for CSWs, one in Chisinau, one in Orhei and one in the northern region of the country covering Balti and Ungheni sites. The numbers of project planned for NFM period is 4 and will cover 5 sites (four existing plus Tiraspol). | The beneficiary is considered "reached" if he/she received at least two services from the package listed below, one of which is the condom. Package of service: condom distribution, distribution of informational materials, specialist consultation (psychologist, social assistant, medical), STI management, VCT, peer to peer counseling, distribution of syringes and distribution of disinfectants. The baseline value (46.6%) is for the covered sites [4]. The targets are cumulative annually. Absolute values will be reported semiannually and percentage will be reported annually. | Numerator: Administrative records; Denominator: Estimated population size [5].
Percentage of MSM reached with HIV prevention programs - defined package of services | Numerator: Number of MSM who have received a defined package of HIV prevention services. Denominator: Estimated number of MSM in the targeted area. Package of service: condom distribution, lubricant distribution, IEC counselling, psychologist consultation, VCT, peer to peer counseling, SSSP activities. The beneficiary is considered "reached" if he received at least two services from the package listed above, one of which is the condom or lubricant distribution. The baseline value (22.6%) is for the covered sites [3]. The targets are cumulative annually. Absolute values will be reported semiannually and percentage will be reported annually. Data source: Numerator: Administrative records; Denominator: Estimated population size [3]. The estimated number of MSMs for the sites currently covered and planned for coverage (3 site Chisinau, Balti si Tiraspol) is 7,100 (the total estimated number of MSMs in RM is 13,500). There is currently one project based in Chisinau which covers beneficiaries from Chisinau, Balti and, starting with May 2013 - from Tiraspol. For the funding period the services will be scaled up through further expansion of services in Balti and Tiraspol. | The beneficiary is considered "reached" if he received at least two services from the package listed below, one of which is the commodity (condom or lubricant) distribution. Package of service: condom distribution, lubricant distribution, IEC counselling, psychologist consultation, VCT, peer to peer counseling, SSSP activities. The baseline value (22.6%) is for the covered sites [3]. The targets are cumulative annually. Absolute values will be reported semiannually and percentage will be reported annually. | Numerator: Administrative records; Denominator: Estimated population size [3].
Proportion of new individuals who test positive for HIV, enrolled in care (pre-ART or ART) services by NGOs | Numerator: Number of new HIV patients tested positive through HIV testing provided by NGOs, who have accessed HIV care/pre-ART, or ART services for the first time during the reporting period. Denominator: Number of new individuals who test positive for HIV during the reporting period. The indicator is linked to percentage and absolute numbers will be provided when reporting results. The baseline will be available at February 15, 2015 when data for year 2014 will be analised. Data source: Numerator: HIV care record; Denominator: NGO VCT record. The data represents ratio between the numbers of PLHIV reported at care sites and the numbers diagnosed positive at NGO VCT sites. | The data represents ratio between the numbers of PLHIV reported at care sites and the numbers diagnosed positive at NGO testing sites where individual level linkage to care is not possible and will be used as a proxy measure to assess linkage to care and treatment. | Vital and disease specific registry
Number of psychosocial support NGO providers that are accredited by state to provide social services for KAP (PLHIV, PWUD, etc.) | The accreditation for NGOs to provide social support legal framework, including minimum required criteria is now in the process of elaboration with the further approval by MLSPF. In terms of feasibility the assumption is that all necessary package of legal framework will be finalized and approved in 2015. In the 2016 the framework and criteria will be analyzed by NGOS and will serve as a benchmark for institutional capacity building and proper mechanisms elaboration in NGO that as a result will undergo the assessment and will receive accreditation by state to provide social services for KAP. In 2017 year another 3 NGOs will undergo the same process resulted in accreditation received. Targets are cumulative over program term. Baseline: there are curently 9 organizations in Moldova that provide care and support to PLHIV, out of which 3 are from Transnistria and can not be accredited in Moldovan, thou the baseline is 6. | The organization is considered accredited by state as social service provider when it receive the Accreditation certificates from specialized agencies. Targets are cumulative over program term. Baseline: there are currently 9 organizations in Moldova that provide care and support to PLHIV, out of which 3 are from Transnistria and cannot be accredited in Moldovan, thou the baseline is 6. The legal framework for accreditation for NGOs to provide social support, including minimum required criteria is now in the process of elaboration. The MLSPF planes to finalize and approve the necessary package of legal framework in 2015. In 2016, the framework and criteria will be analyzed by NGOs and will serve as a benchmark for institutional capacity building and proper mechanisms elaboration in one pilot NGO that as a result will undergo the accreditation process. In 2017 another 3 NGOs will undergo the same process resulting in received accreditation. | Administrative records
Number of human rights strategic litigation cases for PLHIV initiated | Indicator refers to cases of KAP rights violation initiated for strategic litigation in order to change the existing practices. Targets are cummulative annualy. | Indicator refers to cases of PLHIV rights violation initiated for strategic litigation in order to change the existing practices. | Administrative records
Indicator Number: Name (Perf Framework No.) | Definition | Measurement | Data Source
The indicators should be selected by the PRs and members of the CCM or the CCM Technical Committee, from the Performance Framework |  |  | Performance Framework
Menu

## Data Entry
Grant information [Informatia de Grant]
| Country [Țara]: | Moldova |  | Title of the Grant [Numele Grantului]: |  | Strengthening HIV Control in Moldova
| Grant No. [Nr. Grantului]: | MDA-H-PAS |  | Component [Componentul]: |  | HIV / AIDS | Total Funding[Suma totala]: | 8284729
| Principal Recipient [Recipientul Principal]: | Center for Health Policies and Studies (PAS Center) |  |  | Round [Runda]: | NFM | Phase [Faza]:
| Start Date (dd/Mmm/yy) [Data Demarării (zz/ll/aa)]: | 01 January 2015 |  | Local Fund Agent [Agentul Local al Fondului]: |  | PwC (PricewaterhouseCoopers)
| Latest Rating [Ultimul Rating]: | A1 |  | Fund Portfolio Manager [Portfolio Manager]: |  | Tsovinar Sakanyan
Information reporting period [Informația despre perioada raportată]
| Report Period [Perioada de raportare]: | P1 | From [de la]: | 2015-01-01 | To[Pînă la]: | 2015-06-30 | Date of entry of information[Data de introducere a informației]: |  | 2015-09-01
| Prepared by [Pregătit de către]: |  | PAS Center
Information on indicators [Informația despre indicatori]
Enter the data based on the colour-coded cells [Introduceți datele bazîndu-vă de celulele codificate prin culoare]
| Financial Information [Informația Financiară]: |  | Management Information [Informația pe Management]: |  |  | Programmatic Information [Informația Programatică]:
| Financial Information [Informatia Financiara]: | [8 empty] | Enter finance data in every orange cell like this [Introduceți datele financiare in fiecare celula portocaliu ca aceasta].
| Currency of the grant[Valuta Grantului] |  | €
F1: Budget and disbursements by Global Fund [Bugetul și debursările de către Fondul Global]
| Disbursement [Debursări] | [15 empty] | 1489741.6473
| Reporting period [perioada de raportare] | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12 | % Cumulative |  |  | 0
| Budget (in €) | P1: 1489741.6473 | 147.8% |  |  | 0
| Disbursements by GF (in €) | P1: 2201431 |  |  |  | 0
| Cumulative budget [Buget cumulativ] | 1489741.6473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Cumulative disbursements [Debursări cumulative] | 2201431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
|  | 147.8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0
F2: Budget and actual expenditures by Grant Objective [Bugetul și cheltuielile actuale după Obiectivele Grantului]
| Grant Objective [obiectivele Grantului] | P1: Cumulative Budget (in €); P2: Cumulative Expenditures (in €)
1 | To increase access to evidence-based HIV prevention | P1: 921440.9166; P2: 911528.2456
| Prevention programs for MSM and TGs | P1: 86961.5554; P2: 97038
| Prevention programs for sex workers and their clients | P1: 184768.5636; P2: 209589.88
| Prevention programs for people who inject drugs (PWID) and their partners | P1: 649710.7977; P2: 604900.3656
2 | To ensure universal access to comprehensive HIV treatment, care and support | P1: 297176.9491; P2: 347953
| Treatment, care and support | P1: 297176.9491; P2: 347953
| HSS - Health information systems and M&E | P1: 0; P2: 0
3 | To strengthen comminities capacity and to ensure program sustenability | P1: 173663.3666; P2: 185592.4504
| Removing legal barriers to access | P1: 47385.73; P2: 55371
| Community systems strengthening | P1: 126277.6366; P2: 130221.4504
| Program management | P1: 97460.415; P2: 90704.18
| Total | P1: 1489741.6473; P2: 1535777.876; P4: OK: Data match
| F3: Disbursements and expenditures [Debursări și cheltuieli] | [15 empty] | 0
0
|  | P1: Prior to reporting period [Către perioada de raportare]; P2: Current reporting period [Perioada de raportare curentă]; P3: Total Spent and Disbursement (in €) |  |  | 0
| Disbursed by Global Fund (Debursat de către Fondul Global) | P1: 2201431; P3: 2201431
| PR expenditure and disbursement (Cheltuielile și debursările RP ) | P2: 1535777.876; P3: 1535777.876
| Disbursed to SRs (Debursări către SR) | P2: 1215977; P3: 1215977
| SR expenditures (Cheltuielile SR) | P2: 1138287.5222; P3: 1138287.5222
F4: Latest PR reporting and disbursement cycle [Ultima perioadă de raportare și debursare a RP]
Last fund disbursement: Number of calendar days [Ultima debursare a surselor: Număr de zile calendaristice]
|  | Expected (days) Preconizat (zile) | Actual (days) Actual (zile)
| Days taken to submit final PU/DR to LFA (Zile necesare pentru remiterea PU/DR final către ALF) | P1: 45; P2: 45
| Days taken for disbursement to reach PR (Zile necesare pentru debursare către RP) | P1: 45; P2: 0
| Days taken for disbursement to reach SRs (Zile necesare pentru debursare către SR) | P1: 20; P2: 5
| Management Information [Informația pe Management]: | P6: Enter management data in every blue cell [Întroduceți datele pentru management în celulele albastre].
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) [Statutul Condițiilor Precedente și a Acțiunilor Prestabilite în Timp]
|  |  | Fulfilled [Îndeplinite] | Not fulfilled, but within deadline [Ne îndeplinite dar realizarea în conformitate cu planul] | Not fulfilled, and past the deadline [Ne îndeplinite și au depășit termenul de realizare] | Total
| Conditions precedent (CPs) [Conditii precedente] | P3: 2; P5: 2
| Time Bound Actions (TBAs) [Acțiuni Prestabilite în Timp] | P3: 0; P5: 0
M2: Status of key PR management positions
|  | Planned | Filled | Vacant
| PMU | P1: 14; P2: 14; P3: 0
M3: Contractual arrangements (SRs)
|  | Identified | Assessed | Approved | Signed | Receiving Funding
| SRs | P1: 2; P2: 2; P3: 2; P4: 2; P5: 2
M4: Number of complete reports received on time
|  | # Expected | # Received | Pending
| SSR to SR | P1: 16; P2: 16; P3: 0
| SRs to PR | P1: 2; P2: 2; P3: 0
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals
|  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
| Budget Approved* | P1: 194899
Obligations
| Expenditures | P1: 195091
| Budget Approved cumulative* | P1: 194899
| Obligations cumulative | P1: 0
| Expenditures cumulative | P1: 195091
* Includes only EFR category 4 and 5 (Health products and health equipment & Medicines and Pharmaceuticals)
M6: Difference between current and safety stock
| Component | Products | (1) Number of tablets per patient per day (Review country treatment guidelines) | (2 = 1 x 30) Monthly treatment (Tablets per patient x 30 days) | (3) Total patients in treatment | (4 = 2 x 3) Total # tab/pills required for all patients per month | (5) Current stock in central warehouse (that does not expire within the next 3 months) | (6 = 5 / 4) Stock level expressed in months of treatment for all current patients | (7) Level of safety stock (expressed in months and defined by country) | (8 = 6 - 7) Difference between current stock and safety stock
| Please Select | P1: Please Select
Please Select
Please Select
Please Select
| Programmatic Information: | P9: Enter performance data in every yellow cell.
| Programmatic indicators (Performance Framework ) |  |  | Code | Directly Tied? |  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
TOP 3 | Percentage of PWID reached with HIV prevention programs - defined package of services (Procentul consumatorilor de droguri injectabile (CDI) acoperiți cu servicii în cadrul programelor de prevenire HIV - pachet de servicii definit) |  |  | KP-1d | Yes | Target | P1: 3125; P2: 6250
[6 empty] | Achieved | P1: 816; P2: 9164
| Percentage of sex workers reached with HIV prevention programs defined package of services (Procentul lucrătoarelor sexului comercial (LSC) acoperite cu servicii în cadrul programelor de prevenire HIV - pachet de servicii definit) |  |  | KP-1c | Yes | Target | P1: 900; P2: 1800
[6 empty] | Achieved | P1: 347; P2: 3476
| Percentage of MSM reached with HIV prevention programs - defined package of services (Procentul bărbaţilor care fac sex cu barbații (BSB) acoperițicu servicii în cadrul programelor de prevenire HIV - pachet de servicii definit) |  |  | KP-1a | Yes | Target | P1: 675; P2: 1350
[6 empty] | Achieved | P1: 209; P2: 1243
| Percentage of individuals receiving Opioid Substitution Therapy who received treatment for at least 6 months (Procentul persoanelor care au beneficiat de tratament de substituție cu metadonă care s-au aflat în tratament timp de cel puțin 6 luni) |  |  | KP-5 | Yes | Target | P1: n/a; P2: 61%
[6 empty] | Achieved | P1: n/a; P2: 55%
| Number of drug users reached with drug substitution therapy (Numărul consumatorilor de droguri care au inițiat tratamentul de substituție cu metadonă) |  |  |  | Yes | Target | P1: 41; P2: 75
[6 empty] | Achieved | P1: 37; P2: 69
| Proportion of new individuals who test positive for HIV, enrolled in care (pre-ART or ART) services by NGOs (Proporția persoanelor noi testate la HIV cu rezultat pozitiv, înrolațe în servicii de îngrijire (pre-TARV sau TARV) de către ONG-uri.) |  |  |  | Yes | Target | P1: n/a; P2: n/a
[6 empty] | Achieved | P1: n/a; P2: n/a
| Number of psychosocial support NGO providers that are accredited by state to provide social services for KAP (PLHIV, PWUD, etc.) (Numărul ONG-lor prestatoare de support psiho-sociale, acreditate de stat pentru prestarea serviciilor sociale populațiilor cheie afectate (PTHIV, CDI etc.)) |  |  |  | Yes | Target | P1: n/a; P2: n/a
[6 empty] | Achieved | P1: n/a; P2: n/a
| Number of human rights strategic litigation cases for PLHIV initiated (Numărul de cazuri de încălcare a drepturilor PTH inițiate pentru litigare strategică) |  |  |  | Yes | Target | P1: 5; P2: 10
[6 empty] | Achieved | P1: 5; P2: 10
| Table is automatically updated. No data or information is to be entered here. |  |  | Code | Directly Tied? |  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
| Percentage of PWID reached with HIV prevention programs - defined package of services (Procentul consumatorilor de droguri injectabile (CDI) acoperiți cu servicii în cadrul programelor de prevenire HIV - pachet de servicii definit) |  |  | KP-1d | Yes | Target | 3125 | 6250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Achieved | 816 | 9164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Percentage of sex workers reached with HIV prevention programs defined package of services (Procentul lucrătoarelor sexului comercial (LSC) acoperite cu servicii în cadrul programelor de prevenire HIV - pachet de servicii definit) |  |  | KP-1c | Yes | Target | 900 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Achieved | 347 | 3476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Percentage of MSM reached with HIV prevention programs - defined package of services (Procentul bărbaţilor care fac sex cu barbații (BSB) acoperițicu servicii în cadrul programelor de prevenire HIV - pachet de servicii definit) |  |  | KP-1a | Yes | Target | 675 | 1350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Achieved | 209 | 1243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on B30: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.
Note on B76: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B82: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B97: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.
Menu

## Grant Detail
Dashboard: Moldova - HIV / AIDS
Country: | Moldova |  | Title of the Grant: |  | Strengthening HIV Control in Moldova
Component: | HIV / AIDS | Grant No. | MDA-H-PAS | Start Date: |  | 01 January 2015 | Total Funding | 8284729
Round: | NFM | Phase: | 0 | Principal Recipient: |  | Center for Health Policies and Studies (PAS Center)
Report Period: | P1 | from: | 2015-01-01 | to: |  | 2015-06-30 | Latest Rating: | A1
Local Fund Agent: | PwC (PricewaterhouseCoopers) |  |  | Fund Portfolio Manager: |  | Tsovinar Sakanyan
Prepared by: | PAS Center |  |  | Report preparation date: |  | 2015-09-01
http://www.crwflags.com/fotw/flags/country.html
Menu

## Finance
Dashboard: Moldova - HIV / AIDS
NFM | 0 |  |  |  | Report Period [Perioada de raportare]: |  | P1
Latest Rating [Ultimul Rating]: | A1 |  | Center for Health Policies and Studies (PAS Center) |  | From [de la]: |  | 2015-01-01
|  | Strengthening HIV Control in Moldova |  |  |  | To[Pînă la]: | 2015-06-30
Financial Indicators
F1: Budget and disbursements by Global Fund [Bugetul și debursările de către Fondul Global] - in (€) Report Period [Perioada de raportare]: P1 |  |  |  | F3: Disbursements and expenditures [Debursări și cheltuieli] - in (€) Report Period [Perioada de raportare]: P1
Comments: | By June 30, 2015, the total amount disbursed by TGF to PAS Center was EUR 2,201,431 (Actual 2,201,431/Budget 1,489,742). The cumulative disbursement rate is 147,8 %. The variance is due to the amount of EUR 711,689 Euro that is the buffer for quater 3, 2015. (Până la 30 iunie 2015, Centrului PAS i-au fost debursate de către Fondul Global 2,201,431 Euro (Actual 2,201,431/Budget 1,489,742). Rata cumulativă a debursării este de 147,8 %. Variația este cauzată de faptul că disbursarea cumulativă include un buffer pentru trimestrul 3, 2015 în valoare de 711,689 Euro). |  |  | Comments: | The cummulative rate of absorption from disbursement (expenditure at PR&SR level) as of June 30. 2015 is 66% due to the buffer (Actual 1,458,088/Disbursement 2,201,431) and 98% from disbursement for the reported period (Actual 1,458,088/Disbursement 1,489,742). The variance for the reporting period (EUR 31,654) is mainly determined by schedule of payments to SRs and other sub-contractors and engagements to be paid during next period. (Rata cumulative de absorbție din disbursare (cheltuieli la nivel de PR & SR) la data de 30 iunie 2015 este de 66% din cauza buffer-ului (Actual 1,458,088/Ddisbursat 2,201,431) și de 98% din disbursarea pentru perioada raportată (Actual 1,458,088/Disbursat 1,489,742). Variația pentru perioadă raportată (31,654 Euro) este determinată în mare parte de graficul de disbursare către Ssr și alți sub-contractori și angajamentele care urmează să fie plătite în perioada următoare.)
F2: Budget and actual expenditures by Grant Objective [Bugetul și cheltuielile actuale după Obiectivele Grantului] - in (€) Report Period [Perioada de raportare]: P1 |  |  |  | F4: Latest PR reporting and disbursement cycle [Ultima perioadă de raportare și debursare a RP] Report Period [Perioada de raportare]: P1
Comments: | The PR cash outflow rate for the reported period is 103% (Actual 1,535,778/Budget 1,489,742) from the semiannual budget. The variance for the reporting period is over expenditure of EUR 46,036 mainly due to overspendings due to the schedule of disbursement to SR and other sub-contractors that include one buffer month from the following quarter, commitments to be paid during period 2 and payments deducted from disbursements to SR SFM for services planned to start start in semester 2. (Rata de absorbție pentru perioada raportată este de 103% (Actual 1,535.778/Budget 1,489.742 Euro) din bugetul semi anual. Variația dintre buget și cheltuieli pentru perioada raportată constituie o supra cheltuială de 46.036 Euro fiind în mare parte determinată de supra celtuieli asociate graficului de disbursare către SR și alți sub-contractori care include o lună de buffer, angajamente care vor fi acoperite în perioada următoare și plăți deduse din debursarea către SR FSM pentru serviciile planificate pentru semstrul 2. |  |  | Comments: | The PU for Semester 1 year 2015 has been submitted to LFA in due terms (45 days after the end of reported period). The first disbursment under the NFM (for S1, 2015 plus one quarter buffer) grant has been made in advance befor grant implementation start. (Actualizarea progresului pentru semestrul 1 anul 2015 a fost remisa Agentului Local al Fondului în termenii stabiliți (45 de zile după finisarea perioadei raportate). Prima disbursare a forst facută în avans (pentru semestrul 1, 2015 plus un trimestru buffer) pînă la începerea implementării grantului.
Last fund disbursement: Calendar days
[6 empty] | Expected (days) | Actual (days)
|  |  |  | Days taken to submit final PU/DR to LFA (Zile necesare pentru remiterea PU/DR final către ALF) |  | 45 | 45
|  |  |  | Days taken for disbursement to reach PR (Zile necesare pentru debursare către RP) |  | 45 | 0
|  |  |  | Days taken for disbursement to reach SRs (Zile necesare pentru debursare către SR) |  | 20 | 5
Menu

## Management
Dashboard: Moldova - HIV / AIDS
NFM | 0 |  |  |  |  | Report Period [Perioada de raportare]: |  | P1
Latest Rating [Ultimul Rating]: | A1 |  | Center for Health Policies and Studies (PAS Center) |  |  | From [de la]: |  | 2015-01-01
|  | Strengthening HIV Control in Moldova |  |  |  |  | To[Pînă la]: | 2015-06-30
Management Indicators
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) [Statutul Condițiilor Precedente și a Acțiunilor Prestabilite în Timp] Report Period [Perioada de raportare]: P1 |  |  |  | M2: Status of key PR management positions Report Period [Perioada de raportare]: P1
Comments: | There are two conditions applicable to this Grant Confirmation: - 5.1. In accordance with the Global Fund Board Decision Point GF/B28/DP4: Evolving the Funding Model (Part Two), commitment and disbursement of 15% of the Republic of Moldova aggregate allocation of EUR 28,640,132, which is equal to EUR 4,296,020, is subject to the Republic of Moldova compliance with the Global Fund willingness to pay requirement. Status: Unmet - In progress (This is a grant life condition related to both NFM grant in country for HIV and TB. Compliance can be monitored annually based on the fulfilment of country commitments as per the CN for both diseases.) - 5.2. By no later than 31 December 2016, the Principal Recipient, in collaboration with the Country Coordinating Mechanism, other stakeholders and partners in the Republic of Moldova, shall deliver to the Global Fund a sustainability plan for the national HIV program, endorsed by the government of the Republic of Moldova, in form and substance satisfactory to the Global Fund. Status: Unmet - In progress (The development of the sustainability plan has started in 2015 with the development of national HIV/AIDS Program for the period 2016-2020, will continue in 2016 and be finalized in accordance with the schedule. The process will be guided by CCM, and the technical assistance planned under TGF NFM Grant will be supported by PCIMU as part of the Program Management Module; Intervention - Policy, planning, coordination and management; Activity - Assessment of the management of NAP & Development of NAP Sustainability Plan.) (Există două condiții aferente confirmării Grantului curent: - 5.1. În conformitate cu decizia Bordului Fondului Global punctul GF/B28/DP4: Evoluând Modelul de Finanțare (partea a doua), angajamentul și disbursarea a 15% din alocația totală a Republicii Moldova de 28,640,132 Euro, care este egală cu 4,296,020 Euro este condiționată de respectarea de către Republica Moldova a cerințelor Fondului Global privind ”Disponibilitatea de a plăti”. Statut: neîndeplinită - în progres (Aceasta este o condiție întregului ciclu de viață a grantului aferentă ambelor granturi NFM în tara HIV și TB. Respectarea acestei condiții va fi monitorizată anual pe baza îndeplinirea angajamentelor asumate de țărilor în Notele de Concept pentru ambele maladii.) - 5.2. Nu mai târziu la 31 decembrie 2016, Recipienții Principali, în colaborare cu Comitetul National de Coordonare, alți părți interesate și parteneri din Republica Moldova, vor rpezenta Fondul Global un plan de sustenabilitate pentru programul național HIV, aprobat de guvernul Republicii Moldova, în formă și în substanță satisfăcătoare Fondului Global. Statut: neîndeplinită - în progres Elaborarea planului de sustenabilitate a început în 2015 odată cu elaborarea Programului Național HIV/SIDA pentru perioada 2016-2020, va continua în 2016 și va fi finalizat în conformitate cu graficul prestabilit. Procesul va fi ghidat de CNC, iar asistența tehnică prevăzute în Grantul NFM finanțat de Fondul Global va fi asigurată de către UCIMP, ca parte componentă a modulului Managementul Programului; Intervenția - Politici, planificare, coordonare și management; Activitatea - Evaluarea managementului Programului Național HIV & Elaborarea Planul de Sustenabilitate al PN.)) |  |  | Comments: | Three full time positions and 11 part time. (Trei poziţii cu normă plină şi unsprezece - parţială.)
M3: Contractual arrangements (SRs) Report Period [Perioada de raportare]: P1 |  |  |  | M4: Number of complete reports received on time Report Period [Perioada de raportare]: P1
Comments: | Two Sub-recipients (SRs) have been identified to implement different components within the project: Soros Foundation-Moldova (SFM) and Positive Initiative (PI). Both SRs have been assessed by PAS Center. Two sub-grant agreements have been signed following the assessment and both SRs that receive funds within the grant. (Doi Sub-Recipienţi (SR) au fost identificaţi pentru a implementa diferite componente în cadrul proiectului: Fundația Soros-Moldova (FSM) și Inițiativa Pozitivă. Ambii SRs au fost evaluați de către Centrul PAS. Urmare a evaluării au fost semnate două acorduri de sub-grant și ambii SR primesc resurse din cadrul grantului. |  |  | Comments: | The SR’s quarterly reports (financial report, activity report and performance framework) are submitted no later than 25 days after close of each quarter, and are generally submitted on time. The preliminary version of all reports are presented to the Principle Recipient for clearance no later than 15 days after the close of each quarter. The clearance period vary from one SR to an other subject to the completeness and consistence of the reports. For the SR SFM the Sub-subrecipients financial reports are due once in four months and can be submitted during the following 45 days after the period, the activity reports are due not later than 10 days from the end of the reporting period (quarter for care and support services, and - month for the Harm Reduction services) and are generally submitted in time. During the reporting period reflected in this dashboard the reports due from the 14 SRs were submited in time. For the SR New Life the 2 Sub-subrecipient reports (financial, activity and indicators) are due not later than 15 days after the close of each quarter and are generally submitted in time. (Rapoartele trimestriale ale SR (raport financiar, raport de activitate și cadrul de performanță) urmează a fi transmise RP nu mai târziu de 25 de zile de la încheierea fiecărui trimestru. Versiunea preliminară a rapoartelor este prezentată RP pentru verificare nu mai tîrziu de 15 zile după terminarea fiecărui trimestru. Perioada de verificare şi aprobare variază de la un SR la altul în funcţie de exhaustivitatea și consistență rapoartelor. Rapoartele sunt de regulă prezentate la timp. Pentru SR FSM rapoarte financiare ale Sub-subrecipienţilor (Ssr) urmează a fi transmise o dată la patru luni și pot fi prezentate în termen de 45 zile de la finalul perioadei raportate, rapoartele de activitate urmează a fi prezentate nu mai târziu de 10 zile de la sfârșitul perioadei de raportare (trimestrial pentru serviciile de îngrijire și suport și lunar pentru serviciile de reducere a riscurilor) și sunt, în general, prezentate la timp. Pe parcursul perioadei de raportare reflectată în aces raport, raportele de la cei 14 Sub-subrecipienți au fost transmise la timp. Pentru SR Inițiativa Pozitivă cele două rapoarte ale Sub-subrecipientilor (financiare, de activitate și indicatorii) urmează a fi prezentate nu mai târziu de 15 zile de la încheierea fiecărui trimestru și sunt, de regulă, prezentate la timp.)
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals |  |  |  | M6: Difference between current and safety stock Report Period [Perioada de raportare]: P1
Comments: | Procurement for health products has been conducted in accordance with contract provisions, PSM list, Work plan and detailed budget. Achiziția de produse de sanatate a fost efectuat în conformitate cu prevederile contractuale, lista PSM, planul de lucru și bugetul detaliat. |  |  | Comments: | N/A
|  |  |  | Component | Products | Stock level expressed in months of treatment for all current patients | Months of safety stock | Difference between current stock and safety stock
|  |  |  | Please Select | Please Select |  | 0
[5 empty] | Please Select |  | 0
[5 empty] | Please Select |  | 0
[5 empty] | Please Select |  | 0
* Includes only EFR category 4 and 5 (Health products and health equipment & Medicines and Pharmaceuticals)
Menu

## Programmatic
Dashboard: Moldova - HIV / AIDS
NFM | 0 | [8 empty] | Report Period [Perioada de raportare]: |  | P1
Latest Rating [Ultimul Rating]: | A1 |  | Center for Health Policies and Studies (PAS Center) | [7 empty] | From [de la]: | 2015-01-01
|  | Strengthening HIV Control in Moldova | [8 empty] | To[Pînă la]: | 2015-06-30 | [7 empty] | Raiting |  | Valor
Programmatic Indicators
Percentage of PWID reached with HIV prevention programs - defined package of services (Procentul consumatorilor de droguri injectabile (CDI) acoperiți cu servicii în cadrul programelor de prevenire HIV - pachet de servicii definit) |  |  |  | Percentage of sex workers reached with HIV prevention programs defined package of services (Procentul lucrătoarelor sexului comercial (LSC) acoperite cu servicii în cadrul programelor de prevenire HIV - pachet de servicii definit) |  |  |  | Percentage of MSM reached with HIV prevention programs - defined package of services (Procentul bărbaţilor care fac sex cu barbații (BSB) acoperițicu servicii în cadrul programelor de prevenire HIV - pachet de servicii definit)
Comment: P1 | During reporting period a total of 9,164 PWIDs (Male - 6,887, Female - 2,277; Age <25 - - 1, 822, 25+ - 7,342) received at least two services from the package listed above one of which was the needle exchange. The beneficiaries are provided with the following services: needle exchange, condom distribution, specialist consultation (psychologist, social assistant, medical), distribution of informational material, peer to peer counselling, VCT, etc., through 9 projects that cover 28 sites in both civilian and penitentiary sectors (11 penitentiary institutions), including in Transnistria region (4 civil sites and 2 penitentiary institutions). The services have been extended to 4 new sites in 2015, namely Anenii, Comrat, Cahul and Ciadirlunga. The indicator is overachieved for the absolute numbers reported semiannually, but the percentage of coverage from estimated population is measured annually based cumulative results, and that's when we can really judge the achievement of this indicator. [În perioada de raportare un total de 9,164 CDI (bărbați - 6,887, femeie – 2,277; Vârsta <25 - -1, 822, 25+ - 7,342) a primit cel puțin două servicii din pachetul de mai jos unul din care a fost schimb de seringi. Beneficiarii sunt acoperiți cu următoarele servicii: schimb de seringi, distribuirea de prezervative, consultarea de specialitate (psiholog, asistent social, medical), distribuție de materiale informaționale, consultație de la egal la egal, CTV, etc., prin intermediu a 9 proiecte care acoperă 28 de site-uri, atât în sectorul civil cît și penitenciar (11 instituții penitenciare), inclusiv în regiunea transnistreană (4 site-uri în sectorul civil și 2 instituții penitenciare). Serviciile au fost extinse la 4 site-uri noi în 2015, și anume Anenii Noi, Comrat, Cahul și Ceadir Lunga. Indicatorul este depășit pentru cifrele absolute raportate semestrial, dar procentul de acoperire a populației estimate se măsoară anual în baza rezultatelor cumulative, și atunci putem măsura într-adevăr realizarea acestui indicator]. |  |  | Comment: P2 | During reporting period a total of 3,476 sex workers (Age <25 -1255, 25+ 2221), received at least two services from the package listed above one of which was the condom distribution. The beneficiaries are provided with the following services: condom distribution, distribution of informational material, specialist consultation (psychologist, social assistant, medical), STI management, peer to peer counselling, VCT, distribution of syringes and distribution of disinfectants, etc., through 4 projects that cover 8 sites including Transnistria region. The services have been extended to 4 new sites in 2015, namely Ribnita, Tiraspol, Slobozia and Bender. The indicator is overachieved for the absolute numbers reported semiannually, but the percentage of coverage from estimated population is measured annually based cumulative results, and that's when we can really judge the achievement of this indicator. [În perioada de raportare 3,476 lucrătoare a sexului comercial (cu vârsta <25 -1255, 25+ 2221), au primit cel puțin două servicii din pachetul de mai jos, unul din care a fost distribuirea de prezervative. Beneficiarii sunt acoperiți cu următoarele servicii: distribuirea de prezervative, distribuirea materialelor informaționale, consultarea de specialitate (psiholog, asistent social, medical), managementul ITS, consiliere de la egal la egal, CTV, distribuția de seringi și distribuirea dezinfectanților, etc. Serviciile sunt acordate, prin intermediul a 4 proiecte care acoperă 8 site-uri, inclusiv regiunea transnistreană. Serviciile au fost extinse în 4 site-uri noi în 2015, și anume Rîbnița, Tiraspol, Slobozia și Bender. Indicatorul este depășit pentru cifrele absolute raportate semestrial, dar procentul de acoperire de la populația estimată se măsoară anual în baza rezultatelor cumulative, și atunci putem măsura într-adevăr realizarea acestui indicator]. |  |  | Comment: P3 | During reporting period a total of 1,243 MSM (Age <25 - 232, 25+ 1011), received at least two services from the package listed above one of which was the condom or lubricant distribution. The beneficiaries are provided with the following services: condom distribution, lubricant distribution, IEC counselling, psychologist consultation, VCT, peer to peer counseling, SSSP activities, etc., through one project that cover 3 sites including Transnistria region. The indicator is achieved in proportion of 92% for the absolute numbers reported semiannually, but the percentage of coverage from estimated population is measured annually based cumulative results, and that's when we can really judge the achievement of this indicator. [În perioada de raportare 1,243 BSB (cu vârsta <25-232, 25+ - 1,011, au primit cel puțin două servicii din pachetul de mai jos unul dintre care a fost distribuirea de prezervative sau lubrifiant. Beneficiarii sunt acoperiți cu următoarele servicii: distribuirea de prezervative, distribuirea de lubrifiant, IEC consiliere, consultare psihologica, consiliere și testare voluntară, consiliere de la egal la egal, activități SSSP, etc. Serviciile sunt acordate în baza unui proiect care acoperă 3 site-uri, inclusiv regiunea transnistreană. Indicatorul nu atins în proporție de 92% pentru cifrele absolute raportate semestrial, dar procentul de acoperire din populația estimată se măsoară anual în baza rezultatelor cumulative, și atunci putem măsura într-adevăr realizarea acestui indicator].
Indicators |  |  | Target | Achieved | 0% - 59% | 60% - 89% | > 90% | Comments |  |  |  |  | min | 0 | 30% | 60% | 90% | 100% |  | min | 0 | 20% | 40% | 60% | 80%
Percentage of PWID reached with HIV prevention programs - defined package of services (Procentul consumatorilor de droguri injectabile (CDI) acoperiți cu servicii în cadrul programelor de prevenire HIV - pachet de servicii definit) |  |  | 6250 | 9164 | 146.6% |  |  | During reporting period a total of 9,164 PWIDs (Male - 6,887, Female - 2,277; Age <25 - - 1, 822, 25+ - 7,342) received at least two services from the package listed above one of which was the needle exchange. The beneficiaries are provided with the following services: needle exchange, condom distribution, specialist consultation (psychologist, social assistant, medical), distribution of informational material, peer to peer counselling, VCT, etc., through 9 projects that cover 28 sites in both civilian and penitentiary sectors (11 penitentiary institutions), including in Transnistria region (4 civil sites and 2 penitentiary institutions). The services have been extended to 4 new sites in 2015, namely Anenii, Comrat, Cahul and Ciadirlunga. The indicator is overachieved for the absolute numbers reported semiannually, but the percentage of coverage from estimated population is measured annually based cumulative results, and that's when we can really judge the achievement of this indicator. [În perioada de raportare un total de 9,164 CDI (bărbați - 6,887, femeie – 2,277; Vârsta <25 - -1, 822, 25+ - 7,342) a primit cel puțin două servicii din pachetul de mai jos unul din care a fost schimb de seringi. Beneficiarii sunt acoperiți cu următoarele servicii: schimb de seringi, distribuirea de prezervative, consultarea de specialitate (psiholog, asistent social, medical), distribuție de materiale informaționale, consultație de la egal la egal, CTV, etc., prin intermediu a 9 proiecte care acoperă 28 de site-uri, atât în sectorul civil cît și penitenciar (11 instituții penitenciare), inclusiv în regiunea transnistreană (4 site-uri în sectorul civil și 2 instituții penitenciare). Serviciile au fost extinse la 4 site-uri noi în 2015, și anume Anenii Noi, Comrat, Cahul și Ceadir Lunga. Indicatorul este depășit pentru cifrele absolute raportate semestrial, dar procentul de acoperire a populației estimate se măsoară anual în baza rezultatelor cumulative, și atunci putem măsura într-adevăr realizarea acestui indicator]. |  |  |  |  | max | 30% | 60% | 90% | 100% | 200% |  | max | 20% | 40% | 60% | 80% | 100%
Percentage of sex workers reached with HIV prevention programs defined package of services (Procentul lucrătoarelor sexului comercial (LSC) acoperite cu servicii în cadrul programelor de prevenire HIV - pachet de servicii definit) |  |  | 1800 | 3476 | 193% |  |  | During reporting period a total of 3,476 sex workers (Age <25 -1255, 25+ 2221), received at least two services from the package listed above one of which was the condom distribution. The beneficiaries are provided with the following services: condom distribution, distribution of informational material, specialist consultation (psychologist, social assistant, medical), STI management, peer to peer counselling, VCT, distribution of syringes and distribution of disinfectants, etc., through 4 projects that cover 8 sites including Transnistria region. The services have been extended to 4 new sites in 2015, namely Ribnita, Tiraspol, Slobozia and Bender. The indicator is overachieved for the absolute numbers reported semiannually, but the percentage of coverage from estimated population is measured annually based cumulative results, and that's when we can really judge the achievement of this indicator. [În perioada de raportare 3,476 lucrătoare a sexului comercial (cu vârsta <25 -1255, 25+ 2221), au primit cel puțin două servicii din pachetul de mai jos, unul din care a fost distribuirea de prezervative. Beneficiarii sunt acoperiți cu următoarele servicii: distribuirea de prezervative, distribuirea materialelor informaționale, consultarea de specialitate (psiholog, asistent social, medical), managementul ITS, consiliere de la egal la egal, CTV, distribuția de seringi și distribuirea dezinfectanților, etc. Serviciile sunt acordate, prin intermediul a 4 proiecte care acoperă 8 site-uri, inclusiv regiunea transnistreană. Serviciile au fost extinse în 4 site-uri noi în 2015, și anume Rîbnița, Tiraspol, Slobozia și Bender. Indicatorul este depășit pentru cifrele absolute raportate semestrial, dar procentul de acoperire de la populația estimată se măsoară anual în baza rezultatelor cumulative, și atunci putem măsura într-adevăr realizarea acestui indicator]. | [5 empty] | de 0 a 0.3 | de 0.3 a 0.6 | de 0.6 a 0.9 | de 0.9 a 1 | de 1 a 2 | Rating | Valor | de 0 a 0.2 | de 0.2 a 0.4 | de 0.4 a 0.6 | de 0.6 a 0.8 | de 0.8 a 1
Percentage of MSM reached with HIV prevention programs - defined package of services (Procentul bărbaţilor care fac sex cu barbații (BSB) acoperițicu servicii în cadrul programelor de prevenire HIV - pachet de servicii definit) |  |  | 1350 | 1243 | 92.07% |  |  | During reporting period a total of 1,243 MSM (Age <25 - 232, 25+ 1011), received at least two services from the package listed above one of which was the condom or lubricant distribution. The beneficiaries are provided with the following services: condom distribution, lubricant distribution, IEC counselling, psychologist consultation, VCT, peer to peer counseling, SSSP activities, etc., through one project that cover 3 sites including Transnistria region. The indicator is achieved in proportion of 92% for the absolute numbers reported semiannually, but the percentage of coverage from estimated population is measured annually based cumulative results, and that's when we can really judge the achievement of this indicator. [În perioada de raportare 1,243 BSB (cu vârsta <25-232, 25+ - 1,011, au primit cel puțin două servicii din pachetul de mai jos unul dintre care a fost distribuirea de prezervative sau lubrifiant. Beneficiarii sunt acoperiți cu următoarele servicii: distribuirea de prezervative, distribuirea de lubrifiant, IEC consiliere, consultare psihologica, consiliere și testare voluntară, consiliere de la egal la egal, activități SSSP, etc. Serviciile sunt acordate în baza unui proiect care acoperă 3 site-uri, inclusiv regiunea transnistreană. Indicatorul nu atins în proporție de 92% pentru cifrele absolute raportate semestrial, dar procentul de acoperire din populația estimată se măsoară anual în baza rezultatelor cumulative, și atunci putem măsura într-adevăr realizarea acestui indicator]. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Percentage of individuals receiving Opioid Substitution Therapy who received treatment for at least 6 months (Procentul persoanelor care au beneficiat de tratament de substituție cu metadonă care s-au aflat în tratament timp de cel puțin 6 luni) |  |  | 61% | 55% | 90.16% |  |  | A total of 72 individuals out of 131 that initiated OST during semester 2, 2014 (July - December 2014) have completed at least 6 months of continuous treatment on OST. During the period when the evaluated cohort enrolled in treatment, OST was provided in three sites: two civilian - Republican Narcological Dispensary, Balti Municipal Hospital and the Department of Penitentiary Institutions (in 11 penitentiary institutions: #1 Taraclia, #5 Cahul, #6 Soroca, #7 Rusca, #9 Pruncul, #11 Balti, #15 Cricova, #16 Pruncul, #17 Rezina, #18 Branesti, #13 Chisinau). The indicator is achieved in proportion of 90%. Reason for variance: the rate of retention in treatment is determined by a series of factors, namely seasonal migration of patients (both abroad and in country), emergency of seasonal illicit drugs on black market, concurrent use of illicit drugs, methadone distribution restricted to two OST sites in civilian sector (Chisinau and Balti) which make treatment unavailable for migrating patients and linkage to treatment for patients released from prison, methadone distribution restricted to OST sites for all patients including for drug users in stable remission, repeated enrollment in treatment without prior psycho-social support to prepare the patient for the next attempt, misconceptions about OST in both medical and psych-social support teams, negative image of OST among PWID, etc. [Un număr total de 72 de persoane din 131 care au inițiat TSO în semestrul 2, 2014 (iulie-decembrie 2014) au finalizat cel puțin 6 luni de tratament TSO continuu. În perioada în care a fost evaluata cohorta, TSO a fost furnizata în trei site-uri: două civile - Dispensarul Republican de Narcologie, Spitalul Municipal Bălți și Departamentul Instituțiilor Penitenciare (în 11 instituții penitenciare: #1 Taraclia, #5 Cahul, #6 Soroca, #7 Rusca, #9 Pruncul, #11 Blti, #15 Cricova, #16 Pruncul, #17 Rezina, #18 Brănești, #13 Chișinău). Indicatorul este realizată în proporție de 90%. Motivul variației: rata de reținere în tratament este determinat de o serie de factori, și anume migrația sezonieră a pacienților (atât în străinătate cât și în țară); drogurile ilicite de sezon pe piața neagră; utilizarea concomitentă de droguri ilicite; distribuția metadonei limitată la două site-uri TSO în sectorul civil (Chișinău și Bălți), ceea ce restricționează tratamentul pentru pacienții care migrează și continuitatea tratamentului pentru pacienții eliberat din închisoare; distribuția metadonei restricționată la site-uri OST pentru toți pacienții, inclusiv pentru consumatorii de droguri în remisie stabilă; înrolarea repetă în tratamentul fără suport psiho-social înainte de a pregăti pacientul pentru următoarea încercare; concepții greșite despre OST în ambele echipe medicale și de suport psihosocial; imagine negativă a OST printre CDI, etc.]. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number of drug users reached with drug substitution therapy (Numărul consumatorilor de droguri care au inițiat tratamentul de substituție cu metadonă) |  |  | 75 | 69 | 92% |  |  | During reporting period a total of 69 drug users from both civilian and penitentiary sectors were enrolled in drug substitution therapy (naïve patients). From them 24 drug users were enrolled in the Chisinau by the Republican Narcological Dispensary, 10 - by Balti Municipal Hospital, 21 - by Comrat Raional Hospital and 14 - by the Department of Penitentiary Institutions. At the end of June 2015 a total number of 413 daily patients were on methadone substitution treatment, out of them 224 with the Republican Narcological Dispensary; 88 with the Balti Municipal Hospital; 20 with the Comrat Raional Hospital and 81 with the Department of Penitentiary Institutions. During reported period OST services have been extended to one additional site (Comrat), in parallel one additional OST point has opened in Chisinau, and in two additional penitentiary institutions. Respectively by the end of Semester 1, 2015 OST services were provided in four sites through the Narcological Dispensary (in three OST points: Centru, Botanica and Posta Veche), Balti Municipal Hospital (in one OST point), Comrat Raional Hospital (in one OST point) and the Department of Penitentiary Institutions (in 13 penitenciaries: #1 Taraclia, #3 Leova, #4 Cricova, #5 Cahul, #6 Soroca, #7 Rusca, #9 Pruncul, #11 Balti, #15 Cricova, #16 Pruncul, #17 Rezina, #18 Branesti, #13 Chisinau). The indicator is achieved in proportion of 92%. Reason for variance: the enrolment in treatment is directly dependent on demand, there is no waiting lists for OST in existing sites. Geographical availability remains low (3 civilian sites) and the enrolment in long operating sites (Chisinau, Balti) is slightly slowly decreasing. The operation of additional new sites planned to open this year in civil sector (4) is expected to bring new people into the program. [În perioada de raportare au fost înrolați în terapia de substituție 69 consumatori de droguri din ambele sectoarele civil și penitenciar (pacienții naivi). Din ei 24 de consumatori de droguri au fost înrolați în Chișinău de către Dispensarul Republican de Narcologie, 10 - de Spitalul Municipal Bălți, 21 - de Spitalul Raional din Comrat și 14 - de către Departamentul Instituțiilor Penitenciare. La sfârșitul lunii iunie 2015, 413 pacienți zilnici au fost in tratament de substituție cu metadonă, din ei 224 la Dispensarul Republican de Narcologie; 88 la Spitalul Municipal Bălți; 20 la Spitalul Raional din Comrat și 81 în Sistemul Penitenciar În perioada de raportare serviciile TSO au fost extinse într-un sait adițional (Comrat), în paralel un punct TSO suplimentare a fost deschis la Chișinău și două puncte în în două instituții penitenciare adiționale. Respectiv la sfârșitul Semestrului 1, 2015 serviciile de TSO au fost oferite în patru site-uri din sectorul civil prin Dispensarul Narcologic (în trei puncte TSO: Centru, Botanica și Posta Veche), Spitalul Municipal Bălți (într-un punct TSO), Spitalul Raional Comrat (într-una punctul TSO) și Departamentul Instituțiilor Penitenciare (în 13 penitenciare: # 1 Taraclia, # 3 Leova, # 4 Cricova, # 5 Cahul, # 6 Soroca, # 7 Rusca, # 9 Pruncul, # 11 Bălți, # 15 Cricova, # 16 Pruncul, # 17 Rezina, # 18 Branesti, # 13 Chisinau). Indicatorul este realizată în proporție de 92%. Motivul pentru varianță: înscrierea în tratament este direct dependent de cerere, nu există liste de așteptare pentru TSO în site-urile existente. Disponibilitate geografică rămâne mică (3 site-uri în sectorul civil) și înrolarea în site-urile mai vechi (Chișinău, Bălți) este într-o scădere lenta. Se preconizează ca deschiderea site-uri noi planificată pentru anul curent (4 site-uri adiționale în sectorul civil) vor aduce persoane noi în program]. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Proportion of new individuals who test positive for HIV, enrolled in care (pre-ART or ART) services by NGOs (Proporția persoanelor noi testate la HIV cu rezultat pozitiv, înrolațe în servicii de îngrijire (pre-TARV sau TARV) de către ONG-uri.) |  |  | n/a | n/a | n/a |  |  | The indicator is annual and will be reported in the next semester. [Indicatorul este anual și va fi raportat în semestrul următor]. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Number of psychosocial support NGO providers that are accredited by state to provide social services for KAP (PLHIV, PWUD, etc.) (Numărul ONG-lor prestatoare de support psiho-sociale, acreditate de stat pentru prestarea serviciilor sociale populațiilor cheie afectate (PTHIV, CDI etc.)) |  |  | n/a | n/a | n/a |  |  | The indicator is annual and will be reported in the next semester. [Indicatorul este anual si va fi raportat în semestrul următor]. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Number of human rights strategic litigation cases for PLHIV initiated (Numărul de cazuri de încălcare a drepturilor PTH inițiate pentru litigare strategică) |  |  | 10 | 10 | 100% |  |  | A total of 10 litigation cases have been initiated during Semester 1, 2015. The cases were related to disclosure of confidential medical information related to HIV status, unethical and unprofessional behavior of medical staff, refusal to offer medical services, rights to fair defense and trial, etc. The indicator is achieved. [Pe parcursul semestrului 1, 2015 au fost inițiate 10 litigii. Cazurile au fost legate de divulgarea informației medicale confidențiale legate de statutul HIV, comportament neetic și neprofesional al personalului medical, refuzul de a acorda servicii medicale, drepturile la apărare și la un proces echitabil, etc. Indicatorul este atins]. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[5 empty] | n/a | [8 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[5 empty] | n/a | [8 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Menu

## Recommendations
Dashboard: Moldova - HIV / AIDS
NFM | 0 |  |  |  |  | Report Period [Perioada de raportare]: | P1
Latest Rating [Ultimul Rating]: | A1 |  | Center for Health Policies and Studies (PAS Center) |  |  | From [de la]: | 2015-01-01
|  |  | Strengthening HIV Control in Moldova |  |  | To[Pînă la]: | 2015-06-30
Recommendations
Are all funds reaching implementation levels and being spent according to budget?
Financial |  | Summary Comments |  |  | Recommendations
F1 |  | By June 30, 2015, the total amount disbursed by TGF to PAS Center was EUR 2,201,431 (Actual 2,201,431/Budget 1,489,742). The cumulative disbursement rate is 147,8 %. The variance is due to the amount of EUR 711,689 Euro that is the buffer for quater 3, 2015. (Până la 30 iunie 2015, Centrului PAS i-au fost debursate de către Fondul Global 2,201,431 Euro (Actual 2,201,431/Budget 1,489,742). Rata cumulativă a debursării este de 147,8 %. Variația este cauzată de faptul că disbursarea cumulativă include un buffer pentru trimestrul 3, 2015 în valoare de 711,689 Euro).
F2 |  | The PR cash outflow rate for the reported period is 103% (Actual 1,535,778/Budget 1,489,742) from the semiannual budget. The variance for the reporting period is over expenditure of EUR 46,036 mainly due to overspendings due to the schedule of disbursement to SR and other sub-contractors that include one buffer month from the following quarter, commitments to be paid during period 2 and payments deducted from disbursements to SR SFM for services planned to start start in semester 2. (Rata de absorbție pentru perioada raportată este de 103% (Actual 1,535.778/Budget 1,489.742 Euro) din bugetul semi anual. Variația dintre buget și cheltuieli pentru perioada raportată constituie o supra cheltuială de 46.036 Euro fiind în mare parte determinată de supra celtuieli asociate graficului de disbursare către SR și alți sub-contractori care include o lună de buffer, angajamente care vor fi acoperite în perioada următoare și plăți deduse din debursarea către SR FSM pentru serviciile planificate pentru semstrul 2.
F3 |  | The cummulative rate of absorption from disbursement (expenditure at PR&SR level) as of June 30. 2015 is 66% due to the buffer (Actual 1,458,088/Disbursement 2,201,431) and 98% from disbursement for the reported period (Actual 1,458,088/Disbursement 1,489,742). The variance for the reporting period (EUR 31,654) is mainly determined by schedule of payments to SRs and other sub-contractors and engagements to be paid during next period. (Rata cumulative de absorbție din disbursare (cheltuieli la nivel de PR & SR) la data de 30 iunie 2015 este de 66% din cauza buffer-ului (Actual 1,458,088/Ddisbursat 2,201,431) și de 98% din disbursarea pentru perioada raportată (Actual 1,458,088/Disbursat 1,489,742). Variația pentru perioadă raportată (31,654 Euro) este determinată în mare parte de graficul de disbursare către Ssr și alți sub-contractori și angajamentele care urmează să fie plătite în perioada următoare.)
F4 |  | The PU for Semester 1 year 2015 has been submitted to LFA in due terms (45 days after the end of reported period). The first disbursment under the NFM (for S1, 2015 plus one quarter buffer) grant has been made in advance befor grant implementation start. (Actualizarea progresului pentru semestrul 1 anul 2015 a fost remisa Agentului Local al Fondului în termenii stabiliți (45 de zile după finisarea perioadei raportate). Prima disbursare a forst facută în avans (pentru semestrul 1, 2015 plus un trimestru buffer) pînă la începerea implementării grantului.
Are procurement and hiring on schedule?
Management |  | Summary Comments |  |  | Recommendations
M1 |  | There are two conditions applicable to this Grant Confirmation: - 5.1. In accordance with the Global Fund Board Decision Point GF/B28/DP4: Evolving the Funding Model (Part Two), commitment and disbursement of 15% of the Republic of Moldova aggregate allocation of EUR 28,640,132, which is equal to EUR 4,296,020, is subject to the Republic of Moldova compliance with the Global Fund willingness to pay requirement. Status: Unmet - In progress (This is a grant life condition related to both NFM grant in country for HIV and TB. Compliance can be monitored annually based on the fulfilment of country commitments as per the CN for both diseases.) - 5.2. By no later than 31 December 2016, the Principal Recipient, in collaboration with the Country Coordinating Mechanism, other stakeholders and partners in the Republic of Moldova, shall deliver to the Global Fund a sustainability plan for the national HIV program, endorsed by the government of the Republic of Moldova, in form and substance satisfactory to the Global Fund. Status: Unmet - In progress (The development of the sustainability plan has started in 2015 with the development of national HIV/AIDS Program for the period 2016-2020, will continue in 2016 and be finalized in accordance with the schedule. The process will be guided by CCM, and the technical assistance planned under TGF NFM Grant will be supported by PCIMU as part of the Program Management Module; Intervention - Policy, planning, coordination and management; Activity - Assessment of the management of NAP & Development of NAP Sustainability Plan.) (Există două condiții aferente confirmării Grantului curent: - 5.1. În conformitate cu decizia Bordului Fondului Global punctul GF/B28/DP4: Evoluând Modelul de Finanțare (partea a doua), angajamentul și disbursarea a 15% din alocația totală a Republicii Moldova de 28,640,132 Euro, care este egală cu 4,296,020 Euro este condiționată de respectarea de către Republica Moldova a cerințelor Fondului Global privind ”Disponibilitatea de a plăti”. Statut: neîndeplinită - în progres (Aceasta este o condiție întregului ciclu de viață a grantului aferentă ambelor granturi NFM în tara HIV și TB. Respectarea acestei condiții va fi monitorizată anual pe baza îndeplinirea angajamentelor asumate de țărilor în Notele de Concept pentru ambele maladii.) - 5.2. Nu mai târziu la 31 decembrie 2016, Recipienții Principali, în colaborare cu Comitetul National de Coordonare, alți părți interesate și parteneri din Republica Moldova, vor rpezenta Fondul Global un plan de sustenabilitate pentru programul național HIV, aprobat de guvernul Republicii Moldova, în formă și în substanță satisfăcătoare Fondului Global. Statut: neîndeplinită - în progres Elaborarea planului de sustenabilitate a început în 2015 odată cu elaborarea Programului Național HIV/SIDA pentru perioada 2016-2020, va continua în 2016 și va fi finalizat în conformitate cu graficul prestabilit. Procesul va fi ghidat de CNC, iar asistența tehnică prevăzute în Grantul NFM finanțat de Fondul Global va fi asigurată de către UCIMP, ca parte componentă a modulului Managementul Programului; Intervenția - Politici, planificare, coordonare și management; Activitatea - Evaluarea managementului Programului Național HIV & Elaborarea Planul de Sustenabilitate al PN.))
M2 |  | Three full time positions and 11 part time. (Trei poziţii cu normă plină şi unsprezece - parţială.) | #DIV/0! | #DIV/0!
M3 |  | Two Sub-recipients (SRs) have been identified to implement different components within the project: Soros Foundation-Moldova (SFM) and Positive Initiative (PI). Both SRs have been assessed by PAS Center. Two sub-grant agreements have been signed following the assessment and both SRs that receive funds within the grant. (Doi Sub-Recipienţi (SR) au fost identificaţi pentru a implementa diferite componente în cadrul proiectului: Fundația Soros-Moldova (FSM) și Inițiativa Pozitivă. Ambii SRs au fost evaluați de către Centrul PAS. Urmare a evaluării au fost semnate două acorduri de sub-grant și ambii SR primesc resurse din cadrul grantului.
M4 |  | The SR’s quarterly reports (financial report, activity report and performance framework) are submitted no later than 25 days after close of each quarter, and are generally submitted on time. The preliminary version of all reports are presented to the Principle Recipient for clearance no later than 15 days after the close of each quarter. The clearance period vary from one SR to an other subject to the completeness and consistence of the reports. For the SR SFM the Sub-subrecipients financial reports are due once in four months and can be submitted during the following 45 days after the period, the activity reports are due not later than 10 days from the end of the reporting period (quarter for care and support services, and - month for the Harm Reduction services) and are generally submitted in time. During the reporting period reflected in this dashboard the reports due from the 14 SRs were submited in time. For the SR New Life the 2 Sub-subrecipient reports (financial, activity and indicators) are due not later than 15 days after the close of each quarter and are generally submitted in time. (Rapoartele trimestriale ale SR (raport financiar, raport de activitate și cadrul de performanță) urmează a fi transmise RP nu mai târziu de 25 de zile de la încheierea fiecărui trimestru. Versiunea preliminară a rapoartelor este prezentată RP pentru verificare nu mai tîrziu de 15 zile după terminarea fiecărui trimestru. Perioada de verificare şi aprobare variază de la un SR la altul în funcţie de exhaustivitatea și consistență rapoartelor. Rapoartele sunt de regulă prezentate la timp. Pentru SR FSM rapoarte financiare ale Sub-subrecipienţilor (Ssr) urmează a fi transmise o dată la patru luni și pot fi prezentate în termen de 45 zile de la finalul perioadei raportate, rapoartele de activitate urmează a fi prezentate nu mai târziu de 10 zile de la sfârșitul perioadei de raportare (trimestrial pentru serviciile de îngrijire și suport și lunar pentru serviciile de reducere a riscurilor) și sunt, în general, prezentate la timp. Pe parcursul perioadei de raportare reflectată în aces raport, raportele de la cei 14 Sub-subrecipienți au fost transmise la timp. Pentru SR Inițiativa Pozitivă cele două rapoarte ale Sub-subrecipientilor (financiare, de activitate și indicatorii) urmează a fi prezentate nu mai târziu de 15 zile de la încheierea fiecărui trimestru și sunt, de regulă, prezentate la timp.)
M5 |  | Procurement for health products has been conducted in accordance with contract provisions, PSM list, Work plan and detailed budget. Achiziția de produse de sanatate a fost efectuat în conformitate cu prevederile contractuale, lista PSM, planul de lucru și bugetul detaliat.
M6 |  | N/A
Are technical targets being achieved?
Programmatic |  | Summary Comments |  |  | Recommendations
P1 - trend |  | During reporting period a total of 9,164 PWIDs (Male - 6,887, Female - 2,277; Age <25 - - 1, 822, 25+ - 7,342) received at least two services from the package listed above one of which was the needle exchange. The beneficiaries are provided with the following services: needle exchange, condom distribution, specialist consultation (psychologist, social assistant, medical), distribution of informational material, peer to peer counselling, VCT, etc., through 9 projects that cover 28 sites in both civilian and penitentiary sectors (11 penitentiary institutions), including in Transnistria region (4 civil sites and 2 penitentiary institutions). The services have been extended to 4 new sites in 2015, namely Anenii, Comrat, Cahul and Ciadirlunga. The indicator is overachieved for the absolute numbers reported semiannually, but the percentage of coverage from estimated population is measured annually based cumulative results, and that's when we can really judge the achievement of this indicator. [În perioada de raportare un total de 9,164 CDI (bărbați - 6,887, femeie – 2,277; Vârsta <25 - -1, 822, 25+ - 7,342) a primit cel puțin două servicii din pachetul de mai jos unul din care a fost schimb de seringi. Beneficiarii sunt acoperiți cu următoarele servicii: schimb de seringi, distribuirea de prezervative, consultarea de specialitate (psiholog, asistent social, medical), distribuție de materiale informaționale, consultație de la egal la egal, CTV, etc., prin intermediu a 9 proiecte care acoperă 28 de site-uri, atât în sectorul civil cît și penitenciar (11 instituții penitenciare), inclusiv în regiunea transnistreană (4 site-uri în sectorul civil și 2 instituții penitenciare). Serviciile au fost extinse la 4 site-uri noi în 2015, și anume Anenii Noi, Comrat, Cahul și Ceadir Lunga. Indicatorul este depășit pentru cifrele absolute raportate semestrial, dar procentul de acoperire a populației estimate se măsoară anual în baza rezultatelor cumulative, și atunci putem măsura într-adevăr realizarea acestui indicator].
P2 - trend |  | During reporting period a total of 3,476 sex workers (Age <25 -1255, 25+ 2221), received at least two services from the package listed above one of which was the condom distribution. The beneficiaries are provided with the following services: condom distribution, distribution of informational material, specialist consultation (psychologist, social assistant, medical), STI management, peer to peer counselling, VCT, distribution of syringes and distribution of disinfectants, etc., through 4 projects that cover 8 sites including Transnistria region. The services have been extended to 4 new sites in 2015, namely Ribnita, Tiraspol, Slobozia and Bender. The indicator is overachieved for the absolute numbers reported semiannually, but the percentage of coverage from estimated population is measured annually based cumulative results, and that's when we can really judge the achievement of this indicator. [În perioada de raportare 3,476 lucrătoare a sexului comercial (cu vârsta <25 -1255, 25+ 2221), au primit cel puțin două servicii din pachetul de mai jos, unul din care a fost distribuirea de prezervative. Beneficiarii sunt acoperiți cu următoarele servicii: distribuirea de prezervative, distribuirea materialelor informaționale, consultarea de specialitate (psiholog, asistent social, medical), managementul ITS, consiliere de la egal la egal, CTV, distribuția de seringi și distribuirea dezinfectanților, etc. Serviciile sunt acordate, prin intermediul a 4 proiecte care acoperă 8 site-uri, inclusiv regiunea transnistreană. Serviciile au fost extinse în 4 site-uri noi în 2015, și anume Rîbnița, Tiraspol, Slobozia și Bender. Indicatorul este depășit pentru cifrele absolute raportate semestrial, dar procentul de acoperire de la populația estimată se măsoară anual în baza rezultatelor cumulative, și atunci putem măsura într-adevăr realizarea acestui indicator].
P3 - trend |  | During reporting period a total of 1,243 MSM (Age <25 - 232, 25+ 1011), received at least two services from the package listed above one of which was the condom or lubricant distribution. The beneficiaries are provided with the following services: condom distribution, lubricant distribution, IEC counselling, psychologist consultation, VCT, peer to peer counseling, SSSP activities, etc., through one project that cover 3 sites including Transnistria region. The indicator is achieved in proportion of 92% for the absolute numbers reported semiannually, but the percentage of coverage from estimated population is measured annually based cumulative results, and that's when we can really judge the achievement of this indicator. [În perioada de raportare 1,243 BSB (cu vârsta <25-232, 25+ - 1,011, au primit cel puțin două servicii din pachetul de mai jos unul dintre care a fost distribuirea de prezervative sau lubrifiant. Beneficiarii sunt acoperiți cu următoarele servicii: distribuirea de prezervative, distribuirea de lubrifiant, IEC consiliere, consultare psihologica, consiliere și testare voluntară, consiliere de la egal la egal, activități SSSP, etc. Serviciile sunt acordate în baza unui proiect care acoperă 3 site-uri, inclusiv regiunea transnistreană. Indicatorul nu atins în proporție de 92% pentru cifrele absolute raportate semestrial, dar procentul de acoperire din populația estimată se măsoară anual în baza rezultatelor cumulative, și atunci putem măsura într-adevăr realizarea acestui indicator].
P1 |  | During reporting period a total of 9,164 PWIDs (Male - 6,887, Female - 2,277; Age <25 - - 1, 822, 25+ - 7,342) received at least two services from the package listed above one of which was the needle exchange. The beneficiaries are provided with the following services: needle exchange, condom distribution, specialist consultation (psychologist, social assistant, medical), distribution of informational material, peer to peer counselling, VCT, etc., through 9 projects that cover 28 sites in both civilian and penitentiary sectors (11 penitentiary institutions), including in Transnistria region (4 civil sites and 2 penitentiary institutions). The services have been extended to 4 new sites in 2015, namely Anenii, Comrat, Cahul and Ciadirlunga. The indicator is overachieved for the absolute numbers reported semiannually, but the percentage of coverage from estimated population is measured annually based cumulative results, and that's when we can really judge the achievement of this indicator. [În perioada de raportare un total de 9,164 CDI (bărbați - 6,887, femeie – 2,277; Vârsta <25 - -1, 822, 25+ - 7,342) a primit cel puțin două servicii din pachetul de mai jos unul din care a fost schimb de seringi. Beneficiarii sunt acoperiți cu următoarele servicii: schimb de seringi, distribuirea de prezervative, consultarea de specialitate (psiholog, asistent social, medical), distribuție de materiale informaționale, consultație de la egal la egal, CTV, etc., prin intermediu a 9 proiecte care acoperă 28 de site-uri, atât în sectorul civil cît și penitenciar (11 instituții penitenciare), inclusiv în regiunea transnistreană (4 site-uri în sectorul civil și 2 instituții penitenciare). Serviciile au fost extinse la 4 site-uri noi în 2015, și anume Anenii Noi, Comrat, Cahul și Ceadir Lunga. Indicatorul este depășit pentru cifrele absolute raportate semestrial, dar procentul de acoperire a populației estimate se măsoară anual în baza rezultatelor cumulative, și atunci putem măsura într-adevăr realizarea acestui indicator].
P2 |  | During reporting period a total of 3,476 sex workers (Age <25 -1255, 25+ 2221), received at least two services from the package listed above one of which was the condom distribution. The beneficiaries are provided with the following services: condom distribution, distribution of informational material, specialist consultation (psychologist, social assistant, medical), STI management, peer to peer counselling, VCT, distribution of syringes and distribution of disinfectants, etc., through 4 projects that cover 8 sites including Transnistria region. The services have been extended to 4 new sites in 2015, namely Ribnita, Tiraspol, Slobozia and Bender. The indicator is overachieved for the absolute numbers reported semiannually, but the percentage of coverage from estimated population is measured annually based cumulative results, and that's when we can really judge the achievement of this indicator. [În perioada de raportare 3,476 lucrătoare a sexului comercial (cu vârsta <25 -1255, 25+ 2221), au primit cel puțin două servicii din pachetul de mai jos, unul din care a fost distribuirea de prezervative. Beneficiarii sunt acoperiți cu următoarele servicii: distribuirea de prezervative, distribuirea materialelor informaționale, consultarea de specialitate (psiholog, asistent social, medical), managementul ITS, consiliere de la egal la egal, CTV, distribuția de seringi și distribuirea dezinfectanților, etc. Serviciile sunt acordate, prin intermediul a 4 proiecte care acoperă 8 site-uri, inclusiv regiunea transnistreană. Serviciile au fost extinse în 4 site-uri noi în 2015, și anume Rîbnița, Tiraspol, Slobozia și Bender. Indicatorul este depășit pentru cifrele absolute raportate semestrial, dar procentul de acoperire de la populația estimată se măsoară anual în baza rezultatelor cumulative, și atunci putem măsura într-adevăr realizarea acestui indicator].
P3 |  | During reporting period a total of 1,243 MSM (Age <25 - 232, 25+ 1011), received at least two services from the package listed above one of which was the condom or lubricant distribution. The beneficiaries are provided with the following services: condom distribution, lubricant distribution, IEC counselling, psychologist consultation, VCT, peer to peer counseling, SSSP activities, etc., through one project that cover 3 sites including Transnistria region. The indicator is achieved in proportion of 92% for the absolute numbers reported semiannually, but the percentage of coverage from estimated population is measured annually based cumulative results, and that's when we can really judge the achievement of this indicator. [În perioada de raportare 1,243 BSB (cu vârsta <25-232, 25+ - 1,011, au primit cel puțin două servicii din pachetul de mai jos unul dintre care a fost distribuirea de prezervative sau lubrifiant. Beneficiarii sunt acoperiți cu următoarele servicii: distribuirea de prezervative, distribuirea de lubrifiant, IEC consiliere, consultare psihologica, consiliere și testare voluntară, consiliere de la egal la egal, activități SSSP, etc. Serviciile sunt acordate în baza unui proiect care acoperă 3 site-uri, inclusiv regiunea transnistreană. Indicatorul nu atins în proporție de 92% pentru cifrele absolute raportate semestrial, dar procentul de acoperire din populația estimată se măsoară anual în baza rezultatelor cumulative, și atunci putem măsura într-adevăr realizarea acestui indicator].
P4 |  | A total of 72 individuals out of 131 that initiated OST during semester 2, 2014 (July - December 2014) have completed at least 6 months of continuous treatment on OST. During the period when the evaluated cohort enrolled in treatment, OST was provided in three sites: two civilian - Republican Narcological Dispensary, Balti Municipal Hospital and the Department of Penitentiary Institutions (in 11 penitentiary institutions: #1 Taraclia, #5 Cahul, #6 Soroca, #7 Rusca, #9 Pruncul, #11 Balti, #15 Cricova, #16 Pruncul, #17 Rezina, #18 Branesti, #13 Chisinau). The indicator is achieved in proportion of 90%. Reason for variance: the rate of retention in treatment is determined by a series of factors, namely seasonal migration of patients (both abroad and in country), emergency of seasonal illicit drugs on black market, concurrent use of illicit drugs, methadone distribution restricted to two OST sites in civilian sector (Chisinau and Balti) which make treatment unavailable for migrating patients and linkage to treatment for patients released from prison, methadone distribution restricted to OST sites for all patients including for drug users in stable remission, repeated enrollment in treatment without prior psycho-social support to prepare the patient for the next attempt, misconceptions about OST in both medical and psych-social support teams, negative image of OST among PWID, etc. [Un număr total de 72 de persoane din 131 care au inițiat TSO în semestrul 2, 2014 (iulie-decembrie 2014) au finalizat cel puțin 6 luni de tratament TSO continuu. În perioada în care a fost evaluata cohorta, TSO a fost furnizata în trei site-uri: două civile - Dispensarul Republican de Narcologie, Spitalul Municipal Bălți și Departamentul Instituțiilor Penitenciare (în 11 instituții penitenciare: #1 Taraclia, #5 Cahul, #6 Soroca, #7 Rusca, #9 Pruncul, #11 Blti, #15 Cricova, #16 Pruncul, #17 Rezina, #18 Brănești, #13 Chișinău). Indicatorul este realizată în proporție de 90%. Motivul variației: rata de reținere în tratament este determinat de o serie de factori, și anume migrația sezonieră a pacienților (atât în străinătate cât și în țară); drogurile ilicite de sezon pe piața neagră; utilizarea concomitentă de droguri ilicite; distribuția metadonei limitată la două site-uri TSO în sectorul civil (Chișinău și Bălți), ceea ce restricționează tratamentul pentru pacienții care migrează și continuitatea tratamentului pentru pacienții eliberat din închisoare; distribuția metadonei restricționată la site-uri OST pentru toți pacienții, inclusiv pentru consumatorii de droguri în remisie stabilă; înrolarea repetă în tratamentul fără suport psiho-social înainte de a pregăti pacientul pentru următoarea încercare; concepții greșite despre OST în ambele echipe medicale și de suport psihosocial; imagine negativă a OST printre CDI, etc.].
P5 |  | During reporting period a total of 69 drug users from both civilian and penitentiary sectors were enrolled in drug substitution therapy (naïve patients). From them 24 drug users were enrolled in the Chisinau by the Republican Narcological Dispensary, 10 - by Balti Municipal Hospital, 21 - by Comrat Raional Hospital and 14 - by the Department of Penitentiary Institutions. At the end of June 2015 a total number of 413 daily patients were on methadone substitution treatment, out of them 224 with the Republican Narcological Dispensary; 88 with the Balti Municipal Hospital; 20 with the Comrat Raional Hospital and 81 with the Department of Penitentiary Institutions. During reported period OST services have been extended to one additional site (Comrat), in parallel one additional OST point has opened in Chisinau, and in two additional penitentiary institutions. Respectively by the end of Semester 1, 2015 OST services were provided in four sites through the Narcological Dispensary (in three OST points: Centru, Botanica and Posta Veche), Balti Municipal Hospital (in one OST point), Comrat Raional Hospital (in one OST point) and the Department of Penitentiary Institutions (in 13 penitenciaries: #1 Taraclia, #3 Leova, #4 Cricova, #5 Cahul, #6 Soroca, #7 Rusca, #9 Pruncul, #11 Balti, #15 Cricova, #16 Pruncul, #17 Rezina, #18 Branesti, #13 Chisinau). The indicator is achieved in proportion of 92%. Reason for variance: the enrolment in treatment is directly dependent on demand, there is no waiting lists for OST in existing sites. Geographical availability remains low (3 civilian sites) and the enrolment in long operating sites (Chisinau, Balti) is slightly slowly decreasing. The operation of additional new sites planned to open this year in civil sector (4) is expected to bring new people into the program. [În perioada de raportare au fost înrolați în terapia de substituție 69 consumatori de droguri din ambele sectoarele civil și penitenciar (pacienții naivi). Din ei 24 de consumatori de droguri au fost înrolați în Chișinău de către Dispensarul Republican de Narcologie, 10 - de Spitalul Municipal Bălți, 21 - de Spitalul Raional din Comrat și 14 - de către Departamentul Instituțiilor Penitenciare. La sfârșitul lunii iunie 2015, 413 pacienți zilnici au fost in tratament de substituție cu metadonă, din ei 224 la Dispensarul Republican de Narcologie; 88 la Spitalul Municipal Bălți; 20 la Spitalul Raional din Comrat și 81 în Sistemul Penitenciar În perioada de raportare serviciile TSO au fost extinse într-un sait adițional (Comrat), în paralel un punct TSO suplimentare a fost deschis la Chișinău și două puncte în în două instituții penitenciare adiționale. Respectiv la sfârșitul Semestrului 1, 2015 serviciile de TSO au fost oferite în patru site-uri din sectorul civil prin Dispensarul Narcologic (în trei puncte TSO: Centru, Botanica și Posta Veche), Spitalul Municipal Bălți (într-un punct TSO), Spitalul Raional Comrat (într-una punctul TSO) și Departamentul Instituțiilor Penitenciare (în 13 penitenciare: # 1 Taraclia, # 3 Leova, # 4 Cricova, # 5 Cahul, # 6 Soroca, # 7 Rusca, # 9 Pruncul, # 11 Bălți, # 15 Cricova, # 16 Pruncul, # 17 Rezina, # 18 Branesti, # 13 Chisinau). Indicatorul este realizată în proporție de 92%. Motivul pentru varianță: înscrierea în tratament este direct dependent de cerere, nu există liste de așteptare pentru TSO în site-urile existente. Disponibilitate geografică rămâne mică (3 site-uri în sectorul civil) și înrolarea în site-urile mai vechi (Chișinău, Bălți) este într-o scădere lenta. Se preconizează ca deschiderea site-uri noi planificată pentru anul curent (4 site-uri adiționale în sectorul civil) vor aduce persoane noi în program].
P6 |  | The indicator is annual and will be reported in the next semester. [Indicatorul este anual și va fi raportat în semestrul următor].
P7 |  | The indicator is annual and will be reported in the next semester. [Indicatorul este anual si va fi raportat în semestrul următor].
P8 |  | A total of 10 litigation cases have been initiated during Semester 1, 2015. The cases were related to disclosure of confidential medical information related to HIV status, unethical and unprofessional behavior of medical staff, refusal to offer medical services, rights to fair defense and trial, etc. The indicator is achieved. [Pe parcursul semestrului 1, 2015 au fost inițiate 10 litigii. Cazurile au fost legate de divulgarea informației medicale confidențiale legate de statutul HIV, comportament neetic și neprofesional al personalului medical, refuzul de a acorda servicii medicale, drepturile la apărare și la un proces echitabil, etc. Indicatorul este atins].
P9
P10
Menu

## Actions
Dashboard: Moldova - HIV / AIDS
| NFM | 0 |  |  |  | Report Period [Perioada de raportare]: |  | P1
| Latest Rating [Ultimul Rating]: | A1 |  | Center for Health Policies and Studies (PAS Center) |  | From [de la]: |  | 2015-01-01
|  |  | Strengthening HIV Control in Moldova |  |  |  | To[Pînă la]: | 2015-06-30
Decisions and Actions
What is the overall status of this grant implementation?
| Key Recommendations from Oversight Group(s) |  |  |  | CCM Decision | Due Date | Person Responsible
Current Reporting Period
Actions to Implement / Previous Period
What is the overall status of this grant implementation?
| CCM Decision |  |  |  | Action Taken | Date | Person Responsible
Previous Reporting Period
Menu

## Setup (hidden)
Dashboard: Moldova - HIV / AIDS
Set-up = List of validation for Grant Detail page
Component | Currency | Round | Phase | Period | Rating | LFA | Medicaments | Countries
Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select
HIV / AIDS | $ | Round 1 | Phase 1 | P1 | A1 | CA (Crown Agents) | Isoniazid | Afghanistan
MALARIA | € | Round 2 | Phase 2 | P2 | A2 | DEL (Deloitte) | Ethambutol | Albania
TB |  | Round 3 | RCC | P3 | B1 | DTT (DTT Emerging Markets) | Rifampicin | Algeria
HIVAIDS / TB |  | Round 4 |  | P4 | B2 | FIN (Finconsult) | Pyrazimamide | Angola
HSS |  | Round 5 |  | P5 | C | GT (Grant Thornton) | RDT | Argentina
|  | Round 6 |  | P6 |  | H-C (Hodar-Conseil) | NVP | Armenia
|  | Round 7 |  | P7 |  | KPMG (KPMG) | 3TC | Azerbaijan
|  | Round 8 |  | P8 |  | MSCI (MSCI) | D4T | Bangladesh
|  | Round 9 |  | P9 |  | PwC (PricewaterhouseCoopers) | AZT | Belarus
|  | Round 10 |  | P10 |  | STI (Swiss Tropical Institute), | DDI | Belize
|  |  |  | P11 |  | UNOPS | EFV | Benin
|  |  |  | P12 |  |  | AS/LF | Bhutan
[7 empty] | AS/AQ | Bolivia
[7 empty] | AS/MQ | Bosnia and Herzegovina
[7 empty] | Al/Lum | Botswana
Brazil
[7 empty] | TB nutri'l supplements | Bulgaria
[7 empty] | E-PAP | Burkina Faso
Burundi
Cambodia
Cameroon
Cape Verde
Central African Republic
Chad
Chile
China
China
Colombia
Comoros
Congo (Democratic Republic of the)
Congo (Republic of the)
Costa Rica
Cote d'Ivoire
Croatia
Cuba
Djibouti
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Ethiopia
Fiji
Gabon
Gambia
Georgia
Ghana
Global(LWF)
Guatemala
Guinea
Guinea-Bissau
Guyana
Haiti
Honduras
India
Indonesia
Iran (Islamic Republic of)
Iraq
Jamaica
Jordan
Kazakhstan
Kenya
Korea, Democratic Peoples Republic of
Kosovo (Serbia)
Kyrgyzstan
Lao PDR
Lesotho
Liberia
Macedonia, FYR
Madagascar
Malawi
Maldives
Mali
Mauritania
Mauritius
Moldova
Mongolia
Montenegro
Morocco
Mozambique
Multi-country Africa (West Africa Corridor Program)
Multi-country Africa(RMCC)
Multi-country Americas (Andean)
Multi-country Americas (CARICOM)
Multi-country Americas (CRN+)
Multi-country Americas (Meso)
Multi-country Americas (OECS)
Multi-country Americas (REDCA+)
Multi-country Western Pacific
Myanmar
Namibia
Nepal
Nicaragua
Niger
Nigeria
Pakistan
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Romania
Russian Federation
Rwanda
Sao Tome and Principe
Senegal
Serbia
Sierra Leone
Solomon Islands
Somalia
South Africa
Sri Lanka
Sudan
Suriname
Swaziland
Syrian Arab Republic
Tajikistan
Tanzania
Thailand
Timor-Leste
Togo
Tunisia
Turkey
Uganda
Ukraine
UN Theme Group on HIV/AIDS (West Bank and Gaza)
Uzbekistan
Viet Nam
Yemen
Zambia
Zanzibar (Tanzania)
Zimbabwe