## Menu
Dashboard: Moldova - TB
TB NFM, | Grant No. [Nr. Grantului]: MDA-T-PAS
V1.0
Finance
Programmatic
Management
Select the option you want to see:
Recommendations
Actions
Grant Detail
List of Indicators
Data Entry
Grant Information
Indicators
Reports

## List of Indicators
Dashboard: Moldova - TB
Financial information
Name: | Definition | Measurement | Data Sources
F1: Budget and disbursements by Global Fund [Bugetul și debursările de către Fondul Global] | Cumulative budget: Sum of the grant budget from period one (quarter, trimester, or semester) of the current phase, up to and including the dashboard reporting period. Cumulative Disbursments by GF: Sum of all the funds transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to and including the dasboard reporting period. | Currency of the grant ($ or Euro) Cumulative – Figures refer to budget and disbursements for all the periods of the phase up to and including the dashboard reporting period | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F2: Budget and actual expenditures by Grant Objective [Bugetul și cheltuielile actuale după Obiectivele Grantului] | Cumulative Budget per Objective: Sum of the grant budget by Objective, from period one of the current phase up to and including the dashboard reporting period. Cumulative Expenditure per Objective: Sum of amounts spent by Objective directly by the PR plus the amounts transferred by the PR to all SRs from the beginning of the phase up to and including dashboard reporting period, by Objective | • Cumulative – Figures refer to budget, disbursements or expenditure for all the periods of the phase up to and including the dashboard reporting period. | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F3: Disbursements and expenditures [Debursări și cheltuieli] | Disbursement by GF: Prior to this Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to but not including dashboard reporting period. Disbursement by GF: Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), during dashboard reporting period. PR disbursements and expenditure: Prior to this Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) up to but not including dashboard reporting period. PR disbursements and expenditure: Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) during dashboard reporting period. Disbursements to SRs: Prior to this Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), up to but not including dashboard reporting period. Disbursements to SRs:Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), in dashboard reporting period. SR expenditures: Prior to this Reporting period: The sum of all expenditures reported by the SRs, up to but not including dashboard reporting period. SR expenditures: Reporting period: The sum of all expenditures reported by the SRs, during dashboard reporting period. | Currency of the grant ($ or Euro) • Reporting period – Figures refer to budget, disbursements or expenditure for the reporting period to which the dashboard refers. • Prior to reporting period - Figures refer to the total budget, disbursements or expenditure for all the periods before but not including the current period. | PU/DR; PR data: SR reports to PR
F4: Latest PR reporting and disbursement cycle [Ultima perioadă de raportare și debursare a RP] | Days taken to submit final PU/DR to LFA – This indicator measures the number of calendar days it took the PR to send a final Performance Update and Disbursement Request (PU/DR) to the LFA after the end of the period. A 'final' PU/DR would be one for which the LFA did not require any further clarifications from the PR. The expected value is 45 days from the end of the period, as defined in the Grant Agreement. The actual value is the number of calendar days from the end date of the period to the date on which the PR sent to the LFA the final PU/DR. Days taken for disbursement to reach PR – This indicator measures the number of calendar days it took the Global Fund to send the latest disbursement to the PR's account after receipt of the acceptable PU/DR by the LFA. The expected number is 45 days. The actual number is the number of days from the date of transmission by the PR to the LFA of the acceptable PU/DR to the date the disbursement is received by the PR at its bank. Days taken for disbursement to reach SRs – This indicator measures the average number of days for disbursements to be made to all the SRs. The expected value for this indicator will be set locally by the PR and SRs, preferably in the Grant Operations Manual. The actual value is the average of the number of days from the receipt of the funds from the GF by the PR to the date the funds are received by each SR. Different SRs coudl receive funds on different dates and this indicator is the average across all SRs for the latest disbursement. | Number of calendar days; it refers only to reporting period for which the latest disbursement was received and is not cumulative | PR, LFA, GF emails and records; bank notification document or the notice of receipt by the PR to GF; SR reports to PR based on bank records
Management Information
Name: | Definition | Measurement | Data Source
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) [Statutul Condițiilor Precedente și a Acțiunilor Prestabilite în Timp] | Number of Conditions Precedent (CPs) and Time Bound Actions (TBAs ) fulfilled, or unfulfilled. Within the Unfulfilled category, we distinguish between those CPs and TBAs whose deadline has not passed and those for which the deadline has passed. | Number, cumulative to the dashboard reporting period. Number of fulfilled CPs and/or TBAs plus unfulfilled CPs and/or TBAs should equal the total number set by the Global Fund on the grant | PR records; Grant Performance Reports;
M2: Status of key PR management positions | Number of PR grant management positions planned currently filled or vacant. Full time equivalents of the managerial positions that are on the organizational chart (or otherwise planned) and directly responsible for ensuring grant implementation at the PR, and lead SRs (if necessary). This will include new hires, current staff who are assigned to work on the grant’s management, as well as any staff seconded from other divisions or partner organizations. | Number, in current reporting period | PR records
M3: Contractual arrangements (SRs) | Identified: Total number of potential SRs identified by the PR for the phase. Assessed: Total number of potential SRs assessed by the PR to determine whether they qualify to function as SRs for the grant. Approved: Total number of SRs that have been approved. Signed: Total number of SRs that have signed agreements/contracts with the PR under the grant. Receiving funding: Total number of SRs that are getting funds and/or supplies from the PR. Numbers of SRs Identified, Assessed, Approved, Signed and Receiving funds are cumulative for the phase, with the following exceptions: If an SR does not need new approval in Phase II, then approval in Phase I is counted. If an SR was signed in a previous Phase but is not working in the current Phase, that SR is no longer counted in Identified, Assessed, Approved. | Number, cumulative to the reporting period. A SR is an institution or program with its own workplan, budget and performance targets. | PR records; Sub-agreements/MOUs; CCM records
M4: Number of complete reports received on time | The total number of periodic reports with up-to-date financial, management and performance (programmatic) data received by the PR from SRs and by SRs from the SubSRs (SSRs) by the expected date. A 'complete' report is one that contains all the data that the PR requires for the PU/DR. The expected date would be set by the PR in the sub-agreements. | Number of reports received. The figure reflects only the period of reporting; it is not cumulative. | PR and SR records
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals | This indicator measures the budget approved for the current phase of the grant for purchase of health products and equipment and pharmaceuticals and medicines (categories 4 and 5 in the new Enhanced Financial Report), and the cumulative amounts of financial obligations and expenditures up to the dashboard reporting period. Budget approved: Total approved budget for purchases (categories 4 and 5) for the entire phase of the grant. It does not include the amounts for fees, management, operational costs, etc. Cumulative Obligations: Total of all order(s) placed and monies committed for these purchases by the PR up to and including the dashboard reporting period. Ideally, by the end of the Phase, budget should equal obligations. Cumulative expenditure: Total of actual Expenditures on category 4 and 5 up to and including the dashboard reporting period (whether paid by PR or authorized to be paid by another entity like GF or other). | Currency of the grant ($ or Euro) | Grant agreement approved budget (for categories 4 and 5 of Enhanced Finance Reporting in current phase); and PR financial data (for expenditures), and/or PSM unit (for orders placed and funding committed or obligated).
Note: Category 6 of the EFR will not be considered as part of the budget for pharmaceuticals. Category 6 has several expenditures that are difficult to disaggregate or quantify, such as warehousing costs, distribution costs (particularly when distibution is done by MOHs), and others that are related to operational costs of the PSM component.
M6: Difference between current and safety stock | This indicator is a snapshot of the difference between the current (or last month) stock level of a specific product (medicine in single, fixed-dose combination, bednets, diagnostic kits, etc.) of a particular dose, expressed in monthly needs (number of months of treatment available) for all patients in the program, and the safety or buffer stock (also expressed in months) as established by the disease program, warehouse system or essential drugs program, for the particular product and dosage. The table will show the difference in months in colors: • RED: when the difference is negative or 0, showing that months of existing stock are lower than or equal to what has been established as months of safety stock • YELLOW: when we have more than the level of safety stock (>0) but less than 3 months (+3). • GREEN: when the difference is between 3 and 18 months. • VIOLET: When the difference shows that the level above the safety stock is greater than or equal to 18 months indicating a potential overstock) problem. For a full description of how this indicator is calculated, please see the User’s Manual. | Number of months | PR records: Warehouse data.
Programmatic Indicators (from Performance Framework) [Indicatorii programatici]
Indicator | Definition (from M&E Plan, 2014) [Definiție (din planul M&E,2014] | Measurement | Data Source [sursa de date]
MDR TB-4: Percentage of cases with drug resistant TB (RR-TB and/or MDR-TB) started on treatment for MDR-TB who were lost to follow up at six months | Numerator: Number of MDR-TB cases initiated on second line anti-TB treatment regimen during the specified period of time, who were lost to follow up at the end of 6 months of treatment (Year 1 - 2014 cohort; Year 2 - 2015 cohort; Year 3 - 2016 cohort). Denominator: Number of MDR-TB cases initiated on second line anti-TB treatment during the specified period of time. | Recording and reporting system for drug-resistant TB; report of the cases with drug resistant TB started on treatment for MDR-TB, who were lost to follow up at six months. The baseline data refer to the MDR TB cohort registered during the Semester I, 2013. | SYME TB - R&R TB system, quarterly/ annual reports, NTP reports.
Number and percentage of new MDR-TB patients transferred to or initiated DOTS Plus treatment on ambulatory phase and provided with incentives to improve treatment compliance | Numerator: Number of new MDR-TB patients transferred to / or initiated the DOTS Plus treatment in ambulatory conditions and receiving incentives to improve treatment compliance during reported period from right and left bank of the river Nistru. Denominator: Total Number of MDR-TB patients transferred to / or initiated the DOTS Plus treatment in ambulatory conditions during the same period. | The patient is qualified reached by the supporting programme, if he/she benefited from incentive programme. | SYMETB and data base implemented for incentives programmes by the SR AFI.
Number and percentage of new sensitive TB patients transferred to or initiated DOTS treatment on ambulatory level, provided with incentives to improve treatment compliance (Transnistria) | Numerator: Number of new TB patients transferred to / or initiated the DOTS treatment in ambulatory conditions and receiving incentives to improve treatment compliance during reported period. Denominator: Total Number of TB patients transferred to / or initiated the DOTS treatment in ambulatory conditions during the same period. | The patient is qualified reached by the supporting programme, if he/she benefited from incentive programme. | The source of data for the indicator will be SYMETB and data base implemented for incentives programmes by the SR AFI.
Percentage and number of patients with symptoms or signs suggestive to TB, examined by Xpert MTB/RIF | Numerator: Number of patients with symptoms or signs suggestive to TB, examined by Xpert MTB/RIF. Denominator: Total number of patients with symptoms or signs suggestive to TB. | The estimation of the percentage of examination with Xpert MDTB/RIF methodology considers the current coverage and the schedule of full coverage with equipment of the country. The numerator and denominator represents an estimated data, and during the reporting period will be presented the defacto data. | R&R system.
MDR TB-2: Number of bacteriologically confirmed, drug resistant TB cases (RR-TB and/or MDR-TB) notified | Numerator: Number of bacteriologically confirmed, drug resistant TB cases (RR-TB and/or MDR-TB) notified | The indicator shall be reported for the cohort of patients registered 6-12 months ago, to make sure that the final result of the investigation is introduced in the SIME TB database, considering the fact that it takes from 4 to 5 months to perform the test, obtain the result, and further introduce it in the SIME TB account (in the case when patients are investigated using the classical (solid) method of culture and DST). This indicator covers both the civilian and the penitentiary sector, incl. the Transdniester region. | SYME TB - R&R TB system, annual reports, DR routine surveillance.
DOTS-1b Number of notified cases of bacteriologically confirmed TB (new and relapse) | Numerator: Number of bacteriologically confirmed TB cases notified to the national health authority during the reporting period | Process indicator to measure the number of bacteriologically confirmed TB cases notified to the national health authority during the reporting period | R&R system.
Indicator Number: Name (Perf Framework No.) | Definition | Measurement | Data Source
The indicators should be selected by the PRs and members of the CCM or the CCM Technical Committee, from the Performance Framework |  |  | Performance Framework
Menu

## Data Entry
Grant information [Informatia de Grant]
| Country [Țara]: | Moldova |  | Title of the Grant [Numele Grantului]: |  | Strengthening Tuberculosis control in the Republic of Moldova
| Grant No. [Nr. Grantului]: | MDA-T-PAS |  | Component [Componentul]: |  | TB | Total Funding[Suma totala]: | 6116310
| Principal Recipient [Recipientul Principal]: | Center for Health Policies and Studies (PAS Center) |  |  | Round [Runda]: | NFM | Phase [Faza]:
| Start Date (dd/Mmm/yy) [Data Demarării (zz/ll/aa)]: | 01 July 2015 |  | Local Fund Agent [Agentul Local al Fondului]: |  | PwC (PricewaterhouseCoopers)
| Latest Rating [Ultimul Rating]: | A1 |  | Fund Portfolio Manager [Portfolio Manager]: |  | Tsovinar Sakanyan
Information reporting period [Informația despre perioada raportată]
| Report Period [Perioada de raportare]: | P1 | From [de la]: | 2015-07-01 | To[Pînă la]: | 2015-12-31 | Date of entry of information[Data de introducere a informației]: |  | 2016-03-01
| Prepared by [Pregătit de către]: |  | PAS Center
Information on indicators [Informația despre indicatori]
Enter the data based on the colour-coded cells [Introduceți datele bazîndu-vă de celulele codificate prin culoare]
| Financial Information [Informația Financiară]: |  | Management Information [Informația pe Management]: |  |  | Programmatic Information [Informația Programatică]:
| Financial Information [Informatia Financiara]: | [8 empty] | Enter finance data in every orange cell like this [Introduceți datele financiare in fiecare celula portocaliu ca aceasta].
| Currency of the grant[Valuta Grantului] |  | €
F1: Budget and disbursements by Global Fund [Bugetul și debursările de către Fondul Global]
| Disbursement [Debursări] | [15 empty] | 1399791.8563
| Reporting period [perioada de raportare] | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12 | % Cumulative |  |  | 0
| Budget (in €) | P1: 1399791.8563 | 139.5% |  |  | 0
| Disbursements by GF (in €) | [15 empty] | 0
| Cumulative budget [Buget cumulativ] | 1399791.8563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Cumulative disbursements [Debursări cumulative] | 1952798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
|  | 139.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0
F2: Budget and actual expenditures by Grant Objective [Bugetul și cheltuielile actuale după Obiectivele Grantului]
| Grant Objective [obiectivele Grantului] | P1: Cumulative Budget (in €); P2: Cumulative Expenditures (in €)
1 | TB care and prevention | P1: 56524.34; P2: 49789.4999
2 | MDR-TB | P1: 1220007.2155; P2: 1038827.3969
3 | Program management | P1: 123260.3008; P2: 108675.5526
| Total | P1: 1399791.8563; P2: 1197292.4495; P4: OK: Data match
| F3: Disbursements and expenditures [Debursări și cheltuieli] | [15 empty] | 0
0
|  | P1: Prior to reporting period [Către perioada de raportare]; P2: Current reporting period [Perioada de raportare curentă]; P3: Total Spent and Disbursement (in €) |  |  | 0
| Disbursed by Global Fund (Debursat de către Fondul Global) | P1: 1952798; P3: 1952798
| PR expenditure and disbursement (Cheltuielile și debursările RP ) | P2: 1197292.4495; P3: 1197292.4495
| Disbursed to SRs (Debursări către SR) | P2: 477237.76; P3: 477237.76
| SR expenditures (Cheltuielile SR) | P2: 351635.88; P3: 351635.88
F4: Latest PR reporting and disbursement cycle [Ultima perioadă de raportare și debursare a RP]
Last fund disbursement: Number of calendar days [Ultima debursare a surselor: Număr de zile calendaristice]
|  | Expected (days) Preconizat (zile) | Actual (days) Actual (zile)
| Days taken to submit final PU/DR to LFA (Zile necesare pentru remiterea PU/DR final către ALF) | P1: 45; P2: 45
| Days taken for disbursement to reach PR (Zile necesare pentru debursare către RP) | P1: 45; P2: 0
| Days taken for disbursement to reach SRs (Zile necesare pentru debursare către SR) | P1: 20; P2: 5
| Management Information [Informația pe Management]: | P6: Enter management data in every blue cell [Întroduceți datele pentru management în celulele albastre].
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) [Statutul Condițiilor Precedente și a Acțiunilor Prestabilite în Timp]
|  |  | Fulfilled [Îndeplinite] | Not fulfilled, but within deadline [Ne îndeplinite dar realizarea în conformitate cu planul] | Not fulfilled, and past the deadline [Ne îndeplinite și au depășit termenul de realizare] | Total
| Conditions precedent (CPs) [Conditii precedente] | P2: 1; P3: 2; P4: 0; P5: 3
| Time Bound Actions (TBAs) [Acțiuni Prestabilite în Timp] | P2: 0; P3: 0; P4: 0; P5: 0
M2: Status of key PR management positions
|  | Planned | Filled | Vacant
| PMU | P1: 14; P2: 14; P3: 0
M3: Contractual arrangements (SRs)
|  | Identified | Assessed | Approved | Signed | Receiving Funding
| SRs | P1: 2; P2: 0; P3: 2; P4: 2; P5: 2
M4: Number of complete reports received on time
|  | # Expected | # Received | Pending
| SSR to SR | P1: 9; P2: 9; P3: 0
| SRs to PR | P1: 2; P2: 2; P3: 0
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals
|  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
| Budget Approved* | P1: 422100.54
Obligations
| Expenditures | P1: 494949.4814
| Budget Approved cumulative* | P1: 422100.54
Obligations cumulative
| Expenditures cumulative | P1: 494949.4814
* Includes only AFR category 4, 5 and 6 (Health products and health equipment & Medicines and Pharmaceuticals)
M6: Difference between current and safety stock
| Component | Products | (1) Number of tablets per patient per day (Review country treatment guidelines) | (2 = 1 x 30) Monthly treatment (Tablets per patient x 30 days) | (3) Total patients in treatment | (4 = 2 x 3) Total # tab/pills required for all patients per month | (5) Current stock in central warehouse (that does not expire within the next 3 months) | (6 = 5 / 4) Stock level expressed in months of treatment for all current patients | (7) Level of safety stock (expressed in months and defined by country) | (8 = 6 - 7) Difference between current stock and safety stock
| Please Select | P1: Please Select
Please Select
Please Select
Please Select
| Programmatic Information: | P9: Enter performance data in every yellow cell.
| Programmatic indicators (Performance Framework ) |  |  | Code | Directly Tied? |  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
TOP 3 | Percentage of cases with drug resistant TB (RR-TB and/or MDR-TB) started on treatment for MDR-TB who were lost to follow up at six months [Numărul și procentul pacienţilor cu tuberculoză drog-rezistentă (RR-TB și/sau MDR-TB) care au întrerupt tratamentul DOTS-Plus către luna a 6 de la demararea acestuia] |  |  | MDR TB-4 | Yes | Target | bar: P1 to Enter performance data in every yellow cell. P12
[6 empty] | Achieved | P1: 8.7%
| Number and percentage of new MDR-TB patients transferred to or initiated DOTS Plus treatment on ambulatory phase and provided with incentives to improve treatment compliance [Numărul și procentul de pacienți noi MDR-TB transferați sau inițiat tratament DOTS Plus in faza de ambulator și au primit stimulente pentru îmbunătățirea respectării tratamentului] |  |  |  | Yes | Target | P1: 90%
[6 empty] | Achieved | P1: 95%
| Number and percentage of new sensitive TB patients transferred to or initiated DOTS treatment on ambulatory level, provided with incentives to improve treatment compliance (Transnistria) [Numărul și procentul de pacienți noi TB sensibili transferați sau inițiat tratament DOTS in faza de ambulator, au primit stimulente pentru îmbunătățirea respectării tratamentului (Transnistria)] |  |  |  | Yes | Target | P1: 90%
[6 empty] | Achieved | P1: 62%
| Percentage and number of patients with symptoms or signs suggestive to TB, examined by Xpert MTB/RIF [Procentul și numărul de pacienți cu simptome sau semne sugestive pentru TB, examinati de Xpert MTB / RIF] |  |  |  | Yes | Target | P1: n/a
[6 empty] | Achieved | P1: n/a
| Number of bacteriologically confirmed, drug resistant TB cases (RR-TB and/or MDR-TB) notified [Numărul de cazuri de TB DR (RR-TB și/sau MDR-TB), confirmate bacteriologic, notificate] |  |  | MDR TB-2 | Yes | Target | P1: 456
[6 empty] | Achieved | P1: 429
| Number of notified cases of bacteriologically confirmed TB (new and relapse) [Numărul de cazuri notificate cu TB confirmate bacteriologic (nou și recidivă)] |  |  | DOTS-1b | Yes | Target | P1: 1099
[6 empty] | Achieved | P1: 929
[5 empty] | Yes | Target
Achieved
[5 empty] | Yes | Target
Achieved
| Table is automatically updated. No data or information is to be entered here. |  |  | Code | Directly Tied? |  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
| Percentage of cases with drug resistant TB (RR-TB and/or MDR-TB) started on treatment for MDR-TB who were lost to follow up at six months [Numărul și procentul pacienţilor cu tuberculoză drog-rezistentă (RR-TB și/sau MDR-TB) care au întrerupt tratamentul DOTS-Plus către luna a 6 de la demararea acestuia] |  |  | MDR TB-4 | Yes | Target | 7% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Achieved | 8.7% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number and percentage of new MDR-TB patients transferred to or initiated DOTS Plus treatment on ambulatory phase and provided with incentives to improve treatment compliance [Numărul și procentul de pacienți noi MDR-TB transferați sau inițiat tratament DOTS Plus in faza de ambulator și au primit stimulente pentru îmbunătățirea respectării tratamentului] |  |  |  | Yes | Target | 90% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Achieved | 95% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number and percentage of new sensitive TB patients transferred to or initiated DOTS treatment on ambulatory level, provided with incentives to improve treatment compliance (Transnistria) [Numărul și procentul de pacienți noi TB sensibili transferați sau inițiat tratament DOTS in faza de ambulator, au primit stimulente pentru îmbunătățirea respectării tratamentului (Transnistria)] |  |  |  | Yes | Target | 90% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Achieved | 62% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on B30: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.
Note on B68: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B74: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B89: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.
Menu

## Grant Detail
Dashboard: Moldova - TB
Country: | Moldova |  | Title of the Grant: |  | Strengthening Tuberculosis control in the Republic of Moldova
Component: | TB | Grant No. | MDA-T-PAS | Start Date: |  | 01 July 2015 | Total Funding | 6116310
Round: | NFM | Phase: | 0 | Principal Recipient: |  | Center for Health Policies and Studies (PAS Center)
Report Period: | P1 | from: | 2015-07-01 | to: |  | 2015-12-31 | Latest Rating: | A1
Local Fund Agent: | PwC (PricewaterhouseCoopers) |  |  | Fund Portfolio Manager: |  | Tsovinar Sakanyan
Prepared by: | PAS Center |  |  | Report preparation date: |  | 2016-03-01
http://www.crwflags.com/fotw/flags/country.html
Menu

## Finance
Dashboard: Moldova - TB
NFM | 0 |  |  |  | Report Period [Perioada de raportare]: |  | P1
Latest Rating [Ultimul Rating]: | A1 |  | Center for Health Policies and Studies (PAS Center) |  | From [de la]: |  | 2015-07-01
|  | Strengthening Tuberculosis control in the Republic of Moldova |  |  |  | To[Pînă la]: | 2015-12-31
Financial Indicators
F1: Budget and disbursements by Global Fund [Bugetul și debursările de către Fondul Global] - in (€) Report Period [Perioada de raportare]: P1 |  |  |  | F3: Disbursements and expenditures [Debursări și cheltuieli] - in (€) Report Period [Perioada de raportare]: P1
Comments: | The cumulative disbursement is more than cumulative budget, as it includes the buffer period. Suma debursată este mai mare decât bugetul, deoarece include perioada de buffer. |  |  | Comments: | The cumulative disbursement by the GF is more than cumulative cash-out flow of the PR, as it includes the buffer period and committed payments for the reported period. The variance between disbursed amount to SRs and SRs' expenditures is committed: for NGO grant programme implemented by the SR FSM and for incentives programme implemented by the SR AFI. Suma debursată de FG este mai mare decât cheltuielile RP împreună cu debursările către SRi, deoarece include perioada de buffer și sumele angajate pentru plăți aferente perioadei de raportare. Variația dintre suma debursată către SRi și cheltuielile SR-lor este angajată: pentru programul de granturi ONG implementat de SR FSM și pentru programul de suport al pacienților implementat de către SR AFI.
F2: Budget and actual expenditures by Grant Objective [Bugetul și cheltuielile actuale după Obiectivele Grantului] - in (€) Report Period [Perioada de raportare]: P1 |  |  |  | F4: Latest PR reporting and disbursement cycle [Ultima perioadă de raportare și debursare a RP] Report Period [Perioada de raportare]: P1
Comments: | For two of objectives, the expenditures are almost in line with the budget, with a slight variance. The variance between budget and expenditures for the MDR-TB component is committed: for NGO grant programme implemented by the SR FSM for the MDRTB component; for incentives programme implemented by the SR AFI for MDR TB component and other planned grant activities for MDRTB component; for activities linked to the TB CCs extension plan, the TA for TB/HIV and TA data based for Xpert. Pentru două dintre obiective, cheltuielile sunt aproape în conformitate cu bugetul, cu o ușoară variație. Variația dintre bugetul și cheltuielile pentru componenta MDR-TB este angajată: pentru programul de granturi ONG implementat de SR FSM pe componenta TB MDR; pentru programul de suport al pacienților implementat de către SR AFI pentru componenta TB MDR și alte activități de grant planificate pentru componenta TB MDR; pentru activități legate de planul de extindere TB CC, AT pentru TB / HIV si AT pentru Xpert. |  |  | Comments: | The PR always makes the disbursements to SRs in the shortest period when the disbursement request is received and the report is presented. Perioada de debursare către SR este cit mai operativ posibil de la data depunerii cererii de debursare şi prezentare a raportului financiar.
Last fund disbursement: Calendar days
[6 empty] | Expected (days) | Actual (days)
|  |  |  | Days taken to submit final PU/DR to LFA (Zile necesare pentru remiterea PU/DR final către ALF) |  | 45 | 45
|  |  |  | Days taken for disbursement to reach PR (Zile necesare pentru debursare către RP) |  | 45 | 0
|  |  |  | Days taken for disbursement to reach SRs (Zile necesare pentru debursare către SR) |  | 20 | 5
Menu

## Management
Dashboard: Moldova - TB
NFM | 0 |  |  |  |  | Report Period [Perioada de raportare]: |  | P1
Latest Rating [Ultimul Rating]: | A1 |  | Center for Health Policies and Studies (PAS Center) |  |  | From [de la]: |  | 2015-07-01
|  | Strengthening Tuberculosis control in the Republic of Moldova |  |  |  |  | To[Pînă la]: | 2015-12-31
Management Indicators
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) [Statutul Condițiilor Precedente și a Acțiunilor Prestabilite în Timp] Report Period [Perioada de raportare]: P1 |  |  |  | M2: Status of key PR management positions Report Period [Perioada de raportare]: P1
Comments: | 1. No latter than 31 December 2016, the Grantee in collaboration with the CCM, other stakeholders and partners in the Republic of Moldova shall prepare and deliver to the Global Fund a sustainability plan for the national TB programm, endorsed by the government of the R. of Moldova , in forum and substance satisfactory to the Global Fund - The discussion at the CCM and the WTG level on the development the sustainability plan for the National TB programme was initiated (minute of the WTG as of June 2, 2015 and Minute of the Working Group responsible for development of the new TB Programme as of January 28, 2016). The plan will be developed with support planned in the grant implemented by the UCIMP. 2. Prior to financing extension of the TB community centers with the Grant Funds a) the Grantee shall engage a technical assistance partner acceptable to the Global Fund, to review and access the TB community centers model, including effectiveness, TB system integration and sustainability ( the Independent Assessment) and b) the Global Fund shall review the results of the Independent Assessment and if satisfied with the form and substance of the Independent Assessment findings, approve the Grant Funds for financing such TB community Centers - 1. The PR contracted two independent experts following to the WHO Europe recommendations (the contracts was signed on April 8, 2015). The report of the independent assessment was sent to the WHO, GF, CCM, National Programmes and PR. 2. Following the review of the Independent Assessment report and the internal consultations on the issues highlighted in the report, the Global Fund Secretariat requested from the country /MoH to share the following: a) The opinion on the feasibility/readiness of addressing the recommendations, and the timeframes that might be required for it; and b) Based on the considerations above, to provide the Global Fund with an improved, alternative model for the existing CCs, which should be built on the best practices for provision of TB care, coordinated among the TB units, CCs and NGOs. To provide the Secretariat with an assurance, that the new TB CC model will form a part of the costed transition plan, as a demonstration of the government’s readiness to continue countrywide financing of the new CC model for outpatient TB services delivery. At the request of the Global Fund Secretariat, the MoH sent the letter with opinion on feasibility and readiness of addressing the experts recommendations in the country policy documents ( letter 01-15/448 as of 04.12.2015). The presentation of the improved model of the existing CCs was described in the letter 012/2016 as of 15/01/2016. The Global Fund Secretariat did not accept to finance this activity, based on presented additional commitments. Instead, a new activities was requested to be proposed by the coutry. 3. In accordance with the Global Fund Board Decision Point GF/B28/DP4: commitment and disbursement of 15% of the Republic of Moldova aggregate allocation of EUR 28,640,132 for the period of 2014-2017 allocation period, , which is equal to EUR 4,296,020, is subject to the Republic of Moldova compliance with the Global Fund willingness to pay requirement - This is a grant life condition related to both NFM grant in country for HIV and TB. Fulfilment of country commitments for both diseases during grant life is the subject of a permanent monitoring. 1. Nu mai târziu de 31 decembrie 2016, Recipientul Principal în colaborare cu CNC, alte părți interesate și parteneri din Republica Moldova va pregăti și remite Fondului Global un plan de sustenabilitate pentru programul național TB, aprobat de guvernul R. Moldova, în forum și substanță satisfăcătoare pentru Fondul Global. Măsurile întreprinse - discuția la nivel de CNC și GTL privind dezvoltarea planului de sustenabilitate a programului Național TB, a fost inițiată (proces verbal al GTL, din 2 iunie 2015 și Procesul-verbal al Grupului de lucru responsabil pentru dezvoltarea noului PNCT din 28 ianuarie, 2016). Planul va fi dezvoltat cu suportul programat în grantul implementat de UCIMP. 2. Înainte de aprobarea finanțării pentru extinderea modelului de centru comunitar pentru pacienții cu TB, din fondurile grantului a) Recipientul principal va angaja un consultant de asistență tehnică, acceptabil pentru Fondul Global, pentru a revizui și a evalua modelul centrelor comunitare TB, inclusiv eficacitatea, integrarea în sistemul TB și durabilitatea (Evaluare independentă) și b) Fondul Global va analiza rezultatele evaluării independente și, dacă este satisfăcut de forma și fondul constatărilor ale evaluării independente, va aproba fondurile de grant pentru finanțarea centrelor comunitare – Măsurile întreprinse – 1. RP a contractat doi consultanți independenți, la recomandarea biroului OMS pentru Europa (contractele a fost semnat la 8 aprilie 2015). Raportul de evaluare independent a fost trimis la OMS, FG, CNC, programele naționale și RP. 2. În urma revizuirii raportului de evaluare independentă și consultările interne privind aspectele evidențiate în raport, secretariatul Fondul Global a solicitat țării / MS următoarele: a) Avizul privind fezabilitatea / gradul de pregătire al abordării recomandărilor, precum și intervalele de timp care ar putea fi necesare pentru aceasta; și b) În baza considerațiilor de mai sus, să prezinte Fondului Global un model îmbunătățit, alternativ pentru centrele comunitare existente, care ar trebui create în baza celor mai bune practici pentru prestarea serviciilor de îngrijire TB, coordonate între instituțiile medicale implicate în controlul TB, centre comunitare și ONG-uri. La fel, să ofere Secretariatului o asigurare că noul model de centre comunitare TB va forma o parte a planului de tranziție bugetat, ca o dovadă de pregătire a guvernului să continue finanțarea națională a noului model CC pentru livrarea serviciilor de îngrijire ambulatorie TB. La solicitarea Secretariatului Fondului Global, MS a trimis scrisoarea cu avizul privind fezabilitatea și gradul de pregătire a implementării recomandărilor experților în documentele legislative din țară (scrisoare 01-15 / 448 din 04.12.2015). Prezentarea modelului îmbunătățit al centrelor comunitare existente a fost descrisă în scrisoarea 012/2016 de 15/01/2016. Secretariatul Fondul Global nu a susuținut finanțarea acestei activități în pofida angajamentelor suplimentare prezentate. În schimb, a solicitat ca țara să prezinte noi activități în limita bugetului aprobat pentru extinderea centrelor comunitare, la care se lucrează în prezent. 3. În conformitate cu decizia Consiliului Fondului Global, punctul GF / B28 / DP4: angajamentul și plata a 15% din alocarea totală de 28,640,132 EUR pentru Republica Moldova în perioada 2014-2017, care este egală cu 4,296,020 EURO, este condiționată Republicii Moldova de respectarea cerinței Fondului Global de a mări finanțarea din partea statului, în domeniul unde a investit Fondul Global - Aceasta este o condiție pe durata grantului, atât pentru grantul NFM TB, cât și pentru HIV. Îndeplinirea angajamentelor de țară pentru ambele maladii, pe durata granturilor este obiectul unei monitorizări permanente ale acestora. |  |  | Comments: | All key positions of the management department are filled in by the PR. Toate functiile sunt completate de RP.
M3: Contractual arrangements (SRs) Report Period [Perioada de raportare]: P1 |  |  |  | M4: Number of complete reports received on time Report Period [Perioada de raportare]: P1
Comments: | None of the SRs needed to be assessed, due to proved experience within the precedent grant implementation. Nici unul dintre sub-recipienti nu a necesitat să fie evaluat, dat fiind experiența demonstrată în cadrul implementării grantului precedent. |  |  | Comments: | For the reported period, July-December 2015, 9 SSRs were involved in TB related activities, from which one ("Activ" from Bender) is acting as SSR for both SRs - Soros Foundation Moldova and NGO "AFI". Basically, the majority of NGO are implementing one grant, with exception of three NGOs which applied to Soros Foundation - Moldova and were granted with 2 grants each, but within different components and targeted to different populations: NGO "AFI", NGO ”Hope of Land” and NGO ”Medico-Social Programs”. In perioada de raportare, iulie-decembrie 2015, 9 sub-subrecipienți au realizat activități conexe programului de control al TB, din care o organizație (ONG ”Aktiv”) activează în calitate de sub-subrecipient pentru ambii SR: Fundația Soros - Moldova și ONG "AFI". Majoritatea ONG-urilor realizează cîte un grant, excepție fiind 2 ONG care au aplicat către Fundația Soros - Moldova, și au fost aprobate pentru implementarea a câte 2 granturi, în cadrul diferitor componente ale programului de granturi mici și orientate spre diferite populații-cheie - ONG ”AFI”, ONG ”Speranța Terrei” și ”Programe Medico-Sociale”.
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals |  |  |  | M6: Difference between current and safety stock Report Period [Perioada de raportare]: P1
Comments: | EUR 72.849.00 reprezinta suma supraconsumată versus la suma totală estimată pentru procurarea echipamentului Xpert și consumabile pe motiv de modificare a rate EUR/USD, considerate in cererea de finanțare a țării către FG . In cerere rata pentru EUR/ USD a fost de 1,36946, insă la procurarea bunurilor rata a fpst de 1,0927. |  |  | Comments: | Procurarea echipamentului si cartridjelor pentru examinarea pacientilor prin metod rapida s-a realizat in Octombrie - Decemberie, 2015 cu distribuirea in luna Ianuarie 2016. Echipamentul a fost distribuit la 27 institutii medico sanitare unde nu au fost instalate Xpert in cadrul programului de asistenta de la TB Reach. Cartridjele au fost procurate pentru acoperirea necesitatilor intregii tarii. pentru jumate de an. In paralel s-a primit o cantitate de consumabile pentru echipamentul oferit de TB Reach in cantitate ce acoperă necesitatile pina in februarie 2017.
|  |  |  | Component | Products | Stock level expressed in months of treatment for all current patients | Months of safety stock | Difference between current stock and safety stock
|  |  |  | Please Select | Please Select |  | 0
[5 empty] | Please Select |  | 0
[5 empty] | Please Select |  | 0
[5 empty] | Please Select |  | 0
* Includes only AFR category 4, 5 and 6 (Health products and health equipment & Medicines and Pharmaceuticals)
Menu

## Programmatic
Dashboard: Moldova - TB
NFM | 0 | [8 empty] | Report Period [Perioada de raportare]: |  | P1
Latest Rating [Ultimul Rating]: | A1 |  | Center for Health Policies and Studies (PAS Center) | [7 empty] | From [de la]: | 2015-07-01
|  | Strengthening Tuberculosis control in the Republic of Moldova | [8 empty] | To[Pînă la]: | 2015-12-31 | [7 empty] | Raiting |  | Valor
Programmatic Indicators
Percentage of cases with drug resistant TB (RR-TB and/or MDR-TB) started on treatment for MDR-TB who were lost to follow up at six months [Numărul și procentul pacienţilor cu tuberculoză drog-rezistentă (RR-TB și/sau MDR-TB) care au întrerupt tratamentul DOTS-Plus către luna a 6 de la demararea acestuia] |  |  |  | Number and percentage of new MDR-TB patients transferred to or initiated DOTS Plus treatment on ambulatory phase and provided with incentives to improve treatment compliance [Numărul și procentul de pacienți noi MDR-TB transferați sau inițiat tratament DOTS Plus in faza de ambulator și au primit stimulente pentru îmbunătățirea respectării tratamentului] |  |  |  | Number and percentage of new sensitive TB patients transferred to or initiated DOTS treatment on ambulatory level, provided with incentives to improve treatment compliance (Transnistria) [Numărul și procentul de pacienți noi TB sensibili transferați sau inițiat tratament DOTS in faza de ambulator, au primit stimulente pentru îmbunătățirea respectării tratamentului (Transnistria)]
Comment: P1 | Final data for Sem.II.2014 - 41 of 470 patients included in the DOTS Plus treatment in Sem.II.2014, abandoned the treatment after 6 months of treatment DOTS Plus. Reason for variance: The interim rate of lost to follow up of MDR-TB treatment at the six months in 2014 is almost at the same level compared with the 2013 rate (8.3%). [Date finale pentru Sem.II.2014 - 41 din 470 pacienți incluși în tratament DOTS Plus în Sem.II.2014, au abandonat tratamentul după 6 luni de tratament DOTS Plus. Motivul variației: Se observă menținerea ratei interimare de abandon al tratamentului cazurilor MDR-TB pentru anul 2014 la același nivel, în comparație cu rata anului 2013 (8,3%)] |  |  | Comment: P2 | During reporting period a total of 515 MDR-TB patients received incentives for improved treatment compliance from the total number of 543 patients with MDR-TB in ambulatory phase under treatment. The indicator is achieved. [Pe parcursul perioadei de raportare un total de 515 pacienți MDR-TB au primit stimulente pentru îmbunătățirea respectării tratamentului din numărul total de 543 de pacienți cu MDR-TB in faza de ambulator. Indicatorul este atins]. |  |  | Comment: P3 | During reporting period, 173 TB patients registered under DOTS program received incentives for improved treatment compliance from the total number of 278 TB patients, under treatment. The indicator is achieved in proprotion of 69%. The reason for variances are due to following factors: the high number of patients transfered to MDRTB treatment during the intensive phase on TB sensitive treatment, lost to follow -up etc. [Pe parcursul perioadei de raportare, 173 de pacienți TB înregistrați in cadrul programului DOTS au primit stimulente pentru îmbunătățirea respectării tratamentului din numărul total de 278 de pacienți cu TB in tratament. Indicatorul este realizat în proporție de 69%. Motivul varianței: numărul mare de pacienți transferați la tratamentul TB MDR in timpul fazei intensive pe un tratament sensibil TB].
Indicators |  |  | Target | Achieved | 0% - 59% | 60% - 89% | > 90% | Comments |  |  |  |  | min | 0 | 30% | 60% | 90% | 100% |  | min | 0 | 20% | 40% | 60% | 80%
Percentage of cases with drug resistant TB (RR-TB and/or MDR-TB) started on treatment for MDR-TB who were lost to follow up at six months [Numărul și procentul pacienţilor cu tuberculoză drog-rezistentă (RR-TB și/sau MDR-TB) care au întrerupt tratamentul DOTS-Plus către luna a 6 de la demararea acestuia] |  |  | 7% | 8.7% | 80.46% |  |  | Final data for Sem.II.2014 - 41 of 470 patients included in the DOTS Plus treatment in Sem.II.2014, abandoned the treatment after 6 months of treatment DOTS Plus. Reason for variance: The interim rate of lost to follow up of MDR-TB treatment at the six months in 2014 is almost at the same level compared with the 2013 rate (8.3%). [Date finale pentru Sem.II.2014 - 41 din 470 pacienți incluși în tratament DOTS Plus în Sem.II.2014, au abandonat tratamentul după 6 luni de tratament DOTS Plus. Motivul variației: Se observă menținerea ratei interimare de abandon al tratamentului cazurilor MDR-TB pentru anul 2014 la același nivel, în comparație cu rata anului 2013 (8,3%)] |  |  |  |  | max | 30% | 60% | 90% | 100% | 200% |  | max | 20% | 40% | 60% | 80% | 100%
Number and percentage of new MDR-TB patients transferred to or initiated DOTS Plus treatment on ambulatory phase and provided with incentives to improve treatment compliance [Numărul și procentul de pacienți noi MDR-TB transferați sau inițiat tratament DOTS Plus in faza de ambulator și au primit stimulente pentru îmbunătățirea respectării tratamentului] |  |  | 90% | 95% | 105.6% |  |  | During reporting period a total of 515 MDR-TB patients received incentives for improved treatment compliance from the total number of 543 patients with MDR-TB in ambulatory phase under treatment. The indicator is achieved. [Pe parcursul perioadei de raportare un total de 515 pacienți MDR-TB au primit stimulente pentru îmbunătățirea respectării tratamentului din numărul total de 543 de pacienți cu MDR-TB in faza de ambulator. Indicatorul este atins]. | [5 empty] | de 0 a 0.3 | de 0.3 a 0.6 | de 0.6 a 0.9 | de 0.9 a 1 | de 1 a 2 | Rating | Valor | de 0 a 0.2 | de 0.2 a 0.4 | de 0.4 a 0.6 | de 0.6 a 0.8 | de 0.8 a 1
Number and percentage of new sensitive TB patients transferred to or initiated DOTS treatment on ambulatory level, provided with incentives to improve treatment compliance (Transnistria) [Numărul și procentul de pacienți noi TB sensibili transferați sau inițiat tratament DOTS in faza de ambulator, au primit stimulente pentru îmbunătățirea respectării tratamentului (Transnistria)] |  |  | 90% | 62% | 68.89% |  |  | During reporting period, 173 TB patients registered under DOTS program received incentives for improved treatment compliance from the total number of 278 TB patients, under treatment. The indicator is achieved in proprotion of 69%. The reason for variances are due to following factors: the high number of patients transfered to MDRTB treatment during the intensive phase on TB sensitive treatment, lost to follow -up etc. [Pe parcursul perioadei de raportare, 173 de pacienți TB înregistrați in cadrul programului DOTS au primit stimulente pentru îmbunătățirea respectării tratamentului din numărul total de 278 de pacienți cu TB in tratament. Indicatorul este realizat în proporție de 69%. Motivul varianței: numărul mare de pacienți transferați la tratamentul TB MDR in timpul fazei intensive pe un tratament sensibil TB]. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Percentage and number of patients with symptoms or signs suggestive to TB, examined by Xpert MTB/RIF [Procentul și numărul de pacienți cu simptome sau semne sugestive pentru TB, examinati de Xpert MTB / RIF] |  |  | n/a | n/a | n/a |  |  | The indicator will be reported in the next semester. [Indicatorul va fi raportat in semestrul viitor]. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number of bacteriologically confirmed, drug resistant TB cases (RR-TB and/or MDR-TB) notified [Numărul de cazuri de TB DR (RR-TB și/sau MDR-TB), confirmate bacteriologic, notificate] |  |  | 456 | 429 | 94.08% |  |  | Preliminary data for Q1-Q2.2015 - drug resistant tuberculosis patients 429 (RR-TB and / or MDR-TB), confirmed bacteriological were notified to the estimated 456 cases reported period. [Date preliminare pentru Q1-Q2.2015 - 429 pacienți cu tuberculoză drog-rezistentă (RR-TB și/sau MDR-TB), confirmate bacteriologic, au fost notificate, față de 456 cazuri estimate pentru perioada raportată]. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number of notified cases of bacteriologically confirmed TB (new and relapse) [Numărul de cazuri notificate cu TB confirmate bacteriologic (nou și recidivă)] |  |  | 1099 | 929 | 84.53% |  |  | Preliminary data for Sem.II. 2015 - 929 of notified cases of bacteriologically confirmed TB (new and relapse) from them (Sex: Male 699, Female 230; Age: <15 - 9, 15+ 920). It should be noted that for the TB patients registered in November and December of 2015, the final data will be available by January- February 2016, since the culture testing takes about 1- 2 months. As a result the final data will be available in the data system in the I quarter of 2016. Also it should be considered that the total number of notified cases of bacteriologically confirmed TB cases for year 2015 is 2110 cases, where 1181 cases were registered in I semester of 2015. [Datele preliminare pentru Sem. II. 2015 - 929 de cazuri notificate cu TB confirmate bacteriologic (recidivă si caz nou) din ei (Sex: bărbați 699, femei 230; Vârsta: <15 - 9, 15+ 920). Ar trebui de remarcat faptul că, pentru pacienții cu TB înregistrați în noiembrie și decembrie 2015, datele finale vor fi disponibile prin ianuarie-februarie 2016, deoarece testele de cultură durează aproximativ 1- 2 luni. Ca rezultat datele finale vor fi disponibile în sistemul de date în trimestrul I al anului 2016. De asemenea, trebuie luat în considerare faptul că numărul total al cazurilor notificate cu TB confirmate bacteriologic pentru anul 2015 este de 2110 de cazuri, în care au fost înregistrate 1181 de cazuri în I semestru 2015]. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
0 |  |  | 0 | 0 | n/a | [8 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
0 |  |  | 0 | 0 | 0% | [8 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[5 empty] | n/a | [8 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[5 empty] | n/a | [8 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Menu

## Recommendations
Dashboard: Moldova - TB
NFM | 0 |  |  |  |  | Report Period [Perioada de raportare]: | P1
Latest Rating [Ultimul Rating]: | A1 |  | Center for Health Policies and Studies (PAS Center) |  |  | From [de la]: | 2015-07-01
|  |  | Strengthening Tuberculosis control in the Republic of Moldova |  |  | To[Pînă la]: | 2015-12-31
Recommendations
Are all funds reaching implementation levels and being spent according to budget?
Financial |  | Summary Comments |  |  | Recommendations
F1 |  | The cumulative disbursement is more than cumulative budget, as it includes the buffer period. Suma debursată este mai mare decât bugetul, deoarece include perioada de buffer.
F2 |  | For two of objectives, the expenditures are almost in line with the budget, with a slight variance. The variance between budget and expenditures for the MDR-TB component is committed: for NGO grant programme implemented by the SR FSM for the MDRTB component; for incentives programme implemented by the SR AFI for MDR TB component and other planned grant activities for MDRTB component; for activities linked to the TB CCs extension plan, the TA for TB/HIV and TA data based for Xpert. Pentru două dintre obiective, cheltuielile sunt aproape în conformitate cu bugetul, cu o ușoară variație. Variația dintre bugetul și cheltuielile pentru componenta MDR-TB este angajată: pentru programul de granturi ONG implementat de SR FSM pe componenta TB MDR; pentru programul de suport al pacienților implementat de către SR AFI pentru componenta TB MDR și alte activități de grant planificate pentru componenta TB MDR; pentru activități legate de planul de extindere TB CC, AT pentru TB / HIV si AT pentru Xpert.
F3 |  | The cumulative disbursement by the GF is more than cumulative cash-out flow of the PR, as it includes the buffer period and committed payments for the reported period. The variance between disbursed amount to SRs and SRs' expenditures is committed: for NGO grant programme implemented by the SR FSM and for incentives programme implemented by the SR AFI. Suma debursată de FG este mai mare decât cheltuielile RP împreună cu debursările către SRi, deoarece include perioada de buffer și sumele angajate pentru plăți aferente perioadei de raportare. Variația dintre suma debursată către SRi și cheltuielile SR-lor este angajată: pentru programul de granturi ONG implementat de SR FSM și pentru programul de suport al pacienților implementat de către SR AFI.
F4 |  | The PR always makes the disbursements to SRs in the shortest period when the disbursement request is received and the report is presented. Perioada de debursare către SR este cit mai operativ posibil de la data depunerii cererii de debursare şi prezentare a raportului financiar.
Are procurement and hiring on schedule?
Management |  | Summary Comments |  |  | Recommendations
M1 |  | 1. No latter than 31 December 2016, the Grantee in collaboration with the CCM, other stakeholders and partners in the Republic of Moldova shall prepare and deliver to the Global Fund a sustainability plan for the national TB programm, endorsed by the government of the R. of Moldova , in forum and substance satisfactory to the Global Fund - The discussion at the CCM and the WTG level on the development the sustainability plan for the National TB programme was initiated (minute of the WTG as of June 2, 2015 and Minute of the Working Group responsible for development of the new TB Programme as of January 28, 2016). The plan will be developed with support planned in the grant implemented by the UCIMP. 2. Prior to financing extension of the TB community centers with the Grant Funds a) the Grantee shall engage a technical assistance partner acceptable to the Global Fund, to review and access the TB community centers model, including effectiveness, TB system integration and sustainability ( the Independent Assessment) and b) the Global Fund shall review the results of the Independent Assessment and if satisfied with the form and substance of the Independent Assessment findings, approve the Grant Funds for financing such TB community Centers - 1. The PR contracted two independent experts following to the WHO Europe recommendations (the contracts was signed on April 8, 2015). The report of the independent assessment was sent to the WHO, GF, CCM, National Programmes and PR. 2. Following the review of the Independent Assessment report and the internal consultations on the issues highlighted in the report, the Global Fund Secretariat requested from the country /MoH to share the following: a) The opinion on the feasibility/readiness of addressing the recommendations, and the timeframes that might be required for it; and b) Based on the considerations above, to provide the Global Fund with an improved, alternative model for the existing CCs, which should be built on the best practices for provision of TB care, coordinated among the TB units, CCs and NGOs. To provide the Secretariat with an assurance, that the new TB CC model will form a part of the costed transition plan, as a demonstration of the government’s readiness to continue countrywide financing of the new CC model for outpatient TB services delivery. At the request of the Global Fund Secretariat, the MoH sent the letter with opinion on feasibility and readiness of addressing the experts recommendations in the country policy documents ( letter 01-15/448 as of 04.12.2015). The presentation of the improved model of the existing CCs was described in the letter 012/2016 as of 15/01/2016. The Global Fund Secretariat did not accept to finance this activity, based on presented additional commitments. Instead, a new activities was requested to be proposed by the coutry. 3. In accordance with the Global Fund Board Decision Point GF/B28/DP4: commitment and disbursement of 15% of the Republic of Moldova aggregate allocation of EUR 28,640,132 for the period of 2014-2017 allocation period, , which is equal to EUR 4,296,020, is subject to the Republic of Moldova compliance with the Global Fund willingness to pay requirement - This is a grant life condition related to both NFM grant in country for HIV and TB. Fulfilment of country commitments for both diseases during grant life is the subject of a permanent monitoring. 1. Nu mai târziu de 31 decembrie 2016, Recipientul Principal în colaborare cu CNC, alte părți interesate și parteneri din Republica Moldova va pregăti și remite Fondului Global un plan de sustenabilitate pentru programul național TB, aprobat de guvernul R. Moldova, în forum și substanță satisfăcătoare pentru Fondul Global. Măsurile întreprinse - discuția la nivel de CNC și GTL privind dezvoltarea planului de sustenabilitate a programului Național TB, a fost inițiată (proces verbal al GTL, din 2 iunie 2015 și Procesul-verbal al Grupului de lucru responsabil pentru dezvoltarea noului PNCT din 28 ianuarie, 2016). Planul va fi dezvoltat cu suportul programat în grantul implementat de UCIMP. 2. Înainte de aprobarea finanțării pentru extinderea modelului de centru comunitar pentru pacienții cu TB, din fondurile grantului a) Recipientul principal va angaja un consultant de asistență tehnică, acceptabil pentru Fondul Global, pentru a revizui și a evalua modelul centrelor comunitare TB, inclusiv eficacitatea, integrarea în sistemul TB și durabilitatea (Evaluare independentă) și b) Fondul Global va analiza rezultatele evaluării independente și, dacă este satisfăcut de forma și fondul constatărilor ale evaluării independente, va aproba fondurile de grant pentru finanțarea centrelor comunitare – Măsurile întreprinse – 1. RP a contractat doi consultanți independenți, la recomandarea biroului OMS pentru Europa (contractele a fost semnat la 8 aprilie 2015). Raportul de evaluare independent a fost trimis la OMS, FG, CNC, programele naționale și RP. 2. În urma revizuirii raportului de evaluare independentă și consultările interne privind aspectele evidențiate în raport, secretariatul Fondul Global a solicitat țării / MS următoarele: a) Avizul privind fezabilitatea / gradul de pregătire al abordării recomandărilor, precum și intervalele de timp care ar putea fi necesare pentru aceasta; și b) În baza considerațiilor de mai sus, să prezinte Fondului Global un model îmbunătățit, alternativ pentru centrele comunitare existente, care ar trebui create în baza celor mai bune practici pentru prestarea serviciilor de îngrijire TB, coordonate între instituțiile medicale implicate în controlul TB, centre comunitare și ONG-uri. La fel, să ofere Secretariatului o asigurare că noul model de centre comunitare TB va forma o parte a planului de tranziție bugetat, ca o dovadă de pregătire a guvernului să continue finanțarea națională a noului model CC pentru livrarea serviciilor de îngrijire ambulatorie TB. La solicitarea Secretariatului Fondului Global, MS a trimis scrisoarea cu avizul privind fezabilitatea și gradul de pregătire a implementării recomandărilor experților în documentele legislative din țară (scrisoare 01-15 / 448 din 04.12.2015). Prezentarea modelului îmbunătățit al centrelor comunitare existente a fost descrisă în scrisoarea 012/2016 de 15/01/2016. Secretariatul Fondul Global nu a susuținut finanțarea acestei activități în pofida angajamentelor suplimentare prezentate. În schimb, a solicitat ca țara să prezinte noi activități în limita bugetului aprobat pentru extinderea centrelor comunitare, la care se lucrează în prezent. 3. În conformitate cu decizia Consiliului Fondului Global, punctul GF / B28 / DP4: angajamentul și plata a 15% din alocarea totală de 28,640,132 EUR pentru Republica Moldova în perioada 2014-2017, care este egală cu 4,296,020 EURO, este condiționată Republicii Moldova de respectarea cerinței Fondului Global de a mări finanțarea din partea statului, în domeniul unde a investit Fondul Global - Aceasta este o condiție pe durata grantului, atât pentru grantul NFM TB, cât și pentru HIV. Îndeplinirea angajamentelor de țară pentru ambele maladii, pe durata granturilor este obiectul unei monitorizări permanente ale acestora.
M2 |  | All key positions of the management department are filled in by the PR. Toate functiile sunt completate de RP. | #DIV/0! | #DIV/0!
M3 |  | None of the SRs needed to be assessed, due to proved experience within the precedent grant implementation. Nici unul dintre sub-recipienti nu a necesitat să fie evaluat, dat fiind experiența demonstrată în cadrul implementării grantului precedent.
M4 |  | For the reported period, July-December 2015, 9 SSRs were involved in TB related activities, from which one ("Activ" from Bender) is acting as SSR for both SRs - Soros Foundation Moldova and NGO "AFI". Basically, the majority of NGO are implementing one grant, with exception of three NGOs which applied to Soros Foundation - Moldova and were granted with 2 grants each, but within different components and targeted to different populations: NGO "AFI", NGO ”Hope of Land” and NGO ”Medico-Social Programs”. In perioada de raportare, iulie-decembrie 2015, 9 sub-subrecipienți au realizat activități conexe programului de control al TB, din care o organizație (ONG ”Aktiv”) activează în calitate de sub-subrecipient pentru ambii SR: Fundația Soros - Moldova și ONG "AFI". Majoritatea ONG-urilor realizează cîte un grant, excepție fiind 2 ONG care au aplicat către Fundația Soros - Moldova, și au fost aprobate pentru implementarea a câte 2 granturi, în cadrul diferitor componente ale programului de granturi mici și orientate spre diferite populații-cheie - ONG ”AFI”, ONG ”Speranța Terrei” și ”Programe Medico-Sociale”.
M5 |  | EUR 72.849.00 reprezinta suma supraconsumată versus la suma totală estimată pentru procurarea echipamentului Xpert și consumabile pe motiv de modificare a rate EUR/USD, considerate in cererea de finanțare a țării către FG . In cerere rata pentru EUR/ USD a fost de 1,36946, insă la procurarea bunurilor rata a fpst de 1,0927.
M6 |  | Procurarea echipamentului si cartridjelor pentru examinarea pacientilor prin metod rapida s-a realizat in Octombrie - Decemberie, 2015 cu distribuirea in luna Ianuarie 2016. Echipamentul a fost distribuit la 27 institutii medico sanitare unde nu au fost instalate Xpert in cadrul programului de asistenta de la TB Reach. Cartridjele au fost procurate pentru acoperirea necesitatilor intregii tarii. pentru jumate de an. In paralel s-a primit o cantitate de consumabile pentru echipamentul oferit de TB Reach in cantitate ce acoperă necesitatile pina in februarie 2017.
Are technical targets being achieved?
Programmatic |  | Summary Comments |  |  | Recommendations
P1 - trend |  | Final data for Sem.II.2014 - 41 of 470 patients included in the DOTS Plus treatment in Sem.II.2014, abandoned the treatment after 6 months of treatment DOTS Plus. Reason for variance: The interim rate of lost to follow up of MDR-TB treatment at the six months in 2014 is almost at the same level compared with the 2013 rate (8.3%). [Date finale pentru Sem.II.2014 - 41 din 470 pacienți incluși în tratament DOTS Plus în Sem.II.2014, au abandonat tratamentul după 6 luni de tratament DOTS Plus. Motivul variației: Se observă menținerea ratei interimare de abandon al tratamentului cazurilor MDR-TB pentru anul 2014 la același nivel, în comparație cu rata anului 2013 (8,3%)]
P2 - trend |  | During reporting period a total of 515 MDR-TB patients received incentives for improved treatment compliance from the total number of 543 patients with MDR-TB in ambulatory phase under treatment. The indicator is achieved. [Pe parcursul perioadei de raportare un total de 515 pacienți MDR-TB au primit stimulente pentru îmbunătățirea respectării tratamentului din numărul total de 543 de pacienți cu MDR-TB in faza de ambulator. Indicatorul este atins].
P3 - trend |  | During reporting period, 173 TB patients registered under DOTS program received incentives for improved treatment compliance from the total number of 278 TB patients, under treatment. The indicator is achieved in proprotion of 69%. The reason for variances are due to following factors: the high number of patients transfered to MDRTB treatment during the intensive phase on TB sensitive treatment, lost to follow -up etc. [Pe parcursul perioadei de raportare, 173 de pacienți TB înregistrați in cadrul programului DOTS au primit stimulente pentru îmbunătățirea respectării tratamentului din numărul total de 278 de pacienți cu TB in tratament. Indicatorul este realizat în proporție de 69%. Motivul varianței: numărul mare de pacienți transferați la tratamentul TB MDR in timpul fazei intensive pe un tratament sensibil TB].
P1 |  | Final data for Sem.II.2014 - 41 of 470 patients included in the DOTS Plus treatment in Sem.II.2014, abandoned the treatment after 6 months of treatment DOTS Plus. Reason for variance: The interim rate of lost to follow up of MDR-TB treatment at the six months in 2014 is almost at the same level compared with the 2013 rate (8.3%). [Date finale pentru Sem.II.2014 - 41 din 470 pacienți incluși în tratament DOTS Plus în Sem.II.2014, au abandonat tratamentul după 6 luni de tratament DOTS Plus. Motivul variației: Se observă menținerea ratei interimare de abandon al tratamentului cazurilor MDR-TB pentru anul 2014 la același nivel, în comparație cu rata anului 2013 (8,3%)]
P2 |  | During reporting period a total of 515 MDR-TB patients received incentives for improved treatment compliance from the total number of 543 patients with MDR-TB in ambulatory phase under treatment. The indicator is achieved. [Pe parcursul perioadei de raportare un total de 515 pacienți MDR-TB au primit stimulente pentru îmbunătățirea respectării tratamentului din numărul total de 543 de pacienți cu MDR-TB in faza de ambulator. Indicatorul este atins].
P3 |  | During reporting period, 173 TB patients registered under DOTS program received incentives for improved treatment compliance from the total number of 278 TB patients, under treatment. The indicator is achieved in proprotion of 69%. The reason for variances are due to following factors: the high number of patients transfered to MDRTB treatment during the intensive phase on TB sensitive treatment, lost to follow -up etc. [Pe parcursul perioadei de raportare, 173 de pacienți TB înregistrați in cadrul programului DOTS au primit stimulente pentru îmbunătățirea respectării tratamentului din numărul total de 278 de pacienți cu TB in tratament. Indicatorul este realizat în proporție de 69%. Motivul varianței: numărul mare de pacienți transferați la tratamentul TB MDR in timpul fazei intensive pe un tratament sensibil TB].
P4 |  | The indicator will be reported in the next semester. [Indicatorul va fi raportat in semestrul viitor].
P5 |  | Preliminary data for Q1-Q2.2015 - drug resistant tuberculosis patients 429 (RR-TB and / or MDR-TB), confirmed bacteriological were notified to the estimated 456 cases reported period. [Date preliminare pentru Q1-Q2.2015 - 429 pacienți cu tuberculoză drog-rezistentă (RR-TB și/sau MDR-TB), confirmate bacteriologic, au fost notificate, față de 456 cazuri estimate pentru perioada raportată].
P6 |  | Preliminary data for Sem.II. 2015 - 929 of notified cases of bacteriologically confirmed TB (new and relapse) from them (Sex: Male 699, Female 230; Age: <15 - 9, 15+ 920). It should be noted that for the TB patients registered in November and December of 2015, the final data will be available by January- February 2016, since the culture testing takes about 1- 2 months. As a result the final data will be available in the data system in the I quarter of 2016. Also it should be considered that the total number of notified cases of bacteriologically confirmed TB cases for year 2015 is 2110 cases, where 1181 cases were registered in I semester of 2015. [Datele preliminare pentru Sem. II. 2015 - 929 de cazuri notificate cu TB confirmate bacteriologic (recidivă si caz nou) din ei (Sex: bărbați 699, femei 230; Vârsta: <15 - 9, 15+ 920). Ar trebui de remarcat faptul că, pentru pacienții cu TB înregistrați în noiembrie și decembrie 2015, datele finale vor fi disponibile prin ianuarie-februarie 2016, deoarece testele de cultură durează aproximativ 1- 2 luni. Ca rezultat datele finale vor fi disponibile în sistemul de date în trimestrul I al anului 2016. De asemenea, trebuie luat în considerare faptul că numărul total al cazurilor notificate cu TB confirmate bacteriologic pentru anul 2015 este de 2110 de cazuri, în care au fost înregistrate 1181 de cazuri în I semestru 2015].
P7
P8
P9
P10
Menu

## Actions
Dashboard: Moldova - TB
| NFM | 0 |  |  |  | Report Period [Perioada de raportare]: |  | P1
| Latest Rating [Ultimul Rating]: | A1 |  | Center for Health Policies and Studies (PAS Center) |  | From [de la]: |  | 2015-07-01
|  |  | Strengthening Tuberculosis control in the Republic of Moldova |  |  |  | To[Pînă la]: | 2015-12-31
Decisions and Actions
What is the overall status of this grant implementation?
| Key Recommendations from Oversight Group(s) |  |  |  | CCM Decision | Due Date | Person Responsible
Current Reporting Period
Actions to Implement / Previous Period
What is the overall status of this grant implementation?
| CCM Decision |  |  |  | Action Taken | Date | Person Responsible
Previous Reporting Period
Menu

## Setup (hidden)
Dashboard: Moldova - TB
Set-up = List of validation for Grant Detail page
Component | Currency | Round | Phase | Period | Rating | LFA | Medicaments | Countries
Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select
HIV / AIDS | $ | Round 1 | Phase 1 | P1 | A1 | CA (Crown Agents) | Isoniazid | Afghanistan
MALARIA | € | Round 2 | Phase 2 | P2 | A2 | DEL (Deloitte) | Ethambutol | Albania
TB |  | Round 3 | RCC | P3 | B1 | DTT (DTT Emerging Markets) | Rifampicin | Algeria
HIVAIDS / TB |  | Round 4 |  | P4 | B2 | FIN (Finconsult) | Pyrazimamide | Angola
HSS |  | Round 5 |  | P5 | C | GT (Grant Thornton) | RDT | Argentina
|  | Round 6 |  | P6 |  | H-C (Hodar-Conseil) | NVP | Armenia
|  | Round 7 |  | P7 |  | KPMG (KPMG) | 3TC | Azerbaijan
|  | Round 8 |  | P8 |  | MSCI (MSCI) | D4T | Bangladesh
|  | Round 9 |  | P9 |  | PwC (PricewaterhouseCoopers) | AZT | Belarus
|  | Round 10 |  | P10 |  | STI (Swiss Tropical Institute), | DDI | Belize
|  |  |  | P11 |  | UNOPS | EFV | Benin
|  |  |  | P12 |  |  | AS/LF | Bhutan
[7 empty] | AS/AQ | Bolivia
[7 empty] | AS/MQ | Bosnia and Herzegovina
[7 empty] | Al/Lum | Botswana
Brazil
[7 empty] | TB nutri'l supplements | Bulgaria
[7 empty] | E-PAP | Burkina Faso
Burundi
Cambodia
Cameroon
Cape Verde
Central African Republic
Chad
Chile
China
China
Colombia
Comoros
Congo (Democratic Republic of the)
Congo (Republic of the)
Costa Rica
Cote d'Ivoire
Croatia
Cuba
Djibouti
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Ethiopia
Fiji
Gabon
Gambia
Georgia
Ghana
Global(LWF)
Guatemala
Guinea
Guinea-Bissau
Guyana
Haiti
Honduras
India
Indonesia
Iran (Islamic Republic of)
Iraq
Jamaica
Jordan
Kazakhstan
Kenya
Korea, Democratic Peoples Republic of
Kosovo (Serbia)
Kyrgyzstan
Lao PDR
Lesotho
Liberia
Macedonia, FYR
Madagascar
Malawi
Maldives
Mali
Mauritania
Mauritius
Moldova
Mongolia
Montenegro
Morocco
Mozambique
Multi-country Africa (West Africa Corridor Program)
Multi-country Africa(RMCC)
Multi-country Americas (Andean)
Multi-country Americas (CARICOM)
Multi-country Americas (CRN+)
Multi-country Americas (Meso)
Multi-country Americas (OECS)
Multi-country Americas (REDCA+)
Multi-country Western Pacific
Myanmar
Namibia
Nepal
Nicaragua
Niger
Nigeria
Pakistan
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Romania
Russian Federation
Rwanda
Sao Tome and Principe
Senegal
Serbia
Sierra Leone
Solomon Islands
Somalia
South Africa
Sri Lanka
Sudan
Suriname
Swaziland
Syrian Arab Republic
Tajikistan
Tanzania
Thailand
Timor-Leste
Togo
Tunisia
Turkey
Uganda
Ukraine
UN Theme Group on HIV/AIDS (West Bank and Gaza)
Uzbekistan
Viet Nam
Yemen
Zambia
Zanzibar (Tanzania)
Zimbabwe