## Menu
Dashboard: Moldova - TB
TB NFM, | Grant No. [Nr. Grantului]: MDA-T-PAS
V1.0
Finance
Programmatic
Management
Select the option you want to see:
Recommendations
Actions
Grant Detail
List of Indicators
Data Entry
Grant Information
Indicators
Reports

## List of Indicators
Dashboard: Moldova - TB
Financial information
Name: | Definition | Measurement | Data Sources
F1: Budget and disbursements by Global Fund [Bugetul și debursările de către Fondul Global] | Cumulative budget: Sum of the grant budget from period one (quarter, trimester, or semester) of the current phase, up to and including the dashboard reporting period. Cumulative Disbursments by GF: Sum of all the funds transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to and including the dasboard reporting period. | Currency of the grant ($ or Euro) Cumulative – Figures refer to budget and disbursements for all the periods of the phase up to and including the dashboard reporting period | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F2: Budget and actual expenditures by Grant Objective [Bugetul și cheltuielile actuale după Obiectivele Grantului] | Cumulative Budget per Objective: Sum of the grant budget by Objective, from period one of the current phase up to and including the dashboard reporting period. Cumulative Expenditure per Objective: Sum of amounts spent by Objective directly by the PR plus the amounts transferred by the PR to all SRs from the beginning of the phase up to and including dashboard reporting period, by Objective | • Cumulative – Figures refer to budget, disbursements or expenditure for all the periods of the phase up to and including the dashboard reporting period. | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F3: Disbursements and expenditures [Debursări și cheltuieli] | Disbursement by GF: Prior to this Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to but not including dashboard reporting period. Disbursement by GF: Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), during dashboard reporting period. PR disbursements and expenditure: Prior to this Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) up to but not including dashboard reporting period. PR disbursements and expenditure: Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) during dashboard reporting period. Disbursements to SRs: Prior to this Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), up to but not including dashboard reporting period. Disbursements to SRs:Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), in dashboard reporting period. SR expenditures: Prior to this Reporting period: The sum of all expenditures reported by the SRs, up to but not including dashboard reporting period. SR expenditures: Reporting period: The sum of all expenditures reported by the SRs, during dashboard reporting period. | Currency of the grant ($ or Euro) • Reporting period – Figures refer to budget, disbursements or expenditure for the reporting period to which the dashboard refers. • Prior to reporting period - Figures refer to the total budget, disbursements or expenditure for all the periods before but not including the current period. | PU/DR; PR data: SR reports to PR
F4: Latest PR reporting and disbursement cycle [Ultima perioadă de raportare și debursare a RP] | Days taken to submit final PU/DR to LFA – This indicator measures the number of calendar days it took the PR to send a final Performance Update and Disbursement Request (PU/DR) to the LFA after the end of the period. A 'final' PU/DR would be one for which the LFA did not require any further clarifications from the PR. The expected value is 45 days from the end of the period, as defined in the Grant Agreement. The actual value is the number of calendar days from the end date of the period to the date on which the PR sent to the LFA the final PU/DR. Days taken for disbursement to reach PR – This indicator measures the number of calendar days it took the Global Fund to send the latest disbursement to the PR's account after receipt of the acceptable PU/DR by the LFA. The expected number is 45 days. The actual number is the number of days from the date of transmission by the PR to the LFA of the acceptable PU/DR to the date the disbursement is received by the PR at its bank. Days taken for disbursement to reach SRs – This indicator measures the average number of days for disbursements to be made to all the SRs. The expected value for this indicator will be set locally by the PR and SRs, preferably in the Grant Operations Manual. The actual value is the average of the number of days from the receipt of the funds from the GF by the PR to the date the funds are received by each SR. Different SRs coudl receive funds on different dates and this indicator is the average across all SRs for the latest disbursement. | Number of calendar days; it refers only to reporting period for which the latest disbursement was received and is not cumulative | PR, LFA, GF emails and records; bank notification document or the notice of receipt by the PR to GF; SR reports to PR based on bank records
Management Information
Name: | Definition | Measurement | Data Source
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) [Statutul Condițiilor Precedente și a Acțiunilor Prestabilite în Timp] | Number of Conditions Precedent (CPs) and Time Bound Actions (TBAs ) fulfilled, or unfulfilled. Within the Unfulfilled category, we distinguish between those CPs and TBAs whose deadline has not passed and those for which the deadline has passed. | Number, cumulative to the dashboard reporting period. Number of fulfilled CPs and/or TBAs plus unfulfilled CPs and/or TBAs should equal the total number set by the Global Fund on the grant | PR records; Grant Performance Reports;
M2: Status of key PR management positions | Number of PR grant management positions planned currently filled or vacant. Full time equivalents of the managerial positions that are on the organizational chart (or otherwise planned) and directly responsible for ensuring grant implementation at the PR, and lead SRs (if necessary). This will include new hires, current staff who are assigned to work on the grant’s management, as well as any staff seconded from other divisions or partner organizations. | Number, in current reporting period | PR records
M3: Contractual arrangements (SRs) | Identified: Total number of potential SRs identified by the PR for the phase. Assessed: Total number of potential SRs assessed by the PR to determine whether they qualify to function as SRs for the grant. Approved: Total number of SRs that have been approved. Signed: Total number of SRs that have signed agreements/contracts with the PR under the grant. Receiving funding: Total number of SRs that are getting funds and/or supplies from the PR. Numbers of SRs Identified, Assessed, Approved, Signed and Receiving funds are cumulative for the phase, with the following exceptions: If an SR does not need new approval in Phase II, then approval in Phase I is counted. If an SR was signed in a previous Phase but is not working in the current Phase, that SR is no longer counted in Identified, Assessed, Approved. | Number, cumulative to the reporting period. A SR is an institution or program with its own workplan, budget and performance targets. | PR records; Sub-agreements/MOUs; CCM records
M4: Number of complete reports received on time | The total number of periodic reports with up-to-date financial, management and performance (programmatic) data received by the PR from SRs and by SRs from the SubSRs (SSRs) by the expected date. A 'complete' report is one that contains all the data that the PR requires for the PU/DR. The expected date would be set by the PR in the sub-agreements. | Number of reports received. The figure reflects only the period of reporting; it is not cumulative. | PR and SR records
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals | This indicator measures the budget approved for the current phase of the grant for purchase of health products and equipment and pharmaceuticals and medicines (categories 4 and 5 in the new Enhanced Financial Report), and the cumulative amounts of financial obligations and expenditures up to the dashboard reporting period. Budget approved: Total approved budget for purchases (categories 4 and 5) for the entire phase of the grant. It does not include the amounts for fees, management, operational costs, etc. Cumulative Obligations: Total of all order(s) placed and monies committed for these purchases by the PR up to and including the dashboard reporting period. Ideally, by the end of the Phase, budget should equal obligations. Cumulative expenditure: Total of actual Expenditures on category 4 and 5 up to and including the dashboard reporting period (whether paid by PR or authorized to be paid by another entity like GF or other). | Currency of the grant ($ or Euro) | Grant agreement approved budget (for categories 4 and 5 of Enhanced Finance Reporting in current phase); and PR financial data (for expenditures), and/or PSM unit (for orders placed and funding committed or obligated).
Note: Category 6 of the EFR will not be considered as part of the budget for pharmaceuticals. Category 6 has several expenditures that are difficult to disaggregate or quantify, such as warehousing costs, distribution costs (particularly when distibution is done by MOHs), and others that are related to operational costs of the PSM component.
M6: Difference between current and safety stock | This indicator is a snapshot of the difference between the current (or last month) stock level of a specific product (medicine in single, fixed-dose combination, bednets, diagnostic kits, etc.) of a particular dose, expressed in monthly needs (number of months of treatment available) for all patients in the program, and the safety or buffer stock (also expressed in months) as established by the disease program, warehouse system or essential drugs program, for the particular product and dosage. The table will show the difference in months in colors: • RED: when the difference is negative or 0, showing that months of existing stock are lower than or equal to what has been established as months of safety stock • YELLOW: when we have more than the level of safety stock (>0) but less than 3 months (+3). • GREEN: when the difference is between 3 and 18 months. • VIOLET: When the difference shows that the level above the safety stock is greater than or equal to 18 months indicating a potential overstock) problem. For a full description of how this indicator is calculated, please see the User’s Manual. | Number of months | PR records: Warehouse data.
Programmatic Indicators (from Performance Framework) [Indicatorii programatici]
Indicator | Definition (from M&E Plan, 2014) [Definiție (din planul M&E,2014] | Measurement | Data Source [sursa de date]
MDR TB-4: Percentage of cases with drug resistant TB (RR-TB and/or MDR-TB) started on treatment for MDR-TB who were lost to follow up at six months | Numerator: Number of MDR-TB cases initiated on second line anti-TB treatment regimen during the specified period of time, who were lost to follow up at the end of 6 months of treatment (Year 1 - 2014 cohort; Year 2 - 2015 cohort; Year 3 - 2016 cohort). Denominator: Number of MDR-TB cases initiated on second line anti-TB treatment during the specified period of time. | Recording and reporting system for drug-resistant TB; report of the cases with drug resistant TB started on treatment for MDR-TB, who were lost to follow up at six months. The baseline data refer to the MDR TB cohort registered during the Semester I, 2013. | SYME TB - R&R TB system, quarterly/ annual reports, NTP reports.
Number and percentage of new MDR-TB patients transferred to or initiated DOTS Plus treatment on ambulatory phase and provided with incentives to improve treatment compliance | Numerator: Number of new MDR-TB patients transferred to / or initiated the DOTS Plus treatment in ambulatory conditions and receiving incentives to improve treatment compliance during reported period from right and left bank of the river Nistru. Denominator: Total Number of MDR-TB patients transferred to / or initiated the DOTS Plus treatment in ambulatory conditions during the same period. | The patient is qualified reached by the supporting programme, if he/she benefited from incentive programme. | SYMETB and data base implemented for incentives programmes by the SR AFI.
Number and percentage of new sensitive TB patients transferred to or initiated DOTS treatment on ambulatory level, provided with incentives to improve treatment compliance (Transnistria) | Numerator: Number of new TB patients transferred to / or initiated the DOTS treatment in ambulatory conditions and receiving incentives to improve treatment compliance during reported period. Denominator: Total Number of TB patients transferred to / or initiated the DOTS treatment in ambulatory conditions during the same period. | The patient is qualified reached by the supporting programme, if he/she benefited from incentive programme. | The source of data for the indicator will be SYMETB and data base implemented for incentives programmes by the SR AFI.
Percentage and number of patients with symptoms or signs suggestive to TB, examined by Xpert MTB/RIF | Numerator: Number of patients with symptoms or signs suggestive to TB, examined by Xpert MTB/RIF. Denominator: Total number of patients with symptoms or signs suggestive to TB. | The estimation of the percentage of examination with Xpert MDTB/RIF methodology considers the current coverage and the schedule of full coverage with equipment of the country. The numerator and denominator represents an estimated data, and during the reporting period will be presented the defacto data. | R&R system.
MDR TB-2: Number of bacteriologically confirmed, drug resistant TB cases (RR-TB and/or MDR-TB) notified | Numerator: Number of bacteriologically confirmed, drug resistant TB cases (RR-TB and/or MDR-TB) notified | The indicator shall be reported for the cohort of patients registered 6-12 months ago, to make sure that the final result of the investigation is introduced in the SIME TB database, considering the fact that it takes from 4 to 5 months to perform the test, obtain the result, and further introduce it in the SIME TB account (in the case when patients are investigated using the classical (solid) method of culture and DST). This indicator covers both the civilian and the penitentiary sector, incl. the Transdniester region. | SYME TB - R&R TB system, annual reports, DR routine surveillance.
DOTS-1b Number of notified cases of bacteriologically confirmed TB (new and relapse) | Numerator: Number of bacteriologically confirmed TB cases notified to the national health authority during the reporting period | Process indicator to measure the number of bacteriologically confirmed TB cases notified to the national health authority during the reporting period | R&R system.
Indicator Number: Name (Perf Framework No.) | Definition | Measurement | Data Source
The indicators should be selected by the PRs and members of the CCM or the CCM Technical Committee, from the Performance Framework |  |  | Performance Framework
Menu

## Data Entry
Grant information [Informatia de Grant]
| Country [Țara]: | Moldova |  | Title of the Grant [Numele Grantului]: |  | Strengthening Tuberculosis control in the Republic of Moldova
| Grant No. [Nr. Grantului]: | MDA-T-PAS |  | Component [Componentul]: |  | TB | Total Funding[Suma totala]:
| Principal Recipient [Recipientul Principal]: | Center for Health Policies and Studies (PAS Center) |  |  | Round [Runda]: | NFM | Phase [Faza]:
| Start Date (dd/Mmm/yy) [Data Demarării (zz/ll/aa)]: | 01 July 2015 |  | Local Fund Agent [Agentul Local al Fondului]: |  | PwC (PricewaterhouseCoopers)
| Latest Rating [Ultimul Rating]: | B1 |  | Fund Portfolio Manager [Portfolio Manager]: |  | Tsovinar Sakanyan
Information reporting period [Informația despre perioada raportată]
| Report Period [Perioada de raportare]: | P3 | From [de la]: | 2016-07-01 | To[Pînă la]: | 2016-12-31 | Date of entry of information[Data de introducere a informației]: |  | 2017-03-01
| Prepared by [Pregătit de către]: |  | PAS Center
Information on indicators [Informația despre indicatori]
Enter the data based on the colour-coded cells [Introduceți datele bazîndu-vă de celulele codificate prin culoare]
| Financial Information [Informația Financiară]: |  | Management Information [Informația pe Management]: |  |  | Programmatic Information [Informația Programatică]:
| Financial Information [Informatia Financiara]: | [8 empty] | Enter finance data in every orange cell like this [Introduceți datele financiare in fiecare celula portocaliu ca aceasta].
| Currency of the grant[Valuta Grantului] |  | €
F1: Budget and disbursements by Global Fund [Bugetul și debursările de către Fondul Global]
| Disbursement [Debursări] | [15 empty] | 1399791.8563
| Reporting period [perioada de raportare] | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12 | % Cumulative |  |  | 2660836.9231
| Budget (in €) | P1: 1399791.8563; P2: 1261045.0667; P3: 1270558 | 84.35% |  |  | 3931394.9231
| Disbursements by GF (in €) | P2: 662526; P3: 700981 |  |  |  | 0
| Cumulative budget [Buget cumulativ] | 1399791.8563 | 2660836.9231 | 3931394.9231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Cumulative disbursements [Debursări cumulative] | 1952798 | 2615324 | 3316305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
|  | 0% | 0% | 84.35% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0
F2: Budget and actual expenditures by Grant Objective [Bugetul și cheltuielile actuale după Obiectivele Grantului]
| Grant Objective [obiectivele Grantului] | P1: Cumulative Budget (in €); P2: Cumulative Expenditures (in €)
1 | TB care and prevention | P1: 156307.11; P2: 149572.2588
2 | MDR-TB | P1: 3405306.5162; P2: 2758877.7526
3 | Program management | P1: 369780.9024; P2: 328992.9467
| Total | P1: 3931394.5286; P2: 3237442.9581; P4: OK: Data match
| F3: Disbursements and expenditures [Debursări și cheltuieli] | [15 empty] | 0
0
|  | P1: Prior to reporting period [Către perioada de raportare]; P2: Current reporting period [Perioada de raportare curentă]; P3: Total Spent and Disbursement (in €) |  |  | 0
| Disbursed by Global Fund (Debursat de către Fondul Global) | P1: 2615324; P2: 700981; P3: 3316305
| PR expenditure and disbursement (Cheltuielile și debursările RP ) | P1: 2178175.9294; P2: 1059267; P3: 3237442.9294
| Disbursed to SRs (Debursări către SR) | P1: 959041.5758; P2: 481836.0237; P3: 1440877.5995
| SR expenditures (Cheltuielile SR) | P1: 351635.88; P2: 930763.69; P3: 1282399.57
F4: Latest PR reporting and disbursement cycle [Ultima perioadă de raportare și debursare a RP]
Last fund disbursement: Number of calendar days [Ultima debursare a surselor: Număr de zile calendaristice]
|  | Expected (days) Preconizat (zile) | Actual (days) Actual (zile)
| Days taken to submit final PU/DR to LFA (Zile necesare pentru remiterea PU/DR final către ALF) | P1: 60; P2: 60
| Days taken for disbursement to reach PR (Zile necesare pentru debursare către RP) | P1: 45; P2: 45
| Days taken for disbursement to reach SRs (Zile necesare pentru debursare către SR) | P1: 20; P2: 5
| Management Information [Informația pe Management]: | P6: Enter management data in every blue cell [Întroduceți datele pentru management în celulele albastre].
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) [Statutul Condițiilor Precedente și a Acțiunilor Prestabilite în Timp]
|  |  | Fulfilled [Îndeplinite] | Not fulfilled, but within deadline [Ne îndeplinite dar realizarea în conformitate cu planul] | Not fulfilled, and past the deadline [Ne îndeplinite și au depășit termenul de realizare] | Total
| Conditions precedent (CPs) [Conditii precedente] | P2: 2; P3: 1; P4: 0; P5: 3
| Time Bound Actions (TBAs) [Acțiuni Prestabilite în Timp] | P2: 0; P3: 0; P4: 0; P5: 0
M2: Status of key PR management positions
|  | Planned | Filled | Vacant
| PMU | P1: 15; P2: 14; P3: 1
M3: Contractual arrangements (SRs)
|  | Identified | Assessed | Approved | Signed | Receiving Funding
| SRs | P1: 2; P2: 0; P3: 2; P4: 2; P5: 2
M4: Number of complete reports received on time
|  | # Expected | # Received | Pending
| SSR to SR | P1: 11; P2: 11; P3: 0
| SRs to PR | P1: 2; P2: 2; P3: 0
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals
|  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
| Budget Approved* | P1: 422100.54; P2: 180996.18; P3: 226338.18
Obligations
| Expenditures | P1: 494949.4814; P2: 204919.676; P3: 239839.572
| Budget Approved cumulative* | P1: 422100.54; P2: 603096.72; P3: 829434.9
Obligations cumulative
| Expenditures cumulative | P1: 494949.4814; P2: 699869.1574; P3: 939708.7294
* Includes only AFR category 4, 5 and 6 (Health products and health equipment & Medicines and Pharmaceuticals)
M6: Difference between current and safety stock
| Component | Products | (1) Number of tablets per patient per day (Review country treatment guidelines) | (2 = 1 x 30) Monthly treatment (Tablets per patient x 30 days) | (3) Total patients in treatment | (4 = 2 x 3) Total # tab/pills required for all patients per month | (5) Current stock in central warehouse (that does not expire within the next 3 months) | (6 = 5 / 4) Stock level expressed in months of treatment for all current patients | (7) Level of safety stock (expressed in months and defined by country) | (8 = 6 - 7) Difference between current stock and safety stock
| Please Select | P1: Please Select
Please Select
Please Select
Please Select
| Programmatic Information: | P9: Enter performance data in every yellow cell.
| Programmatic indicators (Performance Framework ) |  |  | Code | Directly Tied? |  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
TOP 3 | Percentage of cases with drug resistant TB (RR-TB and/or MDR-TB) started on treatment for MDR-TB who were lost to follow up at six months [Numărul și procentul pacienţilor cu tuberculoză drog-rezistentă (RR-TB și/sau MDR-TB) care au întrerupt tratamentul DOTS-Plus către luna a 6 de la demararea acestuia] |  |  | MDR TB-4 | Yes | Target | P1: 6.6%; P2: 6.3%; P3: 6.1%
[6 empty] | Achieved | P1: 8.7%; P2: 11.46%; P3: 10%
| Number and percentage of new MDR-TB patients transferred to or initiated DOTS Plus treatment on ambulatory phase and provided with incentives to improve treatment compliance [Numărul și procentul de pacienți noi MDR-TB transferați sau inițiat tratament DOTS Plus in faza de ambulator și au primit stimulente pentru îmbunătățirea respectării tratamentului] |  |  |  | Yes | Target | P1: 90%; P2: 312; P3: 624
[6 empty] | Achieved | P1: 95%; P2: 376; P3: 739
| Number and percentage of new sensitive TB patients transferred to or initiated DOTS treatment on ambulatory level, provided with incentives to improve treatment compliance (Transnistria) [Numărul și procentul de pacienți noi TB sensibili transferați sau inițiat tratament DOTS in faza de ambulator, au primit stimulente pentru îmbunătățirea respectării tratamentului (Transnistria)] |  |  |  | Yes | Target | P1: 90%; P2: 223; P3: 444
[6 empty] | Achieved | P1: 62%; P2: 240; P3: 448
| Percentage of new and relapse TB patients tested using WHO recomennded rapid tests at the time of diagnosis [Procentul pacientilor cu TB, cazuri noi si recidiva, care au fost testați folosind teste rapide recomandate de OMS în momentul diagnosticării) |  |  |  | Yes | Target | P1: n/a; P2: n/a; P3: 86%
[6 empty] | Achieved | P1: n/a; P2: n/a; P3: 92%
| Number of bacteriologically confirmed, drug resistant TB cases (RR-TB and/or MDR-TB) notified [Numărul de cazuri de TB DR (RR-TB și/sau MDR-TB), confirmate bacteriologic, notificate] |  |  | MDR TB-2 | Yes | Target | P1: 456; P2: 456; P3: 912
[6 empty] | Achieved | P1: 429; P2: 320; P3: 754
| Number of notified cases of bacteriologically confirmed TB (new and relapse) [Numărul de cazuri notificate cu TB confirmate bacteriologic (nou și recidivă)] |  |  | DOTS-1b | Yes | Target | P1: 1099; P2: 1080; P3: 1079
[6 empty] | Achieved | P1: 929; P2: 962; P3: 2066
[5 empty] | Yes | Target
Achieved
[5 empty] | Yes | Target
Achieved
| Table is automatically updated. No data or information is to be entered here. |  |  | Code | Directly Tied? |  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
| Percentage of cases with drug resistant TB (RR-TB and/or MDR-TB) started on treatment for MDR-TB who were lost to follow up at six months [Numărul și procentul pacienţilor cu tuberculoză drog-rezistentă (RR-TB și/sau MDR-TB) care au întrerupt tratamentul DOTS-Plus către luna a 6 de la demararea acestuia] |  |  | MDR TB-4 | Yes | Target | 6.6% | 6.3% | 6.1% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Achieved | 8.7% | 11.46% | 10% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number and percentage of new MDR-TB patients transferred to or initiated DOTS Plus treatment on ambulatory phase and provided with incentives to improve treatment compliance [Numărul și procentul de pacienți noi MDR-TB transferați sau inițiat tratament DOTS Plus in faza de ambulator și au primit stimulente pentru îmbunătățirea respectării tratamentului] |  |  |  | Yes | Target | 90% | 312 | 624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Achieved | 95% | 376 | 739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number and percentage of new sensitive TB patients transferred to or initiated DOTS treatment on ambulatory level, provided with incentives to improve treatment compliance (Transnistria) [Numărul și procentul de pacienți noi TB sensibili transferați sau inițiat tratament DOTS in faza de ambulator, au primit stimulente pentru îmbunătățirea respectării tratamentului (Transnistria)] |  |  |  | Yes | Target | 90% | 223 | 444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Achieved | 62% | 240 | 448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on B68: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B74: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Menu

## Grant Detail
Dashboard: Moldova - TB
Country: | Moldova |  | Title of the Grant: |  | Strengthening Tuberculosis control in the Republic of Moldova
Component: | TB | Grant No. | MDA-T-PAS | Start Date: |  | 01 July 2015 | Total Funding
Round: | NFM | Phase: | 0 | Principal Recipient: |  | Center for Health Policies and Studies (PAS Center)
Report Period: | P3 | from: | 2016-07-01 | to: |  | 2016-12-31 | Latest Rating: | B1
Local Fund Agent: | PwC (PricewaterhouseCoopers) |  |  | Fund Portfolio Manager: |  | Tsovinar Sakanyan
Prepared by: | PAS Center |  |  | Report preparation date: |  | 2017-03-01
http://www.crwflags.com/fotw/flags/country.html
Menu

## Finance
Dashboard: Moldova - TB
NFM | 0 |  |  |  | Report Period [Perioada de raportare]: |  | P3
Latest Rating [Ultimul Rating]: | B1 |  | Center for Health Policies and Studies (PAS Center) |  | From [de la]: |  | 2016-07-01
|  | Strengthening Tuberculosis control in the Republic of Moldova |  |  |  | To[Pînă la]: | 2016-12-31
Financial Indicators
F1: Budget and disbursements by Global Fund [Bugetul și debursările de către Fondul Global] - in (€) Report Period [Perioada de raportare]: P3 |  |  |  | F3: Disbursements and expenditures [Debursări și cheltuieli] - in (€) Report Period [Perioada de raportare]: P3
Comments: | The cumulative disbursement is less than cumulative budget due to the fact that the projected initial budget contained funds for supporting the extension of the Community Center over the country. Due to the initial GF decision of non- approval extension of the Community Centers, the disbursement was revised in line with temporary revised budget for the TB grant by the Global Fund. Upon presentation by the PR of additional data to the GF concerning activities of TB Community Centers which perform in 10 districts, at mid of December 2016, based on data of the study ,,Audit of MDRTB management", the final decision of the GF on extension TB Community Center in additional 37 health facilitieis were provided at January 10,2017. As well, the Center PAS presented for approval an additional list of interventions under the TB NFM grant 2015-2017 to the GF at 14/02/2017, based on savings generated as result of the late creation of community centers in the 37 sites. These interventions are in line with the focus of the NFM application approved in 2015 by the Global Fund, the goal and objective the new NTP for 2016-2020 and country needs. The new list with interventions were approved by the CCM at the meeting as of 26/01/2017, which have been discussed and agreed in advance at the Technical Working Groups of the CCM. Thus, the budgeted amount wll be disbursed in 2017. Suma debursată este mai mică in raport cu bugetul programat, deoarece bugetul programat includea suma prevăzuta pentru finantarea activitatii modelului - Centre Comunitare extinse in toata țara. Din motiv de neaprobare de către FG al extinderii Centrelor Comunitare in toata tara in 2015, suma debursată este ajustată la bugetul revăzut provizoriu de FG. În urma prezentării de către RP a unor date suplimentare către FG privind activitatea centrelor comunitare pentru TB, realizată în 10 raioane, la mijlocul lunii decembrie 2016, pe baza datelor studiului "Auditul managementului cazurilor de MDRTB", decizia finală a GF privind Centrul comunitar de extindere a modelului de centru comunitar în alte 37 de institutii medico-sanitare, au fost comunicate tarii la 10 ianuarie 2017. De asemenea, Centrul PAS a prezentat spre aprobare o listă suplimentară de intervenții în cadrul grantului TF NFM 2015-2017 către GF la data de 14.02.2017, in baza economiilor generate ca urmare a creării cu întârziere a centrelor comunitare în cele 37 de locații. Aceste intervenții sunt în conformitate cu obiectivul aplicației NFM aprobată în 2015 de Fondul Global, scopul și obiectivele noului PNCT pentru perioada 2016-2020 șinecesitățile țării. Noua listă cu intervenții a fost aprobată de CNC în cadrul întrunirii din 26.01.2017, care a fost discutată și convenită în prealabil în cadrul grupurilor tehnice de lucru ale CNC, astfel încât suma inițial bugetată iîn aplicația de țară, va fi debursată în 2017 . |  |  | Comments: | The cumulative disbursement by the GF is less than cumulative cash-out flow of the PR due to remaning budget at the end of the previos reporting period from the lines linked to the Community Centers component, which was not accepted by the Global Fund ( official letter as of 3 March 2016 to the Ministry of Health ) as well as the buffer stock and committed payments for the reported period. The variance between disbursed amount to SRs and SRs' expenditures includes the sum committed in the previous reporting period: for NGO grant programme implemented by the SR FSM and for incentives programme implemented by the SR AFI. Suma debursată de FG este mai mică decât cheltuielile RP împreună cu debursările către SRi, fiind determinată de bugetul rest la finalul perioadei anterioare de raportare de pe liniile conexe componentei - Centre Comunitare in toata tara, precum și sumei cu statut de buffer și sumelor angajate pentru plăți aferente perioadei de raportare. Variația dintre suma debursată către SRi și cheltuielile SR-lor include sumele angajate pentru programul de granturi ONG implementat de SR FSM și pentru programul de suport al pacienților implementat de către SR AFI.
F2: Budget and actual expenditures by Grant Objective [Bugetul și cheltuielile actuale după Obiectivele Grantului] - in (€) Report Period [Perioada de raportare]: P3 |  |  |  | F4: Latest PR reporting and disbursement cycle [Ultima perioadă de raportare și debursare a RP] Report Period [Perioada de raportare]: P3
Comments: | For two of objectives, the expenditures are almost in line with the budget, with a slight variance. The variance between budget and expenditures for the MDR-TB component is committed: for NGO grant programme implemented by the SR FSM for the MDRTB component; for incentives programme implemented by the SR AFI for MDR TB component and other planned grant activities for MDRTB component; the TA for TB/HIV and TA data based for Xpert. An essential unspent budget is linked to the Global Fund decision of non- approval extension of the Community Centers over the country, as per December 31, 2016. Pentru două dintre obiective, cheltuielile sunt aproape în conformitate cu bugetul, cu o ușoară variație. Variația dintre bugetul și cheltuielile pentru componenta MDR-TB este angajată: pentru programul de granturi ONG implementat de SR FSM pe componenta TB MDR; pentru programul de suport al pacienților implementat de către SR AFI pentru componenta TB MDR și alte activități de grant planificate pentru componenta TB MDR; pentru activități legate de Asistență Tehnică pentru politicile de fortificare a tratamentului in condiții de ambulator, pentru fortificarea colaborarii pe componenta TB / HIV si dezvoltarea sistemelor informaționale pentru Xpert. O suma esențiala neconsumată este determinată de decizia Fondului Global pentru neaprobarea planului de extindere a Centrelor Comunitare în toată țara, la situația din 31 decembrie 2016. |  |  | Comments: | The PR always makes the disbursements to SRs in the shortest period when the disbursement request is received and the report is presented. Perioada de debursare către SR este cit mai operativ posibil de la data depunerii cererii de debursare şi prezentare a raportului financiar.
Last fund disbursement: Calendar days
[6 empty] | Expected (days) | Actual (days)
|  |  |  | Days taken to submit final PU/DR to LFA (Zile necesare pentru remiterea PU/DR final către ALF) |  | 60 | 60
|  |  |  | Days taken for disbursement to reach PR (Zile necesare pentru debursare către RP) |  | 45 | 45
|  |  |  | Days taken for disbursement to reach SRs (Zile necesare pentru debursare către SR) |  | 20 | 5
Menu

## Management
Dashboard: Moldova - TB
NFM | 0 |  |  |  |  | Report Period [Perioada de raportare]: |  | P3
Latest Rating [Ultimul Rating]: | B1 |  | Center for Health Policies and Studies (PAS Center) |  |  | From [de la]: |  | 2016-07-01
|  | Strengthening Tuberculosis control in the Republic of Moldova |  |  |  |  | To[Pînă la]: | 2016-12-31
Management Indicators
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) [Statutul Condițiilor Precedente și a Acțiunilor Prestabilite în Timp] Report Period [Perioada de raportare]: P3 |  |  |  | M2: Status of key PR management positions Report Period [Perioada de raportare]: P3
Comments: | 1. No latter than 31 December 2016, the Grantee in collaboration with the CCM, other stakeholders and partners in the Republic of Moldova shall prepare and deliver to the Global Fund a sustainability plan for the national TB programm, endorsed by the government of the R. of Moldova , in forum and substance satisfactory to the Global Fund . Status: There were initiated discussion at the CCM and the WTG level on the development the sustainability plan for the National TB programme ( minute of the WTG as of 02/06/2015 and Minute of the Working Group responsible for development of the new TB Programme as of 28/01/2016). The new TB programme was endorsed by the Government in October 2016. The drafts of the Transition Plan for the sustainability of National TB Strategies, in English and Romanian with the supporting documents available for the plan were send to the GF on 19/01/2017. The drafts of the Transition Plan for the sustainability of National TB Strategies was part of the agenda of the CCM from March 2017 ( 15/03/2017). 2. Prior to financing extension of the TB community centers with the Grant Funds a) the Grantee shall engage a technical assistance partner acceptable to the Global Fund, to review and access the TB community centers model, including effectiveness, TB system integration and sustainability ( the Independent Assessment) and b) the Global Fund shall review the results of the Independent Assessment and if satisfied with the form and substance of the Independent Assessment findings, approve the Grant Funds for financing such TB community Centers - 1. The PR contracted two independent experts following to the WHO Europe recommendations (the contracts was signed on April 8, 2015). The report of the independent assessment was sent to the WHO, GF, CCM, National Programmes and PR. 2. Following the review of the Independent Assessment report and the internal consultations on the issues highlighted in the report, the Global Fund Secretariat requested from the country /MoH to share the following: a) The opinion on the feasibility/readiness of addressing the recommendations, and the timeframes that might be required for it; and b) Based on the considerations above, to provide the Global Fund with an improved, alternative model for the existing CCs, which should be built on the best practices for provision of TB care, coordinated among the TB units, CCs and NGOs. To provide the Secretariat with an assurance, that the new TB CC model will form a part of the costed transition plan, as a demonstration of the government’s readiness to continue countrywide financing of the new CC model for outpatient TB services delivery. Status: At the request of the Global Fund Secretariat, the MoH sent the letter with opinion on feasibility and readiness of addressing the experts recommendations in the country policy documents ( letter 01-15/448 as of 04.12.2015). The presentation of the improved model of the existing CCs was described in the letter 012/2016 as of 15/01/2016. The decision of the FG on non - aproval of the extension TB Community Centers in 37 health facilities was send to country on March 2016 with request to present additional data or to present proposal for redirection on unused budget. The PR was able to present additional data to the GF concerning activities of TB Community Centers which perform in 10 districts, at mid of December 2016, based on data of the study ,,Audit of MDRTB management,, officially presented round table as of November 30 2016. The final decision of the GF on extension TB Community Center in additional 37 health facilitieis were provided at January 10,2017. Due to unused budget for the line “Support to TB Community Centers”, generated as a result of postponing the extension of the TB Community model over the country during 2015-2016 years, the Center PAS presented for approval an additional list of interventions under the TB NFM grant 2015-2017 to the GF at 14/02/2017. These interventions are in line with the focus of the NFM application approved in 2015 by the Global Fund, the goal and objective the new NTP for 2016-2020 and country needs. The proposed interventions will bring diversification to the package of service oriented to TB patents. The new list with interventions were approved by the CCM at the meeting as of 26/01/2017, which have been discussed and agreed in advance at the Technical Working Groups of the CCM. The estimated budget for implementation of the described activities in the attachment was based on the projected unused budget from TB CC lines. 3. In accordance with the Global Fund Board Decision Point GF/B28/DP4: commitment and disbursement of 15% of the Republic of Moldova aggregate allocation of EUR 28,640,132 for the period of 2014-2017 allocation period, , which is equal to EUR 4,296,020, is subject to the Republic of Moldova compliance with the Global Fund willingness to pay requirement - This is a grant life condition related to both NFM grant in country for HIV and TB. 3a The PR and/or the CCM are requested to submit a report on actual state budget execution for 2015 and the updated level of commitments for 2016 by 30 June 2016 or earlier, if available. Templates for capturing 2015 Budget execution and 2016 Budget for TB and HIV are enclosed to this letter. Please note that there are cash transfers planned under this disbursement decision which are subject to meeting the Counterpart Financing requirements (reported expenditures for 2015 and commitments for 2016). Additionally, we would appreciate if the 'Strategia sectorială de cheltuieli in domeniul ocrotirii sănătăţii, 2016-2018 (CBTM)' can be shared with us. Status: The official letter from the CCM with data concening the commitment to further implement and support the TB and HIV including budget contribution and planned budget for next years, has been sent to the Global Fund on 30/06/2016 in the format requested by the GF. Also there were presented the 'Strategia sectorială de cheltuieli in domeniul ocrotirii sănătăţii, 2016-2018 (CBTM)'. 1. Nu mai târziu de 31 decembrie 2016, Recipientul Principal în colaborare cu CNC, alte părți interesate și parteneri din Republica Moldova va pregăti și remite Fondului Global un plan de sustenabilitate pentru programul național TB, aprobat de guvernul R. Moldova, în forum și substanță satisfăcătoare pentru Fondul Global. Statut: Au fost inițiate discuții la nivelul CNC și GTL privind elaborarea planului de sustenabilitate pentru programul național TB (proces verbal al GTL din 02.06.2015 și proces verbal al Grupului de lucru responsabil pentru dezvoltarea noului program TB din data de 28/01/2016). Noul program de TB a fost aprobat de Guvern în octombrie 2016. Proiectele Planului de tranziție pentru durabilitatea strategiilor naționale de TB, în limbile engleză și română, împreună cu documentele justificative disponibile pentru acest plan, au fost trimise la FG pe 19/01/2017 . Proiectele Planului de tranziție pentru durabilitatea strategiilor naționale de TB au făcut parte din agenda CCM din martie 2017 (15/03/2017). 2. Înainte de aprobarea finanțării pentru extinderea modelului de centru comunitar pentru pacienții cu TB, din fondurile grantului a) Recipientul principal va angaja un consultant de asistență tehnică, acceptabil pentru Fondul Global, pentru a revizui și a evalua modelul centrelor comunitare TB, inclusiv eficacitatea, integrarea în sistemul TB și durabilitatea (Evaluare independentă) și b) Fondul Global va analiza rezultatele evaluării independente și, dacă este satisfăcut de forma și fondul constatărilor ale evaluării independente, va aproba fondurile de grant pentru finanțarea centrelor comunitare – Măsurile întreprinse – 1. RP a contractat doi consultanți independenți, la recomandarea biroului OMS pentru Europa (contractele a fost semnat la 8 aprilie 2015). Raportul de evaluare independent a fost trimis la OMS, FG, CNC, programele naționale și RP. 2. În urma revizuirii raportului de evaluare independentă și consultările interne privind aspectele evidențiate în raport, secretariatul Fondul Global a solicitat țării / MS următoarele: a) Avizul privind fezabilitatea / gradul de pregătire al abordării recomandărilor, precum și intervalele de timp care ar putea fi necesare pentru aceasta; și b) În baza considerațiilor de mai sus, să prezinte Fondului Global un model îmbunătățit, alternativ pentru centrele comunitare existente, care ar trebui create în baza celor mai bune practici pentru prestarea serviciilor de îngrijire TB, coordonate între instituțiile medicale implicate în controlul TB, centre comunitare și ONG-uri. La fel, să ofere Secretariatului o asigurare că noul model de centre comunitare TB va forma o parte a planului de tranziție bugetat, ca o dovadă de pregătire a guvernului să continue finanțarea națională a noului model CC pentru livrarea serviciilor de îngrijire ambulatorie TB. Statut: La cererea Secretariatului Fondului Global, MS a trimis scrisoarea cu avizul cu privire la fezabilitatea și disponibilitatea de a se adresa recomandărilor experților în documentele de politică națională (scrisoarea 01-15 / 448 din 04.12.2015). Prezentarea modelului îmbunătățit al CC existente a fost descrisă în scrisoarea 012/2016 din 15/01/2016. Decizia FG privind ne-aprobarea deciziei de extindere a centrelor comunitare în 37 de instituții medicale a fost trimisă țării în martie 2016 cu solicitarea de a prezenta date suplimentare sau de a prezenta propunerea de redirecționare a bugetului neutilizat. RP a prezentat date suplimentare FG privind activitatea centrelor comunitare pentru TB, realizată în 10 raioane, la mijlocul lunii decembrie 2016, pe baza datelor studiului "Auditul managementului cazurilor de MDRTB", decizia finală a GF privind Centrul comunitar de extindere a modelului de centru comunitar în alte 37 de institutii medico-sanitare, au fost comunicate tarii la 10 ianuarie 2017. Datorită bugetului nefolosit pentru linia "Suport pentru centrele comunitare TB", generată ca urmare a amânării extinderii modelului comunitar al TB în țară în perioada 2015-2016, Centrul PAS a prezentat spre aprobare o listă suplimentară de intervenții în cadrul grantului TF NFM 2015-2017 către GF la data de 14.02.2017. Aceste intervenții sunt în conformitate cu obiectivul aplicației NFM aprobată în 2015 de Fondul Global, scopul și obiectivele noului PNCT pentru perioada 2016-2020 și necesitățile țării. Noua listă cu intervenții a fost aprobată de CNC în cadrul întrunirii din 26.01.2017, care a fost discutată și convenită în prealabil în cadrul grupurilor tehnice de lucru ale CNC. Bugetul estimat pentru implementarea activităților menționate, s-a bazat pe bugetul neutilizat propus din liniile CC TB. 3. În conformitate cu decizia Consiliului Fondului Global, punctul GF / B28 / DP4: angajamentul și plata a 15% din alocarea totală de 28,640,132 EUR pentru Republica Moldova în perioada 2014-2017, care este egală cu 4,296,020 EURO, este condiționată Republicii Moldova de respectarea cerinței Fondului Global de a mări finanțarea din partea statului, în domeniul unde a investit Fondul Global. Aceasta este o condiție pe durata grantului, atât pentru grantul NFM TB, cât și pentru HIV. Statut: O scrisoare oficiala din partea CNC al tarii a fost prezentata la 30/06/2016,care releva angajamentul de implementare si suport al programelor Tb si HIV inclusiv cu date referitor la bugetul alocat, si bugetul planificat pentru urmatorii ani, in formatul solicitat de FG. Deasemenea a fost adusa spre informare FG 'Strategia sectorială de cheltuieli in domeniul ocrotirii sănătăţii, 2016-2018 (CBTM)'. |  |  | Comments: | 14 from 15 positions are fulfilled. 14 din 15 pozitii sunt
M3: Contractual arrangements (SRs) Report Period [Perioada de raportare]: P3 |  |  |  | M4: Number of complete reports received on time Report Period [Perioada de raportare]: P3
Comments: | None of the SRs needed to be assessed, due to proved experience within the precedent grant implementation. Nici unul dintre sub-recipienti nu a necesitat să fie evaluat, dat fiind experiența demonstrată în cadrul implementării grantului precedent. |  |  | Comments: | For the reported period, iulie-decembrie 2016, 11 SSRs were involved in TB related activities, from which one ("Activ" from Bender) is acting as SSR for both SRs - Soros Foundation Moldova and NGO "AFI". Basically, the majority of NGO are implementing one grant, with exception of three NGOs which applied to Soros Foundation - Moldova and were granted with several grants each, but within different components and targeted to different populations: NGO "AFI", NGO ”Hope of Land” and NGO ”Medico-Social Programs”. In perioada de raportare, iulie-decembrie 2016, 11 sub-subrecipienți au realizat activități conexe programului de control al TB, din care o organizație (ONG ”Aktiv”) activează în calitate de sub-subrecipient pentru ambii SR: Fundația Soros - Moldova și ONG "AFI". Majoritatea ONG-urilor realizează cîte un grant, excepție fiind 3 ONG care au aplicat către Fundația Soros - Moldova, și au fost aprobate pentru implementarea a câtorva granturi, în cadrul diferitor componente ale programului de granturi mici și orientate spre diferite populații-cheie - ONG ”AFI”, ONG ”Speranța Terrei” și ”Programe Medico-Sociale”.
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals |  |  |  | M6: Difference between current and safety stock Report Period [Perioada de raportare]: P3
Comments: | Overspendings in the amount of EUR 135,216.89 (for Xpert equipment and cartriges procured during the project life) due to modification of EUR/USD rate considered in the application grant (1,36946) and theaverage rate at the day of payments (1,07) from the TB grant. Supraconsumul in marime de 135,216.89 EUR pentru procurarea echipamentului Xpert si cartridge-utilor pe durata proiectului se datoreaza evolutiei ratei EUR/USD considerata la elaborarea cererii de finantare catre FG (1,36946) si rata medie de facto la ziua procesarii platilor (1,07) din grantul TB. |  |  | Comments: | N/A
|  |  |  | Component | Products | Stock level expressed in months of treatment for all current patients | Months of safety stock | Difference between current stock and safety stock
|  |  |  | Please Select | Please Select |  | 0
[5 empty] | Please Select |  | 0
[5 empty] | Please Select |  | 0
[5 empty] | Please Select |  | 0
* Includes only AFR category 4, 5 and 6 (Health products and health equipment & Medicines and Pharmaceuticals)
Menu

## Programmatic
Dashboard: Moldova - TB
NFM | 0 | [8 empty] | Report Period [Perioada de raportare]: |  | P3
Latest Rating [Ultimul Rating]: | B1 |  | Center for Health Policies and Studies (PAS Center) | [7 empty] | From [de la]: | 2016-07-01
|  | Strengthening Tuberculosis control in the Republic of Moldova | [8 empty] | To[Pînă la]: | 2016-12-31 | [7 empty] | Raiting |  | Valor
Programmatic Indicators
Percentage of cases with drug resistant TB (RR-TB and/or MDR-TB) started on treatment for MDR-TB who were lost to follow up at six months [Numărul și procentul pacienţilor cu tuberculoză drog-rezistentă (RR-TB și/sau MDR-TB) care au întrerupt tratamentul DOTS-Plus către luna a 6 de la demararea acestuia] |  |  |  | Number and percentage of new MDR-TB patients transferred to or initiated DOTS Plus treatment on ambulatory phase and provided with incentives to improve treatment compliance [Numărul și procentul de pacienți noi MDR-TB transferați sau inițiat tratament DOTS Plus in faza de ambulator și au primit stimulente pentru îmbunătățirea respectării tratamentului] |  |  |  | Number and percentage of new sensitive TB patients transferred to or initiated DOTS treatment on ambulatory level, provided with incentives to improve treatment compliance (Transnistria) [Numărul și procentul de pacienți noi TB sensibili transferați sau inițiat tratament DOTS in faza de ambulator, au primit stimulente pentru îmbunătățirea respectării tratamentului (Transnistria)]
Comment: P1 | According to the final data for 2015, 102 patients out of the 1,020 drug resistant TB patients (RR-TB and/or MDR-TB), who began second-line treatment in 2015, were lost to follow up at six months. Note:The analysis of cases enrolled in the DR-TB treatment, who were lost to follow up at six months reveals a difference of the lost to follow up rate registered among different patient categories. Thus, the interim lost to follow up rate among the new cases of DR-TB patients on treatment was 7,2% (30/411), while among the retreatment cases it is of 11,8% (72/609). Nevertheless, the analysis of the interim lost to follow up rate among the previously treated DR-TB patients, indicates a different rate for different types of patients: for the after failure cases it was of 3,7% (8/217); for the relapses it was 10,8% (24/221), and among the after lost to follow up cases - to 23,4% (40/171). (Conform datelor finale pentru anul 2015, 102 pacienți din cei 1 020 de pacienți cu TB rezistentă la medicamente (RR-TB și / sau MDR-TB), care au început tratamentul de linia a doua în 2015, au fost pierduți din supraveghere până la șase luni. Notă: Analiza cazurilor înrolate în tratamentul cu DR-TB, care au fost pierdute din supraveghere până la șase luni, arată o diferență între rata de urmărire înregistrată la diferite categorii de pacienți. Astfel, rata intermediară a celor pierduți din supraveghere în rândul cazurilor noi la pacienții cu DR-TB la tratament a fost de 7,2% (30/411), în timp ce în rândul cazurilor de re-tratament este de 11,8% (72/609). Cu toate acestea, analiza ratei intermediare pentru cei pierduți din supraveghere în rândul pacienților tratați anterior cu DR-TB, indică o rată diferită pentru diferitele tipuri de pacienți: pentru cazurile după eșec a fost de 3,7% (8/217); Pentru recidive a fost de 10,8% (24/221), iar printre cei pierduți din supraveghere - de 23,4% (40/171).) |  |  | Comment: P2 | The indicator was achieved Indicatorul a fost atins |  |  | Comment: P3 | The indicator was achieved Indicatorul a fost atins
Indicators |  |  | Target | Achieved | 0% - 59% | 60% - 89% | > 90% | Comments |  |  |  |  | min | 0 | 30% | 60% | 90% | 100% |  | min | 0 | 20% | 40% | 60% | 80%
Percentage of cases with drug resistant TB (RR-TB and/or MDR-TB) started on treatment for MDR-TB who were lost to follow up at six months [Numărul și procentul pacienţilor cu tuberculoză drog-rezistentă (RR-TB și/sau MDR-TB) care au întrerupt tratamentul DOTS-Plus către luna a 6 de la demararea acestuia] |  |  | 6.1% | 10% | 61% |  |  | According to the final data for 2015, 102 patients out of the 1,020 drug resistant TB patients (RR-TB and/or MDR-TB), who began second-line treatment in 2015, were lost to follow up at six months. Note:The analysis of cases enrolled in the DR-TB treatment, who were lost to follow up at six months reveals a difference of the lost to follow up rate registered among different patient categories. Thus, the interim lost to follow up rate among the new cases of DR-TB patients on treatment was 7,2% (30/411), while among the retreatment cases it is of 11,8% (72/609). Nevertheless, the analysis of the interim lost to follow up rate among the previously treated DR-TB patients, indicates a different rate for different types of patients: for the after failure cases it was of 3,7% (8/217); for the relapses it was 10,8% (24/221), and among the after lost to follow up cases - to 23,4% (40/171). (Conform datelor finale pentru anul 2015, 102 pacienți din cei 1 020 de pacienți cu TB rezistentă la medicamente (RR-TB și / sau MDR-TB), care au început tratamentul de linia a doua în 2015, au fost pierduți din supraveghere până la șase luni. Notă: Analiza cazurilor înrolate în tratamentul cu DR-TB, care au fost pierdute din supraveghere până la șase luni, arată o diferență între rata de urmărire înregistrată la diferite categorii de pacienți. Astfel, rata intermediară a celor pierduți din supraveghere în rândul cazurilor noi la pacienții cu DR-TB la tratament a fost de 7,2% (30/411), în timp ce în rândul cazurilor de re-tratament este de 11,8% (72/609). Cu toate acestea, analiza ratei intermediare pentru cei pierduți din supraveghere în rândul pacienților tratați anterior cu DR-TB, indică o rată diferită pentru diferitele tipuri de pacienți: pentru cazurile după eșec a fost de 3,7% (8/217); Pentru recidive a fost de 10,8% (24/221), iar printre cei pierduți din supraveghere - de 23,4% (40/171).) |  |  |  |  | max | 30% | 60% | 90% | 100% | 200% |  | max | 20% | 40% | 60% | 80% | 100%
Number and percentage of new MDR-TB patients transferred to or initiated DOTS Plus treatment on ambulatory phase and provided with incentives to improve treatment compliance [Numărul și procentul de pacienți noi MDR-TB transferați sau inițiat tratament DOTS Plus in faza de ambulator și au primit stimulente pentru îmbunătățirea respectării tratamentului] |  |  | 624 | 739 | 118.4% |  |  | The indicator was achieved Indicatorul a fost atins | [5 empty] | de 0 a 0.3 | de 0.3 a 0.6 | de 0.6 a 0.9 | de 0.9 a 1 | de 1 a 2 | Rating | Valor | de 0 a 0.2 | de 0.2 a 0.4 | de 0.4 a 0.6 | de 0.6 a 0.8 | de 0.8 a 1
Number and percentage of new sensitive TB patients transferred to or initiated DOTS treatment on ambulatory level, provided with incentives to improve treatment compliance (Transnistria) [Numărul și procentul de pacienți noi TB sensibili transferați sau inițiat tratament DOTS in faza de ambulator, au primit stimulente pentru îmbunătățirea respectării tratamentului (Transnistria)] |  |  | 444 | 448 | 100.9% |  |  | The indicator was achieved Indicatorul a fost atins | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Percentage of new and relapse TB patients tested using WHO recomennded rapid tests at the time of diagnosis [Procentul pacientilor cu TB, cazuri noi si recidiva, care au fost testați folosind teste rapide recomandate de OMS în momentul diagnosticării) |  |  | 86% | 92% | 132% |  |  | The data are preliminary for 2016. The indicator was achieved due to extension of the rapid method, improvement capacity of the health staff, and close monitoring of implementation the method. (Datele sunt preliminare pentru anul 2016. Indicatorul a fost realizat datorită extinderii metodei rapide, a fortificării capacităților personalului medical și a monitorizării stricte a implementării metodei). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number of bacteriologically confirmed, drug resistant TB cases (RR-TB and/or MDR-TB) notified [Numărul de cazuri de TB DR (RR-TB și/sau MDR-TB), confirmate bacteriologic, notificate] |  |  | 912 | 754 | 82.68% |  |  | Final data for 2015 - 754 drug resistant TB patients (RR-TB an MDR-TB), bacteriologically confirmed, were notified, compared to the 912 estimated cases for the reported period. Note: The decreasing number of DR TB patients notified is in direct correlation with the decreasing TB incidence. (Date finale pentru 2015- 754 pacienții cu TB rezistenta la medicamente (RR-TB și MDR-TB), confirmată bacteriologic, în comparație cu cele 912 de cazuri estimate pentru perioada de referință. Notă: Numărul descrescător al pacienților cu DR TB notificați este în corelație directă cu incidența scăzută a TB). | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number of notified cases of bacteriologically confirmed TB (new and relapse) [Numărul de cazuri notificate cu TB confirmate bacteriologic (nou și recidivă)] |  |  | 1079 | 2066 | 191.5% |  |  | The indicator was achieved Indicatorul a fost atins | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
0 |  |  | 0 | 0 | n/a | [8 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
0 |  |  | 0 | 0 | 0% | [8 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[5 empty] | n/a | [8 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[5 empty] | n/a | [8 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Menu

## Recommendations
Dashboard: Moldova - TB
NFM | 0 |  |  |  |  | Report Period [Perioada de raportare]: | P3
Latest Rating [Ultimul Rating]: | B1 |  | Center for Health Policies and Studies (PAS Center) |  |  | From [de la]: | 2016-07-01
|  |  | Strengthening Tuberculosis control in the Republic of Moldova |  |  | To[Pînă la]: | 2016-12-31
Recommendations
Are all funds reaching implementation levels and being spent according to budget?
Financial |  | Summary Comments |  |  | Recommendations
F1 |  | The cumulative disbursement is less than cumulative budget due to the fact that the projected initial budget contained funds for supporting the extension of the Community Center over the country. Due to the initial GF decision of non- approval extension of the Community Centers, the disbursement was revised in line with temporary revised budget for the TB grant by the Global Fund. Upon presentation by the PR of additional data to the GF concerning activities of TB Community Centers which perform in 10 districts, at mid of December 2016, based on data of the study ,,Audit of MDRTB management", the final decision of the GF on extension TB Community Center in additional 37 health facilitieis were provided at January 10,2017. As well, the Center PAS presented for approval an additional list of interventions under the TB NFM grant 2015-2017 to the GF at 14/02/2017, based on savings generated as result of the late creation of community centers in the 37 sites. These interventions are in line with the focus of the NFM application approved in 2015 by the Global Fund, the goal and objective the new NTP for 2016-2020 and country needs. The new list with interventions were approved by the CCM at the meeting as of 26/01/2017, which have been discussed and agreed in advance at the Technical Working Groups of the CCM. Thus, the budgeted amount wll be disbursed in 2017. Suma debursată este mai mică in raport cu bugetul programat, deoarece bugetul programat includea suma prevăzuta pentru finantarea activitatii modelului - Centre Comunitare extinse in toata țara. Din motiv de neaprobare de către FG al extinderii Centrelor Comunitare in toata tara in 2015, suma debursată este ajustată la bugetul revăzut provizoriu de FG. În urma prezentării de către RP a unor date suplimentare către FG privind activitatea centrelor comunitare pentru TB, realizată în 10 raioane, la mijlocul lunii decembrie 2016, pe baza datelor studiului "Auditul managementului cazurilor de MDRTB", decizia finală a GF privind Centrul comunitar de extindere a modelului de centru comunitar în alte 37 de institutii medico-sanitare, au fost comunicate tarii la 10 ianuarie 2017. De asemenea, Centrul PAS a prezentat spre aprobare o listă suplimentară de intervenții în cadrul grantului TF NFM 2015-2017 către GF la data de 14.02.2017, in baza economiilor generate ca urmare a creării cu întârziere a centrelor comunitare în cele 37 de locații. Aceste intervenții sunt în conformitate cu obiectivul aplicației NFM aprobată în 2015 de Fondul Global, scopul și obiectivele noului PNCT pentru perioada 2016-2020 șinecesitățile țării. Noua listă cu intervenții a fost aprobată de CNC în cadrul întrunirii din 26.01.2017, care a fost discutată și convenită în prealabil în cadrul grupurilor tehnice de lucru ale CNC, astfel încât suma inițial bugetată iîn aplicația de țară, va fi debursată în 2017 .
F2 |  | For two of objectives, the expenditures are almost in line with the budget, with a slight variance. The variance between budget and expenditures for the MDR-TB component is committed: for NGO grant programme implemented by the SR FSM for the MDRTB component; for incentives programme implemented by the SR AFI for MDR TB component and other planned grant activities for MDRTB component; the TA for TB/HIV and TA data based for Xpert. An essential unspent budget is linked to the Global Fund decision of non- approval extension of the Community Centers over the country, as per December 31, 2016. Pentru două dintre obiective, cheltuielile sunt aproape în conformitate cu bugetul, cu o ușoară variație. Variația dintre bugetul și cheltuielile pentru componenta MDR-TB este angajată: pentru programul de granturi ONG implementat de SR FSM pe componenta TB MDR; pentru programul de suport al pacienților implementat de către SR AFI pentru componenta TB MDR și alte activități de grant planificate pentru componenta TB MDR; pentru activități legate de Asistență Tehnică pentru politicile de fortificare a tratamentului in condiții de ambulator, pentru fortificarea colaborarii pe componenta TB / HIV si dezvoltarea sistemelor informaționale pentru Xpert. O suma esențiala neconsumată este determinată de decizia Fondului Global pentru neaprobarea planului de extindere a Centrelor Comunitare în toată țara, la situația din 31 decembrie 2016.
F3 |  | The cumulative disbursement by the GF is less than cumulative cash-out flow of the PR due to remaning budget at the end of the previos reporting period from the lines linked to the Community Centers component, which was not accepted by the Global Fund ( official letter as of 3 March 2016 to the Ministry of Health ) as well as the buffer stock and committed payments for the reported period. The variance between disbursed amount to SRs and SRs' expenditures includes the sum committed in the previous reporting period: for NGO grant programme implemented by the SR FSM and for incentives programme implemented by the SR AFI. Suma debursată de FG este mai mică decât cheltuielile RP împreună cu debursările către SRi, fiind determinată de bugetul rest la finalul perioadei anterioare de raportare de pe liniile conexe componentei - Centre Comunitare in toata tara, precum și sumei cu statut de buffer și sumelor angajate pentru plăți aferente perioadei de raportare. Variația dintre suma debursată către SRi și cheltuielile SR-lor include sumele angajate pentru programul de granturi ONG implementat de SR FSM și pentru programul de suport al pacienților implementat de către SR AFI.
F4 |  | The PR always makes the disbursements to SRs in the shortest period when the disbursement request is received and the report is presented. Perioada de debursare către SR este cit mai operativ posibil de la data depunerii cererii de debursare şi prezentare a raportului financiar.
Are procurement and hiring on schedule?
Management |  | Summary Comments |  |  | Recommendations
M1 |  | 1. No latter than 31 December 2016, the Grantee in collaboration with the CCM, other stakeholders and partners in the Republic of Moldova shall prepare and deliver to the Global Fund a sustainability plan for the national TB programm, endorsed by the government of the R. of Moldova , in forum and substance satisfactory to the Global Fund . Status: There were initiated discussion at the CCM and the WTG level on the development the sustainability plan for the National TB programme ( minute of the WTG as of 02/06/2015 and Minute of the Working Group responsible for development of the new TB Programme as of 28/01/2016). The new TB programme was endorsed by the Government in October 2016. The drafts of the Transition Plan for the sustainability of National TB Strategies, in English and Romanian with the supporting documents available for the plan were send to the GF on 19/01/2017. The drafts of the Transition Plan for the sustainability of National TB Strategies was part of the agenda of the CCM from March 2017 ( 15/03/2017). 2. Prior to financing extension of the TB community centers with the Grant Funds a) the Grantee shall engage a technical assistance partner acceptable to the Global Fund, to review and access the TB community centers model, including effectiveness, TB system integration and sustainability ( the Independent Assessment) and b) the Global Fund shall review the results of the Independent Assessment and if satisfied with the form and substance of the Independent Assessment findings, approve the Grant Funds for financing such TB community Centers - 1. The PR contracted two independent experts following to the WHO Europe recommendations (the contracts was signed on April 8, 2015). The report of the independent assessment was sent to the WHO, GF, CCM, National Programmes and PR. 2. Following the review of the Independent Assessment report and the internal consultations on the issues highlighted in the report, the Global Fund Secretariat requested from the country /MoH to share the following: a) The opinion on the feasibility/readiness of addressing the recommendations, and the timeframes that might be required for it; and b) Based on the considerations above, to provide the Global Fund with an improved, alternative model for the existing CCs, which should be built on the best practices for provision of TB care, coordinated among the TB units, CCs and NGOs. To provide the Secretariat with an assurance, that the new TB CC model will form a part of the costed transition plan, as a demonstration of the government’s readiness to continue countrywide financing of the new CC model for outpatient TB services delivery. Status: At the request of the Global Fund Secretariat, the MoH sent the letter with opinion on feasibility and readiness of addressing the experts recommendations in the country policy documents ( letter 01-15/448 as of 04.12.2015). The presentation of the improved model of the existing CCs was described in the letter 012/2016 as of 15/01/2016. The decision of the FG on non - aproval of the extension TB Community Centers in 37 health facilities was send to country on March 2016 with request to present additional data or to present proposal for redirection on unused budget. The PR was able to present additional data to the GF concerning activities of TB Community Centers which perform in 10 districts, at mid of December 2016, based on data of the study ,,Audit of MDRTB management,, officially presented round table as of November 30 2016. The final decision of the GF on extension TB Community Center in additional 37 health facilitieis were provided at January 10,2017. Due to unused budget for the line “Support to TB Community Centers”, generated as a result of postponing the extension of the TB Community model over the country during 2015-2016 years, the Center PAS presented for approval an additional list of interventions under the TB NFM grant 2015-2017 to the GF at 14/02/2017. These interventions are in line with the focus of the NFM application approved in 2015 by the Global Fund, the goal and objective the new NTP for 2016-2020 and country needs. The proposed interventions will bring diversification to the package of service oriented to TB patents. The new list with interventions were approved by the CCM at the meeting as of 26/01/2017, which have been discussed and agreed in advance at the Technical Working Groups of the CCM. The estimated budget for implementation of the described activities in the attachment was based on the projected unused budget from TB CC lines. 3. In accordance with the Global Fund Board Decision Point GF/B28/DP4: commitment and disbursement of 15% of the Republic of Moldova aggregate allocation of EUR 28,640,132 for the period of 2014-2017 allocation period, , which is equal to EUR 4,296,020, is subject to the Republic of Moldova compliance with the Global Fund willingness to pay requirement - This is a grant life condition related to both NFM grant in country for HIV and TB. 3a The PR and/or the CCM are requested to submit a report on actual state budget execution for 2015 and the updated level of commitments for 2016 by 30 June 2016 or earlier, if available. Templates for capturing 2015 Budget execution and 2016 Budget for TB and HIV are enclosed to this letter. Please note that there are cash transfers planned under this disbursement decision which are subject to meeting the Counterpart Financing requirements (reported expenditures for 2015 and commitments for 2016). Additionally, we would appreciate if the 'Strategia sectorială de cheltuieli in domeniul ocrotirii sănătăţii, 2016-2018 (CBTM)' can be shared with us. Status: The official letter from the CCM with data concening the commitment to further implement and support the TB and HIV including budget contribution and planned budget for next years, has been sent to the Global Fund on 30/06/2016 in the format requested by the GF. Also there were presented the 'Strategia sectorială de cheltuieli in domeniul ocrotirii sănătăţii, 2016-2018 (CBTM)'. 1. Nu mai târziu de 31 decembrie 2016, Recipientul Principal în colaborare cu CNC, alte părți interesate și parteneri din Republica Moldova va pregăti și remite Fondului Global un plan de sustenabilitate pentru programul național TB, aprobat de guvernul R. Moldova, în forum și substanță satisfăcătoare pentru Fondul Global. Statut: Au fost inițiate discuții la nivelul CNC și GTL privind elaborarea planului de sustenabilitate pentru programul național TB (proces verbal al GTL din 02.06.2015 și proces verbal al Grupului de lucru responsabil pentru dezvoltarea noului program TB din data de 28/01/2016). Noul program de TB a fost aprobat de Guvern în octombrie 2016. Proiectele Planului de tranziție pentru durabilitatea strategiilor naționale de TB, în limbile engleză și română, împreună cu documentele justificative disponibile pentru acest plan, au fost trimise la FG pe 19/01/2017 . Proiectele Planului de tranziție pentru durabilitatea strategiilor naționale de TB au făcut parte din agenda CCM din martie 2017 (15/03/2017). 2. Înainte de aprobarea finanțării pentru extinderea modelului de centru comunitar pentru pacienții cu TB, din fondurile grantului a) Recipientul principal va angaja un consultant de asistență tehnică, acceptabil pentru Fondul Global, pentru a revizui și a evalua modelul centrelor comunitare TB, inclusiv eficacitatea, integrarea în sistemul TB și durabilitatea (Evaluare independentă) și b) Fondul Global va analiza rezultatele evaluării independente și, dacă este satisfăcut de forma și fondul constatărilor ale evaluării independente, va aproba fondurile de grant pentru finanțarea centrelor comunitare – Măsurile întreprinse – 1. RP a contractat doi consultanți independenți, la recomandarea biroului OMS pentru Europa (contractele a fost semnat la 8 aprilie 2015). Raportul de evaluare independent a fost trimis la OMS, FG, CNC, programele naționale și RP. 2. În urma revizuirii raportului de evaluare independentă și consultările interne privind aspectele evidențiate în raport, secretariatul Fondul Global a solicitat țării / MS următoarele: a) Avizul privind fezabilitatea / gradul de pregătire al abordării recomandărilor, precum și intervalele de timp care ar putea fi necesare pentru aceasta; și b) În baza considerațiilor de mai sus, să prezinte Fondului Global un model îmbunătățit, alternativ pentru centrele comunitare existente, care ar trebui create în baza celor mai bune practici pentru prestarea serviciilor de îngrijire TB, coordonate între instituțiile medicale implicate în controlul TB, centre comunitare și ONG-uri. La fel, să ofere Secretariatului o asigurare că noul model de centre comunitare TB va forma o parte a planului de tranziție bugetat, ca o dovadă de pregătire a guvernului să continue finanțarea națională a noului model CC pentru livrarea serviciilor de îngrijire ambulatorie TB. Statut: La cererea Secretariatului Fondului Global, MS a trimis scrisoarea cu avizul cu privire la fezabilitatea și disponibilitatea de a se adresa recomandărilor experților în documentele de politică națională (scrisoarea 01-15 / 448 din 04.12.2015). Prezentarea modelului îmbunătățit al CC existente a fost descrisă în scrisoarea 012/2016 din 15/01/2016. Decizia FG privind ne-aprobarea deciziei de extindere a centrelor comunitare în 37 de instituții medicale a fost trimisă țării în martie 2016 cu solicitarea de a prezenta date suplimentare sau de a prezenta propunerea de redirecționare a bugetului neutilizat. RP a prezentat date suplimentare FG privind activitatea centrelor comunitare pentru TB, realizată în 10 raioane, la mijlocul lunii decembrie 2016, pe baza datelor studiului "Auditul managementului cazurilor de MDRTB", decizia finală a GF privind Centrul comunitar de extindere a modelului de centru comunitar în alte 37 de institutii medico-sanitare, au fost comunicate tarii la 10 ianuarie 2017. Datorită bugetului nefolosit pentru linia "Suport pentru centrele comunitare TB", generată ca urmare a amânării extinderii modelului comunitar al TB în țară în perioada 2015-2016, Centrul PAS a prezentat spre aprobare o listă suplimentară de intervenții în cadrul grantului TF NFM 2015-2017 către GF la data de 14.02.2017. Aceste intervenții sunt în conformitate cu obiectivul aplicației NFM aprobată în 2015 de Fondul Global, scopul și obiectivele noului PNCT pentru perioada 2016-2020 și necesitățile țării. Noua listă cu intervenții a fost aprobată de CNC în cadrul întrunirii din 26.01.2017, care a fost discutată și convenită în prealabil în cadrul grupurilor tehnice de lucru ale CNC. Bugetul estimat pentru implementarea activităților menționate, s-a bazat pe bugetul neutilizat propus din liniile CC TB. 3. În conformitate cu decizia Consiliului Fondului Global, punctul GF / B28 / DP4: angajamentul și plata a 15% din alocarea totală de 28,640,132 EUR pentru Republica Moldova în perioada 2014-2017, care este egală cu 4,296,020 EURO, este condiționată Republicii Moldova de respectarea cerinței Fondului Global de a mări finanțarea din partea statului, în domeniul unde a investit Fondul Global. Aceasta este o condiție pe durata grantului, atât pentru grantul NFM TB, cât și pentru HIV. Statut: O scrisoare oficiala din partea CNC al tarii a fost prezentata la 30/06/2016,care releva angajamentul de implementare si suport al programelor Tb si HIV inclusiv cu date referitor la bugetul alocat, si bugetul planificat pentru urmatorii ani, in formatul solicitat de FG. Deasemenea a fost adusa spre informare FG 'Strategia sectorială de cheltuieli in domeniul ocrotirii sănătăţii, 2016-2018 (CBTM)'.
M2 |  | 14 from 15 positions are fulfilled. 14 din 15 pozitii sunt | #DIV/0! | #DIV/0!
M3 |  | None of the SRs needed to be assessed, due to proved experience within the precedent grant implementation. Nici unul dintre sub-recipienti nu a necesitat să fie evaluat, dat fiind experiența demonstrată în cadrul implementării grantului precedent.
M4 |  | For the reported period, iulie-decembrie 2016, 11 SSRs were involved in TB related activities, from which one ("Activ" from Bender) is acting as SSR for both SRs - Soros Foundation Moldova and NGO "AFI". Basically, the majority of NGO are implementing one grant, with exception of three NGOs which applied to Soros Foundation - Moldova and were granted with several grants each, but within different components and targeted to different populations: NGO "AFI", NGO ”Hope of Land” and NGO ”Medico-Social Programs”. In perioada de raportare, iulie-decembrie 2016, 11 sub-subrecipienți au realizat activități conexe programului de control al TB, din care o organizație (ONG ”Aktiv”) activează în calitate de sub-subrecipient pentru ambii SR: Fundația Soros - Moldova și ONG "AFI". Majoritatea ONG-urilor realizează cîte un grant, excepție fiind 3 ONG care au aplicat către Fundația Soros - Moldova, și au fost aprobate pentru implementarea a câtorva granturi, în cadrul diferitor componente ale programului de granturi mici și orientate spre diferite populații-cheie - ONG ”AFI”, ONG ”Speranța Terrei” și ”Programe Medico-Sociale”.
M5 |  | Overspendings in the amount of EUR 135,216.89 (for Xpert equipment and cartriges procured during the project life) due to modification of EUR/USD rate considered in the application grant (1,36946) and theaverage rate at the day of payments (1,07) from the TB grant. Supraconsumul in marime de 135,216.89 EUR pentru procurarea echipamentului Xpert si cartridge-utilor pe durata proiectului se datoreaza evolutiei ratei EUR/USD considerata la elaborarea cererii de finantare catre FG (1,36946) si rata medie de facto la ziua procesarii platilor (1,07) din grantul TB.
M6 |  | N/A
Are technical targets being achieved?
Programmatic |  | Summary Comments |  |  | Recommendations
P1 - trend |  | According to the final data for 2015, 102 patients out of the 1,020 drug resistant TB patients (RR-TB and/or MDR-TB), who began second-line treatment in 2015, were lost to follow up at six months. Note:The analysis of cases enrolled in the DR-TB treatment, who were lost to follow up at six months reveals a difference of the lost to follow up rate registered among different patient categories. Thus, the interim lost to follow up rate among the new cases of DR-TB patients on treatment was 7,2% (30/411), while among the retreatment cases it is of 11,8% (72/609). Nevertheless, the analysis of the interim lost to follow up rate among the previously treated DR-TB patients, indicates a different rate for different types of patients: for the after failure cases it was of 3,7% (8/217); for the relapses it was 10,8% (24/221), and among the after lost to follow up cases - to 23,4% (40/171). (Conform datelor finale pentru anul 2015, 102 pacienți din cei 1 020 de pacienți cu TB rezistentă la medicamente (RR-TB și / sau MDR-TB), care au început tratamentul de linia a doua în 2015, au fost pierduți din supraveghere până la șase luni. Notă: Analiza cazurilor înrolate în tratamentul cu DR-TB, care au fost pierdute din supraveghere până la șase luni, arată o diferență între rata de urmărire înregistrată la diferite categorii de pacienți. Astfel, rata intermediară a celor pierduți din supraveghere în rândul cazurilor noi la pacienții cu DR-TB la tratament a fost de 7,2% (30/411), în timp ce în rândul cazurilor de re-tratament este de 11,8% (72/609). Cu toate acestea, analiza ratei intermediare pentru cei pierduți din supraveghere în rândul pacienților tratați anterior cu DR-TB, indică o rată diferită pentru diferitele tipuri de pacienți: pentru cazurile după eșec a fost de 3,7% (8/217); Pentru recidive a fost de 10,8% (24/221), iar printre cei pierduți din supraveghere - de 23,4% (40/171).)
P2 - trend |  | The indicator was achieved Indicatorul a fost atins
P3 - trend |  | The indicator was achieved Indicatorul a fost atins
P1 |  | According to the final data for 2015, 102 patients out of the 1,020 drug resistant TB patients (RR-TB and/or MDR-TB), who began second-line treatment in 2015, were lost to follow up at six months. Note:The analysis of cases enrolled in the DR-TB treatment, who were lost to follow up at six months reveals a difference of the lost to follow up rate registered among different patient categories. Thus, the interim lost to follow up rate among the new cases of DR-TB patients on treatment was 7,2% (30/411), while among the retreatment cases it is of 11,8% (72/609). Nevertheless, the analysis of the interim lost to follow up rate among the previously treated DR-TB patients, indicates a different rate for different types of patients: for the after failure cases it was of 3,7% (8/217); for the relapses it was 10,8% (24/221), and among the after lost to follow up cases - to 23,4% (40/171). (Conform datelor finale pentru anul 2015, 102 pacienți din cei 1 020 de pacienți cu TB rezistentă la medicamente (RR-TB și / sau MDR-TB), care au început tratamentul de linia a doua în 2015, au fost pierduți din supraveghere până la șase luni. Notă: Analiza cazurilor înrolate în tratamentul cu DR-TB, care au fost pierdute din supraveghere până la șase luni, arată o diferență între rata de urmărire înregistrată la diferite categorii de pacienți. Astfel, rata intermediară a celor pierduți din supraveghere în rândul cazurilor noi la pacienții cu DR-TB la tratament a fost de 7,2% (30/411), în timp ce în rândul cazurilor de re-tratament este de 11,8% (72/609). Cu toate acestea, analiza ratei intermediare pentru cei pierduți din supraveghere în rândul pacienților tratați anterior cu DR-TB, indică o rată diferită pentru diferitele tipuri de pacienți: pentru cazurile după eșec a fost de 3,7% (8/217); Pentru recidive a fost de 10,8% (24/221), iar printre cei pierduți din supraveghere - de 23,4% (40/171).)
P2 |  | The indicator was achieved Indicatorul a fost atins
P3 |  | The indicator was achieved Indicatorul a fost atins
P4 |  | The data are preliminary for 2016. The indicator was achieved due to extension of the rapid method, improvement capacity of the health staff, and close monitoring of implementation the method. (Datele sunt preliminare pentru anul 2016. Indicatorul a fost realizat datorită extinderii metodei rapide, a fortificării capacităților personalului medical și a monitorizării stricte a implementării metodei).
P5 |  | Final data for 2015 - 754 drug resistant TB patients (RR-TB an MDR-TB), bacteriologically confirmed, were notified, compared to the 912 estimated cases for the reported period. Note: The decreasing number of DR TB patients notified is in direct correlation with the decreasing TB incidence. (Date finale pentru 2015- 754 pacienții cu TB rezistenta la medicamente (RR-TB și MDR-TB), confirmată bacteriologic, în comparație cu cele 912 de cazuri estimate pentru perioada de referință. Notă: Numărul descrescător al pacienților cu DR TB notificați este în corelație directă cu incidența scăzută a TB).
P6 |  | The indicator was achieved Indicatorul a fost atins
P7
P8
P9
P10
Menu

## Actions
Dashboard: Moldova - TB
| NFM | 0 |  |  |  | Report Period [Perioada de raportare]: |  | P3
| Latest Rating [Ultimul Rating]: | B1 |  | Center for Health Policies and Studies (PAS Center) |  | From [de la]: |  | 2016-07-01
|  |  | Strengthening Tuberculosis control in the Republic of Moldova |  |  |  | To[Pînă la]: | 2016-12-31
Decisions and Actions
What is the overall status of this grant implementation?
| Key Recommendations from Oversight Group(s) |  |  |  | CCM Decision | Due Date | Person Responsible
Current Reporting Period
Actions to Implement / Previous Period
What is the overall status of this grant implementation?
| CCM Decision |  |  |  | Action Taken | Date | Person Responsible
Previous Reporting Period
Menu

## Setup (hidden)
Dashboard: Moldova - TB
Set-up = List of validation for Grant Detail page
Component | Currency | Round | Phase | Period | Rating | LFA | Medicaments | Countries
Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select
HIV / AIDS | $ | Round 1 | Phase 1 | P1 | A1 | CA (Crown Agents) | Isoniazid | Afghanistan
MALARIA | € | Round 2 | Phase 2 | P2 | A2 | DEL (Deloitte) | Ethambutol | Albania
TB |  | Round 3 | RCC | P3 | B1 | DTT (DTT Emerging Markets) | Rifampicin | Algeria
HIVAIDS / TB |  | Round 4 |  | P4 | B2 | FIN (Finconsult) | Pyrazimamide | Angola
HSS |  | Round 5 |  | P5 | C | GT (Grant Thornton) | RDT | Argentina
|  | Round 6 |  | P6 |  | H-C (Hodar-Conseil) | NVP | Armenia
|  | Round 7 |  | P7 |  | KPMG (KPMG) | 3TC | Azerbaijan
|  | Round 8 |  | P8 |  | MSCI (MSCI) | D4T | Bangladesh
|  | Round 9 |  | P9 |  | PwC (PricewaterhouseCoopers) | AZT | Belarus
|  | Round 10 |  | P10 |  | STI (Swiss Tropical Institute), | DDI | Belize
|  |  |  | P11 |  | UNOPS | EFV | Benin
|  |  |  | P12 |  |  | AS/LF | Bhutan
[7 empty] | AS/AQ | Bolivia
[7 empty] | AS/MQ | Bosnia and Herzegovina
[7 empty] | Al/Lum | Botswana
Brazil
[7 empty] | TB nutri'l supplements | Bulgaria
[7 empty] | E-PAP | Burkina Faso
Burundi
Cambodia
Cameroon
Cape Verde
Central African Republic
Chad
Chile
China
China
Colombia
Comoros
Congo (Democratic Republic of the)
Congo (Republic of the)
Costa Rica
Cote d'Ivoire
Croatia
Cuba
Djibouti
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Ethiopia
Fiji
Gabon
Gambia
Georgia
Ghana
Global(LWF)
Guatemala
Guinea
Guinea-Bissau
Guyana
Haiti
Honduras
India
Indonesia
Iran (Islamic Republic of)
Iraq
Jamaica
Jordan
Kazakhstan
Kenya
Korea, Democratic Peoples Republic of
Kosovo (Serbia)
Kyrgyzstan
Lao PDR
Lesotho
Liberia
Macedonia, FYR
Madagascar
Malawi
Maldives
Mali
Mauritania
Mauritius
Moldova
Mongolia
Montenegro
Morocco
Mozambique
Multi-country Africa (West Africa Corridor Program)
Multi-country Africa(RMCC)
Multi-country Americas (Andean)
Multi-country Americas (CARICOM)
Multi-country Americas (CRN+)
Multi-country Americas (Meso)
Multi-country Americas (OECS)
Multi-country Americas (REDCA+)
Multi-country Western Pacific
Myanmar
Namibia
Nepal
Nicaragua
Niger
Nigeria
Pakistan
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Romania
Russian Federation
Rwanda
Sao Tome and Principe
Senegal
Serbia
Sierra Leone
Solomon Islands
Somalia
South Africa
Sri Lanka
Sudan
Suriname
Swaziland
Syrian Arab Republic
Tajikistan
Tanzania
Thailand
Timor-Leste
Togo
Tunisia
Turkey
Uganda
Ukraine
UN Theme Group on HIV/AIDS (West Bank and Gaza)
Uzbekistan
Viet Nam
Yemen
Zambia
Zanzibar (Tanzania)
Zimbabwe