## Menu
Dashboard: Moldova - TB
TB NFM, | Grant No. [Nr. Grantului]: MDA-T-PAS
V1.0
Finance
Programmatic
Management
Select the option you want to see:
Recommendations
Actions
Grant Detail
List of Indicators
Data Entry
Grant Information
Indicators
Reports

## List of Indicators
Dashboard: Moldova - TB
Financial information
Name: | Definition | Measurement | Data Sources
F1: Budget and disbursements by Global Fund [Bugetul și debursările de către Fondul Global] | Cumulative budget: Sum of the grant budget from period one (quarter, trimester, or semester) of the current phase, up to and including the dashboard reporting period. Cumulative Disbursments by GF: Sum of all the funds transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to and including the dasboard reporting period. | Currency of the grant ($ or Euro) Cumulative – Figures refer to budget and disbursements for all the periods of the phase up to and including the dashboard reporting period | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F2: Budget and actual expenditures by Grant Objective [Bugetul și cheltuielile actuale după Obiectivele Grantului] | Cumulative Budget per Objective: Sum of the grant budget by Objective, from period one of the current phase up to and including the dashboard reporting period. Cumulative Expenditure per Objective: Sum of amounts spent by Objective directly by the PR plus the amounts transferred by the PR to all SRs from the beginning of the phase up to and including dashboard reporting period, by Objective | • Cumulative – Figures refer to budget, disbursements or expenditure for all the periods of the phase up to and including the dashboard reporting period. | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F3: Disbursements and expenditures [Debursări și cheltuieli] | Disbursement by GF: Prior to this Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to but not including dashboard reporting period. Disbursement by GF: Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), during dashboard reporting period. PR disbursements and expenditure: Prior to this Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) up to but not including dashboard reporting period. PR disbursements and expenditure: Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) during dashboard reporting period. Disbursements to SRs: Prior to this Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), up to but not including dashboard reporting period. Disbursements to SRs:Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), in dashboard reporting period. SR expenditures: Prior to this Reporting period: The sum of all expenditures reported by the SRs, up to but not including dashboard reporting period. SR expenditures: Reporting period: The sum of all expenditures reported by the SRs, during dashboard reporting period. | Currency of the grant ($ or Euro) • Reporting period – Figures refer to budget, disbursements or expenditure for the reporting period to which the dashboard refers. • Prior to reporting period - Figures refer to the total budget, disbursements or expenditure for all the periods before but not including the current period. | PU/DR; PR data: SR reports to PR
F4: Latest PR reporting and disbursement cycle [Ultima perioadă de raportare și debursare a RP] | Days taken to submit final PU/DR to LFA – This indicator measures the number of calendar days it took the PR to send a final Performance Update and Disbursement Request (PU/DR) to the LFA after the end of the period. A 'final' PU/DR would be one for which the LFA did not require any further clarifications from the PR. The expected value is 45 days from the end of the period, as defined in the Grant Agreement. The actual value is the number of calendar days from the end date of the period to the date on which the PR sent to the LFA the final PU/DR. Days taken for disbursement to reach PR – This indicator measures the number of calendar days it took the Global Fund to send the latest disbursement to the PR's account after receipt of the acceptable PU/DR by the LFA. The expected number is 45 days. The actual number is the number of days from the date of transmission by the PR to the LFA of the acceptable PU/DR to the date the disbursement is received by the PR at its bank. Days taken for disbursement to reach SRs – This indicator measures the average number of days for disbursements to be made to all the SRs. The expected value for this indicator will be set locally by the PR and SRs, preferably in the Grant Operations Manual. The actual value is the average of the number of days from the receipt of the funds from the GF by the PR to the date the funds are received by each SR. Different SRs coudl receive funds on different dates and this indicator is the average across all SRs for the latest disbursement. | Number of calendar days; it refers only to reporting period for which the latest disbursement was received and is not cumulative | PR, LFA, GF emails and records; bank notification document or the notice of receipt by the PR to GF; SR reports to PR based on bank records
Management Information
Name: | Definition | Measurement | Data Source
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) [Statutul Condițiilor Precedente și a Acțiunilor Prestabilite în Timp] | Number of Conditions Precedent (CPs) and Time Bound Actions (TBAs ) fulfilled, or unfulfilled. Within the Unfulfilled category, we distinguish between those CPs and TBAs whose deadline has not passed and those for which the deadline has passed. | Number, cumulative to the dashboard reporting period. Number of fulfilled CPs and/or TBAs plus unfulfilled CPs and/or TBAs should equal the total number set by the Global Fund on the grant | PR records; Grant Performance Reports;
M2: Status of key PR management positions | Number of PR grant management positions planned currently filled or vacant. Full time equivalents of the managerial positions that are on the organizational chart (or otherwise planned) and directly responsible for ensuring grant implementation at the PR, and lead SRs (if necessary). This will include new hires, current staff who are assigned to work on the grant’s management, as well as any staff seconded from other divisions or partner organizations. | Number, in current reporting period | PR records
M3: Contractual arrangements (SRs) | Identified: Total number of potential SRs identified by the PR for the phase. Assessed: Total number of potential SRs assessed by the PR to determine whether they qualify to function as SRs for the grant. Approved: Total number of SRs that have been approved. Signed: Total number of SRs that have signed agreements/contracts with the PR under the grant. Receiving funding: Total number of SRs that are getting funds and/or supplies from the PR. Numbers of SRs Identified, Assessed, Approved, Signed and Receiving funds are cumulative for the phase, with the following exceptions: If an SR does not need new approval in Phase II, then approval in Phase I is counted. If an SR was signed in a previous Phase but is not working in the current Phase, that SR is no longer counted in Identified, Assessed, Approved. | Number, cumulative to the reporting period. A SR is an institution or program with its own workplan, budget and performance targets. | PR records; Sub-agreements/MOUs; CCM records
M4: Number of complete reports received on time | The total number of periodic reports with up-to-date financial, management and performance (programmatic) data received by the PR from SRs and by SRs from the SubSRs (SSRs) by the expected date. A 'complete' report is one that contains all the data that the PR requires for the PU/DR. The expected date would be set by the PR in the sub-agreements. | Number of reports received. The figure reflects only the period of reporting; it is not cumulative. | PR and SR records
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals | This indicator measures the budget approved for the current phase of the grant for purchase of health products and equipment and pharmaceuticals and medicines (categories 4 and 5 in the new Enhanced Financial Report), and the cumulative amounts of financial obligations and expenditures up to the dashboard reporting period. Budget approved: Total approved budget for purchases (categories 4 and 5) for the entire phase of the grant. It does not include the amounts for fees, management, operational costs, etc. Cumulative Obligations: Total of all order(s) placed and monies committed for these purchases by the PR up to and including the dashboard reporting period. Ideally, by the end of the Phase, budget should equal obligations. Cumulative expenditure: Total of actual Expenditures on category 4 and 5 up to and including the dashboard reporting period (whether paid by PR or authorized to be paid by another entity like GF or other). | Currency of the grant ($ or Euro) | Grant agreement approved budget (for categories 4 and 5 of Enhanced Finance Reporting in current phase); and PR financial data (for expenditures), and/or PSM unit (for orders placed and funding committed or obligated).
Note: Category 6 of the EFR will not be considered as part of the budget for pharmaceuticals. Category 6 has several expenditures that are difficult to disaggregate or quantify, such as warehousing costs, distribution costs (particularly when distibution is done by MOHs), and others that are related to operational costs of the PSM component.
M6: Difference between current and safety stock | This indicator is a snapshot of the difference between the current (or last month) stock level of a specific product (medicine in single, fixed-dose combination, bednets, diagnostic kits, etc.) of a particular dose, expressed in monthly needs (number of months of treatment available) for all patients in the program, and the safety or buffer stock (also expressed in months) as established by the disease program, warehouse system or essential drugs program, for the particular product and dosage. The table will show the difference in months in colors: • RED: when the difference is negative or 0, showing that months of existing stock are lower than or equal to what has been established as months of safety stock • YELLOW: when we have more than the level of safety stock (>0) but less than 3 months (+3). • GREEN: when the difference is between 3 and 18 months. • VIOLET: When the difference shows that the level above the safety stock is greater than or equal to 18 months indicating a potential overstock) problem. For a full description of how this indicator is calculated, please see the User’s Manual. | Number of months | PR records: Warehouse data.
Programmatic Indicators (from Performance Framework) [Indicatorii programatici]
Indicator | Definition (from M&E Plan, 2014) [Definiție (din planul M&E,2014] | Measurement | Data Source [sursa de date]
MDR TB-4: Percentage of cases with drug resistant TB (RR-TB and/or MDR-TB) started on treatment for MDR-TB who were lost to follow up at six months | Numerator: Number of MDR-TB cases initiated on second line anti-TB treatment regimen during the specified period of time, who were lost to follow up at the end of 6 months of treatment (Year 1 - 2014 cohort; Year 2 - 2015 cohort; Year 3 - 2016 cohort). Denominator: Number of MDR-TB cases initiated on second line anti-TB treatment during the specified period of time. | Recording and reporting system for drug-resistant TB; report of the cases with drug resistant TB started on treatment for MDR-TB, who were lost to follow up at six months. The baseline data refer to the MDR TB cohort registered during the Semester I, 2013. | SYME TB - R&R TB system, quarterly/ annual reports, NTP reports.
Number and percentage of new MDR-TB patients transferred to or initiated DOTS Plus treatment on ambulatory phase and provided with incentives to improve treatment compliance | Numerator: Number of new MDR-TB patients transferred to / or initiated the DOTS Plus treatment in ambulatory conditions and receiving incentives to improve treatment compliance during reported period from right and left bank of the river Nistru. Denominator: Total Number of MDR-TB patients transferred to / or initiated the DOTS Plus treatment in ambulatory conditions during the same period. | The patient is qualified reached by the supporting programme, if he/she benefited from incentive programme. | SYMETB and data base implemented for incentives programmes by the SR AFI.
Number and percentage of new sensitive TB patients transferred to or initiated DOTS treatment on ambulatory level, provided with incentives to improve treatment compliance (Transnistria) | Numerator: Number of new TB patients transferred to / or initiated the DOTS treatment in ambulatory conditions and receiving incentives to improve treatment compliance during reported period. Denominator: Total Number of TB patients transferred to / or initiated the DOTS treatment in ambulatory conditions during the same period. | The patient is qualified reached by the supporting programme, if he/she benefited from incentive programme. | The source of data for the indicator will be SYMETB and data base implemented for incentives programmes by the SR AFI.
Percentage and number of patients with symptoms or signs suggestive to TB, examined by Xpert MTB/RIF | Numerator: Number of patients with symptoms or signs suggestive to TB, examined by Xpert MTB/RIF. Denominator: Total number of patients with symptoms or signs suggestive to TB. | The estimation of the percentage of examination with Xpert MDTB/RIF methodology considers the current coverage and the schedule of full coverage with equipment of the country. The numerator and denominator represents an estimated data, and during the reporting period will be presented the defacto data. | R&R system.
MDR TB-2: Number of bacteriologically confirmed, drug resistant TB cases (RR-TB and/or MDR-TB) notified | Numerator: Number of bacteriologically confirmed, drug resistant TB cases (RR-TB and/or MDR-TB) notified | The indicator shall be reported for the cohort of patients registered 6-12 months ago, to make sure that the final result of the investigation is introduced in the SIME TB database, considering the fact that it takes from 4 to 5 months to perform the test, obtain the result, and further introduce it in the SIME TB account (in the case when patients are investigated using the classical (solid) method of culture and DST). This indicator covers both the civilian and the penitentiary sector, incl. the Transdniester region. | SYME TB - R&R TB system, annual reports, DR routine surveillance.
DOTS-1b Number of notified cases of bacteriologically confirmed TB (new and relapse) | Numerator: Number of bacteriologically confirmed TB cases notified to the national health authority during the reporting period | Process indicator to measure the number of bacteriologically confirmed TB cases notified to the national health authority during the reporting period | R&R system.
Indicator Number: Name (Perf Framework No.) | Definition | Measurement | Data Source
The indicators should be selected by the PRs and members of the CCM or the CCM Technical Committee, from the Performance Framework |  |  | Performance Framework
Menu

## Data Entry
Grant information [Informatia de Grant]
| Country [Țara]: | Moldova |  | Title of the Grant [Numele Grantului]: |  | Strengthening Tuberculosis control in the Republic of Moldova
| Grant No. [Nr. Grantului]: | MDA-T-PAS |  | Component [Componentul]: |  | TB | Total Funding[Suma totala]:
| Principal Recipient [Recipientul Principal]: | Center for Health Policies and Studies (PAS Center) |  |  | Round [Runda]: | NFM | Phase [Faza]:
| Start Date (dd/Mmm/yy) [Data Demarării (zz/ll/aa)]: | 2018-01-01 |  | Local Fund Agent [Agentul Local al Fondului]: |  | PwC (PricewaterhouseCoopers)
| Latest Rating [Ultimul Rating]: | A2 |  | Fund Portfolio Manager [Portfolio Manager]: |  | Tsovinar Sakanyan
Information reporting period [Informația despre perioada raportată]
| Report Period [Perioada de raportare]: | P3 | From [de la]: | 2019-01-01 | To[Pînă la]: | 2019-06-30 | Date of entry of information[Data de introducere a informației]: |  | 2019-07-30
| Prepared by [Pregătit de către]: |  | PAS Center
Information on indicators [Informația despre indicatori]
Enter the data based on the colour-coded cells [Introduceți datele bazîndu-vă de celulele codificate prin culoare]
| Financial Information [Informația Financiară]: |  | Management Information [Informația pe Management]: |  |  | Programmatic Information [Informația Programatică]:
| Financial Information [Informatia Financiara]: | [8 empty] | Enter finance data in every orange cell like this [Introduceți datele financiare in fiecare celula portocaliu ca aceasta].
| Currency of the grant[Valuta Grantului] |  | €
F1: Budget and disbursements by Global Fund [Bugetul și debursările de către Fondul Global]
Disbursement [Debursări]
| Reporting period [perioada de raportare] | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12 | % Cumulative
| Budget (in €) | P1: 666424; P2: 837928; P3: 750063 | 117.1%
| Disbursements by GF (in €) | P1: 1274305.27; P2: 346491.56; P3: 1019352.73
| Cumulative budget [Buget cumulativ] | P1: 666424; P2: 1504352; P3: 2254415
| Cumulative disbursements [Debursări cumulative] | P1: 1274305.27; P2: 1620796.83; P3: 2640149.56
|  | 0% | 0% | 117.1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
F2: Budget and actual expenditures by Grant Objective [Bugetul și cheltuielile actuale după Obiectivele Grantului]
| Grant Objective [obiectivele Grantului] | P1: Cumulative Budget (in €); P2: Cumulative Expenditures (in €)
1 | TB care and prevention | bar: P1 to P2
2 | MDR-TB | P1: 2027205.4; P2: 1942548.3107
3 | Program management | P1: 227209.4; P2: 239116
| Total | P1: 2254414.8; P2: 2181664.3107; P4: OK: Data match
F3: Disbursements and expenditures [Debursări și cheltuieli]
|  | Prior to reporting period [Către perioada de raportare] | Current reporting period [Perioada de raportare curentă] | Total Spent and Disbursement (in €)
| Disbursed by Global Fund (Debursat de către Fondul Global) | P1: 1620796.83; P2: 1019352.73; P3: 2640149.56
| PR expenditure and disbursement (Cheltuielile și debursările RP ) | P1: 377052.81; P2: 519405.035; P3: 896457.845
| Disbursed to SRs (Debursări către SR) | P1: 612954.02; P2: 210521.22; P3: 823475.24
| SR expenditures (Cheltuielile SR) | P1: 525504.35; P2: 259504.44; P3: 785008.79
F4: Latest PR reporting and disbursement cycle [Ultima perioadă de raportare și debursare a RP]
Last fund disbursement: Number of calendar days [Ultima debursare a surselor: Număr de zile calendaristice]
|  | Expected (days) Preconizat (zile) | Actual (days) Actual (zile)
| Days taken to submit final PU/DR to LFA (Zile necesare pentru remiterea PU/DR final către ALF) | P1: 90; P2: 88
| Days taken for disbursement to reach PR (Zile necesare pentru debursare către RP) | P1: 7; P2: 5
| Days taken for disbursement to reach SRs (Zile necesare pentru debursare către SR) | P1: 5; P2: 5
| Management Information [Informația pe Management]: | P6: Enter management data in every blue cell [Întroduceți datele pentru management în celulele albastre].
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) [Statutul Condițiilor Precedente și a Acțiunilor Prestabilite în Timp]
|  |  | Fulfilled [Îndeplinite] | Not fulfilled, but within deadline [Ne îndeplinite dar realizarea în conformitate cu planul] | Not fulfilled, and past the deadline [Ne îndeplinite și au depășit termenul de realizare] | Total
| Conditions precedent (CPs) [Conditii precedente] | P2: 3; P3: 0; P4: 0; P5: 3
| Time Bound Actions (TBAs) [Acțiuni Prestabilite în Timp] | P2: 0; P3: 0; P4: 0; P5: 0
M2: Status of key PR management positions
|  | Planned | Filled | Vacant
| PMU | P1: 14; P2: 14; P3: 0
M3: Contractual arrangements (SRs)
|  | Identified | Assessed | Approved | Signed | Receiving Funding
| SRs | P1: 2; P2: 0; P3: 2; P4: 2; P5: 2
M4: Number of complete reports received on time
|  | # Expected | # Received | Pending
| SSR to SR | P1: 9; P2: 9; P3: 0
| SRs to PR | P1: 2; P2: 2; P3: 0
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals
|  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
| Budget Approved* | P1: 23226.39; P2: 172298.3703
Obligations
| Expenditures | P1: 9822.769; P2: 141952.7074
| Budget Approved cumulative* | P1: 23226.39; P2: 195524.7603
Obligations cumulative
| Expenditures cumulative | P1: 9822.769; P2: 151775.4765
* Includes only AFR category 4, 5 and 6 (Health products and health equipment & Medicines and Pharmaceuticals)
M6: Difference between current and safety stock
| Component | Products | (1) Number of tablets per patient per day (Review country treatment guidelines) | (2 = 1 x 30) Monthly treatment (Tablets per patient x 30 days) | (3) Total patients in treatment | (4 = 2 x 3) Total # tab/pills required for all patients per month | (5) Current stock in central warehouse (that does not expire within the next 3 months) | (6 = 5 / 4) Stock level expressed in months of treatment for all current patients | (7) Level of safety stock (expressed in months and defined by country) | (8 = 6 - 7) Difference between current stock and safety stock
| Please Select | P1: Please Select
Please Select
Please Select
Please Select
| Programmatic Information: | P9: Enter performance data in every yellow cell.
| Programmatic indicators (Performance Framework ) |  |  | Code | Directly Tied? |  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9
TOP 3 | Number of TB cases with RR-TB and/or MDR-TB notified [Numărul de cazuri de TB (RR-TB și/sau MDR-TB), notificate] |  |  | MDR TB-2(M) | Yes | Target | P1: 535; P2: 1069; P3: 512
[6 empty] | Achieved | P1: 376; P2: 811; P3: 348
| Percentage of cases with RR-TB and/or MDR-TB) started on treatment for MDR-TB who were lost to follow up during the first six months of treatment [Procentul cazurilor cu RR-TB și/sau MDR-TB care au întrerupt tratamentul DOTS-Plus către luna a 6 de la demararea acestuia] |  |  | MDR TB-4 | Yes | Target | P1: 8.7%; P2: 8.7%; P3: 7.6%
[6 empty] | Achieved | P1: 9.27%; P2: 9.55%; P3: 8.83%
| Percentage of new and relapse TB patients tested using WHO recomennded rapid tests at the time of diagnosis [Procentul pacientilor cu TB, cazuri noi si recidiva, care au fost testați folosind teste rapide recomandate de OMS în momentul diagnosticării] |  |  | TCP-8 | Yes | Target | P1: 93%; P2: 93%; P3: 94%
[6 empty] | Achieved | P1: 95%; P2: 96%; P3: 93%
| Table is automatically updated. No data or information is to be entered here. |  |  | Code | Directly Tied? |  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9
| Percentage of new and relapse TB patients tested using WHO recomennded rapid tests at the time of diagnosis [Procentul pacientilor cu TB, cazuri noi si recidiva, care au fost testați folosind teste rapide recomandate de OMS în momentul diagnosticării] |  |  | MDR TB-2(M) | Yes | Target | P1: 535; P2: 1069; P3: 512; P9: 0
[6 empty] | Achieved | P1: 376; P2: 811; P3: 348; P9: 0
| Percentage of cases with RR-TB and/or MDR-TB) started on treatment for MDR-TB who were lost to follow up during the first six months of treatment [Procentul cazurilor cu RR-TB și/sau MDR-TB care au întrerupt tratamentul DOTS-Plus către luna a 6 de la demararea acestuia] |  |  | MDR TB-4 | Yes | Target | P1: 8.7%; P2: 8.7%; P3: 7.6%; P9: 0
[6 empty] | Achieved | P1: 9.27%; P2: 9.55%; P3: 8.83%; P9: 0
| Percentage of new and relapse TB patients tested using WHO recomennded rapid tests at the time of diagnosis [Procentul pacientilor cu TB, cazuri noi si recidiva, care au fost testați folosind teste rapide recomandate de OMS în momentul diagnosticării] |  |  | TCP-8 | Yes | Target | P1: 93%; P2: 93%; P3: 94%; P9: 0
[6 empty] | Achieved | P1: 95%; P2: 96%; P3: 93%; P9: 0
Note on B68: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B74: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Menu

## Grant Detail
Dashboard: Moldova - TB
Country: | Moldova |  | Title of the Grant: |  | Strengthening Tuberculosis control in the Republic of Moldova
Component: | TB | Grant No. | MDA-T-PAS | Start Date: |  | 2018-01-01 | Total Funding
Round: | NFM | Phase: | 0 | Principal Recipient: |  | Center for Health Policies and Studies (PAS Center)
Report Period: | P3 | from: | 2019-01-01 | to: |  | 2019-06-30 | Latest Rating: | A2
Local Fund Agent: | PwC (PricewaterhouseCoopers) |  |  | Fund Portfolio Manager: |  | Tsovinar Sakanyan
Prepared by: | PAS Center |  |  | Report preparation date: |  | 2019-07-30
http://www.crwflags.com/fotw/flags/country.html
Menu

## Finance
Dashboard: Moldova - TB
NFM | 0 |  |  |  | Report Period [Perioada de raportare]: |  | P3
Latest Rating [Ultimul Rating]: | A2 |  | Center for Health Policies and Studies (PAS Center) |  | From [de la]: |  | 2019-01-01
|  | Strengthening Tuberculosis control in the Republic of Moldova |  |  |  | To[Pînă la]: | 2019-06-30
Financial Indicators
F1: Budget and disbursements by Global Fund [Bugetul și debursările de către Fondul Global] - in (€) Report Period [Perioada de raportare]: P3 |  |  |  | F3: Disbursements and expenditures [Debursări și cheltuieli] - in (€) Report Period [Perioada de raportare]: P3
Comments: | The cumulative disbursement is more than cumulative budget due to the buffer amount of 345,470.06 EUR disbursed to the PR, to prepare for the activities in 2019, at the end of 2018 and at the end of Semeters. Suma debursată este mai mare in raport cu bugetul programat, deoarece suma de 345,470.06 EUR reprezinta perioada de buffer pentru asigurarea continuitatii activitatilor din 2019, la final de 2018 si la final de semestru. |  |  | Comments: | The cumulative disbursement by the GF is more than cumulative cash-out flow of the PR due to buffer amount and committed budget. The variance between disbursed amount to SRs and SRs' expenditures includes the sum committed for incentives to TB patients, based on June lists, to be paid in July- August 2019 by the SR AFI. As well, the identified savings at SR SFM level in 2018 were redirected for one additional grant in Transnistria in 2019. Suma debursată de FG este mai mare decât cheltuielile RP împreună cu debursările către SRi, fiind determinată de suma debursta în calitate de bufer și sumele angajate pentru activități. Variația dintre suma debursată către SRi și cheltuielile SR-lor include suma angajată pentru programul de suport al pacienților pe luna Iunie care a fost plătită în luna Iulie- August 2019 de către SR AFI, în baza listelor primite de la medicii ftiziopneumologi. De asemenea, economiile identificate la nivelul SR SFM din 2018 au fost redirecționate pentru un grant suplimentar în Transnistria în 2019.
F2: Budget and actual expenditures by Grant Objective [Bugetul și cheltuielile actuale după Obiectivele Grantului] - in (€) Report Period [Perioada de raportare]: P3 |  |  |  | F4: Latest PR reporting and disbursement cycle [Ultima perioadă de raportare și debursare a RP] Report Period [Perioada de raportare]: P3
Comments: | The budget was spent as planned, in general ( 2,027,205.00 EUR vs 1,942,548.00 EUR). The variance between budget and expenditures is caused several factors:1. By the difference due to the factual exchange rate of the bank applied for each disbursement, which was lower vs the rate EUR/lei MD provided by the GF (21,767181) wich conducted to the budget deficit; 2. By the committed/ forecasted activities to be realiased in 2019. Bugetul a fost cheltuit conform planificărilor, in general ( 2,027,205.00 EUR vs 1,942,548.00 EUR). Diferența dintre buget și cheltuieli este cauzată de diferite motive:1) diferența datorată cursului de schimb real al băncii aplicate pentru fiecare plată, care a fost mai mic față de rata MDL lei / lei inclusă în aplicația de grant către FG (21.767181, ceia ce a format un deficit bugetar. 2) De sumele programate pentru activitatile in realizate in 2019. |  |  | Comments: | The PR always makes the disbursements to SRs in the shortest period when the disbursement request is received and the report is presented. Perioada de debursare către SR este cit mai operativ posibil de la data depunerii cererii de debursare şi prezentare a raportului financiar.
Last fund disbursement: Calendar days
[6 empty] | Expected (days) | Actual (days)
|  |  |  | Days taken to submit final PU/DR to LFA (Zile necesare pentru remiterea PU/DR final către ALF) |  | 90 | 88
|  |  |  | Days taken for disbursement to reach PR (Zile necesare pentru debursare către RP) |  | 7 | 5
|  |  |  | Days taken for disbursement to reach SRs (Zile necesare pentru debursare către SR) |  | 5 | 5
Menu

## Management
Dashboard: Moldova - TB
NFM | 0 |  |  |  |  | Report Period [Perioada de raportare]: |  | P3
Latest Rating [Ultimul Rating]: | A2 |  | Center for Health Policies and Studies (PAS Center) |  |  | From [de la]: |  | 2019-01-01
|  | Strengthening Tuberculosis control in the Republic of Moldova |  |  |  |  | To[Pînă la]: | 2019-06-30
Management Indicators
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) [Statutul Condițiilor Precedente și a Acțiunilor Prestabilite în Timp] Report Period [Perioada de raportare]: P3 |  |  |  | M2: Status of key PR management positions Report Period [Perioada de raportare]: P3
Comments: | 1) The condition included in the grant agreement is "The Republic of Moldova should comply with the requirements to access the ‘co-financing incentive’ as set forth in the STC Policy (the “Co-Financing Incentive Requirements”). The commitment and disbursement of 15% of the Republic of Moldova’s HIV and TB allocation of Euro 15,896,721 for the 2017-2019 allocation period, which is equal to Euro 2,384,508 (the “Co-Financing Incentive”), is subject to the Global Fund’s satisfaction with the Republic of Moldova’s compliance with the Co-Financing Incentive Requirements". The status of the condition is reported annualy. Therefore the next ordinary information on this topic is going to be reported with the Dashboard for S2 2019. 2) Second condition included in the grant agreement is related to transition between grants: a. The Program budget reflects the total amount of Global Fund funding to be made available for the Program. The Program budget may be funded in part by grant funds disbursed to the PR under a previous Grant Agreement, which the Global Fund has approved to be used for the Program under the current Grant Agreement (“Previously Disbursed Grant Funds”), as well as additional Grant Funds up to the amount set forth in Section 3.6 of the Grant Confirmation. Where the Global Fund has approved the use of Previously Disbursed Grant Funds, the Global Fund may reduce the amount of Grant Funds set forth in Section 3.6 of the Grant Confirmation by the amount of any Previously Disbursed Grant Funds, and the definition of Grant Funds set forth in Section 2.2 of the Global Fund Grant Regulations (2014) shall include any Previously Disbursed Grant Funds. b. All non-cash assets remaining under any previous Grant Agreements as of the start date of the Implementation Period shall be fully accounted for and duly documented (“Previous Program Assets”). Unless otherwise agreed with the Global Fund, the definition of Program Assets set forth in Section 2.2 of the Global Fund Grant Regulations (2014) shall include any Previous Program Assets. c. For the avoidance of doubt, except as explicitly set forth herein, nothing in the instant Grant Agreement shall impact the obligations of the PR under any previous Grant Agreement(s) (including, but not limited to, those concerning financial and other reporting). The status of the condition is met. a. According to the GF regulations, the disbursements into the current grant, took into acount the previously disbursed Grants Funds. Consolidations of the grant budget considering previous and current disbursements were documented and recorded as per requests. b. All non - cash assests were accounted and documented at the level of PR and SR, SSR. 3)Third condition is related to the use of GF name and logos as set forth in the “Identity Guide for Partners” (as amended from time to time), available at the Global Fund’s Internet site. The PR has to agree that if the PR intends to use the Global Fund’s name and/or logos in relation to any Program Activities, the PR is required (1) to seek the prior approval of the Global Fund by submitting a plan of use in accordance with the Identity Guide for Partners to the Global Fund and, if such plan is approved, (2) to sign a trademark license agreement in form and substance acceptable to the Global Fund. The status of the condition is met. The plan on use of Global Fund's name and / or logos in relations with Program Activities was approved by the Global Fund in S1 2019. 1) O condiție înaintată țării este că angajamentul și plata a 15% din alocarea totală pentru TB și HIV de 15,896,721 EUR pentru Republica Moldova în perioada 2018-2020, care este egală cu 2,384,508 EURO, este condiționată Republicii Moldova de respectarea cerinței Fondului Global de a mări finanțarea din partea statului, în domeniul unde a investit Fondul Global. Aceasta este o condiție pe durata grantului si se raporteaza anual. Astfel informatia ordinară pe acest aspect se va prezenta in procesul de raportare pentru S 2 2019. 2) A doua condiție inclusă în acordul de grant se referă la tranziția între granturi: A. Bugetul programului reflectă suma totală a finațării din partea Fondului Global care urmează să fie puse la dispoziție pentru implementarea Programului. Bugetul programului poate fi finanțat în parte prin fonduri debursate către RP în baza unui acord de grant anterior, pe care Fondul Global l-a aprobat pentru a fi utilizat în cadrul programului din acordul de grant actual ("Fonduri de finanțare acordate anterior"), precum și Fonduri suplimentare de finanțare până la suma stabilită în secțiunea 3.6 a Confirmării de grant. În cazul în care Fondul Global a aprobat utilizarea fondurilor de finanțare debursate anterior, Fondul Global poate reduce suma prezentată în secțiunea 3.6 a Confirmării de grant cu sumadebursată anterior și modificarea definiției fondurilor de grant în secțiunea 2.2 a Reglamentărilor privind implementarea granturilor FG (2014), iar suma totală va include fondurile existente debursate anterior. b. Toate activele nemonetare rămase în temeiul oricăror acorduri de grant anterioare de la începutul perioadei de implementare vor fi pe deplin contabilizate și documentate corespunzător ("Active anterioare programului"). Definiția activelor programului prezentată în secțiunea 2.2 a Reglamentărilor privind implementarea granturilor FG (2014) va include orice active anterioare ale programului, cu excepția cazului în care s-a convenit altfel cu Fondul Global. c. Pentru a evita orice dubiu, cu excepția celor expuse în mod explicit în Acordul de grant, nici o clauză din Acordul de grant curent nu afectează obligațiile RP în cadrul acordurilor de grant anterioare (inclusiv, dar fără a se limita la cele care privesc raportarea financiară și de altă natură). Statutul acestei condiții este îndeplinit. A. Conform regulamentelor FG, plățile în grantul actual au fost efectuate luând în considerare fondurile existente debursate în grantul precedent. Consolidarea bugetului a fost documentată și înregistrată conform cerințelor, ținând cont de debursările anterioare și curente. b. Toate activele nemonetare au fost contabilizate și documentate la nivel de RP și SR, SSR. 3) A treia condiție se referă la utilizarea denumirii și logoului FG, așa cum este prevăzut în "Ghidul de identitate pentru parteneri" (modificat din când în când), disponibil pe site-ul oficial al Fondului Global. RP trebuie să convină că, dacă RP intenționează să utilizeze numele și / sau logo-urile Fondului Global în legătură cu orice Activități ale Programului, RP este obligat (1) să solicite aprobarea prealabilă a Fondului Global prin prezentarea unui plan de utilizare în conformitate cu Ghidul de identitate pentru partenerii Fondului global și, în cazul aprobării acestui plan, (2) să semneze un acord de utilizare a logo-urilor, în formatul acceptabil pentru Fondul Global. Statutul acestei condiții este indeplinit. Planul privind utilizarea numelui și / sau logoului Fondului Global în activitățile programului este aprobat de Fondului Global în S1 2019. |  |  | Comments: | All positions are fulfilled. Toate posturile de munca sunt suplinite.
M3: Contractual arrangements (SRs) Report Period [Perioada de raportare]: P3 |  |  |  | M4: Number of complete reports received on time Report Period [Perioada de raportare]: P3
Comments: | None of the SRs needed to be assessed, due to proved experience within the precedent grant implementation. Nici unul dintre sub-recipienti nu a necesitat să fie evaluat, dat fiind experiența demonstrată în cadrul implementării grantului precedent. |  |  | Comments: | For the reported period, January - June 2019, 9 SSRs were involved in TB related activities, stria and 10 NGOs (among which NGO AFI as well) are acting as SSRs of the SR SFM, implementing small grants programme. Basically, the majority of NGO are implementing one grant, with exception of two NGOs which applied to Soros Foundation - Moldova and were granted with several grants each, but within different components and targeted to different populations: NGO "AFI" which implements one grant in "TB, DR-TB and TB/HIV control in prisoners and ex-prisoners" and one grant in "TB, DR-TB and TB/HIV control for homeless people in mun. Chisinau "; and NGO ”Medico-Social Programs” which implements two grants in TB, DR-TB and TB/HIV control in groups at-risk,. The second grant allocated to Medico_Social Programs from Transnistria was approved, following savings on the budget line for the first component of small gransts with approval from the GF . In perioada de raportare, Ianuari - Iunie 2019, 9 sub-subrecipienți au realizat activități conexe programului de control al TB, un SSR fiind implicat în distribuirea pachetelor motivaționale în Transnistria împreună cu SR AFI , iar 10 ONG-uri (printre care și ONG-ul AFI) implementează programul de granturi mici împruenă cu SR SFM. Majoritatea ONG-urilor realizează cîte un grant, excepție fiind 2 ONG care au aplicat către Fundația Soros - Moldova, și au fost aprobate pentru implementarea a câtorva granturi, în cadrul diferitor componente ale programului de granturi mici și orientate spre diferite populații-cheie - ONG ”AFI” care implementează un proiect în controlul tuberculozei, tuberculozei drog-rezistente și tuberculozei asociate cu HIV printre deținuți și foști deținuți și un proiect în domeniul controlului tuberculozei, tuberculozei drog-rezistente și tuberculozei asociate cu HIV îpentru persoanele fără adopost din mun. Chisinau și ONG ”Programe Medico-Sociale” care implementează 2 proiecte proiecte în domeniul controlului tuberculozei, tuberculozei drog-rezistente și tuberculozei asociate cu HIV în grupurile cu risc sporit de îmbolnăvire, in baza sumelor salvate in 2018 din primul grup de grant, cu confirmarea de la FG.
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals |  |  |  | M6: Difference between current and safety stock Report Period [Perioada de raportare]: P3
Comments: | EUR 43,750.00 were unused defined by the real needs in maintenance services. Also this budget is forecasted to fulfill and cover the services costs for calibration of GeneXpert equipments and procurement of consumables for solving/replacing any technical issues that might be identified after calibration. Diferența dintre suma bugetată și suma cheltuită este explicată de următoarele variații - 43, 750.00 EUR au fost neutilizate, sumă determinată de nevoile reale pentru serviciile de mentenanță. De asemenea, acest buget este prevăzut să complementeze și să acopere costurile serviciilor de calibrare a echipamentelor GeneXpert și achiziționarea de consumabile pentru rezolvarea / înlocuirea oricăror probleme tehnice care ar putea fi identificate după calibrare. |  |  | Comments: | N/A
|  |  |  | Component | Products | Stock level expressed in months of treatment for all current patients | Months of safety stock | Difference between current stock and safety stock
|  |  |  | Please Select | Please Select |  | 0
[5 empty] | Please Select |  | 0
[5 empty] | Please Select |  | 0
[5 empty] | Please Select |  | 0
* Includes only AFR category 4, 5 and 6 (Health products and health equipment & Medicines and Pharmaceuticals)
Menu

## Programmatic
Dashboard: Moldova - TB
NFM | 0 | [8 empty] | Report Period [Perioada de raportare]: |  | P3
Latest Rating [Ultimul Rating]: | A2 |  | Center for Health Policies and Studies (PAS Center) | [7 empty] | From [de la]: | 2019-01-01
|  | Strengthening Tuberculosis control in the Republic of Moldova | [8 empty] | To[Pînă la]: | 2019-06-30 | [7 empty] | Raiting |  | Valor
Programmatic Indicators
Percentage of new and relapse TB patients tested using WHO recomennded rapid tests at the time of diagnosis [Procentul pacientilor cu TB, cazuri noi si recidiva, care au fost testați folosind teste rapide recomandate de OMS în momentul diagnosticării] |  |  |  | Percentage of cases with RR-TB and/or MDR-TB) started on treatment for MDR-TB who were lost to follow up during the first six months of treatment [Procentul cazurilor cu RR-TB și/sau MDR-TB care au întrerupt tratamentul DOTS-Plus către luna a 6 de la demararea acestuia]
Comment: P1 | Conform datelor preliminare pentru semestrul 1 al anului 2019, 348 cazuri cu tuberculoză drogrezistentă (RR-TB și/sau MDR-TB), confirmate bacteriologic, au fost notificate, față de 512 cazuri estimate pentru perioada raportată.Una din motivele de neatingere al acestei ținte este descreșterea incidenței cazurilor de TB. |  |  | Comment: P2 | Conform datelor preliminare pentru semestrul 1 al anului 2018, 43 pacienți din 487 incluși în tratamentul DOTS Plus în sem.I 2018, au abandonat tratamentul către luna a 6-a de la demararea acestuia. |  |  | Comment: P3 | The indicator shows that the country achieved universal use of Xpert as the point of care method, as 93% of all new cases registered in first semester of year 2019 were tested with the Xpert method at the time of diagnosis. The indicator is achieved at 99% in general, considering the limitation of testing due to postponed tenders on procurement cartridges from public budget for 2019, from November 2018 up to October 2019, risk of stock-out and reschedule of procurement cartridges from the GF budget. Indicatorul arată că țara a atins utilizarea universal a Xpert ca metodă de îngrijire, 93% din toate cazurile noi înregistrate în primil semestru al anului 2019 au fost testate prin metoda Xpert la momentul diagnosticării. Indicatorul este atins in marime de 99%, fiind determinata acest raport si de limitarile in testare legate de aminarea tenderelor de procurare a cartuselor din bugetul public pentru 2019, din Noiembrie 2018 pina la Octombrie 2019, riscurile de stock-out si reprogramarea livrarilor de cartuse din sursele FG.
Indicators |  |  | Target | Achieved | 0% - 59% | 60% - 89% | > 90% | Comments |  |  |  |  | min | 0 | 30% | 60% | 90% | 100% |  | min | 0 | 20% | 40% | 60% | 80%
Number of TB cases with RR-TB and/or MDR-TB notified [Numărul de cazuri de TB (RR-TB și/sau MDR-TB), notificate] |  |  | 512 | 348 | 67.97% |  |  | Conform datelor preliminare pentru semestrul 1 al anului 2019, 348 cazuri cu tuberculoză drogrezistentă (RR-TB și/sau MDR-TB), confirmate bacteriologic, au fost notificate, față de 512 cazuri estimate pentru perioada raportată.Una din motivele de neatingere al acestei ținte este descreșterea incidenței cazurilor de TB. |  |  |  |  | max | 30% | 60% | 90% | 100% | 200% |  | max | 20% | 40% | 60% | 80% | 100%
Percentage of cases with RR-TB and/or MDR-TB) started on treatment for MDR-TB who were lost to follow up during the first six months of treatment [Procentul cazurilor cu RR-TB și/sau MDR-TB care au întrerupt tratamentul DOTS-Plus către luna a 6 de la demararea acestuia] |  |  | 7.6% | 8.83% | 86.07% |  |  | Conform datelor preliminare pentru semestrul 1 al anului 2018, 43 pacienți din 487 incluși în tratamentul DOTS Plus în sem.I 2018, au abandonat tratamentul către luna a 6-a de la demararea acestuia. | [5 empty] | de 0 a 0.3 | de 0.3 a 0.6 | de 0.6 a 0.9 | de 0.9 a 1 | de 1 a 2 | Rating | Valor | de 0 a 0.2 | de 0.2 a 0.4 | de 0.4 a 0.6 | de 0.6 a 0.8 | de 0.8 a 1
Percentage of new and relapse TB patients tested using WHO recomennded rapid tests at the time of diagnosis [Procentul pacientilor cu TB, cazuri noi si recidiva, care au fost testați folosind teste rapide recomandate de OMS în momentul diagnosticării] |  |  | 94% | 93% | 98.94% |  |  | The indicator shows that the country achieved universal use of Xpert as the point of care method, as 93% of all new cases registered in first semester of year 2019 were tested with the Xpert method at the time of diagnosis. The indicator is achieved at 99% in general, considering the limitation of testing due to postponed tenders on procurement cartridges from public budget for 2019, from November 2018 up to October 2019, risk of stock-out and reschedule of procurement cartridges from the GF budget. Indicatorul arată că țara a atins utilizarea universal a Xpert ca metodă de îngrijire, 93% din toate cazurile noi înregistrate în primil semestru al anului 2019 au fost testate prin metoda Xpert la momentul diagnosticării. Indicatorul este atins in marime de 99%, fiind determinata acest raport si de limitarile in testare legate de aminarea tenderelor de procurare a cartuselor din bugetul public pentru 2019, din Noiembrie 2018 pina la Octombrie 2019, riscurile de stock-out si reprogramarea livrarilor de cartuse din sursele FG. | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[14 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
[14 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Menu

## Recommendations
Dashboard: Moldova - TB
NFM | 0 |  |  |  |  | Report Period [Perioada de raportare]: | P3
Latest Rating [Ultimul Rating]: | A2 |  | Center for Health Policies and Studies (PAS Center) |  |  | From [de la]: | 2019-01-01
|  |  | Strengthening Tuberculosis control in the Republic of Moldova |  |  | To[Pînă la]: | 2019-06-30
Recommendations
Are all funds reaching implementation levels and being spent according to budget?
Financial |  | Summary Comments |  |  | Recommendations
F1 |  | The cumulative disbursement is more than cumulative budget due to the buffer amount of 345,470.06 EUR disbursed to the PR, to prepare for the activities in 2019, at the end of 2018 and at the end of Semeters. Suma debursată este mai mare in raport cu bugetul programat, deoarece suma de 345,470.06 EUR reprezinta perioada de buffer pentru asigurarea continuitatii activitatilor din 2019, la final de 2018 si la final de semestru.
F2 |  | The budget was spent as planned, in general ( 2,027,205.00 EUR vs 1,942,548.00 EUR). The variance between budget and expenditures is caused several factors:1. By the difference due to the factual exchange rate of the bank applied for each disbursement, which was lower vs the rate EUR/lei MD provided by the GF (21,767181) wich conducted to the budget deficit; 2. By the committed/ forecasted activities to be realiased in 2019. Bugetul a fost cheltuit conform planificărilor, in general ( 2,027,205.00 EUR vs 1,942,548.00 EUR). Diferența dintre buget și cheltuieli este cauzată de diferite motive:1) diferența datorată cursului de schimb real al băncii aplicate pentru fiecare plată, care a fost mai mic față de rata MDL lei / lei inclusă în aplicația de grant către FG (21.767181, ceia ce a format un deficit bugetar. 2) De sumele programate pentru activitatile in realizate in 2019.
F3 |  | The cumulative disbursement by the GF is more than cumulative cash-out flow of the PR due to buffer amount and committed budget. The variance between disbursed amount to SRs and SRs' expenditures includes the sum committed for incentives to TB patients, based on June lists, to be paid in July- August 2019 by the SR AFI. As well, the identified savings at SR SFM level in 2018 were redirected for one additional grant in Transnistria in 2019. Suma debursată de FG este mai mare decât cheltuielile RP împreună cu debursările către SRi, fiind determinată de suma debursta în calitate de bufer și sumele angajate pentru activități. Variația dintre suma debursată către SRi și cheltuielile SR-lor include suma angajată pentru programul de suport al pacienților pe luna Iunie care a fost plătită în luna Iulie- August 2019 de către SR AFI, în baza listelor primite de la medicii ftiziopneumologi. De asemenea, economiile identificate la nivelul SR SFM din 2018 au fost redirecționate pentru un grant suplimentar în Transnistria în 2019.
F4 |  | The PR always makes the disbursements to SRs in the shortest period when the disbursement request is received and the report is presented. Perioada de debursare către SR este cit mai operativ posibil de la data depunerii cererii de debursare şi prezentare a raportului financiar.
Are procurement and hiring on schedule?
Management |  | Summary Comments |  |  | Recommendations
M1 |  | 1) The condition included in the grant agreement is "The Republic of Moldova should comply with the requirements to access the ‘co-financing incentive’ as set forth in the STC Policy (the “Co-Financing Incentive Requirements”). The commitment and disbursement of 15% of the Republic of Moldova’s HIV and TB allocation of Euro 15,896,721 for the 2017-2019 allocation period, which is equal to Euro 2,384,508 (the “Co-Financing Incentive”), is subject to the Global Fund’s satisfaction with the Republic of Moldova’s compliance with the Co-Financing Incentive Requirements". The status of the condition is reported annualy. Therefore the next ordinary information on this topic is going to be reported with the Dashboard for S2 2019. 2) Second condition included in the grant agreement is related to transition between grants: a. The Program budget reflects the total amount of Global Fund funding to be made available for the Program. The Program budget may be funded in part by grant funds disbursed to the PR under a previous Grant Agreement, which the Global Fund has approved to be used for the Program under the current Grant Agreement (“Previously Disbursed Grant Funds”), as well as additional Grant Funds up to the amount set forth in Section 3.6 of the Grant Confirmation. Where the Global Fund has approved the use of Previously Disbursed Grant Funds, the Global Fund may reduce the amount of Grant Funds set forth in Section 3.6 of the Grant Confirmation by the amount of any Previously Disbursed Grant Funds, and the definition of Grant Funds set forth in Section 2.2 of the Global Fund Grant Regulations (2014) shall include any Previously Disbursed Grant Funds. b. All non-cash assets remaining under any previous Grant Agreements as of the start date of the Implementation Period shall be fully accounted for and duly documented (“Previous Program Assets”). Unless otherwise agreed with the Global Fund, the definition of Program Assets set forth in Section 2.2 of the Global Fund Grant Regulations (2014) shall include any Previous Program Assets. c. For the avoidance of doubt, except as explicitly set forth herein, nothing in the instant Grant Agreement shall impact the obligations of the PR under any previous Grant Agreement(s) (including, but not limited to, those concerning financial and other reporting). The status of the condition is met. a. According to the GF regulations, the disbursements into the current grant, took into acount the previously disbursed Grants Funds. Consolidations of the grant budget considering previous and current disbursements were documented and recorded as per requests. b. All non - cash assests were accounted and documented at the level of PR and SR, SSR. 3)Third condition is related to the use of GF name and logos as set forth in the “Identity Guide for Partners” (as amended from time to time), available at the Global Fund’s Internet site. The PR has to agree that if the PR intends to use the Global Fund’s name and/or logos in relation to any Program Activities, the PR is required (1) to seek the prior approval of the Global Fund by submitting a plan of use in accordance with the Identity Guide for Partners to the Global Fund and, if such plan is approved, (2) to sign a trademark license agreement in form and substance acceptable to the Global Fund. The status of the condition is met. The plan on use of Global Fund's name and / or logos in relations with Program Activities was approved by the Global Fund in S1 2019. 1) O condiție înaintată țării este că angajamentul și plata a 15% din alocarea totală pentru TB și HIV de 15,896,721 EUR pentru Republica Moldova în perioada 2018-2020, care este egală cu 2,384,508 EURO, este condiționată Republicii Moldova de respectarea cerinței Fondului Global de a mări finanțarea din partea statului, în domeniul unde a investit Fondul Global. Aceasta este o condiție pe durata grantului si se raporteaza anual. Astfel informatia ordinară pe acest aspect se va prezenta in procesul de raportare pentru S 2 2019. 2) A doua condiție inclusă în acordul de grant se referă la tranziția între granturi: A. Bugetul programului reflectă suma totală a finațării din partea Fondului Global care urmează să fie puse la dispoziție pentru implementarea Programului. Bugetul programului poate fi finanțat în parte prin fonduri debursate către RP în baza unui acord de grant anterior, pe care Fondul Global l-a aprobat pentru a fi utilizat în cadrul programului din acordul de grant actual ("Fonduri de finanțare acordate anterior"), precum și Fonduri suplimentare de finanțare până la suma stabilită în secțiunea 3.6 a Confirmării de grant. În cazul în care Fondul Global a aprobat utilizarea fondurilor de finanțare debursate anterior, Fondul Global poate reduce suma prezentată în secțiunea 3.6 a Confirmării de grant cu sumadebursată anterior și modificarea definiției fondurilor de grant în secțiunea 2.2 a Reglamentărilor privind implementarea granturilor FG (2014), iar suma totală va include fondurile existente debursate anterior. b. Toate activele nemonetare rămase în temeiul oricăror acorduri de grant anterioare de la începutul perioadei de implementare vor fi pe deplin contabilizate și documentate corespunzător ("Active anterioare programului"). Definiția activelor programului prezentată în secțiunea 2.2 a Reglamentărilor privind implementarea granturilor FG (2014) va include orice active anterioare ale programului, cu excepția cazului în care s-a convenit altfel cu Fondul Global. c. Pentru a evita orice dubiu, cu excepția celor expuse în mod explicit în Acordul de grant, nici o clauză din Acordul de grant curent nu afectează obligațiile RP în cadrul acordurilor de grant anterioare (inclusiv, dar fără a se limita la cele care privesc raportarea financiară și de altă natură). Statutul acestei condiții este îndeplinit. A. Conform regulamentelor FG, plățile în grantul actual au fost efectuate luând în considerare fondurile existente debursate în grantul precedent. Consolidarea bugetului a fost documentată și înregistrată conform cerințelor, ținând cont de debursările anterioare și curente. b. Toate activele nemonetare au fost contabilizate și documentate la nivel de RP și SR, SSR. 3) A treia condiție se referă la utilizarea denumirii și logoului FG, așa cum este prevăzut în "Ghidul de identitate pentru parteneri" (modificat din când în când), disponibil pe site-ul oficial al Fondului Global. RP trebuie să convină că, dacă RP intenționează să utilizeze numele și / sau logo-urile Fondului Global în legătură cu orice Activități ale Programului, RP este obligat (1) să solicite aprobarea prealabilă a Fondului Global prin prezentarea unui plan de utilizare în conformitate cu Ghidul de identitate pentru partenerii Fondului global și, în cazul aprobării acestui plan, (2) să semneze un acord de utilizare a logo-urilor, în formatul acceptabil pentru Fondul Global. Statutul acestei condiții este indeplinit. Planul privind utilizarea numelui și / sau logoului Fondului Global în activitățile programului este aprobat de Fondului Global în S1 2019.
M2 |  | All positions are fulfilled. Toate posturile de munca sunt suplinite. | #DIV/0! | #DIV/0!
M3 |  | None of the SRs needed to be assessed, due to proved experience within the precedent grant implementation. Nici unul dintre sub-recipienti nu a necesitat să fie evaluat, dat fiind experiența demonstrată în cadrul implementării grantului precedent.
M4 |  | For the reported period, January - June 2019, 9 SSRs were involved in TB related activities, stria and 10 NGOs (among which NGO AFI as well) are acting as SSRs of the SR SFM, implementing small grants programme. Basically, the majority of NGO are implementing one grant, with exception of two NGOs which applied to Soros Foundation - Moldova and were granted with several grants each, but within different components and targeted to different populations: NGO "AFI" which implements one grant in "TB, DR-TB and TB/HIV control in prisoners and ex-prisoners" and one grant in "TB, DR-TB and TB/HIV control for homeless people in mun. Chisinau "; and NGO ”Medico-Social Programs” which implements two grants in TB, DR-TB and TB/HIV control in groups at-risk,. The second grant allocated to Medico_Social Programs from Transnistria was approved, following savings on the budget line for the first component of small gransts with approval from the GF . In perioada de raportare, Ianuari - Iunie 2019, 9 sub-subrecipienți au realizat activități conexe programului de control al TB, un SSR fiind implicat în distribuirea pachetelor motivaționale în Transnistria împreună cu SR AFI , iar 10 ONG-uri (printre care și ONG-ul AFI) implementează programul de granturi mici împruenă cu SR SFM. Majoritatea ONG-urilor realizează cîte un grant, excepție fiind 2 ONG care au aplicat către Fundația Soros - Moldova, și au fost aprobate pentru implementarea a câtorva granturi, în cadrul diferitor componente ale programului de granturi mici și orientate spre diferite populații-cheie - ONG ”AFI” care implementează un proiect în controlul tuberculozei, tuberculozei drog-rezistente și tuberculozei asociate cu HIV printre deținuți și foști deținuți și un proiect în domeniul controlului tuberculozei, tuberculozei drog-rezistente și tuberculozei asociate cu HIV îpentru persoanele fără adopost din mun. Chisinau și ONG ”Programe Medico-Sociale” care implementează 2 proiecte proiecte în domeniul controlului tuberculozei, tuberculozei drog-rezistente și tuberculozei asociate cu HIV în grupurile cu risc sporit de îmbolnăvire, in baza sumelor salvate in 2018 din primul grup de grant, cu confirmarea de la FG.
M5 |  | EUR 43,750.00 were unused defined by the real needs in maintenance services. Also this budget is forecasted to fulfill and cover the services costs for calibration of GeneXpert equipments and procurement of consumables for solving/replacing any technical issues that might be identified after calibration. Diferența dintre suma bugetată și suma cheltuită este explicată de următoarele variații - 43, 750.00 EUR au fost neutilizate, sumă determinată de nevoile reale pentru serviciile de mentenanță. De asemenea, acest buget este prevăzut să complementeze și să acopere costurile serviciilor de calibrare a echipamentelor GeneXpert și achiziționarea de consumabile pentru rezolvarea / înlocuirea oricăror probleme tehnice care ar putea fi identificate după calibrare.
M6 |  | N/A
Are technical targets being achieved?
Programmatic |  | Summary Comments |  |  | Recommendations
P1 - trend |  | Conform datelor preliminare pentru semestrul 1 al anului 2019, 348 cazuri cu tuberculoză drogrezistentă (RR-TB și/sau MDR-TB), confirmate bacteriologic, au fost notificate, față de 512 cazuri estimate pentru perioada raportată.Una din motivele de neatingere al acestei ținte este descreșterea incidenței cazurilor de TB.
P2 - trend |  | Conform datelor preliminare pentru semestrul 1 al anului 2018, 43 pacienți din 487 incluși în tratamentul DOTS Plus în sem.I 2018, au abandonat tratamentul către luna a 6-a de la demararea acestuia.
P3 - trend |  | The indicator shows that the country achieved universal use of Xpert as the point of care method, as 93% of all new cases registered in first semester of year 2019 were tested with the Xpert method at the time of diagnosis. The indicator is achieved at 99% in general, considering the limitation of testing due to postponed tenders on procurement cartridges from public budget for 2019, from November 2018 up to October 2019, risk of stock-out and reschedule of procurement cartridges from the GF budget. Indicatorul arată că țara a atins utilizarea universal a Xpert ca metodă de îngrijire, 93% din toate cazurile noi înregistrate în primil semestru al anului 2019 au fost testate prin metoda Xpert la momentul diagnosticării. Indicatorul este atins in marime de 99%, fiind determinata acest raport si de limitarile in testare legate de aminarea tenderelor de procurare a cartuselor din bugetul public pentru 2019, din Noiembrie 2018 pina la Octombrie 2019, riscurile de stock-out si reprogramarea livrarilor de cartuse din sursele FG.
P1 |  | Conform datelor preliminare pentru semestrul 1 al anului 2019, 348 cazuri cu tuberculoză drogrezistentă (RR-TB și/sau MDR-TB), confirmate bacteriologic, au fost notificate, față de 512 cazuri estimate pentru perioada raportată.Una din motivele de neatingere al acestei ținte este descreșterea incidenței cazurilor de TB.
P2 |  | Conform datelor preliminare pentru semestrul 1 al anului 2018, 43 pacienți din 487 incluși în tratamentul DOTS Plus în sem.I 2018, au abandonat tratamentul către luna a 6-a de la demararea acestuia.
P3 |  | The indicator shows that the country achieved universal use of Xpert as the point of care method, as 93% of all new cases registered in first semester of year 2019 were tested with the Xpert method at the time of diagnosis. The indicator is achieved at 99% in general, considering the limitation of testing due to postponed tenders on procurement cartridges from public budget for 2019, from November 2018 up to October 2019, risk of stock-out and reschedule of procurement cartridges from the GF budget. Indicatorul arată că țara a atins utilizarea universal a Xpert ca metodă de îngrijire, 93% din toate cazurile noi înregistrate în primil semestru al anului 2019 au fost testate prin metoda Xpert la momentul diagnosticării. Indicatorul este atins in marime de 99%, fiind determinata acest raport si de limitarile in testare legate de aminarea tenderelor de procurare a cartuselor din bugetul public pentru 2019, din Noiembrie 2018 pina la Octombrie 2019, riscurile de stock-out si reprogramarea livrarilor de cartuse din sursele FG.
P4
P5
P6
P7
P8
P9
P10
Menu

## Actions
Dashboard: Moldova - TB
| NFM | 0 |  |  |  | Report Period [Perioada de raportare]: |  | P3
| Latest Rating [Ultimul Rating]: | A2 |  | Center for Health Policies and Studies (PAS Center) |  | From [de la]: |  | 2019-01-01
|  |  | Strengthening Tuberculosis control in the Republic of Moldova |  |  |  | To[Pînă la]: | 2019-06-30
Decisions and Actions
What is the overall status of this grant implementation?
| Key Recommendations from Oversight Group(s) |  |  |  | CCM Decision | Due Date | Person Responsible
Current Reporting Period
Actions to Implement / Previous Period
What is the overall status of this grant implementation?
| CCM Decision |  |  |  | Action Taken | Date | Person Responsible
Previous Reporting Period
Menu

## Setup (hidden)
Dashboard: Moldova - TB
Set-up = List of validation for Grant Detail page
Component | Currency | Round | Phase | Period | Rating | LFA | Medicaments | Countries
Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select
HIV / AIDS | $ | Round 1 | Phase 1 | P1 | A1 | CA (Crown Agents) | Isoniazid | Afghanistan
MALARIA | € | Round 2 | Phase 2 | P2 | A2 | DEL (Deloitte) | Ethambutol | Albania
TB |  | Round 3 | RCC | P3 | B1 | DTT (DTT Emerging Markets) | Rifampicin | Algeria
HIVAIDS / TB |  | Round 4 |  | P4 | B2 | FIN (Finconsult) | Pyrazimamide | Angola
HSS |  | Round 5 |  | P5 | C | GT (Grant Thornton) | RDT | Argentina
|  | Round 6 |  | P6 |  | H-C (Hodar-Conseil) | NVP | Armenia
|  | Round 7 |  | P7 |  | KPMG (KPMG) | 3TC | Azerbaijan
|  | Round 8 |  | P8 |  | MSCI (MSCI) | D4T | Bangladesh
|  | Round 9 |  | P9 |  | PwC (PricewaterhouseCoopers) | AZT | Belarus
|  | Round 10 |  | P10 |  | STI (Swiss Tropical Institute), | DDI | Belize
|  |  |  | P11 |  | UNOPS | EFV | Benin
|  |  |  | P12 |  |  | AS/LF | Bhutan
[7 empty] | AS/AQ | Bolivia
[7 empty] | AS/MQ | Bosnia and Herzegovina
[7 empty] | Al/Lum | Botswana
Brazil
[7 empty] | TB nutri'l supplements | Bulgaria
[7 empty] | E-PAP | Burkina Faso
Burundi
Cambodia
Cameroon
Cape Verde
Central African Republic
Chad
Chile
China
China
Colombia
Comoros
Congo (Democratic Republic of the)
Congo (Republic of the)
Costa Rica
Cote d'Ivoire
Croatia
Cuba
Djibouti
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Ethiopia
Fiji
Gabon
Gambia
Georgia
Ghana
Global(LWF)
Guatemala
Guinea
Guinea-Bissau
Guyana
Haiti
Honduras
India
Indonesia
Iran (Islamic Republic of)
Iraq
Jamaica
Jordan
Kazakhstan
Kenya
Korea, Democratic Peoples Republic of
Kosovo (Serbia)
Kyrgyzstan
Lao PDR
Lesotho
Liberia
Macedonia, FYR
Madagascar
Malawi
Maldives
Mali
Mauritania
Mauritius
Moldova
Mongolia
Montenegro
Morocco
Mozambique
Multi-country Africa (West Africa Corridor Program)
Multi-country Africa(RMCC)
Multi-country Americas (Andean)
Multi-country Americas (CARICOM)
Multi-country Americas (CRN+)
Multi-country Americas (Meso)
Multi-country Americas (OECS)
Multi-country Americas (REDCA+)
Multi-country Western Pacific
Myanmar
Namibia
Nepal
Nicaragua
Niger
Nigeria
Pakistan
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Romania
Russian Federation
Rwanda
Sao Tome and Principe
Senegal
Serbia
Sierra Leone
Solomon Islands
Somalia
South Africa
Sri Lanka
Sudan
Suriname
Swaziland
Syrian Arab Republic
Tajikistan
Tanzania
Thailand
Timor-Leste
Togo
Tunisia
Turkey
Uganda
Ukraine
UN Theme Group on HIV/AIDS (West Bank and Gaza)
Uzbekistan
Viet Nam
Yemen
Zambia
Zanzibar (Tanzania)
Zimbabwe